## rfd_sub_station
REPORT INDICATING STATUS OF CONSTRUCTION OF SUB STATIONS (220 kV & ABOVE) IN RFD PROGRAMME DURING 2023-24
As on 31-AUG-2023
Sl No | Name of Sub Stations | Voltage Ratio (kV/kV) | Capacity (No.xMVA) | Date of Award | Cummulative progress till date |  |  |  |  | Commissioning |  | Tag Type | Remarks
[5 empty] | Land Acquired (%) | Civil works completed (%) | Materials / Equipments Received (%) | Materials / Equipments erected (%) | Capacity Tested/ Commissio ned (MVA) | Original | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | 220 kv Infrastructure at MTPS (Powerhouse Switchyard) | 400/220 | 1x315 |  | 100 | 40 | 70 | 10 |  | JAN-24 | JAN-24 | RFD | Scheduled target - Jan'24
2 | 220 kv Infrastructure at RTPS (Powerhouse Switchyard) | 400/220 | 2x315 |  | 100 | 30 | 70 | 10 |  | JAN-24 | JAN-24 | RFD | Scheduled target - Jan'24
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | 1x1500MVA 765/400kV ICT (3rd) at Nizamabad (PG) SS (2x1500MVA already existing) | 765/400 | 1x1500 | [6 empty] | JUN-23 |  | RFD
2 | 1x500MVA 400/220kV ICT (3rd) at Bhatapara (PG) | 400/220 | 500 | [6 empty] | JUN-23 |  | RFD
3 | 1x500MVA 400/220kV ICT (3rd) at Kolar (PG) SS (2x500MVA already existing) | 400/220 | 500 | [6 empty] | JUL-23 |  | RFD
4 | 1x500MVA 400/220kV ICT (3rd) at Palakkad (PG) SS (2x315MVA already existing) | 400/220 | 500 | [6 empty] | JUL-23 |  | RFD
5 | 1x500MVA 400/220kV ICT (3rd) at Ranchi (PG) S/S | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUN-23 | RFD | Commissioned 05/23.
6 | 1X500MVA 400/220kV ICT (6th) at Pavagada (Tumkur) PS | 400/220 | 500 | [6 empty] | FEB-24 |  | RFD
7 | 1x500MVA 400/220kV ICT along with associated bays at Kurukshetra (PG) GIS S/S | 400/220 | 500 | [6 empty] | JUN-23 |  | RFD
8 | 1x500MVA 400/220kV ICT at Jind | 400/220 | 500 | [6 empty] | MAR-24 |  | RFD
9 | 1x500MVA 400/220kV ICT at Kochi SS | 400/220 | 1x500 |  | 100 | 100 | 100 | 100 |  | JUN-23 | AUG-23 | RFD | Commissioned 07/23.
10 | 1x500 MVA 400/230kV ICT (4th) at Arasur S/S | 400/230 | 500 | [6 empty] | MAR-24 |  | RFD
11 | 2x500MVA 400/230kV (4th and 5th) ICT at Tuticorin-II GIS S/S | 400/230 | 2x500 | [6 empty] | JUL-23 |  | RFD
12 | 400/220kV Ramgarh II PS (4x500 MVA Transformer) | 400/220 | 2000 | [6 empty] | NOV-23 |  | RFD
13 | 765/400 1x1500MVA T/F (3rd) at Bikaner(PG) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | APR-23 | MAY-23 | RFD | Commissioned 04/23.
14 | 765/400/220kV Extension at Bhadla-II (400/220kV 500MVA( 8th) ICT | 400/220 | 500 |  | 100 | 96 | 95 | 90 |  | OCT-23 | MAR-23 | RFD | Extn. at 765/400/220 kV, MVA 500 Bhadla-II 6th has been commissioned in 08/22.
15 | 765/400/220kV Extension at Bhadla-II (765/400kV 1500MVA 4th ICT) | 765/400 | 1x1500 |  | 0 | 0 | 0 | 0 |  | MAR-24 | MAR-23 | RFD
13.: Page 1 of | 11
Report generated through NPP |  | 2023-09-05 20:47
16 | 765/400/220kV Extension at Fatehgarh-II (400/220kV 500MVA (9th )) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-23 | AUG-23 | RFD | Commissioned 07/23.
17 | 765/400/220kV Extension at Fatehgarh-II 765/400kV 1500MVA 6th ICT | 765/400 | 1500 | [6 empty] | JAN-24 |  | RFD
18 | 765/400 kV 1x1500 MVA (5th) ICT at Fatehgarh-II PS( SE Rajasthan (8.1 GW) under Phase II- Part- A1 | 765/400 | 1x1500 |  | 100 | 95 | 100 | 80 |  | OCT-23 | MAR-23 | RFD
19 | 765/400kV GIS Narela(1x1500MVA 765/400kV ICT)(solar energy zones in Rajasthan under phase II Part G) | 765/400 | 1x1500 | [6 empty] | MAR-24 |  | RFD
20 | Aug. of 1x315MVA 400/220kV ICT to 1x500MVA 400/220kV ICT at Patiala (PG) S/S | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-23 | AUG-23 | RFD | Commissioned 07/23.
21 | Aug. of Transformation capacity by 1X500MVA 400/230kV ICT (4th) at Hosur S/S | 400/230 | 500 | [6 empty] | MAR-24 |  | RFD
22 | Ext at 765/400kV Padghe (GIS) PG SS (2 no. 400kV line bays) (1x1500MVA 765/400kV ICT) | 765/400 | 1x1500 | [6 empty] | FEB-24 |  | RFD
23 | Extension 765/400/220kV Bhadla-II PS (500MVA ICT- 5th)(Out of which 3 commissioned) | 400/220 | 500 | [6 empty] | MAY-23 |  | RFD
24 | Extn. at Bhadla-II PS (500MVAICT-2nd 3rd 4th and 5th ) at Bikaner (PG) Fategarh-II and Bhadla-II) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | MAY-23 | MAY-23 | RFD | Commissioned 04/23.
25 | Implementation of 220 kV bays for RE generators and2x500MVA 400/220kV ICT at Bikaner II PS | 400/220 | 2x500 | [6 empty] | FEB-24 |  | RFD
26 | Replacement of 1x250 MVA 400/220 kV ICT at 765/400/220 kV Moga (PG) S/s with 1x500 MVA 400/220kV ICT | 400/220 | 250 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUN-23 | RFD | Commissioned 05/23.
27 | Replacement of 1x315 MVA 400/220kV ICT (ICT-1) at 400/220 kV Ludhiana (PG) S/s with 1x500 MVA | 400/220 | 185 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUN-23 | RFD | Commissioned 05/23.
28 | Repl. of 220/132KV 1x50 MVA to 1x160 MVA at Kopili S/stn. | 220/132 | 110 |  | 100 | 90 | 85 | 75 |  | SEP-23 | MAR-23 | RFD | Substation submerged due to bursting of penstock of Kopili HEP.
29 | Salakati- ICT under (NERSS-XI) | 220/132 | 1x100 |  | 0 | 0 | 0 | 0 |  | SEP-23 | MAR-23 | RFD
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | Bakhtiyarpur (GIS) s/s (2x160)) | 220/132 | 2x160 | [6 empty] | JUL-23 |  | RFD
2 | Bakhtiyarpur (GIS) s/s (2x500) | 400/220 | 2x500 |  | 0 | 0 | 0 | 0 |  | JUL-23 | DEC-22 | RFD | NOA issued on 26.11.2019
3 | Dumraon (GIS) s/s (2nd T/F) | 220/132 | 1x160 | [6 empty] | APR-23 |  | RFD
13.: Page 2 of | 11
Report generated through NPP |  | 2023-09-05 20:47
4 | Naubatpur GIS (Balanced) ( 220/132 kV T/Fs of 160 MVA ) | 220/132 | 1x160 | [6 empty] | JUN-23 |  | RFD
5 | Raxaul (New) s/s (T/F I) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | APR-23 | AUG-23 | RFD | Commissioned 03/23 (Late Reported).
6 | Raxaul (New) s/s (T/F II) | 220/132 | 200 | [6 empty] | AUG-23 |  | RFD
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | Patan (Up-gradation of existing 132/33 KV Patan S/s) (2x160) | 220/132 | 2x160 | [6 empty] | OCT-23 |  | RFD
DELHI TRANSCO LIMITED ( DTL )
1 | 220kV GIS Substation at Rajghat (Conversion of Existing AIS Rajghat to New Rajghat GIS Substation) | 220/33 | 300 | [6 empty] | JUN-23 |  | RFD
2 | 220kV GIS Substation at Timarpur | 220/33 | 300 | [6 empty] | SEP-23 |  | RFD
GOA ELECTRICITY DEPARTMENT ( ED-GOA )
1 | Tivim (3rd Trf.) (Aug.) | 220/33 | 63 |  | 100 | 0 | 0 | 0 | 0 | MAY-23 | MAR-17 | RFD | Work in progress.
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | Besan | 220/66 | 320 |  | 100 | 77 | 0 | 54 |  | NOV-23 |  | RFD
2 | Ghiyavad | 220/66 | 320 |  | 0 | 0 | 0 | 0 |  | FEB-24 | MAR-23 | RFD
3 | Kamlapur | 220/66 | 1x160 |  | 100 | 100 | 0 | 88 |  | NOV-23 | MAR-23 | RFD
4 | Mera | 220/66 | 2x160 |  | 100 | 100 | 0 | 77 |  | NOV-23 | MAR-23 | RFD
5 | Metoda | 220/66 | 320 | [6 empty] | NOV-23 |  | RFD
6 | Patkhilori | 220/66 | 320 |  | 100 | 92 | 0 | 69 |  | DEC-23 |  | RFD
7 | Sevaliya | 220/66 | 320 |  | 100 | 100 | 0 | 99 |  | OCT-23 |  | RFD
8 | Ukai | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | JUN-23 | MAR-23 | RFD
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | GIS sector-15 II Gurugram | 220/66 | 2x160 |  | 100 | 96 | 90 | 80 |  | FEB-24 | DEC-23 | RFD | Work in progress
2 | Gurgaon Sector-69 GIS (T/F II) | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  | JUN-23 | JUL-23 | RFD | Commissioned 06/23.
3 | Harfali (AIS) Palwal | 220/66 | 2x100 |  | 100 | 21 | 20 | 2 |  | FEB-24 | JAN-24 | RFD | Work awarded on 23.06.2022.
4 | HSIIDC Rai Sonepat | 220/33 | 2x100 |  | 100 | 60 | 50 | 50 |  | AUG-23 | MAY-23 | RFD | Contract terminated and would be done departmentally
5 | HSIIDC Rai Sonepat | 220/132 | 2x160 |  | 100 | 60 | 50 | 50 |  | AUG-23 | MAY-23 | RFD | Contract terminated and would be done departmentally
6 | Roj-Ka-Meo Palwal | 220/66 | 2x160 |  | 100 | 37 | 54 | 5 |  | JAN-24 | JAN-24 | RFD | Terminated, work to be done departmentally.
7 | Roj-Ka-Meo Palwal | 220/33 | 1x100 |  | 100 | 56 | 54 | 5 |  | JAN-24 | JAN-24 | RFD | Terminated, work to be done departmentally.
13.: Page 3 of | 11
Report generated through NPP |  | 2023-09-05 20:47
8 | Transport Hub Sector-8 IMT Manesar | 220/66 | 2x160 |  | 100 | 62 | 20 | 3 |  | FEB-24 | FEB-24 | RFD | Terminated, work to be done departmentally.
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | 80/100 MVA GIS Sub-Station at Heiling | 220/66 | 1x100 | [6 empty] | SEP-23 |  | RFD
2 | Charor (Additional T/F) | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUN-23 | RFD | Commissioned 05/23.
3 | Charor GIS | 220/132 | 1x100 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 05/23.
4 | Kala Amb S/S | 220/132 | 200 |  | 100 | 5 | 0 | 0 |  | JUN-23 | MAR-23 | RFD | Design of the Substation, Supply of Material and Civil works are in progress.
5 | Kangoo s/s | 220/132 | 200 |  | 0 | 0 | 0 | 0 |  | FEB-24 | MAR-23 | RFD
6 | Mazra (Chamba) s/s | 220/132 | 200 |  | 0 | 0 | 0 | 0 |  | JUN-23 | MAR-23 | RFD | Under planning stage.
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | Latehar GSS | 400/220 | 630 | [6 empty] | JUL-23 |  | RFD
2 | Lohardaga GSS (PGCIL) | 220/132 | 300 |  | 100 | 95 | 90 | 90 |  | JUN-23 | MAR-23 | RFD | Work in Progress.
J&K POWER DEVELOPMENT DEPARTMENT ( JKPDD )
1 | Haripora | 220/33 | 1x160 | [6 empty] | SEP-23 |  | RFD
2 | Nagrota GSS | 220/33 | 1x100 |  | 0 | 0 | 0 | 0 |  | JAN-24 | MAR-23 | RFD
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | Bilagi s/s | 220/110 | 2x100 | [6 empty] | FEB-24 |  | RFD
2 | Ghanagapura | 220/110 | 2x100 | [6 empty] | JAN-24 |  | RFD
3 | Keonics (Electronic City) s/s | 220/66 | 2x150 | [6 empty] | FEB-24 |  | RFD
4 | Kushtagi (3rd T/F) | 220/110 | 1x100 |  | 100 | 100 | 100 | 100 |  | JUN-23 | AUG-23 | RFD | Commissioned 07/23.
5 | Malur s/s | 220/66 | 1x100 | [6 empty] | JAN-24 |  | RFD
6 | Puttenahalli (DG Plant) (Additional 3rd T/F) | 220/66 | 1x150 | [6 empty] | JAN-24 |  | RFD
7 | Somasamudra | 220/110 | 2x100 | [6 empty] | JAN-24 |  | RFD
8 | Srinivasapura s/s | 220/66 | 2x100 | [6 empty] | AUG-23 |  | RFD
9 | Yerandanahalli Replacing 2x100MVA 220/66kV PT by 2x150MVA 220/66kV PT (1st T/F replacement) | 220/66 | 50 |  | 100 | 100 | 100 | 100 |  | MAY-23 | AUG-23 | RFD | Commissioned 07/23.
10 | Yerandanahalli replacing 2x100 MVA 220/66 kv PT by 2x150 MVA 220/66 kv PT(2nd T/F replacement) | 220/66 | 50 | [6 empty] | MAY-23 |  | RFD
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kakkad | 220/110 | 1x100 |  | 0 | 28 | 8 | 0 |  | JUN-23 | NOV-23 | RFD | Work in progress.
2 | Kottayam (T/F - I) | 400/220 | 315 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 05/23.
13.: Page 4 of | 11
Report generated through NPP |  | 2023-09-05 20:47
3 | Kottayam (T/F - II) | 400/220 | 315 |  | 100 | 100 | 100 | 100 |  | APR-23 | SEP-23 | RFD | Commissioned 08/23.
4 | Pathanamthitta | 220/110 | 1x100 |  | 0 | 32 | 8 | 0 |  | JUN-23 | NOV-23 | RFD | Work in progress
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220/33KV GIS at Ulwe node | 220/33 | 2x50 |  | 100 | 100 | 100 | 100 |  | APR-23 | AUG-23 | RFD | Commissioned 07/23.
2 | 220kV Boisar-II Substation(Aug.) (1x 200-150) | 220/132 | 50 | [6 empty] | SEP-23 |  | RFD
3 | 220kV Chalisgaon Substation (1x200) | 220/132 | 200 |  | 100 | 90 | 90 | 80 |  | SEP-23 | MAR-19 | RFD | Work in progress. ICT awaited.
4 | 220kV Nanded City Substation (1x50) | 220/22 | 1x50 | [6 empty] | DEC-23 |  | RFD
5 | 220 kV Walchandnagar Substation(Aug.) (1x200-100) | 220/132 | 100 | [6 empty] | DEC-23 |  | RFD
6 | 400kV Babhaleshwar S/S (3x167) | 400/220 | 500 | [6 empty] | JUL-23 |  | RFD
7 | 400kV Khadka Substation (3x105) | 400/220 | 3x105 | [6 empty] | SEP-23 |  | RFD
8 | 400kV Lonikand Substation (1x50) | 220/22 | 1x50 | [6 empty] | SEP-23 |  | RFD
9 | 400kV Waluj Substation (1x50) | 220/33 | 1x50 | [6 empty] | DEC-23 |  | RFD
10 | Establishment of 220/ 33 kV Naghbid Substation | 220/33 | 125 |  | 100 | 88 | 100 | 99 |  | DEC-23 | MAR-21 | RFD | S/s backcharged on 26.07.2020.
11 | GIS at New Timber Market (Panvel-II) | 220/33 | 2x50 |  | 100 | 90 | 85 | 55 |  | DEC-23 | DEC-23 | RFD | 220kV GIS dispatched from China, reached at Vishakhapattanam on 25.05.2023. Work in progress.
12 | New Koyna (Aug) (3x105 MVA) | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 0/23 (Late Reported).
13 | Pandharpur Substation(Aug.) (1x200-100) | 220/132 | 100 | [6 empty] | DEC-23 |  | RFD
14 | Pardi SS (220/132 2x100 MVA and 220/33 2x50 MVA) | 220/132/33 | 2x100+2x50 |  | 100 | 100 | 98 | 95 |  | DEC-23 | MAR-23 | RFD | All erection work completed & Only Testing work Balance. Associated Uppalwadi- Pardi Line UG cable work is in progress.
15 | Shendra GIS (DMIC) | 220/33 | 2x50 |  | 100 | 84 | 100 | 89 |  | DEC-23 | DEC-23 | RFD | 2X50MVA, 220/33kV Power T/F testing work balance, 33kV GIS scheme testing balance. Minor earthing work balance at 33kV side which is kept on hold due to the cable trench work by M/S AITL (DMIC). All material received
16 | Shendra s/s (2 x 100MVA 220/132kV ICTs) | 220/132 | 2x100 |  | 100 | 100 | 100 | 100 |  | DEC-23 | JUN-23 | RFD | Commissioned 05/23 (Late Reported).
17 | Up-gradation of existing 132 kV Pandharkawda S/S to 220 kV level | 220/132 | 1x100 | [6 empty] | DEC-23 |  | RFD
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
13.: Page 5 of | 11
Report generated through NPP |  | 2023-09-05 20:47
1 | Chichli Addl. T/F | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 05/23.
2 | Indore -SZ 220 kV S/s Replacement of 3x40MVA by 1x160MVA X-mer | 220/132 | 40 |  | 100 | 100 | 100 | 100 |  | DEC-23 | JUL-23 | RFD | Commissioned 06/23.
3 | Itarsi 220 kV S/s replacement of 3x40MVA by 1x160MVA X-mer | 220/132 | 40 |  | 100 | 100 | 100 | 100 |  | DEC-23 | SEP-23 | RFD | Commissioned 08/23.
4 | Jabalpur 220 kV S/s replacement of 3x40MVA by 1x160MVA X-mer | 220/132 | 40 |  | 100 | 100 | 100 | 100 |  | JUN-23 | JUN-23 | RFD | Commissioned 05/23.
5 | Julwaniya S/s (Addl. 160MVA X-mer ) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-23 | JUL-23 | RFD | Commissioned 06/23.
6 | Kirnapur Addl. T/F | 400/132 | 1x100 |  | 100 | 97 | 57 | 57 |  | APR-23 | JAN-23 | RFD | Additional 100MVA X-mer work in progress
7 | Nagda 220 kV S/s Aug. (200-125) | 220/132 | 75 |  | 100 | 70 | 35 | 35 |  | SEP-23 |  | RFD | Work in progress
8 | Nimrani Addl. T/F | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 05/23.
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | 2X160 MVA 220/132kV Turumunga S/s | 220/132 | 2x160 |  | 100 | 90 | 100 | 90 |  | FEB-24 | FEB-24 | RFD
2 | 2X20 MVA 220/33kV Balichandrapur (Palei) S/s | 220/33 | 40 |  | 100 | 80 | 90 | 80 |  | JUN-23 | NOV-23 | RFD
3 | 2X63 MVA 220/33kV Kantabada S/s | 220/33 | 126 |  | 100 | 100 | 100 | 100 |  | MAY-23 | MAY-23 | RFD | Commissioned 04/23.
4 | Bamra S/s (160 MVA T/F - II) | 220/132 | 1x160 |  | 100 | 40 | 50 | 40 |  | JUN-23 | OCT-23 | RFD | one no 160 MVA commissioned on 24.01.23. 2nd 160 MVA will be commissioned on Oct 23
5 | Dhamra S/s (T/F -I) | 220/132 | 160 |  | 100 | 100 | 100 | 100 |  | APR-23 | MAY-23 | RFD | Commissioned 04/23.
6 | Dhamra S/S (T/F - II) | 220/132 | 160 | [6 empty] | APR-23 |  | RFD
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | 220 kV S/S Banga (Addl. 100 MVA T/F) | 220/132 | 1x100 |  |  | 70 | 90 | 80 |  | JAN-24 |  | RFD | Works in progress. T/F reached at site
2 | 220 kV S/S Banur (Aug. of 1x100 MVA T/F with 1x160 MVA T/F) | 220/66 | 60 |  | 0 | 0 | 0 | 0 |  | NOV-23 | MAR-24 | RFD | T/F supply in pipeline. Likely to be commissioned by March-2024
3 | 220 kV S/S Budhlada (1x160 MVA T/F) (Upgraded from 66 KV to 220 KV) | 220/66 | 160 |  | 0 | 50 | 40 | 30 |  | DEC-23 | MAR-24 | RFD | Work in progress. Likely to be commissioned by March-2024
4 | 220 kV S/S G-1. (Aug. of 1x100 MVA T/F with 1x160 MVA) | 220/66 | 60 | [6 empty] | MAY-23 |  | RFD
5 | 220 kV S/S G-1. (Aug. of 2x100 MVA T/F with 2x160 MVA) T/F-II Aug. | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUL-23 | RFD | Commissioned 06/23.
6 | 220 kV S/S Kharar (Aug. of 1x100 MVA T/F with 1x160 MVA T/F) | 220/66 | 60 |  | 0 | 0 | 0 | 0 |  | NOV-23 |  | RFD
7 | 220 kV S/S Naraingarh (Addl. 100 MVA T/F) | 220/66 | 1x100 |  | 100 | 80 | 75 | 65 |  | DEC-23 |  | RFD | Work in progress.
13.: Page 6 of | 11
Report generated through NPP |  | 2023-09-05 20:47
8 | 400 kV S/S Dhanansu (1x315 MVA) | 400/220 | 1x315 |  | 0 | 80 | 85 | 80 |  | SEP-23 | DEC-23 | RFD | Work in progress. (Revised to 500 MVA). Likely to be commissioned by Dec-2023
9 | Dhandari Kalan-2 (Aug. of 2x100 MVA T/F with 2x160 MVA T/F) | 220/66 | 120 |  | 0 | 70 | 60 | 40 |  | JUL-23 | DEC-23 | RFD | 1x100 MVA T/F was augmented to 160 MVA and was commissioned on 09.08.2023 but the same has been damaged on 13.08.2023. Now the T/F will be replaced after receipt of repaired T/F from BHEL or some other T/F in pipeline. The augmentation of other 100 MVA T/F to 160 MVA likely to be completed in Dec.-2023
10 | Gurdaspur (1x100 MVA) (Upgraded from 66 KV to 220 KV) | 220/66 | 1x100 |  | 0 | 50 | 50 | 45 |  | AUG-23 | NOV-23 | RFD | Work in progress. Likely to be completed by Nov.-2023
11 | Nakodar (Aug .of 1x315 MVA T/F 1 with 1x500 MVA T/F) | 400/220 | 185 |  | 100 | 100 | 100 | 100 |  | AUG-23 | JUL-23 | RFD | Commissioned 06/23.
12 | Ropar ( New 1x500 MVA ) 1st T/F | 400/220 | 500 |  | 0 | 80 | 90 | 80 |  | NOV-23 | MAR-24 | RFD | Work in progress. Likely to be commissioned by March-2024
13 | Ropar (New 1x500 MVA ) 2nd T/F | 400/220 | 500 |  | 0 | 80 | 90 | 80 |  | DEC-23 | MAR-24 | RFD | Work in progress. Likely to be commissioned by March-2024
14 | Udhoke (Addl. T/F) | 220/66 | 1x100 |  |  | 90 | 90 | 90 |  | JUN-23 | SEP-23 | RFD | Work in progress. Likely to be completed by Sept.-2023
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED ( RVPNL )
1 | Banar GIS (Distt. Jodhpur) | 220/132 | 200 |  | 100 | 36 | 41 | 6 |  | AUG-23 | DEC-23 | RFD | work under progress
2 | Reodar (Distt.Sirohi) | 220/132 | 1x160 |  | 100 | 80 | 70 | 70 |  | AUG-23 | AUG-23 | RFD | Work order issued on 26.05.2021 to M/s Sumaja , New Delhi. Work under progress. Work stopped since. 9.6.23 Work order issued on 26.05.2021 to M/s Sumaja , New Delhi. Work under progress.
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | Ariyalur S/S | 765/400 | 2x1500 |  | 100 | 95 | 95 | 95 |  | SEP-23 | JUN-23 | RFD | Work under progress.
2 | Erode (T/F - II) | 230/110 | 100 |  | 100 | 100 | 100 | 100 |  | JUN-23 | AUG-23 | RFD | Commissioned 07/23.
3 | Karuppur | 230/110 | 200 |  | 100 | 100 | 100 | 98 |  | APR-23 | MAR-24 | RFD | All work completed and testing under progress
4 | Maraimalai Nagar | 230/110 | 2x100 |  | 100 | 95 | 95 | 90 |  | JUL-23 | MAR-24 | RFD | Testing work completed.Ready for back charging
13.: Page 7 of | 11
Report generated through NPP |  | 2023-09-05 20:47
5 | Nanguneri | 230/110 | 2x100 |  | 95 | 0 | 0 | 0 |  | FEB-24 | MAR-24 | RFD | Structure and Equipment erection tender under evaluation.
6 | North Chennai Pooling Station (GIS) (3X1500) | 765/400 | 3x1500 |  | 100 | 98 | 98 | 98 |  | AUG-23 | MAR-24 | RFD | All erection work testing completed
7 | Selvapuram | 230/110 | 2x100 |  | 100 | 80 | 95 | 95 |  | JUL-23 | MAR-24 | RFD | slow progress of work by the contractor.
8 | Thiruvanmiyur | 230/110 | 200 |  | 100 | 90 | 85 | 85 |  | APR-23 | MAR-24 | RFD | Relay testing under progress
9 | Vellalaviduthi (2X200) | 400/110 | 2x200 |  | 100 | 98 | 100 | 100 |  | SEP-23 | MAR-23 | RFD | Work under progress.
10 | Vellalaviduthi (2X315 ) | 400/230 | 2x315 |  | 100 | 95 | 95 | 90 |  | SEP-23 | MAR-23 | RFD | Work under progress.
11 | Vembakkam | 230/110 | 2x100 |  | 100 | 90 | 90 | 60 |  | FEB-24 | MAR-24 | RFD | work in progress. Structure material tender awarded.
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | Aug. at Jammalamadugu | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | SEP-23 | MAY-23 | RFD | Commissioned 04/23.
2 | Aug.at Kalpaka -4th (500MVA) | 400/220 | 500 |  | 100 | 50 | 25 | 15 |  | MAY-21 | DEC-23 | RFD | Work in Progress.
3 | Dharmavaram | 220/132 | 2x100 |  | 100 | 90 | 100 | 100 |  | JUN-23 | SEP-23 | RFD | Works are under progress.
4 | Hindupur (ICT 3rd ) | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  | JUN-23 | JUN-23 | RFD | Commissioned 05/23.
5 | Hindupur (ICT 4th ) | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  |  | SEP-23 | RFD | SAS integration works are under progress.
6 | Pampanur Tanda (GEC-I) | 220/132 | 2x160 |  | 100 | 100 | 100 | 90 |  | SEP-23 |  | RFD | Substation charged on 18.05.2023 without PTRs.
7 | Penukonda(GEC-I) | 220/132 | 2x160 |  | 100 | 80 | 90 | 80 |  | JUN-23 | SEP-23 | RFD | Works under Progress.
8 | Piduguralla (Upgradation) | 220/132 | 160 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUL-23 | RFD | Commissioned 06/23.
9 | Tiruvuru | 220/132 | 3x100 |  | 100 | 70 | 80 | 80 |  | JUN-23 | OCT-23 | RFD | Work in Progress.
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | Ammavaripet | 220/132 | 200 |  | 100 | 100 | 95 | 95 |  | APR-23 | JUL-23 | RFD | Works under progress.
2 | Bhupalapally (KTPP) SS (2x160) | 220/132 | 2x160 | [6 empty] | JUL-23 |  | RFD
3 | Bhupalapally (KTPP) SS (2x500 ) | 400/220 | 2x500 |  | 100 | 75 | 80 | 80 |  | JUL-23 | JUL-23 | RFD
4 | Chandanvally (T/F II) | 220/132 | 1x100 |  | 100 | 95 | 95 | 95 |  | JUN-23 | DEC-23 | RFD | 2nd PTR works to be taken up and commissioned in June-2023
5 | Choutuppal S/S (T/F - II) | 400/220 | 500 |  | 100 | 100 | 95 | 90 |  | SEP-23 |  | RFD | 2nd PTR works to be taken up and commissioned in Sep-2023
6 | Devannapet LI SS (3x40 2x25 MVA) | 220/11 | 170 |  | 100 | 100 | 100 | 100 |  | MAY-23 | JUL-23 | RFD | Commissioned 06/23.
7 | Husnabad | 220/132 | 200 |  | 100 | 100 | 90 | 90 |  | APR-23 | AUG-23 | RFD | Works under progress. This SS is conventional and not GIS SS
8 | KMTP SS (2x160) | 220/132 | 2x160 |  | 100 | 35 | 47 | 0 |  | FEB-24 | FEB-24 | RFD | Works under progress.
13.: Page 8 of | 11
Report generated through NPP |  | 2023-09-05 20:47
9 | Yacharam Thanda LI SS (3x40 2x25 MVA) | 220/11 | 170 |  | 100 | 70 | 90 | 60 |  | JAN-24 | DEC-23 | RFD | Works are under progress
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | 220/132/33 KV S/s DataganjBadaun (New) T/F- I and II | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | MAY-23 | SEP-23 | RFD | Commissioned 08/23.
2 | 220 kV S/s Morta Ghaziabad (New) T/F- II and III | 220/33 | 1x120 |  | 100 | 100 | 100 | 100 |  | AUG-23 | SEP-23 | RFD | Commissioned 08/23.
3 | Anandnagar (Gorakhpur) S/s | 220/132 | 2x160 |  | 100 | 95 | 100 | 95 |  | JUL-23 | SEP-23 | RFD | 160MVA T/F-I & II Likely to be charged by September-2023.
4 | Babina S/s Jhansi (T/F II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-23 | MAY-23 | RFD | Commissioned 04/23.
5 | Balrampur S/s (T/F II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | SEP-23 | MAY-23 | RFD | Commissioned 04/23.
6 | Bhadohi S/S(T/F - I) | 220/132 | 200 |  | 100 | 88 | 98 | 87 |  | MAY-23 | SEP-23 | RFD | 200 MVA T/F-I : Likely to be charged by 30.09.2023.
7 | Bhadohi s/s (T/F - II) | 220/132 | 200 |  | 100 | 88 | 98 | 87 |  | SEP-23 |  | RFD | 200 MVA T/F-II Likely to be charged in October, 2023
8 | Deoband (Saharanpur) S/s | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | MAY-23 | MAY-23 | RFD | Commissioned 04/23.
9 | Faridpur (Bareilly) - T/F-II | 220/132 | 1x100 |  | 100 | 88 | 92 | 90 |  | APR-23 | SEP-23 | RFD | T/F-I : Commissioned in Sep, 22 T/F-II : Emulsifire and Centrifusing work is pending, showcause notice served to firm.
10 | Farrukhabad S/s (T/F II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-23 | MAY-23 | RFD | Commissioned 04/23.
11 | Jalpura S/s | 220/132 | 2x160 |  | 100 | 90 | 95 | 78 |  | AUG-23 | SEP-23 | RFD | Work in progress.
12 | Kanduni S/s | 220/132 | 2x160 |  | 100 | 93 | 97 | 92 |  | NOV-23 |  | RFD | T/F-I : Likely to be charged in September,2023 T/F-II: Repaired transformer will be available in the month of Nov'23 and likely to be charged in Jan'24.
13 | Khatauli S/s (T/F-II) | 220/132 | 1x160 |  | 100 | 79 | 95 | 80 |  | JUN-23 | SEP-23 | RFD | 160 MVA T/F-II : Available at site, likely to be energised in Sept-23.
14 | Khorabar S/s | 220/132 | 180 |  | 100 | 89 | 95 | 55 |  | NOV-23 |  | RFD | Work in progress.
15 | Kidwainagar S/s Kanpur (T/F III) | 220/33 | 60 |  | 100 | 100 | 100 | 100 |  | APR-23 | JUN-23 | RFD | Commissioned 05/23.
16 | Kirawali S/S | 220/132 | 2x100 |  | 100 | 92 | 95 | 88 |  | JUL-23 | SEP-23 | RFD | Work in progress.
17 | Knowledge Park-5 S/s | 220/132 | 2x160 |  | 100 | 82 | 73 | 51 |  | AUG-23 | SEP-23 | RFD | Work in progress.
18 | Maharajganj S/s | 220/132 | 1x160 |  | 100 | 86 | 95 | 92 |  | MAY-23 | SEP-23 | RFD | 160 MVA T/F-I : Back charged on 08.06.2023 and will be charged at 220 kV voltage level in Sept-2023.
19 | Modipuram-II (T/F II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | SEP-23 | JUL-23 | RFD | Commissioned 06/23.
20 | Moth-II Jhansi T/F-I | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUL-23 | MAY-23 | RFD | Commissioned 04/23.
13.: Page 9 of | 11
Report generated through NPP |  | 2023-09-05 20:47
21 | Rasra S/s (T/F II) | 400/220 | 500 |  | 100 | 96 | 95 | 91 |  | OCT-23 |  | RFD | Work in progress. T/F-II Likely to be charged in Oct,2023.
22 | Sahupuri S/S | 400/220 | 2x500 |  | 100 | 95 | 95 | 90 |  | OCT-23 | DEC-23 | RFD | Likely to be back charged by 08.09.2023 . 500MVA T/F-II Not alloted.
23 | Sangipur S/s Pratapgarh (T/F II) | 220/132 | 1x160 |  | 100 | 83 | 90 | 88 |  | MAY-23 | DEC-23 | RFD | 160 MVA T/F-II: To be diverted from Sahupuri 220 in Dec'2023
24 | Shamli S/s (T/F -II) | 400/220 | 500 |  | 100 | 99 | 95 | 90 |  | AUG-23 | DEC-23 | RFD | 500MVA T/F-II Likely to be charged in Dec,2023
25 | YEIDA Sec-18 S/s | 220/33 | 180 |  | 100 | 98 | 99 | 98 |  | MAY-23 | SEP-23 | RFD | Work in progress.
26 | YEIDA Sec-24 S/s | 220/132 | 2x160 |  | 100 | 63 | 78 | 58 |  | DEC-23 |  | RFD | Work in progress.
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
1 | Durgapur 400KV SS Tr. Aug. | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  | DEC-23 | SEP-23 | RFD | Commissioned 08/23.
2 | Durgapur AB Zone 220 KV GIS | 220/132 | 2x160 |  | 0 | 0 | 0 | 0 | 0 | OCT-23 | MAR-19 | RFD
3 | Falakata 220 KV GIS | 220/132 | 2x160 | [6 empty] | JAN-24 |  | RFD
4 | Food Park 220 KV GIS | 220/33 | 2x50 | [6 empty] | JAN-24 |  | RFD
5 | Gokarna 400KV SS Tr. Aug. | 400/220 | 1x315 |  | 0 | 0 | 0 | 0 |  | APR-23 | MAR-23 | RFD
6 | Jangalpur GIS | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | MAY-23 | AUG-23 | RFD | Commissioned 07/23.
7 | Mangalpur 220/33 kV GIS | 220/132 | 2x100 | [6 empty] | OCT-23 |  | RFD
8 | New Town AA-IIC GIS | 220/132 | 2x160 |  | 100 | 98 | 97 | 90 |  | OCT-23 | DEC-22 | RFD
9 | New Town AA-IIC (GIS) | 220/132 | 2x100 | [6 empty] | OCT-23 |  | RFD
PRIVATE SECTOR
ADANI POWER LTD. ( APL )
1 | 2x500MVA (400/230 kV) Karur Pooling Station | 400/230 | 2x500 | [6 empty] | JUL-23 |  | RFD
2 | Warangal (New) S/S with 2X1500 MVA transformers and 2X240 MVAR bus reactors. | 765/400 | 2x1500 | [6 empty] | APR-23 |  | RFD
G R Infraprojects Limited ( GRINFRA )
1 | Establishment of 400/220 kV 3X500 MVA at Pachora SEZ PP with 420 kV (125 MVAR) bus reactor | 400/220 | 1500 | [6 empty] | NOV-23 |  | RFD
Indigrid Ltd ( INDIGRID )
13.: Page 10 of | 11
Report generated through NPP |  | 2023-09-05 20:47
1 | Establishment of 2x500MVA (400/220kV) near Kallam PS | 400/220 | 2x500 |  | 100 | 75 | 98 | 25 |  | DEC-23 | OCT-23 | RFD | Due to onset of timely monsoon, we are facing challenges in civil work. We have lost around 50% time in last one month. We are working with 100% resources on ground to complete our daily and monthly targets. We are positive with our monthly planning and likely to make up in upcoming month-on-month progress.
ReNew Transmission Ventures Private Limited ( RTVPL )
1 | Aug. Koppal (PS) | 400/220 | 2x500 |  | 100 | 46 | 88 | 19 |  | JAN-24 | DEC-23 | RFD
2 | Gadag (PS) 2X500 MVA) | 400/220 | 2x500 |  | 100 | 48 | 86 | 10 |  | OCT-23 | SEP-23 | RFD
3 | Koppal (PS) | 400/220 | 1500 |  | 100 | 99 | 100 | 100 |  | NOV-23 | JUN-23 | RFD
STERLITE GRID LTD. ( SGL )
1 | Nangalbibra S/S | 220/132 | 2x160 | [6 empty] | DEC-23 |  | RFD
13.: Page 11 of | 11
Report generated through NPP |  | 2023-09-05 20:47