## rfd_sub_station
REPORT INDICATING STATUS OF CONSTRUCTION OF SUB STATIONS (220 kV & ABOVE) IN RFD PROGRAMME DURING 2024-25
As on 31-AUG-2024
Sl No | Name of Sub Stations | Voltage Ratio (kV/kV) | Capacity (No.xMVA) | Date of Award | Cummulative progress till date |  |  |  |  | Commissioning |  | Tag Type | Remarks
[5 empty] | Land Acquired (%) | Civil works completed (%) | Materials / Equipments Received (%) | Materials / Equipments erected (%) | Capacity Tested/ Commissio ned (MVA) | Original | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | 220KV GIS Infrastructure at MTPS | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  | MAY-24 | SEP-24 | RFD | Commissioned 08/24.
2 | 220KV GIS Infrastructure at RTPS | 400/220 | 2x315 |  | 100 | 99 | 100 | 98 |  | MAY-24 | SEP-24 | RFD | Scheduled target - Jan24, Revised Target - July'24. Progress of the work suffered due to severe heat wave and delay in availability of OEM personnel during testing procedures and pre-commissioning checks.
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | 1x1500MVA 765/400 4th ICT Bikaner (PG) | 765/400 | 1x1500 |  | 100 | 45 | 55 | 0 |  | DEC-24 | SEP-24 | RFD
2 | 1X1500 MVA 765/400 KV (5th) ICT at Fatehgarh-II PS (Rajasthan (8.1 GW) under Phase II- Part- A1) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | AUG-24 | AUG-24 | RFD | Commissioned 07/24.
3 | 1X1500MVA 765/400KV ICT-1 at Fategarh-3 (New Section) Phase-III Part E1 | 765/400 | 1x1500 |  | 100 | 15 | 5 | 0 |  | FEB-25 |  | RFD
4 | 1X1500MVA 765/400KV ICT-1 at Kurnool (III) (AP) -Part-A and Part-B | 765/400 | 1500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
5 | 1X1500 MVA 765/400KV ICT-1 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1x1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
6 | 1X1500 MVA 765/400KV ICT-1 at Navsari along with associated ICT Bays at 765 kV and 400kV end | 765/400 | 1x1500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
7 | 1X1500 MVA 765/400KV ICT-1 at Navsari along with associated ICT Bays at 765 kV and 400kV end(Part B) | 765/400 | 1x1500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
8 | 1x1500 MVA 765/400kV ICT-1 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | 1x1500 |  | 100 | 60 | 35 | 15 |  | DEC-24 |  | RFD
9 | 1X1500MVA 765/400KV ICT-2 at Kurnool (III) (AP) -Part-A and Part-B | 765/400 | 1500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
10 | 1X1500 MVA 765/400KV ICT-2 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
11 | 1x1500 MVA 765/400kV ICT-2 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | 1x1500 |  | 100 | 60 | 35 | 15 |  | DEC-24 |  | RFD
13.: Page 1 of | 15
Report generated through NPP |  | 2024-09-11 14:34
12 | 1X1500 MVA 765/400KV ICT-3 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1x1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
13 | 1X1500MVA 765/400KV ICT (3rd) at Pune (PG) SS | 765/400 | 1x1500 |  | 100 | 25 | 5 | 0 |  | OCT-24 |  | RFD
14 | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-A) | 765/400 | 1x1500 |  | 100 | 45 | 30 | 0 |  | OCT-24 |  | RFD
15 | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-B) | 765/400 | 1x1500 |  | 100 | 45 | 30 | 0 |  | FEB-25 |  | RFD
16 | 1X1500MVA 765/400KV ICT (4th) at 765/400KV Bhadla-II PS (Phase -II Part -BI) | 765/400 | 1x1500 |  | 100 | 90 | 85 | 85 |  | JUN-24 | AUG-24 | RFD | Transformer diverted to other site where RE generation was coming up.
17 | 1X1500MVA 765/400 KV ICT-4th at Raigarh Kotra Section-B) | 765/400 | 1x1500 |  | 100 | 45 | 30 | 0 |  | FEB-25 |  | RFD
18 | 1x1500MVA ICT at Padghe (GIS) Trans. Network Expansion in Gujarat to increase ATC from ISTS Part B | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUL-24 | RFD | Commissioned 06/24.
19 | 1X200 MVA 220/132 kV (4th) ICT at Ara POWERGRID S/S under ER Expansion Scheme-XXXVI (ERES-XXXVI) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | OCT-24 | SEP-24 | RFD | Commissioned 08/24.
20 | 1X500 MVA 400/220 kV (2nd) ICT at Shikrapur (PG) GIS under Western Region Expansion Scheme-XXVI | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | SEP-24 | SEP-24 | RFD | Commissioned 08/24.
21 | 1X500 MVA 400/220KV 3rd ICT Jind SS | 400/220 | 500 |  | 100 | 75 | 60 | 35 |  | JUL-24 | SEP-24 | RFD
22 | 1x500 MVA 400/220KV ICT-1 along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 |  | 100 | 95 | 60 | 25 |  | MAR-25 |  | RFD
23 | 1X500 MVA 400/220 KV ICT-1 along with associated ICT Bays at 765/400 kV Raipur Pool S/S | 400/220 | 500 |  | 100 | 40 | 40 | 5 |  | DEC-24 |  | RFD
24 | 1X500 MVA 400/220 kV ICT-1 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
25 | 1x500 MVA 400/220kV ICT-1 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
26 | 1X500 MVA 400/220 KV ICT-1at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
27 | 1X500MVA 400/220KV ICT-1 at Shikrapur (PG) GIS | 400/220 | 500 |  | 100 | 90 | 55 | 25 |  | SEP-24 |  | RFD
28 | 1x500 MVA 400/220KV ICT-2 along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 |  | 100 | 95 | 60 | 25 |  | MAR-25 |  | RFD
13.: Page 2 of | 15
Report generated through NPP |  | 2024-09-11 14:34
29 | 1X500 MVA 400/220 KV ICT-2 along with associated ICT Bays at 765/400 kV Raipur Pool S/S | 400/220 | 500 |  | 100 | 40 | 40 | 5 |  | DEC-24 |  | RFD
30 | 1X500 MVA, 400/220 kV ICT-2 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUL-24 | AUG-24 | RFD | Commissioned 07/24.
31 | 1x500 MVA 400/220kV ICT-2 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
32 | 1X500 MVA 400/220 KV ICT-2 at Navsari along with associated ICT Bays at 400KV and 220KV end Part B | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
33 | 1X500 MVA 400/220 KV ICT-2 at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 | [6 empty] | DEC-24 |  | RFD
34 | 1X500 MVA 400/220KV ICT-3 at Bikaner II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | AUG-24 | SEP-24 | RFD | Commissioned 08/24.
35 | 1x500 MVA 400/220kV ICT-3 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
36 | 1X500 MVA 400/220 KV ICT-3 at Navsari along with associated ICT Bays at 400KV and 220KV end Part B | 400/200 | 500 | [8 empty] | RFD
37 | 1X500 MVA 400/220 KV ICT-3 at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
38 | 1X500 MVA 400/220 KV ICT (3 rd) at Bahadurgarh along with Extension | 400/220 | 500 |  | 100 | 65 | 45 | 10 |  | SEP-24 |  | RFD
39 | 1x500 MVA 400/220 kV ICT 3rd at Bikaner PS to Cater N-1 Contigency at Bikaner PS (Rajasthan) | 400/220 | 500 |  | 100 | 65 | 65 | 0 |  | JUN-24 | AUG-24 | RFD | Order for transformer was delayed due to very high cost.
40 | 1X500 MVA 400/220KV ICT-4 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 65 | 50 | 20 |  | DEC-24 |  | RFD
41 | 1x500 MVA 400/220kV ICT-4 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
42 | 1X500 MVA 400/220KV ICT (4th) Mysore s/s (Karnataka) | 400/220 | 500 |  | 100 | 80 | 70 | 40 |  | JUN-24 | SEP-24 | RFD | Work affected due to delay in supply of GIB & Bushings from M/s. Hyosung.
43 | 1X500 MVA 400/220KV ICT-5 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 65 | 50 | 20 |  | DEC-24 |  | RFD
44 | 1x500 MVA 400/220kV ICT-5 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
13.: Page 3 of | 15
Report generated through NPP |  | 2024-09-11 14:34
45 | 1x500 MVA 400/220kV ICT-6 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
46 | 1X500 MVA 400/220 KV ICT (6th) at Fatehgarh II to cater to the N-1 Contingency Requirement (Raj.) | 400/220 | 500 |  | 100 | 45 | 55 | 0 |  | AUG-24 | SEP-24 | RFD
47 | 1x500 MVA 400/220kV ICT-7 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | MAR-25 |  | RFD
48 | 1x500 MVA 400/220kV ICT-8 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | MAR-25 |  | RFD
49 | 1X500 MVA 400/220KV ICT-8th at Bikaner-II PS ( ICT (3rd)-PBTSL) | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | DEC-24 |  | RFD
50 | 1x500MVA 400/220kV ICT at Jind | 400/220 | 500 | [6 empty] | MAR-24 |  | RFD
51 | 1X500 MVA 400/230KV ICT (4th) at Aasur s/s | 400/230 | 500 | [6 empty] | JUN-24 |  | RFD
52 | 1X500MVA 765/400 ICT-1 at KPS-2 New S/S | 765/400 | 1x1500 | [6 empty] | DEC-24 |  | RFD
53 | 1X500MVA 765/400 ICT-1 at KPS-3 New S/S | 765/400 | 1x1500 |  | 100 | 25 | 20 | 0 |  | FEB-25 |  | RFD
54 | 1X500MVA 765/400 ICT-2 at KPS-2 New S/S | 765/400 | 1x1500 | [6 empty] | JAN-25 |  | RFD
55 | 1X500MVA 765/400 ICT-2 at KPS-3 New S/S | 765/400 | 1x1500 |  | 100 | 25 | 20 | 0 |  | MAR-25 |  | RFD
56 | 1X500MVA ICT-1 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | 500 |  | 100 | 95 | 50 | 50 |  | OCT-24 |  | RFD
57 | 1X500MVA ICT-2 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | 500 |  | 100 | 95 | 50 | 50 |  | OCT-24 |  | RFD
58 | 1X500MVA ICT(4TH) at ARASUR s/s (Aug. of T/F Capacity by 500 MVA ICT(4th) at Arasur) | 400/230 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUL-24 | RFD | Commissioned 06/24.
59 | 765/400kV 1x1500MVA Transformer (5th) at Bhadla-2 PS (Rajasthan (20GW) under Phase-III Part J) | 765/400 | 1x1500 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
60 | Augmentaion of 1x500MVA 400/220kV ICT at Raipur Pool s/s along with associated ICT Bays (200kV-GIS) | 400/220 | 500 |  | 100 | 40 | 40 | 5 |  | DEC-24 |  | RFD
61 | Implementation of 220 kV bays for RE generators and2x500MVA 400/220kV ICT at Bikaner II PS | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | FEB-24 | APR-24 | RFD | Commissioned 03/24. (RTM To SPV (PBTSL))
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | Bakhtiyarpur (GIS) s/s (2x160)) | 220/132 | 2x160 | [6 empty] | OCT-24 | MAY-24 | RFD
2 | Bakhtiyarpur (GIS) s/s (2x500) | 400/220 | 2x500 |  | 0 | 0 | 0 | 0 |  | OCT-24 | DEC-22 | RFD | NOA issued on 26.11.2019
13.: Page 4 of | 15
Report generated through NPP |  | 2024-09-11 14:34
3 | Thakurganj GSS | 220/132 | 2x160 | [6 empty] | FEB-25 |  | RFD
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | Dhardehi (Upgradation of existing 220/132 KV) | 400/220 | 630 | [6 empty] | MAR-25 |  | RFD
2 | Kurud (Dhamtari) (Capacity Augmentation i.e. additional 315 MVA) | 400/220 | 1x315 | [6 empty] | SEP-24 |  | RFD
3 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUL-24 | RFD | Commissioned 06/24.
4 | Rajim ( Upgradation of existing 132/33 KV S/s) | 220/132 | 2x160 | [6 empty] | FEB-25 |  | RFD
5 | Semariya | 220/132/33 | 2x160 | [6 empty] | DEC-24 |  | RFD
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | 220 kV Besan | 220/66 | 320 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
2 | 220kV Ghodasar | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
3 | 220kV Sisrana | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
4 | 400kV Kalawad GIS | 400/220 | 1x1500 | [6 empty] | MAR-25 |  | RFD
5 | Patkhilori | 220/66 | 320 |  | 100 | 92 | 0 | 40 |  | MAR-25 | JAN-24 | RFD
6 | Radhanesda s/s | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
7 | Ukai | 400/220 | 500 |  | 100 | 100 | 100 | 20 |  | MAY-24 | MAR-23 | RFD
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | 220 kV GIS S/S Roj-ka-Meo Nuh (2x100MVA 220/33KV T/F-I) | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | SEP-24 |  | RFD
2 | Chikenwas Hisar (2x100 MVA 220/33 kV T/F) | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
3 | Faridabad (2x100MVA 220/33 kV T/F) 220kV GIS S/S Sector-89 | 220/33 | 200 |  | 0 | 0 | 0 | 0 |  | AUG-24 |  | RFD
4 | GIS Sector-15 II Gurugram | 220/66 | 2x160 |  | 100 | 96 | 90 | 80 |  | JUN-24 | DEC-23 | RFD | Work in progress
5 | GIS S/S Pocket B IMT Kharkhoda Sonipat (2x100MVA 220/33kV T/F-I) | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
6 | GIS S/S Roj-ka-Meo Nuh (2x160MVA 220/66kV ) | 220/66 | 2x160 |  | 0 | 0 | 0 | 0 |  | SEP-24 |  | RFD
7 | GIS Sub Station Pocket A IMT Kharkhoda Sonipat (2x100MVA 220/33kV T/F) | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
8 | GIS Transport Hub Sector-8 IMT Manesar (2X160 MVA 220/66) | 220/66 | 2x160 |  | 100 | 62 | 20 | 3 |  | JUN-24 | FEB-24 | RFD | Terminated, work to be done departmentally.
9 | Gurugram(2x100MVA 220/33KV T/F) GIS S/S Sector-99 | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
10 | Harfali (Palwal) (2x100MVA220/66 kV T/F) | 220/66 | 2x100 |  | 100 | 21 | 20 | 2 |  | JUN-24 | JAN-24 | RFD | Work awarded on 23.06.2022.
13.: Page 5 of | 15
Report generated through NPP |  | 2024-09-11 14:34
11 | HSIIDC Rai Sonepat 220/132 kV T/F-II | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
12 | HSIIDC Rai Sonepat (220/33 kV 100 MVA T/F-II)(charged on 02-05-2024 however late reported by HVPNL) | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  |  | AUG-24 | RFD | Commissioned 07/24.
13 | HSIIDC Rai Sonepat 220/33 kV T/F-I | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
14 | Ramana-Ramani (Karnal) ( 2x100MVA 220/33KV T/F-II) | 220/33 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
15 | Ramana-Ramani (Karnal) (2x160MVA 220/132kV T/F-I) | 220/132 | 2x160 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
16 | Sadhaura Ambala (1x100 MVA 220/33 Kv T/F-I) | 220/33 | 1x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
17 | Sadhaura Ambala (2x100 MVA 220/66 kV T/F) | 220/66 | 2x100 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | 220/132/33 kV AIS at Andheri (Kala Amb) District Sirmaur H.P. | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
2 | 220/132kV Kangoo S/S | 220/132 | 200 |  | 0 | 0 | 0 | 0 |  | SEP-24 | MAR-23 | RFD
3 | 80/100 MVA GIS Sub-Station at Heiling | 220/66 | 1x100 | [6 empty] | JUL-24 |  | RFD
4 | Tahliwal by S/C LILO of 220 kV Bhakhra- Jamalpur line GIS S/S at Tahliwal | 220/132 | 1x100 | [6 empty] | MAR-25 |  | RFD
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | Jainamore GSS | 220/132 | 3x100 |  | 100 | 90 | 100 | 90 |  | JUL-24 | MAR-23 | RFD | Work in Progress.
2 | Latehar GSS | 400/220 | 630 | [6 empty] | AUG-24 |  | RFD
3 | Lohardaga GSS (PGCIL) | 220/132 | 300 |  | 100 | 95 | 90 | 90 |  | MAY-24 | MAR-23 | RFD | Work in Progress.
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | Bilagi s/s | 220/110 | 2x100 |  | 100 | 55 | 100 | 100 |  | OCT-24 |  | RFD | Work under progress
2 | GIS Chikkaballapura Establishing 2x100MVA 220/66 kV s/s at Chikkaballapura I/A | 220/66 | 2x100 |  | 100 | 95 | 100 | 95 |  | NOV-24 |  | RFD | Work under progress
3 | Hangal Establishing 2x100 MVA 220/66 KV Power T/F at Hangal GEC Phase-2 | 220/66 | 2x100 |  | 100 | 80 | 90 | 90 |  | FEB-25 |  | RFD | Work under progress
4 | Keonics (Electronic City) s/s | 220/66 | 2x150 |  | 100 | 98 | 100 | 100 |  | MAY-24 |  | RFD | Work under progress
5 | Santhpur Establishing 220kV 2X100MVA Aurad (B) taluka and Bidar Dist. (GEC PHASE II) | 220/110 | 2x100 |  | 100 | 75 | 100 | 80 |  | AUG-24 |  | RFD | Work under progress
6 | Somasamudra | 220/110 | 2x100 |  | 100 | 95 | 100 | 100 |  | AUG-24 |  | RFD | PC testing under progress
7 | Yelburga Establishing 2x100MVA and 110MVA 220/110/11kV S/S | 220/110 | 2x100 |  | 100 | 70 | 100 | 95 |  | JAN-25 |  | RFD | Work under progress
13.: Page 6 of | 15
Report generated through NPP |  | 2024-09-11 14:34
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kakkad | 220/110 | 1x100 |  | 100 | 65 | 70 | 20 |  | JUN-24 | DEC-24 | RFD | Civil and erection works are in progress.
2 | Pathanamthitta | 220/110 | 1x100 |  | 100 | 68 | 70 | 25 |  | JUN-24 | DEC-24 | RFD | Civil and erection works are in progress.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220/22 kV Mankoli GIS | 220/22 | 1x100 |  | 100 | 42 | 40 | 0 |  | DEC-24 | DEC-24 | RFD | Work in progress .
2 | 220/33KV GIS at New Timber Market (Panvel-II) | 220/33 | 50 |  | 100 | 100 | 95 | 85 |  | MAY-24 | SEP-24 | RFD | 50 MVA, T/F-I commissioned on 28.06.2024. Work of 2nd transformer is in progress.
3 | 220/33kV New Timber Market GIS (Panvel -II )(50 MVA T/F) | 220/33 | 50 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUL-24 | RFD | Commissioned 06/24.
4 | 220kV Chalisgaon Substation(1x200 MVA Additional T/F) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
5 | 220kV Jambhul | 220/22 | 50 | [8 empty] | RFD
6 | 220kV Jambhul (Additional T/F) | 220/22 | 1x50 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUN-24 | RFD | Commissioned 05/24.
7 | 220 kV Tembhurni substation (replacement of 25 MVA by 100 MVA T/F) | 220/33 | 25 |  | 100 | 100 | 100 | 100 |  | DEC-24 | SEP-24 | RFD | Commissioned 08/24.
8 | 220kV Walchandnagar substation (replacement of 100 MVA by 200 MVA T/F) | 220/132 | 100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
9 | 400kV Khadka Substation (3x105) | 400/220 | 1x315 | [6 empty] | JUN-24 |  | RFD
10 | 400kV Lonikand Substation (1x50) | 220/22 | 1x50 | [6 empty] | JUN-24 |  | RFD
11 | 400kV Padghe | 400/220 | 185 | [6 empty] | DEC-24 |  | RFD
12 | 400kV Thapti Tanda | 400/220 | 500 | [6 empty] | MAR-25 |  | RFD
13 | Bhigwan | 220/33 | 25 | [6 empty] | MAR-25 |  | RFD
14 | Five Star MIDC | 220/33 | 1x50 |  | 100 | 100 | 100 | 100 |  | DEC-24 |  | RFD | T/F commissioned on 31.12.2018.
15 | Georai | 220/33 | 50 | [6 empty] | MAR-25 |  | RFD
16 | Jeur | 220/132 | 1x100 | [6 empty] | MAR-25 |  | RFD
17 | Kolshet | 220/22 | 50 | [6 empty] | MAR-25 |  | RFD
18 | Pardi SS (220/132 2x100 MVA and 220/33 2x50 MVA) | 220/132/33 | 2x100+2x50 |  | 100 | 100 | 98 | 95 |  | JUN-24 | JUL-24 | RFD | Substation work completed. Associated line work in progress.
13.: Page 7 of | 15
Report generated through NPP |  | 2024-09-11 14:34
19 | Shendra GIS (DMIC) | 220/33 | 2x50 |  | 100 | 86 | 100 | 90 |  | JUN-24 | SEP-24 | RFD | 2X50MVA, 220/33kV Power T/F testing work balance, 33kV GIS scheme testing balance. Minor earthing work balance at 33kV side which is kept on hold due to the cable trench work by M/S AITL (DMIC). All material received
20 | Temghar Replacement T/F (1x (100-50) | 220/22 | 1x50 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD | Repeated at sr no 76, to be deleted.
21 | Tilawani | 220/33 | 1x100 | [6 empty] | MAR-25 |  | RFD
22 | Vairag | 220/33 | 50 | [6 empty] | MAR-25 |  | RFD
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
1 | 220/132/33kV Ajaygarh S/s (TBCB) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | DEC-24 | JUL-24 | RFD | Commissioned 06/24.
2 | Bairagarh (Bhopal) 220 KV S/s Addl. 1x160MVA X-mer | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUN-24 | RFD | Commissioned 05/24.
3 | Barwana 220kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 | [6 empty] | MAR-25 |  | RFD
4 | Bhopal 400kv s/s replacement of 315MVA by 500MVA X-mer | 400/220 | 185 | [6 empty] | MAR-25 |  | RFD
5 | Construction of 220/132/33kV substation Bisonikala | 220/132 | 2x160 |  | 100 | 4 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
6 | Construction of 220/132 kV substation at Bargawan | 220/132 | 2x160 |  | 100 | 100 | 60 | 60 |  | DEC-24 |  | RFD | TBCB work
7 | Construction of 220/132kV substation at Khargone | 220/132 | 2x160 | [6 empty] | JAN-25 |  | RFD
8 | Construction of 220/33kV substation at Shahpur | 220/33 | 1x100 |  | 100 | 16 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
9 | Construction of 400/220kV GIS substation at Mandideep (2x160 MVA T/F-I) | 220/132 | 2x160 | [6 empty] | JAN-25 |  | RFD
10 | Construction of 400/220kV GIS substation at Mandideep (2X500 MVA T/F) | 400/220 | 2x500 |  | 100 | 31 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
11 | Construction of Begamganj SS (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | AUG-24 | RFD | Commissioned 04/24 (Late Reported).
12 | Installation for addll. T/F at Indore-II Jetpura Supply-MR-10 and Gandhi NagarMetro Rail s/s Indore | 220/132 | 1x160 |  | 100 | 100 | 67 | 67 |  | DEC-24 |  | RFD | work under progress
13 | Julwaniya 400 KV S/s addl.500 MVA X-mer | 400/220 | 500 |  | 100 | 32 | 0 | 0 |  | MAR-25 |  | RFD | work under progress
14 | Mandsaur 400KV S/s additional 500MVA 400/220KV | 400/220 | 500 | [6 empty] | MAR-25 |  | RFD
15 | Nepanagar 220 kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 | [6 empty] | DEC-24 |  | RFD
13.: Page 8 of | 15
Report generated through NPP |  | 2024-09-11 14:34
16 | Pritampura (sector III) 220kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 | [6 empty] | MAR-25 |  | RFD
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | 220/132kV GIS Balianta GIS | 220/132 | 2x160 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD | May be deleted repeat project
2 | 220/33 KV Grid S/S Dasapalla | 220/33 | 40 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD | May be deleted repeat project
3 | 220/33 KV GSS Balichandrapur Palei | 220/33 | 20 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
4 | 2X20 MVA 220/33kV Balichandrapur (Palei) S/s | 220/33 | 20 | [6 empty] | APR-24 |  | RFD
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | 220 kV S/S Banur (Aug. of 1x100 MVA T/F with 1x160 MVA T/F) | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
2 | 220 kV S/S Budhlada (1x160 MVA T/F) (Upgraded from 66 KV to 220 KV) | 220/66 | 160 |  | 100 | 60 | 70 | 60 |  | JUL-24 | NOV-24 | RFD | Work in progress, T/f has been reached at site (But work pending due to line work.) Tr. Line work will be completed by Nov.24
3 | 220 kV S/S Gurdaspur (1x100 MVA) (Upgraded from 132 KV to 220 KV) | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
4 | 400 kV S/S Ropar (1x500 MVA ) 1st T/F | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
5 | 400 kV S/S Ropar (1x500 MVA ) 2nd T/F | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
6 | Additional 1X160 MVA 220/66kV T/F at 220 kV S/Stn. Sherpur | 220/66 | 1x160 |  | 100 | 70 | 90 | 70 |  | DEC-24 | DEC-24 | RFD | Work in progress.
7 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Badhshahpur | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUN-24 | RFD | Commissioned 05/24.
8 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Majitha (N-1) | 220/66 | 1x100 |  | 100 | 70 | 60 | 60 |  | MAY-24 | OCT-24 | RFD | Work in progress, likely to be completed by 31-10-24.
9 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Naraingarh (N-1) | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
10 | Addl. 100MVA 220/66kV T/F at 220kV S/Stn Badni Kalan | 220/66 | 1x100 |  | 100 | 60 | 60 | 60 |  | MAR-25 | MAR-25 | RFD | Work in progress.
11 | Addl. 100MVA 220/66kV T/F at 220kV S/Stn Maur | 220/22 | 1x100 |  | 100 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work not started yet
12 | Addl 100 MVA at 220 KV S/S Goraya | 220/66 | 1x100 |  | 100 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work not started yet,
13 | Aug. 100 MVA 220/66 T/F to 160 MVA 220/66 T/F at 220 KV S/S Ghulal | 220/66 | 60 |  | 100 | 0 | 0 | 0 |  | SEP-24 | NOV-24 | RFD | Work not started yet,
14 | Aug 100 to 160 MVA at 220 KV S/S Bassi Pathana | 220/66 | 60 |  | 100 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work not started yet
15 | Aug 100 to 160 MVA at 220 KV S/S Kartarpur | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUL-24 | RFD | Commissioned 06/24.
13.: Page 9 of | 15
Report generated through NPP |  | 2024-09-11 14:34
16 | Aug. 100 to 160 MVA at 220 KV S/S Mandi Gobindgarh G-2 | 220/66 | 60 |  | 0 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD
17 | Aug 100 to 160 MVA at 220 KV S/S Rajpura | 220/66 | 60 |  | 100 | 0 | 0 | 0 |  | MAR-25 |  | RFD | Work not started yet,
18 | Aug. of 100MVA 220/66kV T/F to 160MVA 220/66kV T/F at 220kV S/Stn Bajakhana | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUN-24 | RFD | Commissioned 05/24.
19 | Aug. of 100 MVA T/F to 160 MVA T/F at 220 kV SS Mandi Gobindgarh G-3 | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | SEP-24 | AUG-24 | RFD | Commissioned 07/24.
20 | Aug of 100 MVA to 160 MVA at GNDTP Bathinda | 220/66 | 60 |  | 100 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work not started yet,
21 | Dhandari Kalan-2 (Aug. of 2x100 MVA T/F with 2x160 MVA T/F) | 220/66 | 60 |  | 100 | 75 | 60 | 40 |  | SEP-24 | NOV-24 | RFD | Work in progress. T/f placed, but comissioning pending due to Shutdown issues.
22 | Upgradation of 66 kV Sherpur to 220kV by installing 1X160 MVA 220/66kV T/F at 220 kV S/Stn. Sherpur | 220/66 | 1x160 |  | 100 | 70 | 90 | 70 |  | JUN-24 |  | RFD | Work in progress (Minor changes has been made in Civil Drawing) likely to be completed by Oct'24.
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED ( RVPNL )
1 | 220 KV GSS Chandan (Upg.) | 220/132 | 1x160 |  | 0 | 0 | 0 | 0 |  | OCT-24 |  | RFD | Work Order to M/s Tarun Electricals bkn on 04.10.23. Work to start soon
2 | 220 kV GSS Rayla(Upg.) | 220/132 | 1x160 |  | 100 | 15 | 10 | 3 |  | JUN-24 | NOV-24 | RFD | Work Order to M/s S.K. Engineers, Vijay Nagar on 06.10.23. Civil work under progress.
3 | Banar GIS (Distt. Jodhpur) | 220/132 | 200 |  | 100 | 90 | 90 | 90 |  | JUN-24 | AUG-24 | RFD | work under progress Transformer received at site on 29.07.24..Erection work for transformer completed.
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | Avadi 230KV SS | 230/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
2 | Ganesh Nagar 230KV SS | 230/33 | 2x100 | [6 empty] | JUN-24 |  | RFD
3 | Hosur 230 KV SS -Enhancement 2x100 1X160 to 3160 MVA | 230/110 | 120 | [6 empty] | MAR-25 |  | RFD
4 | Kalivelampatty | 230/110 | 200 |  | 100 | 100 | 40 | 30 |  | NOV-24 | JUN-24 | RFD | Work under progress
5 | Karuppur (T/F- II) | 230/110 | 1x100 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUL-24 | RFD | Commissioned 06/24.
6 | Korattur (GIS) | 400/230/110 | 1x1400 |  | 100 | 90 | 90 | 90 |  | JUN-24 | MAR-24 | RFD | Work under progress
7 | K.R.Thoppur 400/230-110 KV SS -Additional 400/110 1x200MVA T/F | 400/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
8 | K.R.Thoppur 400/230-110 KV SS -Addl. 400/230KV 1x500MVA T/F | 400/230 | 500 | [6 empty] | JUN-24 |  | RFD
13.: Page 10 of | 15
Report generated through NPP |  | 2024-09-11 14:34
9 | Mambakkam 230KV SS | 230/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
10 | Maraimalai Nagar | 230/110 | 2x100 |  | 100 | 95 | 95 | 95 |  | SEP-24 | MAR-24 | RFD | Testing work completed.Ready for back charging
11 | Nallur 230/110 KV SS 2X100 MVA - New | 230/110 | 2x100 | [6 empty] | MAR-25 |  | RFD
12 | Nanguneri | 230/110 | 2x100 |  | 100 | 90 | 50 | 0 |  | SEP-24 | MAR-24 | RFD | Work under progress
13 | Panjetti 230KV SS | 230/110 | 3x100 | [6 empty] | JUN-24 |  | RFD
14 | Sathumadurai | 230/110 | 2x160 |  | 100 | 60 | 0 | 0 |  | MAR-25 | JUN-24 | RFD | Work under progress
15 | Selvapuram 230/110 kV SS (T/F-I) | 230/110 | 100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | AUG-24 | RFD | Commissioned 07/24.
16 | Selvapuram 230/110 kV SS (T/F-II) | 230/110 | 1x100 | [6 empty] | JUN-24 |  | RFD
17 | Thervoikandigai 400KV SS | 400/230 | 1x315 | [6 empty] | JUN-24 |  | RFD
18 | Thiruvalam 400/230 KV SS- Capacity enhancement from 2x315 to 2x315 + 1x500 MVA | 400/230 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
19 | Thiruvanmiyur | 230/33 | 200 |  | 100 | 90 | 85 | 85 |  | DEC-24 | NOV-23 | RFD | Relay testing under progress
20 | Vellalaviduthi (400/110 kV T/F-II) | 400/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
21 | Vellalaviduthi (T/F-I) (400/110 (2X200 MVA) | 400/110 | 2x100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | MAY-24 | RFD | Commissioned 04/24.
22 | Vembakkam | 230/110 | 3x100 |  | 100 | 90 | 90 | 60 |  | JUN-24 | MAR-24 | RFD | Work under progress
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | Atchuthapuram GIS | 220/132/33 | 2x100 |  | 100 | 75 | 65 | 65 |  | JUN-24 | JUN-24 | RFD | Works are under progress.
2 | Aug.at Kalpaka -4th (500MVA) | 400/220 | 500 |  | 100 | 60 | 40 | 30 |  | MAY-21 | JUN-24 | RFD | Work in Progress.
3 | Augmentation of 1no. 500MVA ICT at 400/220kV SS Kalapaka | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD
4 | Augmentation of ICTs from 1x160 1x100MVA to 2x160 1x100MVA at Rachagunneri | 400/220 | 1x160 |  | 0 | 0 | 0 | 0 |  | DEC-24 |  | RFD
5 | Augmentation of ICTs from 2x315 1x500MVA to 2x3152x500MVA at 400/220KV SS Maradam | 400/220 | 500 |  | 100 | 50 | 40 | 35 |  | AUG-24 | JAN-25 | RFD
6 | Augmentation of ICTs from 2x315MVA to 2x315 1500MVA at 400/220KV SS Narnoor | 400/220 | 500 |  | 100 | 70 | 70 | 60 |  | MAY-24 | AUG-24 | RFD | work under progress
7 | Augmentation of ICTs from 2x315MVA to 2x315 1x500MVA SS Rachagunneri | 400/220 | 500 |  | 100 | 40 | 35 | 20 |  | DEC-24 | JAN-25 | RFD | work under progress
8 | Bethamcherla | 220/132/33 | 2x160 |  | 100 | 95 | 95 | 90 |  | JUN-24 | JUN-24 | RFD | work under progress
9 | Chandanada | 220/132/33 | 4x100 |  | 100 | 35 | 30 | 0 |  | DEC-24 | JAN-25 | RFD | work under progress
10 | Dharmavaram | 220/132 | 2x100 |  | 100 | 80 | 95 | 90 |  | JUN-24 | JUL-24 | RFD | Works are under progress.
13.: Page 11 of | 15
Report generated through NPP |  | 2024-09-11 14:34
11 | Gudivada (2x500 MVA 2x100 MVA) | 400/132 | 2x500 |  | 100 | 50 | 40 | 30 |  | MAR-25 | APR-25 | RFD | Works under progress
12 | Inavolu S/s (Thallayapalem GIS) | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Works are under progress.
13 | Pampanur Tanda (GEC-I) (160 MVA T/F-II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 90 |  | JUN-24 | AUG-24 | RFD | Substation charged on 18.05.2023. PTR-1 Charged on 08.12.2023
14 | Penukonda (Gorantla) (GEC-I) | 220/132 | 1x160 | [6 empty] | JUN-24 |  | RFD
15 | Penukonda (Gorantla) (GEC-I) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
16 | Punganur | 220/132/33 | 2x100 |  | 100 | 80 | 95 | 90 |  | JUN-24 | JUN-24 | RFD | work under progress
17 | Racherla | 220/132 | 2x160 |  | 100 | 40 | 80 | 70 |  | MAY-24 |  | RFD | Work short closed due to pending SS Court case. Balance works Tenders to be called for.
18 | Tiruvuru | 220/132 | 3x100 |  | 100 | 70 | 80 | 80 |  | JUL-24 | JUL-24 | RFD | Work in Progress.
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | Ammavaripet (T/F-II) | 220/132 | 2x100 |  | 100 | 100 | 70 | 70 |  | AUG-24 | AUG-24 | RFD | One commissioned in March-24 and remaining in FY 2024-25
2 | Bhoopalapally (KTPP) S/S 400/220/ 132 kV | 220/132 | 2x160 | [6 empty] | JUN-24 |  | RFD
3 | Bhoopalapally (KTPP) SS 400/220/ 132 kV | 400/220 | 2x500 | [6 empty] | JUN-24 |  | RFD
4 | Husnabad s/s | 220/132 | 2x100 |  | 0 | 100 | 100 | 95 |  | AUG-24 | AUG-24 | RFD | Works under progress.
5 | Kakatiya Mega Textile Park (KMTP) SS (2x160) | 220/132 | 2x160 |  | 0 | 75 | 90 | 60 |  | DEC-24 | DEC-24 | RFD | Works under progress.
6 | Yacharam Thanda LI SS (3x40 2x25 MVA) | 220/11 | 170 |  | 100 | 85 | 95 | 90 |  | OCT-24 | OCT-24 | RFD | Works are under progress. Balance works to be completed in co-ordination with I&CADD.
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | 220 kV S/s Darshan Nagar Ayodhya (New) T/F-I | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
2 | 220 kV S/s Kanduni Sitapur (New) T/F-II | 220/132 | 2x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
3 | 220 kV S/s Khorabar Gorakhpur (New) T/F-II | 220/33 | 60 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
4 | 220 kV S/s Knowledge Park-5 Gr. Noida GB Nagar (New) T/F-II | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUL-24 | RFD | Commissioned 06/24.
5 | 220 kV S/s Metro Depot Gr. Noida GB Nagar (New) T/F-I and T/F-II | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
6 | 400 kV S/s Dahi Chaoki Unnao (Capacity Aug.) (315) MVA (500-315) | 400/220 | 1x315 |  | 0 | 0 | 0 | 0 |  |  |  | RFD
7 | 400 kV S/s Dahi Chaoki Unnao (Capacity Aug.) (500-315) | 400/220 | 185 |  | 100 | 100 | 100 | 100 |  |  | MAY-24 | RFD | Commissioned 04/24.
13.: Page 12 of | 15
Report generated through NPP |  | 2024-09-11 14:34
8 | 400 kV S/s Machhalishahar Jaunpur (New) T/F-III | 400/220 | 315 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
9 | Badaun Road | 220/33 | 120 |  | 100 | 87 | 97 | 35 |  | JUL-24 | OCT-24 | RFD | Work in progress.T/F-I & T/F-II are likely to be charged by 31 Oct, 2024.
10 | Dahi Chaoki (Capacity Aug) | 400/220 | 500 |  | 100 | 0 | 0 | 0 |  | OCT-24 |  | RFD | (500-315) charged on dt. 23.04.2024
11 | Faridpur (Bareilly) - T/F-II | 220/132 | 1x100 |  | 100 | 95 | 96 | 50 |  | JUN-24 | OCT-24 | RFD | T/F diverted from Mainpuri S/s reached at site. Civil work is in progress, after then erection work will be carried out.
12 | Jewar (Extn.) | 220/132 | 2x160 |  | 100 | 76 | 90 | 60 |  | JUN-24 | OCT-24 | RFD | Both T/F have been received and erection work in progress.
13 | Khorabar S/s (T/F-III) | 220/33 | 60 |  | 100 | 95 | 100 | 90 |  | JUL-24 | OCT-24 | RFD | T/F available at site. Firm is not available for completion of 33kV side pending work.
14 | Moradabad (Capacity Aug.) | 400/220 | 315 |  | 100 | 0 | 0 | 0 |  | FEB-25 |  | RFD | Trnansformer is to be diverted from 400kV S/s Panki.
15 | Sahupuri T/F-II | 400/220 | 500 |  | 100 | 99 | 99 | 95 |  | JUL-24 | SEP-24 | RFD | Transformer available at site. Erection work to be start. Erection team of M/s G.E. are not coming for start of erection work of T/F-II.
16 | Sector-62 Noida | 220/132 | 2x160 |  | 100 | 41 | 65 | 10 |  | OCT-24 |  | RFD | Fund issue with Noida Authority. Commissioning and erection work will be possible after resolve the fund issue.
17 | Shamli S/s (T/F -II) | 400/220 | 500 |  | 100 | 100 | 0 | 0 |  | AUG-24 | OCT-24 | RFD | Transformer failed in internal testing by M/s Siemens. To be supplied after conducting successful test. Commissioning and erection work will be possible after receiving the T/F-II.
18 | Trans Ganga city | 220/33 | 120 |  | 100 | 49 | 20 | 9 |  | NOV-24 |  | RFD | Both T/F received. Erection work of structure in progress.
19 | Yeida Sec-24 T/F-II | 220/132 | 1x160 |  | 100 | 100 | 0 | 0 |  | DEC-24 |  | RFD | There are lack of fund issues with YEIDA. 160 MVA T/F-II. Will be allotted after fund transfered to UPPTCL.
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
13.: Page 13 of | 15
Report generated through NPP |  | 2024-09-11 14:34
1 | Durgapur (T/F-I) AB Zone 220 KV GIS | 220/132 | 1x160 |  | 100 | 76 | 90 | 76 |  | JUL-24 | SEP-24 | RFD | Delay in supply of Control Relay Panel due to non-availability of some imported items.
2 | Durgapur (T/F-II) AB Zone 220 KV GIS | 220/132 | 1x160 |  | 100 | 76 | 90 | 76 |  | JUL-24 | SEP-24 | RFD | Delay in supply of Control Relay Panel due to non-availability of some imported items.
3 | Falakata 220 KV GIS | 220/132/33 | 420 |  | 100 | 25 | 74 | 1 |  | SEP-24 | DEC-24 | RFD | Delay in supply of Control Relay Panel due to non-availability of some imported items.
4 | Food Park (T/F-I) 220 KV GIS | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
5 | Food Park (T/F-II) 220 KV GIS | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 09/24.
6 | Khanakul 220 KV GIS | 220/33 | 1x100 |  | 100 | 18 | 21 | 0 |  | MAR-25 | MAR-25 | RFD
7 | Raghunathpur 220 KV GIS (Upg) | 220/132 | 320 |  | 100 | 72 | 62 | 69 |  | MAR-25 | MAR-25 | RFD
8 | Satgachhia 400KV GIS (Upg) | 400/220 | 1000 |  | 100 | 47 | 81 | 8 |  | JAN-25 | JAN-25 | RFD
9 | Shamli T/F-II | 400/220 | 500 | [6 empty] | AUG-24 |  | RFD
PRIVATE SECTOR
ADANI POWER LIMITED ( APL )
1 | Narendra New (upgradation to its rated voltage of 765 Kv along with 4x1500 MVA T/F) | 765/400 | 6000 | [6 empty] | DEC-24 |  | RFD
Apraava Energy Pvt. Ltd. ( APRAAVA )
1 | 5x500MVA 400/220kV pooling station at Fatehgarh-4 | 400/220 | 2500 | [6 empty] | FEB-25 |  | RFD
Megha Engineering & Infrastructures Limited ( MEGHA )
1 | Khavda PS1 Augmentation | 765/400 | 6000 | [6 empty] | JAN-25 |  | RFD
PATRAN TRANSMISSION COMPANY LIMITED ( PATRANTCL )
1 | 1x500 MVA 400/220KV ICT-I along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 | [6 empty] | MAR-25 |  | RFD
POWERICA Ltd. ( POWERICA )
1 | 1x 500MVA 765/400kV ICT-1 at Fatehgarh-3 (New Section) | 765/400 | 1x1500 | [6 empty] | FEB-25 |  | RFD
ReNew Transmission Ventures Private Limited ( RTVPL )
1 | 400/220kV Gadag PS (2X500 MVA) | 400/220 | 2x500 |  | 100 | 48 | 86 | 10 |  | MAY-24 | SEP-23 | RFD
2 | Augmentation of 400/220 KV Gadag S/S with 3x500 MVA ICT | 400/220 | 1500 | [6 empty] | MAY-24 |  | RFD
STERLITE GRID LTD. ( SGL )
1 | Beawar 2x1500 MVA 765/400 kV S/S | 765/400 | 2x1500 | [6 empty] | MAR-25 |  | RFD
13.: Page 14 of | 15
Report generated through NPP |  | 2024-09-11 14:34
2 | Nangalbibra 220/132 kV (2x160MVA) | 220/132 | 2x160 | [6 empty] | JUN-24 |  | RFD
3 | Vapi (Ambheti) (Vapi-II) (VNLTL-TBCB) | 400/220 | 2x500 |  | 0 | 0 | 0 | 0 |  | MAY-24 | MAR-23 | RFD
4 | Xeldem (Goa) S/S (G-TTPL - TBCB) | 400/220 | 2x500 |  | 100 | 0 | 0 | 0 |  | JUN-24 | DEC-22 | RFD | 1.Delay due to occurrence of Force Majeure (FM) event i.e. outbreak of COVID-19 and this FM event has been intimated to all LTTCs 2. The construction work will be started after getting Conversion Sanad order from Revenue authorities. The construction License from Gram Panchayat, Molem has been received on 13 Nov 2020. 3.The progress is suffered due to petition filed by Goa Foundation in Central Empowered Committee (CEC) constituted by Supreme court and High Court of Mumbai and Goa
13.: Page 15 of | 15
Report generated through NPP |  | 2024-09-11 14:34