## rfd_sub_station
REPORT INDICATING STATUS OF CONSTRUCTION OF SUB STATIONS (220 kV & ABOVE) IN RFD PROGRAMME DURING 2024-25
As on 30-NOV-2024
Sl No | Name of Sub Stations | Voltage Ratio (kV/kV) | Capacity (No.xMVA) | Date of Award | Cummulative progress till date |  |  |  |  | Commissioning |  | Tag Type | Remarks
[5 empty] | Land Acquired (%) | Civil works completed (%) | Materials / Equipments Received (%) | Materials / Equipments erected (%) | Capacity Tested/ Commissio ned (MVA) | Original | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. | 13. | 14.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | 220KV GIS Infrastructure at MTPS | 400/220 | 1x315 |  | 100 | 100 | 100 | 100 |  | MAY-24 | SEP-24 | RFD | Commissioned 08/24.
2 | 220 kV GIS Infrastructure at RTPS | 400/220 | 2x315 |  | 100 | 100 | 100 | 100 |  | MAY-24 | DEC-24 | RFD | Commissioned 11/24.
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | 1x1500MVA 765/400 4th ICT Bikaner (PG) | 765/400 | 1x1500 |  | 100 | 45 | 55 | 0 |  | DEC-24 | SEP-24 | RFD
2 | 1X1500 MVA 765/400 KV (5th) ICT at Fatehgarh-II PS (Rajasthan (8.1 GW) under Phase II- Part- A1) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | AUG-24 | AUG-24 | RFD | Commissioned 07/24.
3 | 1X1500MVA 765/400KV ICT-1 at Fategarh-3 (New Section) Phase-III Part E1 | 765/400 | 1x1500 |  | 100 | 15 | 5 | 0 |  | FEB-25 |  | RFD
4 | 1X1500MVA 765/400KV ICT-1 at Kurnool (III) (AP) -Part-A and Part-B | 765/400 | 1500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
5 | 1X1500 MVA 765/400KV ICT-1 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1x1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
6 | 1X1500 MVA 765/400KV ICT-1 at Navsari along with associated ICT Bays at 765 kV and 400kV end | 765/400 | 1x1500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
7 | 1X1500 MVA 765/400KV ICT-1 at Navsari along with associated ICT Bays at 765 kV and 400kV end(Part B) | 765/400 | 1x1500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
8 | 1x1500 MVA 765/400kV ICT-1 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | DEC-24 | NOV-24 | RFD | Commissioned 10/24.
9 | 1X1500MVA 765/400KV ICT-2 at Kurnool (III) (AP) -Part-A and Part-B | 765/400 | 1500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
10 | 1X1500 MVA 765/400KV ICT-2 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
11 | 1x1500 MVA 765/400kV ICT-2 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | DEC-24 | NOV-24 | RFD | Commissioned 10/24.
12 | 1X1500 MVA 765/400KV ICT-3 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) | 765/400 | 1x1500 |  | 100 | 85 | 85 | 55 |  | JUL-24 | SEP-24 | RFD
13 | 1X1500MVA 765/400KV ICT (3rd) at Pune (PG) SS | 765/400 | 1x1500 |  | 100 | 25 | 5 | 0 |  | OCT-24 |  | RFD
14 | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-A) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | OCT-24 | NOV-24 | RFD | Commissioned 10/24.
13.: Page 1 of | 14
Report generated through NPP |  | 2024-12-17 15:30
15 | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-B) | 765/400 | 1x1500 |  | 100 | 45 | 30 | 0 |  | FEB-25 |  | RFD
16 | 1X1500 MVA 765/400 kV ICT (4th) at 765/400 kV Bhadla-II PS under (Phase -II Part -BI) | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | OCT-24 | RFD | Commissioned 09/24.
17 | 1X1500MVA 765/400 KV ICT-4th at Raigarh Kotra Section-B) | 765/400 | 1x1500 |  | 100 | 45 | 30 | 0 |  | FEB-25 |  | RFD
18 | 1x1500MVA ICT at Padghe (GIS) Trans. Network Expansion in Gujarat to increase ATC from ISTS Part B | 765/400 | 1x1500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUL-24 | RFD | Commissioned 06/24.
19 | 1X200 MVA 220/132 kV (4th) ICT at Ara POWERGRID S/S under ER Expansion Scheme-XXXVI (ERES-XXXVI) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | OCT-24 | SEP-24 | RFD | Commissioned 08/24.
20 | 1X500 MVA, 400/220 kV (1st) ICT at Raipur Pool S/s ( WRES XXVIII (Project: WRES-XXVIII & WRES-XXIX) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | DEC-24 | OCT-24 | RFD | Commissioned 09/24.
21 | 1X500 MVA, 400/220 kV (1st) ICT at Shikrapur (PG) GIS under Western Region Expansion Scheme-XXVI | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | SEP-24 | OCT-24 | RFD | Commissioned 09/24.
22 | 1X500 MVA, 400/220 kV (2nd) ICT at Raipur Pool S/s (WRES XXVIII (Project: WRES-XXVIII & WRES-XXIX) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | DEC-24 | OCT-24 | RFD | Commissioned 09/24.
23 | 1X500 MVA 400/220 kV (2nd) ICT at Shikrapur (PG) GIS under Western Region Expansion Scheme-XXVI | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | SEP-24 | SEP-24 | RFD | Commissioned 08/24.
24 | 1X500 MVA, 400/220 kV (4th) ICT at Mysore under Aug. of transformation capacity at Mysore | 400/220 | 500 |  | 100 | 80 | 70 | 40 |  | JUN-24 | SEP-24 | RFD | Work affected due to delay in supply of GIB & Bushings from M/s. Hyosung.
25 | 1x500 MVA 400/220KV ICT-1 along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 |  | 100 | 95 | 60 | 25 |  | MAR-25 |  | RFD
26 | 1X500 MVA 400/220 kV ICT-1 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
27 | 1x500 MVA 400/220kV ICT-1 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
28 | 1X500 MVA 400/220 KV ICT-1at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
29 | 1x500 MVA 400/220KV ICT-2 along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 |  | 100 | 95 | 60 | 25 |  | MAR-25 |  | RFD
13.: Page 2 of | 14
Report generated through NPP |  | 2024-12-17 15:30
30 | 1X500 MVA, 400/220 kV ICT-2 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUL-24 | AUG-24 | RFD | Commissioned 07/24.
31 | 1x500 MVA 400/220kV ICT-2 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
32 | 1X500 MVA 400/220 KV ICT-2 at Navsari along with associated ICT Bays at 400KV and 220KV end Part B | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
33 | 1X500 MVA 400/220 KV ICT-2 at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 | [6 empty] | DEC-24 |  | RFD
34 | 1X500 MVA 400/220 kV ICT-3 at Bikaner II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | AUG-24 | DEC-24 | RFD | Commissioned 11/24.
35 | 1x500 MVA 400/220kV ICT-3 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | JAN-25 |  | RFD
36 | 1X500 MVA 400/220 KV ICT-3 at Navsari along with associated ICT Bays at 400KV and 220KV end Part B | 400/200 | 500 | [8 empty] | RFD
37 | 1X500 MVA 400/220 KV ICT-3 at Navsari along with associated ICT Bays at 400KV and 220KV end (Part B) | 400/220 | 500 |  | 100 | 90 | 85 | 60 |  | DEC-24 |  | RFD
38 | 1x500 MVA 400/220 kV ICT 3rd at Bikaner PS to Cater N-1 Contigency at Bikaner PS (Rajasthan) | 400/220 | 500 |  | 100 | 65 | 65 | 0 |  | JUN-24 | AUG-24 | RFD | Order for transformer was delayed due to very high cost.
39 | 1X500 MVA 400/220KV ICT-4 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 65 | 50 | 20 |  | DEC-24 |  | RFD
40 | 1x500 MVA 400/220kV ICT-4 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
41 | 1X500 MVA 400/220KV ICT-5 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | 500 |  | 100 | 65 | 50 | 20 |  | DEC-24 |  | RFD
42 | 1x500 MVA 400/220kV ICT-5 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
43 | 1x500 MVA 400/220kV ICT-6 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | FEB-25 |  | RFD
44 | 1X500 MVA 400/220 KV ICT (6th) at Fatehgarh II to cater to the N-1 Contingency Requirement (Raj.) | 400/220 | 500 |  | 100 | 45 | 55 | 0 |  | AUG-24 | SEP-24 | RFD
45 | 1x500 MVA 400/220kV ICT-7 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | MAR-25 |  | RFD
46 | 1x500 MVA 400/220kV ICT-8 at Kurnool PS (Part-A and Part-B | 400/220 | 500 |  | 100 | 25 | 25 | 0 |  | MAR-25 |  | RFD
13.: Page 3 of | 14
Report generated through NPP |  | 2024-12-17 15:30
47 | 1X500 MVA 400/220KV ICT-8th at Bikaner-II PS ( ICT (3rd)-PBTSL) | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | DEC-24 |  | RFD
48 | 1X500 MVA 400/230KV ICT (4th) at Aasur s/s | 400/230 | 500 | [6 empty] | JUN-24 |  | RFD
49 | 1X500MVA 765/400 ICT-1 at KPS-2 New S/S | 765/400 | 1x1500 | [6 empty] | DEC-24 |  | RFD
50 | 1X500MVA 765/400 ICT-1 at KPS-3 New S/S | 765/400 | 1x1500 |  | 100 | 25 | 20 | 0 |  | FEB-25 |  | RFD
51 | 1X500MVA 765/400 ICT-2 at KPS-2 New S/S | 765/400 | 1x1500 | [6 empty] | JAN-25 |  | RFD
52 | 1X500MVA 765/400 ICT-2 at KPS-3 New S/S | 765/400 | 1x1500 |  | 100 | 25 | 20 | 0 |  | MAR-25 |  | RFD
53 | 1X500MVA ICT-1 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | OCT-24 | NOV-24 | RFD | Commissioned 10/24.
54 | 1X500MVA ICT-2 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | OCT-24 | NOV-24 | RFD | Commissioned 10/24.
55 | 1x500 MVA ICT (3rd ) at 400/220 kV Bahadurgarh (PG) S/s under Aug. of ISTS of HVPNL TS | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | SEP-24 | OCT-24 | RFD | Commissioned 09/24.
56 | 1X500MVA ICT(4TH) at ARASUR s/s (Aug. of T/F Capacity by 500 MVA ICT(4th) at Arasur) | 400/230 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUL-24 | RFD | Commissioned 06/24.
57 | 765/400kV 1x1500MVA Transformer (5th) at Bhadla-2 PS (Rajasthan (20GW) under Phase-III Part J) | 765/400 | 1x1500 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
58 | Aug. by 1x500 MVA 400/220 kV ICT (3rd )at 400/220 kV Jind (PG) S/s under Aug. of ISTS for HVPNL TS | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUL-24 | OCT-24 | RFD | Commissioned 09/24.
59 | Augmentaion of 1x500MVA 400/220kV ICT at Raipur Pool s/s along with associated ICT Bays (200kV-GIS) | 400/220 | 500 |  | 100 | 40 | 40 | 5 |  | DEC-24 |  | RFD
60 | Implementation of 220 kV bays for RE generators and2x500MVA 400/220kV ICT at Bikaner II PS | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | FEB-24 | APR-24 | RFD | Commissioned 03/24. (RTM To SPV (PBTSL))
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | Bakhtiyarpur (GIS) s/s (2x160)) | 220/132 | 2x160 | [6 empty] | OCT-24 | MAY-24 | RFD
2 | Bakhtiyarpur (GIS) s/s (2x500) | 400/220 | 2x500 |  | 0 | 0 | 0 | 0 |  | OCT-24 | DEC-22 | RFD | NOA issued on 26.11.2019
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | Dhardehi (Upgradation of existing 220/132 KV) | 400/220 | 630 | [6 empty] | MAR-25 |  | RFD
13.: Page 4 of | 14
Report generated through NPP |  | 2024-12-17 15:30
2 | Kurud (Dhamtari) (Capacity Augmentation i.e. additional 315 MVA) | 400/220 | 1x315 | [6 empty] | SEP-24 |  | RFD
3 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUL-24 | RFD | Commissioned 06/24.
4 | Rajim ( Upgradation of existing 132/33 KV S/s) | 220/132 | 2x160 | [6 empty] | FEB-25 |  | RFD
5 | Semariya | 220/132/33 | 2x160 | [6 empty] | DEC-24 |  | RFD
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | 220 kV Besan | 220/66 | 320 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
2 | 220kV Ghodasar | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
3 | 220kV Sisrana | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
4 | 400kV Kalawad GIS | 400/220 | 1x1500 | [6 empty] | MAR-25 |  | RFD
5 | Patkhilori | 220/66 | 320 |  | 100 | 92 | 0 | 40 |  | MAR-25 | JAN-24 | RFD
6 | Radhanesda s/s | 220/66 | 2x160 | [6 empty] | MAR-25 |  | RFD
7 | Ukai | 400/220 | 500 |  | 100 | 100 | 100 | 20 |  | MAY-24 | MAR-23 | RFD
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | 220 kV GIS Transport Hub, Sector-8 IMT Manesar | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | OCT-24 | RFD | Commissioned 09/24.
2 | Chikenwas Hisar (2x100 MVA 220/33 kV T/F) | 220/33 | 2x100 |  | 100 | 21 | 15 | 6 |  | MAR-25 | MAR-25 | RFD | Work in progress.
3 | Faridabad (2x100MVA 220/33 kV T/F) 220kV GIS S/S Sector-89 | 220/33 | 200 |  | 100 | 70 | 90 | 35 |  | AUG-24 | DEC-24 | RFD | Work in progress.
4 | GIS Sector-15 II Gurugram | 220/66 | 2x160 |  | 100 | 96 | 95 | 95 |  | JUN-24 | OCT-24 | RFD | Work in progress
5 | GIS S/S Pocket B IMT Kharkhoda Sonipat (2x100MVA 220/33kV T/F-I) | 220/33 | 2x100 |  | 100 | 52 | 25 | 22 |  | MAR-25 | MAR-25 | RFD | Work in progress.
6 | GIS Sub Station Pocket A IMT Kharkhoda Sonipat (2x100MVA 220/33kV T/F) | 220/33 | 2x100 |  | 100 | 48 | 30 | 35 |  | MAR-25 | MAR-25 | RFD | Work in progress.
7 | Gurugram(2x100MVA 220/33KV T/F) GIS S/S Sector-99 | 220/33 | 2x100 |  | 100 | 16 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work in progress.
8 | Harfali (Palwal) (2x100MVA220/66 kV T/F) | 220/66 | 2x100 |  | 100 | 83 | 80 | 60 |  | JUN-24 | SEP-24 | RFD | Work in progress
9 | HSIIDC Rai Sonepat 220/132 kV T/F-II | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
10 | HSIIDC Rai Sonepat (220/33 kV 100 MVA T/F-II)(charged on 02-05-2024 however late reported by HVPNL) | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  |  | AUG-24 | RFD | Commissioned 07/24.
11 | HSIIDC Rai Sonepat 220/33 kV T/F-I | 220/33 | 1x100 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
12 | Ramana-Ramani (Karnal) ( 2x100MVA 220/33KV T/F-II) | 220/33 | 2x100 |  | 100 | 55 | 40 | 0 |  | MAR-25 | MAR-25 | RFD | Work in progress.
13.: Page 5 of | 14
Report generated through NPP |  | 2024-12-17 15:30
13 | Ramana-Ramani (Karnal) (2x160MVA 220/132kV T/F-I) | 220/132 | 2x160 |  | 100 | 50 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work in progress.
14 | Sadhaura Ambala (1x100 MVA 220/33 Kv T/F-I) | 220/33 | 1x100 |  | 100 | 40 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work in progress.
15 | Sadhaura Ambala (2x100 MVA 220/66 kV T/F) | 220/66 | 2x100 |  | 100 | 90 | 50 | 50 |  | MAR-25 | MAR-25 | RFD | Work in progress.
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | 220/132/33 kV AIS at Andheri (Kala Amb) District Sirmaur H.P. | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
2 | 220/132kV Kangoo S/S | 220/132 | 200 |  | 0 | 0 | 0 | 0 |  | SEP-24 | MAR-23 | RFD
3 | 80/100 MVA GIS Sub-Station at Heiling | 220/66 | 1x100 | [6 empty] | JUL-24 |  | RFD
4 | Tahliwal by S/C LILO of 220 kV Bhakhra- Jamalpur line GIS S/S at Tahliwal | 220/132 | 1x100 | [6 empty] | MAR-25 |  | RFD
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | Jainamore GSS | 220/132 | 3x100 |  | 100 | 90 | 100 | 90 |  | JUL-24 | MAR-23 | RFD | Work in Progress.
2 | Latehar GSS | 400/220 | 630 | [6 empty] | AUG-24 |  | RFD
3 | Lohardaga GSS (PGCIL) | 220/132 | 300 |  | 100 | 95 | 90 | 90 |  | MAY-24 | MAR-23 | RFD | Work in Progress.
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | Bilagi s/s | 220/110 | 2x100 |  | 100 | 60 | 100 | 100 |  | OCT-24 |  | RFD | Work under progress
2 | GIS Chikkaballapura Establishing 2x100MVA 220/66 kV s/s at Chikkaballapura I/A | 220/66 | 2x100 |  | 100 | 85 | 100 | 95 |  | NOV-24 |  | RFD | Work under progress
3 | Hangal Establishing 2x100 MVA 220/66 KV Power T/F at Hangal GEC Phase-2 | 220/66 | 2x100 |  | 100 | 85 | 90 | 90 |  | FEB-25 | FEB-25 | RFD | Work under progress
4 | Keonics (Electronic City): 2x150 MVA ICT | 220/66 | 300 |  | 100 | 100 | 100 | 100 |  | MAY-24 | OCT-24 | RFD | Commissioned 09/24.
5 | Santhpur Establishing 220kV 2X100MVA Aurad (B) taluka and Bidar Dist. (GEC PHASE II) | 220/110 | 2x100 |  | 100 | 80 | 100 | 90 |  | AUG-24 | DEC-24 | RFD | Work under progress
6 | Yelburga Establishing 2x100MVA and 110MVA 220/110/11kV S/S | 220/110 | 2x100 |  | 100 | 85 | 100 | 95 |  | JAN-25 | JAN-25 | RFD | Work under progress
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kakkad | 220/110 | 1x100 |  | 100 | 75 | 85 | 60 |  | JUN-24 | MAR-25 | RFD | Civil and erection works are in progress.
2 | Pathanamthitta | 220/110 | 1x100 |  | 100 | 85 | 85 | 80 |  | JUN-24 | JAN-25 | RFD | Civil and erection works are in progress.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220/22 kV Mankoli GIS | 220/22 | 1x100 |  | 100 | 68 | 40 | 5 |  | DEC-24 | MAR-25 | RFD | Work in progress .
2 | 220/33 kV New Timber Market GIS (Panvel -II ) | 220/33 | 50 |  | 100 | 100 | 100 | 100 |  | MAY-24 | DEC-24 | RFD | Commissioned 11/24.
13.: Page 6 of | 14
Report generated through NPP |  | 2024-12-17 15:30
3 | 220/33kV New Timber Market GIS (Panvel -II )(50 MVA T/F) | 220/33 | 50 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUL-24 | RFD | Commissioned 06/24.
4 | 220/33 kV Shendra GIS (DMIC)(2X50 MVA T/F) | 220/33 | 2x50 |  | 100 | 100 | 100 | 100 |  | JUN-24 | OCT-24 | RFD | Commissioned 09/24.
5 | 220kV Chalisgaon Substation(1x200 MVA Additional T/F) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
6 | 220kV Jambhul | 220/22 | 50 |  | 100 | 100 | 100 | 80 |  |  | JAN-24 | RFD | Out of total 2X 50 MVA T/F capacity 1 X 50 MVA T/F is already commissioned on 02.05.2024and other one will be commissioned in Dec 24
7 | 220kV Jambhul (Additional T/F) | 220/22 | 1x50 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUN-24 | RFD | Commissioned 05/24.
8 | 220 kV Jeur (Replacement of 100 MVA T/F with 200 MVA T/F) | 220/132 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAR-25 | OCT-24 | RFD | Commissioned 09/24.
9 | 220 kV Tembhurni substation (replacement of 25 MVA by 100 MVA T/F) | 220/33 | 25 |  | 100 | 100 | 100 | 100 |  | DEC-24 | SEP-24 | RFD | Commissioned 08/24.
10 | 220kV Walchandnagar substation (replacement of 100 MVA by 200 MVA T/F) | 220/132 | 100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
11 | 400kV Khadka Substation (3x105) | 400/220 | 1x315 |  | 100 | 90 | 100 | 80 |  | JUN-24 | DEC-24 | RFD | Work in progress and will be expected shortly
12 | 400kV Lonikand Substation (1x50) | 220/22 | 1x50 | [6 empty] | JUN-24 |  | RFD
13 | 400kV Padghe | 400/220 | 185 | [6 empty] | DEC-24 |  | RFD
14 | 400kV Thapti Tanda | 400/220 | 500 | [6 empty] | MAR-25 |  | RFD
15 | Bhigwan | 220/33 | 25 | [6 empty] | MAR-25 |  | RFD
16 | Five Star MIDC | 220/33 | 1x50 |  | 100 | 100 | 100 | 100 |  | DEC-24 |  | RFD | T/F commissioned on 31.12.2018.
17 | Georai | 220/33 | 50 | [6 empty] | MAR-25 |  | RFD
18 | Kolshet | 220/22 | 50 | [6 empty] | MAR-25 |  | RFD
19 | Pardi SS (220/132 2x100 MVA and 220/33 2x50 MVA) | 220/132/33 | 2x100+2x50 |  | 100 | 100 | 98 | 95 |  | JUN-24 | JUL-24 | RFD | Substation work completed. Associated line work in progress.
20 | Temghar Replacement T/F (1x (100-50) | 220/22 | 1x50 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD | Repeated at sr no 76, to be deleted.
21 | Tilawani | 220/33 | 1x100 | [6 empty] | MAR-25 |  | RFD
22 | Vairag | 220/33 | 50 | [6 empty] | MAR-25 |  | RFD
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
1 | 220/132/33kV Ajaygarh S/s (TBCB) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | DEC-24 | JUL-24 | RFD | Commissioned 06/24.
2 | Bairagarh (Bhopal) 220 KV S/s Addl. 1x160MVA X-mer | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUN-24 | RFD | Commissioned 05/24.
3 | Barwana 220kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
13.: Page 7 of | 14
Report generated through NPP |  | 2024-12-17 15:30
4 | Bhopal 400 kV SS (replacement of 315 MVA by 500 MVA T/F) | 400/220 | 185 |  | 100 | 100 | 100 | 100 |  | MAR-25 | DEC-24 | RFD | Commissioned 11/24.
5 | Construction of 220/132/33kV substation Bisonikala | 220/132 | 2x160 |  | 100 | 4 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
6 | Construction of 220/132 kV substation at Bargawan | 220/132 | 2x160 |  | 100 | 100 | 60 | 60 |  | DEC-24 |  | RFD | TBCB work
7 | Construction of 220/33kV substation at Shahpur | 220/33 | 1x100 |  | 100 | 17 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
8 | Construction of 400/220kV GIS substation at Mandideep (2x160 MVA T/F-I) | 220/132 | 2x160 | [6 empty] | JAN-25 |  | RFD
9 | Construction of 400/220kV GIS substation at Mandideep (2X500 MVA T/F) | 400/220 | 2x500 |  | 100 | 35 | 0 | 0 |  | JAN-25 |  | RFD | TBCB work
10 | Construction of Begamganj SS (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | APR-24 | AUG-24 | RFD | Commissioned 04/24 (Late Reported).
11 | Installation for addll. T/F at Indore-II Jetpura Supply-MR-10 and Gandhi NagarMetro Rail s/s Indore | 220/132 | 1x160 |  | 100 | 100 | 95 | 90 |  | DEC-24 |  | RFD | work under progress
12 | Julwaniya 400 KV S/s addl.500 MVA X-mer | 400/220 | 500 |  | 100 | 63 | 0 | 0 |  | MAR-25 |  | RFD | work under progress
13 | Mandsaur 400KV S/s additional 500MVA 400/220KV | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
14 | Nepanagar 220 kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 | [6 empty] | DEC-24 |  | RFD
15 | Pritampura (sector III) 220kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | 40 |  | 0 | 0 | 0 | 0 |  | MAR-25 |  | RFD
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | 220/132kV GIS Balianta GIS | 220/132 | 2x160 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD | May be deleted repeat project
2 | 220/33 KV Grid S/S Dasapalla | 220/33 | 40 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD | May be deleted repeat project
3 | 220/33 KV GSS Balichandrapur Palei | 220/33 | 20 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
4 | 2X20 MVA 220/33kV Balichandrapur (Palei) S/s | 220/33 | 20 |  | 0 | 0 | 0 | 0 |  | APR-24 |  | RFD | Already charged
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | 220 kV S/S Banur (Aug. of 1x100 MVA T/F with 1x160 MVA T/F) | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
2 | 220 kV S/S Budhlada (1x160 MVA T/F) (Upgraded from 66 KV to 220 KV) | 220/66 | 160 |  | 100 | 60 | 70 | 60 |  | JUL-24 | NOV-24 | RFD | Work in progress, T/f has been reached at site (But work pending due to line work.) Tr. Line work will be completed by Nov.24
13.: Page 8 of | 14
Report generated through NPP |  | 2024-12-17 15:30
3 | 220 kV S/S Gurdaspur (1x100 MVA) (Upgraded from 132 KV to 220 KV) | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
4 | 400 kV S/S Ropar (1x500 MVA ) 1st T/F | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
5 | 400 kV S/S Ropar (1x500 MVA ) 2nd T/F | 400/220 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
6 | Additional 1X160 MVA 220/66kV T/F at 220 kV S/Stn. Sherpur | 220/66 | 1x160 |  | 100 | 70 | 90 | 70 |  | DEC-24 | DEC-24 | RFD | Work in progress.
7 | Addl. 100 MVA 220/66 kV T/F at 220 kV Badni Kalan SS | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAR-25 | DEC-24 | RFD | Commissioned 11/24.
8 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Badhshahpur | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUN-24 | RFD | Commissioned 05/24.
9 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Majitha (N-1) | 220/66 | 1x100 |  | 100 | 70 | 60 | 60 |  | MAY-24 | OCT-24 | RFD | Work in progress, likely to be completed by 31-10-24.
10 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Naraingarh (N-1) | 220/66 | 1x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
11 | Addl. 100MVA 220/66kV T/F at 220kV S/Stn Maur | 220/22 | 1x100 |  | 100 | 60 | 20 | 10 |  | MAR-25 | MAR-25 | RFD | Work in progress.
12 | Aug 100 to 160 MVA at 220 KV S/S Kartarpur | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUL-24 | RFD | Commissioned 06/24.
13 | Aug. 100 to 160 MVA at 220 KV S/S Mandi Gobindgarh G-2 | 220/66 | 60 |  | 0 | 0 | 0 | 0 |  | MAR-25 | MAR-25 | RFD | Work not started yet
14 | Aug 100 to 160 MVA at 220 KV S/S Rajpura | 220/66 | 60 |  | 100 | 0 | 0 | 0 |  | MAR-25 |  | RFD | Work not started yet,
15 | Aug. of 100MVA 220/66kV T/F to 160MVA 220/66kV T/F at 220kV S/Stn Bajakhana | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | MAR-25 | JUN-24 | RFD | Commissioned 05/24.
16 | Aug. of 100 MVA T/F to 160 MVA T/F at 220 kV SS Mandi Gobindgarh G-3 | 220/66 | 60 |  | 100 | 100 | 100 | 100 |  | SEP-24 | AUG-24 | RFD | Commissioned 07/24.
17 | Dhandari Kalan-2 (Aug. of 2x100 MVA T/F with 2x160 MVA T/F) | 220/66 | 60 |  | 100 | 75 | 60 | 40 |  | SEP-24 | NOV-24 | RFD | Work in progress. T/f placed, but comissioning pending due to Shutdown issues.
18 | Upgradation of 66 kV Sherpur to 220kV by installing 1X160 MVA 220/66kV T/F at 220 kV S/Stn. Sherpur | 220/66 | 1x160 |  | 100 | 70 | 90 | 70 |  | JUN-24 |  | RFD | Work in progress (Minor changes has been made in Civil Drawing) likely to be completed by Oct'24.
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED ( RVPNL )
1 | 220 kV GSS Rayla(Upg.) | 220/132 | 1x160 |  | 100 | 25 | 12 | 3 |  | JUN-24 | FEB-25 | RFD | Work Order to M/s S.K. Engineers, Vijay Nagar on 06.10.23. Civil work under progress.
2 | Banar GIS (Distt. Jodhpur) | 220/132 | 200 |  | 100 | 100 | 100 | 100 |  | JUN-24 | NOV-24 | RFD | Commissioned 10/24.
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | Avadi 230KV SS | 230/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
13.: Page 9 of | 14
Report generated through NPP |  | 2024-12-17 15:30
2 | Ganesh Nagar 230KV SS | 230/33 | 2x100 | [6 empty] | JUN-24 |  | RFD
3 | Hosur 230 KV SS -Enhancement 2x100 1X160 to 3160 MVA | 230/110 | 120 | [6 empty] | MAR-25 |  | RFD
4 | Kalivelampatty | 230/110 | 200 |  | 100 | 100 | 40 | 30 |  | NOV-24 | JUN-24 | RFD | Work under progress
5 | Karuppur (T/F- II) | 230/110 | 1x100 |  | 100 | 100 | 100 | 100 |  | SEP-24 | JUL-24 | RFD | Commissioned 06/24.
6 | Korattur (GIS) | 400/230/110 | 1x1400 |  | 100 | 90 | 90 | 90 |  | JUN-24 | MAR-24 | RFD | Work under progress
7 | K.R.Thoppur 400/230-110 KV SS -Addl. 400/230KV 1x500MVA T/F | 400/230 | 500 | [6 empty] | JUN-24 |  | RFD
8 | Mambakkam 230KV SS | 230/110 | 2x100 | [6 empty] | JUN-24 |  | RFD
9 | Maraimalai Nagar | 230/110 | 2x100 |  | 100 | 95 | 95 | 95 |  | SEP-24 | MAR-24 | RFD | Testing work completed.Ready for back charging
10 | Nallur 230/110 KV SS 2X100 MVA - New | 230/110 | 2x100 | [6 empty] | MAR-25 |  | RFD
11 | Nanguneri | 230/110 | 2x100 |  | 100 | 90 | 50 | 0 |  | SEP-24 | MAR-24 | RFD | Work under progress
12 | Panjetti 230KV SS | 230/110 | 3x100 | [6 empty] | JUN-24 |  | RFD
13 | Sathumadurai | 230/110 | 2x160 |  | 100 | 60 | 0 | 0 |  | MAR-25 | JUN-24 | RFD | Work under progress
14 | Selvapuram 230/110 kV SS (T/F-I) | 230/110 | 100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | AUG-24 | RFD | Commissioned 07/24.
15 | Selvapuram 230/110 kV SS (T/F-II) | 230/110 | 1x100 | [6 empty] | JUN-24 |  | RFD
16 | Thervoikandigai 400KV SS | 400/230 | 1x315 | [6 empty] | JUN-24 |  | RFD
17 | Thiruvalam 400/230 KV SS- Capacity enhancement from 2x315 to 2x315 + 1x500 MVA | 400/230 | 500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
18 | Thiruvanmiyur | 230/33 | 200 |  | 100 | 90 | 85 | 85 |  | DEC-24 | NOV-23 | RFD | Relay testing under progress
19 | Vellalaviduthi (400/110 kV T/F-II) | 400/110 | 2x100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | DEC-24 | RFD | Commissioned 11/24.
20 | Vellalaviduthi (T/F-I) (400/110 (2X200 MVA) | 400/110 | 2x100 |  | 100 | 100 | 100 | 100 |  | JUN-24 | MAY-24 | RFD | Commissioned 04/24.
21 | Vembakkam | 230/110 | 3x100 |  | 100 | 90 | 90 | 60 |  | JUN-24 | MAR-24 | RFD | Work under progress
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | Atchuthapuram GIS | 220/132/33 | 2x100 |  | 100 | 75 | 65 | 65 |  | JUN-24 | JUN-24 | RFD | Works are under progress.
2 | Aug.at Kalpaka -4th (500MVA) | 400/220 | 500 |  | 100 | 60 | 40 | 30 |  | MAY-21 | JUN-24 | RFD | Work in Progress.
3 | Augmentation of 1no. 500MVA ICT at 400/220kV SS Kalapaka | 400/220 | 500 |  | 0 | 0 | 0 | 0 |  | JUN-24 |  | RFD
4 | Augmentation of ICTs from 1x160 1x100MVA to 2x160 1x100MVA at Rachagunneri | 400/220 | 1x160 |  | 0 | 0 | 0 | 0 |  | DEC-24 |  | RFD
5 | Augmentation of ICTs from 2x315 1x500MVA to 2x3152x500MVA at 400/220KV SS Maradam | 400/220 | 500 |  | 100 | 50 | 40 | 35 |  | AUG-24 | JAN-25 | RFD
13.: Page 10 of | 14
Report generated through NPP |  | 2024-12-17 15:30
6 | Augmentation of ICTs from 2x315MVA to 2x315 1500MVA at 400/220KV SS Narnoor | 400/220 | 500 |  | 100 | 70 | 70 | 60 |  | MAY-24 | AUG-24 | RFD | work under progress
7 | Augmentation of ICTs from 2x315MVA to 2x315 1x500MVA SS Rachagunneri | 400/220 | 500 |  | 100 | 40 | 35 | 20 |  | DEC-24 | JAN-25 | RFD | work under progress
8 | Bethamcherla | 220/132/33 | 2x160 |  | 100 | 95 | 95 | 90 |  | JUN-24 | JUN-24 | RFD | work under progress
9 | Bethamcherla in Kurnool District (GEC-I) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  |  | DEC-24 | RFD | Commissioned 11/24.
10 | Dharmavaram | 220/132 | 2x100 |  | 100 | 80 | 95 | 90 |  | JUN-24 | JUL-24 | RFD | Works are under progress.
11 | Inavolu S/s (Thallayapalem GIS) | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Works are under progress.
12 | Pampanur Tanda (GEC-I) (160 MVA T/F-II) | 220/132 | 1x160 |  | 100 | 100 | 100 | 90 |  | JUN-24 | AUG-24 | RFD | Substation charged on 18.05.2023. PTR-1 Charged on 08.12.2023
13 | Penukonda (Gorantla) (GEC-I) | 220/132 | 1x160 | [6 empty] | JUN-24 |  | RFD
14 | Penukonda (Gorantla) (GEC-I) | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | JUN-24 | RFD | Commissioned 05/24.
15 | Punganur | 220/132/33 | 2x100 |  | 100 | 80 | 95 | 90 |  | JUN-24 | JUN-24 | RFD | work under progress
16 | Tiruvuru | 220/132 | 3x100 |  | 100 | 70 | 80 | 80 |  | JUL-24 | JUL-24 | RFD | Work in Progress.
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | Ammavaripet (T/F-II) | 220/132 | 2x100 |  | 100 | 100 | 70 | 70 |  | AUG-24 | AUG-24 | RFD | One commissioned in March-24 and remaining in FY 2024-25
2 | Bhoopalapally (KTPP) S/S 400/220/ 132 kV | 220/132 | 2x160 | [6 empty] | JUN-24 |  | RFD
3 | Bhoopalapally (KTPP) SS 400/220/ 132 kV | 400/220 | 2x500 | [6 empty] | JUN-24 |  | RFD
4 | Husnabad s/s | 220/132 | 2x100 |  | 0 | 100 | 100 | 95 |  | AUG-24 | AUG-24 | RFD | Works under progress.
5 | Kakatiya Mega Textile Park (KMTP) SS (2x160) | 220/132 | 2x160 |  | 0 | 75 | 90 | 60 |  | DEC-24 | DEC-24 | RFD | Works under progress.
6 | Yacharam Thanda LI SS (3x40 2x25 MVA) | 220/11 | 170 |  | 100 | 85 | 95 | 90 |  | OCT-24 | OCT-24 | RFD | Works are under progress. Balance works to be completed in co-ordination with I&CADD.
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | 220 kV GIS S/s Badaun Road Bareilly (New) GIS | 220/33 | 60 |  | 100 | 100 | 100 | 100 |  | JUL-24 | NOV-24 | RFD | Commissioned 10/24.
2 | 220 kV GIS SS Badaun Road Bareilly (T/F-II) | 220/33 | 60 |  | 100 | 100 | 100 | 100 |  |  | DEC-24 | RFD | Commissioned 11/24.
3 | 220 kV S/s Darshan Nagar Ayodhya (New) T/F-I | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
4 | 220 kV S/s Kanduni Sitapur (New) T/F-II | 220/132 | 2x100 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
5 | 220 kV S/s Khorabar Gorakhpur (New) T/F-II | 220/33 | 60 |  | 100 | 100 | 100 | 100 |  | APR-24 | JUN-24 | RFD | Commissioned 05/24.
13.: Page 11 of | 14
Report generated through NPP |  | 2024-12-17 15:30
6 | 220 kV S/s Knowledge Park-5 Gr. Noida GB Nagar (New) T/F-II | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUL-24 | RFD | Commissioned 06/24.
7 | 220 kV S/s Metro Depot Gr. Noida GB Nagar (New) T/F-I and T/F-II | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | MAY-24 | AUG-24 | RFD | Commissioned 07/24.
8 | 400 kV S/s Dahi Chaoki Unnao (Capacity Aug.) (315) MVA (500-315) | 400/220 | 1x315 |  | 100 | 0 | 0 | 0 |  |  |  | RFD | To be deleted
9 | 400 kV S/s Dahi Chaoki Unnao (Capacity Aug.) (500-315) | 400/220 | 185 |  | 100 | 100 | 100 | 100 |  |  | MAY-24 | RFD | Commissioned 04/24.
10 | 400 kV S/s Machhalishahar Jaunpur (New) T/F-III | 400/220 | 315 |  | 100 | 100 | 100 | 100 |  | MAY-24 | JUN-24 | RFD | Commissioned 05/24.
11 | Dahi Chaoki (Capacity Aug) | 400/220 | 500 |  | 100 | 0 | 0 | 0 |  | OCT-24 |  | RFD | Commissioned (only 185 mva commissioned as 315 replaced with 500 MVA instead of additional 500 MVA)
12 | Faridpur (Bareilly) - T/F-II | 220/132 | 1x100 |  | 100 | 88 | 95 | 99 |  | JUN-24 | DEC-24 | RFD | Testing work held up due to delay in providing protection relays from M/s ABB. Electrical safety NOC applied.
13 | Jewar (Extn.) | 220/132 | 2x160 |  | 100 | 82 | 91 | 79 |  | JUN-24 | DEC-24 | RFD | Both T/F have been received and erection work in progress. High voltage testing of GIS modules is planned from 15 Dec-2024.
14 | Khorabar S/s (T/F-III) | 220/33 | 60 |  | 100 | 95 | 100 | 90 |  | JUL-24 | MAR-25 | RFD | T/F available at site. Firm is not responding to available manpower for completion of 33kV side pending works.
15 | Moradabad (Capacity Aug.) | 400/220 | 315 |  | 100 | 0 | 0 | 0 |  | FEB-25 |  | RFD | Trnansformer is to be diverted from 400kV S/s Panki after increasing capacity from 315MVA to 500MVA. Delay in delivery of 500 MVA T/F from M/s Siemens is causing the delay in release of 315MVA transformer from Panki.
16 | Sahupuri T/F-II | 400/220 | 500 |  | 100 | 99 | 99 | 95 |  | JUL-24 | DEC-24 | RFD | Commissioning work of T/F-II is in progress under supervision of M/s G.E.
17 | Sector-62 Noida | 220/132 | 2x160 |  | 100 | 41 | 65 | 12 |  | OCT-24 | FEB-25 | RFD | Fund issue with Noida Authority. Commissioning and erection work will be possible after resolve the fund issue.
13.: Page 12 of | 14
Report generated through NPP |  | 2024-12-17 15:30
18 | Shamli S/s (T/F -II) | 400/220 | 500 |  | 100 | 100 | 0 | 0 |  | AUG-24 | MAR-25 | RFD | Delay in delivery of 500 MVA T/F from M/s Siemens on account of failure of job in dynamic short circuit test. Commissioning and erection work will be possible after receiving the T/F-II.
19 | Trans Ganga city | 220/33 | 120 |  | 100 | 80 | 51 | 42 |  | NOV-24 | FEB-25 | RFD | Both T/F received. Erection work of structure in progress. Charging of line is delayed due to RoW issue with NHAI which is expected to be resolved after approval of ammended route by NHAI.
20 | Yeida Sec-24 T/F-II | 220/132 | 1x160 |  | 100 | 100 | 0 | 0 |  | DEC-24 |  | RFD | There are lack of fund issues with YEIDA. 160 MVA T/F-II. Will be allotted after fund transfered to UPPTCL.
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
1 | AB Zone 220 KV GIS (upgraded to 220 kV from 132 kV) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | JUL-24 | DEC-24 | RFD | Commissioned 11/24.
2 | Falakata 220 KV GIS | 220/132/33 | 420 |  | 100 | 31 | 80 | 10 |  | SEP-24 | MAR-25 | RFD | Work in progress.
3 | Food Park (T/F-I) 220 KV GIS | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 08/24.
4 | Food Park (T/F-II) 220 KV GIS | 220/132 | 1x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 | SEP-24 | RFD | Commissioned 09/24.
5 | Khanakul 220 KV GIS | 220/33 | 1x100 |  | 100 | 20 | 66 | 0 |  | MAR-25 | MAR-25 | RFD | work in progress.
6 | Raghunathpur 220 KV GIS (Upg) | 220/132 | 320 |  | 100 | 43 | 14 | 0 |  | MAR-25 | MAR-25 | RFD
7 | Satgachhia 400KV GIS (Upg) | 400/220 | 1000 |  | 100 | 53 | 87 | 12 |  | JAN-25 | JAN-25 | RFD
8 | Shamli T/F-II | 400/220 | 500 | [6 empty] | AUG-24 |  | RFD
PRIVATE SECTOR
ADANI POWER LIMITED ( APL )
1 | Narendra New (upgradation to its rated voltage of 765 Kv along with 4x1500 MVA T/F) | 765/400 | 6000 | [6 empty] | DEC-24 |  | RFD
Apraava Energy Pvt. Ltd. ( APRAAVA )
1 | 5x500MVA 400/220kV pooling station at Fatehgarh-4 | 400/220 | 2500 | [6 empty] | FEB-25 |  | RFD
Megha Engineering & Infrastructures Limited ( MEGHA )
1 | Khavda PS1 Augmentation | 765/400 | 6000 | [6 empty] | JAN-25 |  | RFD
PATRAN TRANSMISSION COMPANY LIMITED ( PATRANTCL )
13.: Page 13 of | 14
Report generated through NPP |  | 2024-12-17 15:30
1 | 1x500 MVA 400/220KV ICT-I along with associated ICT bays at 765/400kV Dharamjaigarh S/S | 400/220 | 500 | [6 empty] | MAR-25 |  | RFD
POWERICA Ltd. ( POWERICA )
1 | 1x 500MVA 765/400kV ICT-1 at Fatehgarh-3 (New Section) | 765/400 | 1x1500 | [6 empty] | FEB-25 |  | RFD
ReNew Transmission Ventures Private Limited ( RTVPL )
1 | Augmentation of 400/220 KV Gadag S/S with 3x500 MVA ICT | 400/220 | 1500 | [6 empty] | MAY-24 |  | RFD
2 | Gadag PS (Trans Scheme for Solar Energy Zone in Gadag (1000 MW) Karnataka Part-A Phase-I) | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | MAY-24 | OCT-24 | RFD | Commissioned 09/24.
STERLITE GRID LTD. ( SGL )
1 | Beawar 2x1500 MVA 765/400 kV S/S | 765/400 | 2x1500 | [6 empty] | MAR-25 |  | RFD
2 | Nangalbibra 220/132 kV (2x160MVA) | 220/132 | 2x160 |  | 100 | 100 | 100 | 100 |  | JUN-24 |  | RFD | Ready for commissioning on Oct-24
3 | Vapi -II (Western Region Strengthening Scheme-XIX (WRSS-XIX and NERSS - IX) | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | MAY-24 | OCT-24 | RFD | Commissioned 09/24.
4 | Xeldem New SS (GTTPL - TBCB) | 400/220 | 2x500 |  | 100 | 100 | 100 | 100 |  | JUN-24 | NOV-24 | RFD | Commissioned 10/24.
13.: Page 14 of | 14
Report generated through NPP |  | 2024-12-17 15:30