## State_trans_utility_wise_prt1
CENTRAL ELECTRICITY AUTHORITY POWER SYSTEM WING Power System Project Monitoring Division
Sub-Stations Completed During FY - 2024-25
As on 31-Mar-25
Sl No | Name of Sub Stations | Voltage Ratio (kV/kV) | Executing Agency | Capacity (MW/MVA) |  | Month of Completion
1. | 2. | 3. | 4. | 5. |  | 6.
765 kV
CENTRAL SECTOR
1 | 1x1500 MVA 765/400 kV ICT (3rd) at Pune (PG) GIS under Western Region Expansion Scheme-XXXI Part C | 765/400 | PGCIL | 1500 |  | FEB-25
2 | 1X1500 MVA 765/400 KV (5th) ICT at Fatehgarh-II PS (Rajasthan (8.1 GW) under Phase II- Part- A1) | 765/400 | PGCIL | 1500 |  | JUL-24
3 | 1x1500MVA ICT at Padghe (GIS) Trans. Network Expansion in Gujarat to increase ATC from ISTS Part B | 765/400 | PGCIL | 1500 |  | JUN-24
4 | Kurnool-III (ICT3)(Trans. Sys. for Kurnool Wind Energy Zone/ Solar Energy Zone (AP)-Part-A & Part-B) | 765/400 | PGCIL | 1500 |  | MAR-25
5 | Kurnool-III (ICT1&2)(Trans. Sys. for Kurnool Wind Energy Zone/Solar Energy Zone (AP)-Part-A & B) | 765/400 | PGCIL | 3000 |  | MAR-25
6 | Banaskantha SS (Transmission network expansion in Gujarat to increase its ATC from ISTS Part C) | 765/400 | PGCIL | 1500 |  | NOV-24
7 | 1x1500 MVA 765/400kV ICT-2 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | PGCIL | 1500 |  | OCT-24
8 | 1x1500 MVA 765/400kV ICT-1 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) | 765/400 | PGCIL | 1500 |  | OCT-24
9 | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-A) | 765/400 | PGCIL | 1500 |  | OCT-24
10 | 1X1500 MVA 765/400 kV ICT (4th) at 765/400 kV Bhadla-II PS under (Phase -II Part -BI) | 765/400 | PGCIL | 1500 |  | SEP-24
| TOTAL CENTRAL SECTOR |  |  | 16500
| TOTAL 765 kV |  |  | 16500
400 kV
CENTRAL SECTOR
11 | 220KV GIS Infrastructure at MTPS | 400/220 | DVC | 315 |  | AUG-24
12 | 220 kV GIS Infrastructure at RTPS | 400/220 | DVC | 630 |  | NOV-24
13 | 1x500 MVA 400/220 kV ICT 3rd at Bikaner PS to Cater N-1 Contigency at Bikaner PS (Rajasthan) | 400/220 | PGCIL | 500 |  | AUG-24
14 | 1X500 MVA 400/220 kV (2nd) ICT at Shikrapur (PG) GIS under Western Region Expansion Scheme-XXVI | 400/220 | PGCIL | 500 |  | AUG-24
15 | 1X500 MVA, ICT-1 at Dharamjaigarh S/s (WRES XXIX {Project name: WRES-XXVIII & WRES-XXIX) | 400/220 | PGCIL | 500 |  | DEC-24
16 | 1X500 MVA, (3rd) ICT at Raipur Pool S/s (WRES XXVIII {Project name: WRES-XXVIII & WRES-XXIX) | 400/220 | PGCIL | 500 |  | DEC-24
17 | 1X500 MVA 400/220kV ICT-6th at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | PGCIL | 500 |  | DEC-24
18 | 1X500 MVA 400/220 kV ICT-7th at Bikaner-II PS REZ (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | PGCIL | 500 |  | FEB-25
19 | 1x500 MVA 400/220 kV ICT (6th) at Fatehgarh-II PS (PG) to cater the N-1 Contigenecy | 400/220 | PGCIL | 500 |  | FEB-25
20 | 1X500 MVA, 400/220 kV ICT-2 at Dharamjaigarh S/s under WRES XXIX | 400/220 | PGCIL | 500 |  | JAN-25
21 | 1X500 MVA, 400/220 kV ICT-4th at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | PGCIL | 500 |  | JUL-24
22 | Shifting of ICT from Ludiana to Bhinmal(PG) SS (Aug. of T/F capacity at Bhinmal (PG) SS by ICT 3rd) | 400/220 | PGCIL | 315 |  | JUN-24
23 | 1X500MVA ICT(4TH) at ARASUR s/s (Aug. of T/F Capacity by 500 MVA ICT(4th) at Arasur) | 400/230 | PGCIL | 500 |  | JUN-24
24 | 1X500 MVA, 400/220 kV ICT (3rd) ICT at Bikaner-II PS (8th ICT) (Aug. at Bikaner-II PS ICT(3rd)- | 400/220 | PGCIL | 500 |  | MAR-25
PBTSL
25 | Kurnool-III (ICT-1to4, 6&7)(Trans. Sys. for Kurnool Wind Energy Zone/Solar Energy Zone(AP)-Part-A&B) | 400/220 | PGCIL | 3000 |  | MAR-25
26 | Navsari SS (ICT 1& 2) (Trans. Network Expansion in Gujarat to increase its ATC from ISTS Part B) | 400/220 | PGCIL | 1000 |  | MAR-25
27 | 1X500 MVA 400/220 kV ICT-3rd at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E | 400/220 | PGCIL | 500 |  | MAY-24
28 | 1X500 MVA 400/220 kV ICT-5th at Bikaner II PS (Phase-IV (Part 1) Bikaner Complex- PART E) | 400/220 | PGCIL | 500 |  | NOV-24
29 | 1X500MVA ICT-1 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | PGCIL | 500 |  | OCT-24
30 | 1X500MVA ICT-2 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka | 400/220 | PGCIL | 500 |  | OCT-24
31 | Aug. by 1x500 MVA 400/220 kV ICT (3rd )at 400/220 kV Jind (PG) S/s under Aug. of ISTS for HVPNL TS | 400/220 | PGCIL | 500 |  | SEP-24
32 | 1X500 MVA, 400/220 kV (1st) ICT at Raipur Pool S/s ( WRES XXVIII (Project: WRES-XXVIII & WRES-XXIX) | 400/220 | PGCIL | 500 |  | SEP-24
33 | 1X500 MVA, 400/220 kV (1st) ICT at Shikrapur (PG) GIS under Western Region Expansion Scheme-XXVI | 400/220 | PGCIL | 500 |  | SEP-24
34 | 1X500 MVA, 400/220 kV (2nd) ICT at Raipur Pool S/s (WRES XXVIII (Project: WRES-XXVIII & WRES-XXIX) | 400/220 | PGCIL | 500 |  | SEP-24
35 | 1X500 MVA, 400/220 kV (4th) ICT at Mysore under Aug. of transformation capacity at Mysore | 400/220 | PGCIL | 500 |  | SEP-24
36 | 1x500 MVA ICT (3rd ) at 400/220 kV Bahadurgarh (PG) S/s under Aug. of ISTS of HVPNL TS | 400/220 | PGCIL | 500 |  | SEP-24
| TOTAL CENTRAL SECTOR |  |  | 15760
| TOTAL 400 kV |  |  | 15760
220 kV
CENTRAL SECTOR
37 | 1X200 MVA 220/132 kV (4th) ICT at Ara POWERGRID S/S under ER Expansion Scheme-XXXVI (ERES-XXXVI) | 220/132 | PGCIL | 200 |  | AUG-24
| TOTAL CENTRAL SECTOR |  |  | 200
| TOTAL 220 kV |  |  | 200
765 kV
STATE SECTOR
38 | Ariyalur (1500 MVA ICT-II) | 765/400 | TANTRANSCO | 1500 |  | DEC-24
| TOTAL STATE SECTOR |  |  | 1500
| TOTAL 765 kV |  |  | 1500
400 kV
STATE SECTOR
39 | Jammalamadugu SS in Kadapa Dist | 400/220 | APTRANSCO | 500 |  | DEC-24
40 | 400 kV GIS Thallayapalem in Guntur Dist (T/F-I) | 400/220 | APTRANSCO | 500 |  | FEB-25
41 | Augmentation of 400 kV SS Narnoor at Kurnool Dist | 400/220 | APTRANSCO | 500 |  | MAR-25
42 | Augmentation of 400 kV SS Maradam at Vizianagaram Dist | 400/220 | APTRANSCO | 500 |  | MAR-25
43 | 400/220/132 kV GIS Bakhtiyarpur (2x500 MVA) | 400/220/132 | BSPTCL | 1000 |  | MAR-25
44 | Kurud (Dhamtari) | 400/220 | CSPTCL | 315 |  | MAR-25
45 | Latehar SS (2X315 MVA T/F) | 400/220 | JUSNL | 630 |  | DEC-24
46 | Bhopal 400 kV SS (replacement of 315 MVA by 500 MVA T/F) | 400/220 | MPPTCL | 185 |  | NOV-24
47 | 400 kV Khadka S/s (3x105 MVA ICT) | 400/220/33 | MSETCL | 315 |  | DEC-24
48 | 400 kV Padghe substation ( 3x167 MVA, | 400/220/33 | MSETCL | 500 |  | MAR-25
400/220/33 kV ICT )
49 | 400 kV Kharghar substation (3x167 MVA, 400/220/33 kV ICT) | 400/220/33 | MSETCL | 500 |  | MAR-25
50 | 400 kV S/S Ropar (1x500 MVA ) 2nd T/F | 400/220 | PSTCL | 500 |  | AUG-24
51 | 400 kV S/S Ropar (1x500 MVA ) 1st T/F | 400/220 | PSTCL | 500 |  | AUG-24
52 | 400 kV S/S Nakodar | 400/220 | PSTCL | 500 |  | NOV-24
53 | 400 kV GSS Pachpadra | 400/220 | RVPNL | 500 |  | DEC-24
54 | 400 kV GSS Hindaun (Augmentation) | 400/220 | RVPNL | 500 |  | JAN-25
55 | 400 kV GSS Jaisalmer-2 (Bhensara) (MVA, 3x500) | 400/220/33 | RVPNL | 1500 |  | MAR-25
56 | Vellalaviduthi (T/F-I) (400/110 (2X200 MVA) | 400/110 | TANTRANSCO | 200 |  | APR-24
57 | Kayathar 400/230-110 KV SS | 400/110 | TANTRANSCO | 200 |  | JUL-24
58 | Alamathy 400/230-110 kV SS (enhancement of capacity at from 2x200 MVA to 3x200 MVA | 400/110 | TANTRANSCO | 200 |  | JUN-24
59 | Sriperumbudhur 400/230-110 kV SS- capacity enhancement from 3x315 MVA to 3x315MVA+ 1x500MVA | 400/230 | TANTRANSCO | 500 |  | MAY-24
60 | Thiruvalam 400/230 KV SS- Capacity enhancement from 2x315 to 2x315 + 1x500 MVA | 400/230 | TANTRANSCO | 500 |  | MAY-24
61 | Vellalaviduthi (400/110 kV T/F-II) | 400/110 | TANTRANSCO | 200 |  | NOV-24
62 | Sriperumbudur 400/230 kV SS (enhancement from 3x315+1x500 MVA to 2x315+2x500 MVA) | 400/230 | TANTRANSCO | 185 |  | NOV-24
63 | Kamalapuram Substation (3rd ICT) | 400/220 | TSTRANSCO | 315 |  | APR-24
64 | KTPP Bhupalapally SS (2x500 MVA) | 400/220 | TSTRANSCO | 1000 |  | FEB-25
65 | Asupaka LI Substation T/F-II (late reported, commissioned in Oct-2024) | 400/220 | TSTRANSCO | 315 |  | JAN-25
66 | 400 kV S/s Dahi Chaoki Unnao (Capacity Aug.) (500-315) | 400/220 | UPPTCL | 185 |  | APR-24
67 | 400 kV S/s Sahupuri, Chandauli T/F-I | 400/220 | UPPTCL | 500 |  | JAN-25
68 | 400 kV S/s Sector-123 Noida, GB Nagar (T/F-III) | 400/220 | UPPTCL | 200 |  | JAN-25
69 | 400 kV S/s Motiram Adda Gorakhpur Capacity Aug. (500-240) T/F-II | 400/220 | UPPTCL | 260 |  | JUN-24
70 | 400 kV S/s Machhalishahar Jaunpur (New) T/F-III | 400/220 | UPPTCL | 315 |  | MAY-24
71 | New Chanditala (4th ICT) | 400/220 | WBSETCL | 315 |  | OCT-24
| TOTAL STATE SECTOR |  |  | 14835
| TOTAL 400 kV |  |  | 14835
230 kV
STATE SECTOR
72 | Karaikudi 230/110 kV SS (50 MVA to 100MVA enhancement) | 230/110 | TANTRANSCO | 50 |  | AUG-24
73 | Oragadam 230 kV SS (160-100 MVA) | 230/110 | TANTRANSCO | 60 |  | FEB-25
74 | Kavanoor 230 kV SS (100-50 MVA) | 230/110 | TANTRANSCO | 50 |  | FEB-25
75 | Kumbakonam SS (Additional 100 MVA) | 230/110 | TANTRANSCO | 100 |  | JAN-25
76 | Tiruppur 230/110 kV SS (Enhancement from 100 MVA to 160 MVA) | 230/110 | TANTRANSCO | 60 |  | JAN-25
77 | Selvapuram T/F-II | 230/110 | TANTRANSCO | 100 |  | JAN-25
78 | Kadapperi 230/110 kV SS (Enhancement from 100 MVA to 160 MVA) | 230/110 | TANTRANSCO | 60 |  | JAN-25
79 | Selvapuram 230/110 kV SS (T/F-I) | 230/110 | TANTRANSCO | 100 |  | JUL-24
80 | Karuppur (T/F- II) | 230/110 | TANTRANSCO | 100 |  | JUN-24
81 | Siruseri 230 KV SS (enhancement of capacity from 2x100MVA to 3x100MVA) | 230/110 | TANTRANSCO | 100 |  | JUN-24
82 | Kadalangudi 230/110 kV SS (enhancement from 100 MVA to 160 MVA) | 230/110 | TANTRANSCO | 60 |  | MAR-25
83 | Cuddalore 230/110 kV S/S(Enhancement from 100 MVA to 160 MVA) | 230/110 | TANTRANSCO | 60 |  | MAR-25
84 | Mondipatty SS (replacement of 80 MVA T/F with 100 MVA) | 230/110 | TANTRANSCO | 20 |  | NOV-24
| TOTAL STATE SECTOR |  |  | 920
| TOTAL 230 kV |  |  | 920
220 kV
STATE SECTOR
85 | 220/132 kV SS Madanapalli in Chittoor Dist. (3X100-2X100) | 220/132 | APTRANSCO | 100 |  | APR-24
86 | Punganur SS in Chittoor Dist. (T/F-I) | 220/132 | APTRANSCO | 100 |  | DEC-24
87 | Betamcherla SS in Kurnool District (T/F-II) (GEC-I) | 220/132 | APTRANSCO | 160 |  | FEB-25
88 | Somayajulapalli SS in kurnool Dist | 220/132 | APTRANSCO | 100 |  | FEB-25
89 | 220 kV SS AP Carbides in Kurnool District (3x160+1x100 - 2x160 +1x100) | 220/132 | APTRANSCO | 160 |  | JUL-24
90 | Krishnagiri S/s (T/F-II) | 220/33 | APTRANSCO | 50 |  | JUN-24
91 | 220kV SS Kuppam in Chittoor District (3x100-2x100) | 220/132 | APTRANSCO | 100 |  | JUN-24
92 | 220 kV SS Nidadavole at West Godavari Dist | 220/132 | APTRANSCO | 60 |  | MAR-25
93 | 220 kV SS Narasaraopeta at Guntur District | 220/132 | APTRANSCO | 60 |  | MAR-25
94 | Augmentation of 400 kV SS Rachaganneri at Chittoor Dist | 220/132 | APTRANSCO | 160 |  | MAR-25
95 | 220KV SS Pallantla in West Godavari Dist. (2 x100-1x100) | 220/132 | APTRANSCO | 100 |  | MAY-24
96 | Penukonda (Gorantla) (GEC-I) | 220/132 | APTRANSCO | 160 |  | MAY-24
97 | Bethamcherla in Kurnool District (GEC-I) | 220/132 | APTRANSCO | 160 |  | NOV-24
98 | 220 kV SS Nansuralla in Kurnool District (Additional 50 MVA T/F) | 220/33 | APTRANSCO | 50 |  | NOV-24
99 | Bhimadole Aug. (100 to 160MVA) | 220/132 | APTRANSCO | 60 |  | OCT-24
100 | Jakkanpur (GIS) s/s (160 MVA T/F-II) | 220/132 | BSPTCL | 160 |  | APR-24
101 | 220/132/33 kV GSS Thakurganj (1x160 MVA) | 220/132 | BSPTCL | 160 |  | MAR-25
102 | 400/220/132 kV GIS Bakhtiyarpur (1x160 MVA) | 220/132 | BSPTCL | 160 |  | MAR-25
103 | Jakkanpur (GIS) s/s (160 MVA T/F-III) | 220/132 | BSPTCL | 160 |  | MAY-24
104 | Rajim SS (T/F-I) | 220/132 | CSPTCL | 160 |  | FEB-25
105 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | 220/132 | CSPTCL | 320 |  | JUN-24
106 | Parchanpal (Jagdalpur) SS (late reported, commissioned in October-2024) | 220/132 | CSPTCL | 160 |  | NOV-24
107 | GIS Timarpur (100 MVA T/F) | 220/33 | DTL | 100 |  | APR-24
108 | 220kV GIS Substation at Timarpur (100 MVA T/F-II) | 220/33 | DTL | 100 |  | JUL-24
109 | Tivim SS | 220/33 | ED-GOA | 63 |  | FEB-25
110 | 220 kV Besan | 220/66 | GETCO | 320 |  | AUG-24
111 | 220 kV Jamla (Aug. from 410 MVA to 520 MVA) | 220/66 | GETCO | 110 |  | DEC-24
112 | Mera (Mithi Paldi) (T/F-II) (late reported commissioned in Nov-2024) | 220/66 | GETCO | 160 |  | DEC-24
113 | 220 kV Chandrapura (Aug. from 360 to 470 MVA) | 220/66 | GETCO | 110 |  | DEC-24
114 | 220 kV Kim (Aug. from 560 to 620 MVA) | 220/66 | GETCO | 60 |  | FEB-25
115 | 220 kV Babarzar | 220/66 | GETCO | 320 |  | FEB-25
116 | 220 kV Ichhapore (Augmentation from 410 MVA to 520 MVA) | 220/66 | GETCO | 110 |  | JAN-25
117 | 400 kV Vav (Augmentation from 660 MVA to 720 MVA) | 220/66 | GETCO | 60 |  | JAN-25
118 | 220 kV Anjar (Augmentation from 300 MVA to 360 MVA) | 220/66 | GETCO | 60 |  | JAN-25
119 | 220 kV Talangpor | 220/66 | GETCO | 60 |  | JUL-24
120 | 220 kV Kukma | 220/66 | GETCO | 100 |  | MAR-25
121 | 220 kV Ghodasar | 220/66 | GETCO | 160 |  | MAR-25
122 | 400 kV Vadavi | 220/66 | GETCO | 60 |  | MAR-25
123 | 220 kV Jangral | 220/66 | GETCO | 160 |  | MAR-25
124 | 220 kV Tappar | 220/66 | GETCO | 160 |  | MAR-25
125 | 220 kV Sisrana | 220/66 | GETCO | 160 |  | MAR-25
126 | 220 kV Sarigam (Upgradation 66kV) | 220/66 | GETCO | 320 |  | MAR-25
127 | 220 kV Mitha | 220/66 | GETCO | 100 |  | MAR-25
128 | 220 kV Deodar (Vakha) | 220/66 | GETCO | 60 |  | MAR-25
129 | 220 kV Suva (late reported, commissioned in October-2024) | 220/66 | GETCO | 160 |  | NOV-24
130 | 220 kV Jambuva (Augmentation from 260 MVA to 420MVA) | 220/66 | GETCO | 160 |  | NOV-24
131 | 220/66 kV Heiling Sub-Station | 220/66 | HPPTCL | 100 |  | DEC-24
132 | 220/132/33 kV AIS at Andheri (Kala Amb) District Sirmaur H.P. | 220/132 | HPPTCL | 200 |  | MAY-24
133 | 220kV I.A. Hisar (160-100) | 220/132 | HVPNL | 60 |  | APR-24
134 | 220KV Chormar (100 MVA T/F) | 220/132 | HVPNL | 100 |  | APR-24
135 | 220kV Samain | 220/33 | HVPNL | 100 |  | AUG-24
136 | 220 kV Rohtak (augmentation from 100 to 160 MVA) | 220/132 | HVPNL | 60 |  | DEC-24
137 | GIS Sector-15 II Gurugram (T/F-I) | 220/66 | HVPNL | 160 |  | DEC-24
138 | 220 kV Rangala Rajpur (additional 100 MVA) | 220/66 | HVPNL | 100 |  | DEC-24
139 | 220 kV Fatehabad (augmentation from 100 to 160 MVA) | 220/132 | HVPNL | 60 |  | DEC-24
140 | 220 kV A-5 Faridabad | 220/66 | HVPNL | 60 |  | FEB-25
141 | 220 kV Mehna Khera | 220/33 | HVPNL | 100 |  | JAN-25
142 | 220 kV Sampla | 220/132 | HVPNL | 100 |  | JAN-25
143 | 400 kV Nawada | 220/33 | HVPNL | 100 |  | JAN-25
144 | HSIIDC Rai Sonepat (220/33 kV 100 MVA T/F-II)(charged on 02-05-2024 however late reported by HVPNL) | 220/33 | HVPNL | 100 |  | JUL-24
145 | 220 kV Sector-32 Panchkula | 220/66 | HVPNL | 100 |  | MAR-25
146 | 220 kV Harfali ( New) | 220/66 | HVPNL | 200 |  | MAR-25
147 | 220 kV Tepla | 220/66 | HVPNL | 60 |  | MAR-25
148 | 220 kV Sector-15-II Gurugram ( 2nd T/F) | 220/66 | HVPNL | 160 |  | MAR-25
149 | HSIIDC Rai Sonepat 220/33 kV T/F-I | 220/33 | HVPNL | 100 |  | MAY-24
150 | Sonta ss (160-100 MVA) | 220/66 | HVPNL | 60 |  | MAY-24
151 | HSIIDC Rai Sonepat 220/132 kV T/F-II | 220/132 | HVPNL | 160 |  | MAY-24
152 | Augmentation at 220 kV Masudpur SS | 220/132 | HVPNL | 100 |  | NOV-24
153 | 220 kV GIS Transport Hub, Sector-8 IMT Manesar | 220/66 | HVPNL | 100 |  | SEP-24
154 | Lohardaga GSS | 220/132 | JUSNL | 300 |  | DEC-24
155 | Santhpur SS (2X100 MVA T/F at Kappakera | 220/110 | KPTCL | 200 |  | FEB-25
village, Santapur Hobli, in Bidar Dist.) (GEC-II)
156 | Basarkod ( Establishing 2x100 MVA, 220/110 kV Sub-station ) | 220/110 | KPTCL | 100 |  | MAR-25
157 | Hosakote (Ekarajapura) Providing Additional 1X100 MVA, 220/66 kV Transformer | 220/66 | KPTCL | 100 |  | MAR-25
158 | Somasamudra SS (2X100 MVA T/F) | 220/110 | KPTCL | 200 |  | NOV-24
159 | Keonics (Electronic City): 2x150 MVA ICT | 220/66 | KPTCL | 300 |  | SEP-24
160 | 220 kV GIS Pathnamthitta | 220/110 | KSEB | 100 |  | MAR-25
161 | Construction of 220/132 kV substation at Bargawan (TBCB) (late reported commissioned in Sept-2024) | 220/132 | MPPTCL | 320 |  | DEC-24
162 | Indore II (Jaitpura) 220 kV S/s (additional T/F) | 220/132 | MPPTCL | 160 |  | JAN-25
163 | Pithampur (sector III) 220 kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | MPPTCL | 40 |  | JAN-25
164 | Nepanagar 220 kV S/s (agumentation of 160 MVA by 200 MVA X-mer) | 220/132 | MPPTCL | 40 |  | JAN-25
165 | Construction of Begamganj SS (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | 220/132 | MPPTCL | 320 |  | JUL-24
166 | 220/132/33kV Ajaygarh S/s (TBCB) | 220/132 | MPPTCL | 320 |  | JUN-24
167 | Malanpur 220 kV s/s Repl of 160 MVA by new 200 MVA X-mer | 220/132 | MPPTCL | 40 |  | MAR-25
168 | Bairagarh (Bhopal) 220 KV S/s Addl. 1x160MVA X-mer | 220/132 | MPPTCL | 160 |  | MAY-24
169 | Nagda 220 kV SS (replacement of 160 MVA by 200 MVA T/F) | 220/132 | MPPTCL | 40 |  | NOV-24
170 | 220 kV Nalasopara substation (additional 100 MVA T/F) | 220/22 | MSETCL | 100 |  | AUG-24
171 | 220 kV Tembhurni substation (replacement of 25 MVA by 100 MVA T/F) | 220/33 | MSETCL | 25 |  | AUG-24
172 | 220 kV Vairag S/s (replacement of 2X25 MVA by 2X50 MVA T/F) | 220/33 | MSETCL | 50 |  | DEC-24
173 | 220 kV Bhigwan S/s (replacement of 25 MVA by 50 MVA T/F) | 220/33 | MSETCL | 25 |  | DEC-24
174 | 220 kV Palghar SS (ICT-II) | 220/132 | MSETCL | 100 |  | FEB-25
175 | 220 kV Jalna substation (Replacement of 50 MVA T/F with 100 MVA T/F) | 220/132 | MSETCL | 50 |  | JAN-25
176 | 220kV Walchandnagar substation (replacement of 100 MVA by 200 MVA T/F) | 220/132 | MSETCL | 100 |  | JUL-24
177 | 220/33kV New Timber Market GIS (Panvel -II )(50 MVA T/F) | 220/33 | MSETCL | 50 |  | JUN-24
178 | 220 kV Tilwani substation ( 1X 100 MVA, 220/33 kV T/F) | 220/22 | MSETCL | 100 |  | MAR-25
179 | 220 kV Colourchem substation ( 1 x(100-50) MVA, 220/22-22 kV) | 220/22 | MSETCL | 50 |  | MAR-25
180 | 220 kV Nagewadi substation ( 1X 50 MVA, 220/33 kV T/F ) | 220/33 | MSETCL | 50 |  | MAR-25
181 | 220 kV Five star MIDC substation ( 1x50 MVA, 220/33kV T/F ) | 220/33 | MSETCL | 50 |  | MAR-25
182 | 220 kV Anand Nagar substation (1x(100-50) MVA, 220/22-22 kV) | 220/22 | MSETCL | 50 |  | MAR-25
183 | 400 kV Lonikand-I substation (1x50 MVA, 220/33 kV T/F ) | 220/33 | MSETCL | 50 |  | MAR-25
184 | 220 kV Colourchem substation (1x(100-50) MVA, 220/22-22 kV) | 220/22 | MSETCL | 50 |  | MAR-25
185 | 220 kV Jambhul substation ( 1 x50 MVA, 220/22 kV T/F ) | 220/22 | MSETCL | 50 |  | MAR-25
186 | 220kV Jambhul (Additional T/F) | 220/22 | MSETCL | 50 |  | MAY-24
187 | 220kV Chalisgaon Substation(1x200 MVA Additional T/F) | 220/132 | MSETCL | 200 |  | MAY-24
188 | 220/33 kV New Timber Market GIS (Panvel -II ) | 220/33 | MSETCL | 50 |  | NOV-24
189 | 220/33 kV Shendra GIS (DMIC)(2X50 MVA T/F) | 220/33 | MSETCL | 100 |  | SEP-24
190 | 220 kV Jeur (Replacement of 100 MVA T/F with 200 MVA T/F) | 220/132 | MSETCL | 100 |  | SEP-24
191 | Balichandarpur Palei GSS (T/F-II) | 220/33 | OPTCL | 40 |  | DEC-24
192 | 220/132/33 kV Turmunga GSS (20 MVA T/F-I)(late reported, commissioned in August-2024) | 220/33 | OPTCL | 20 |  | JAN-25
193 | 220/132/33KV Turmunga GSS (1st 160 MVA Auto | 220/132 | OPTCL | 160 |  | JUL-24
Transformer)
194 | 220/132/33kV Kuarnmunda GSS (2nd 160 MVA Auto transformer) | 220/132 | OPTCL | 160 |  | JUL-24
195 | 220/33 KV GSS Balichandrapur Palei | 220/33 | OPTCL | 20 |  | MAY-24
196 | 220 kV S/S Botianwala (Addl. 100 MVA 220/66 kV PT/f) | 220/66 | PSTCL | 100 |  | APR-24
197 | 220 kV S/S Bhari (Addl. 100 MVA 220/66 kV PT/f) | 220/66 | PSTCL | 100 |  | APR-24
198 | 220 kV Rajpura SS (Aug. of 100 MVA by 160 MVA) | 220/66 | PSTCL | 60 |  | DEC-24
199 | 220 kV Gurdaspur SS (T/F-II) | 220/66 | PSTCL | 100 |  | DEC-24
200 | 220 kV Mohali-2 SS (Aug of 100 MVA to 160 MVA ) | 220/66 | PSTCL | 60 |  | FEB-25
201 | 220 kV Ghulal SS (Aug. 100 MVA to 160 MVA) | 220/66 | PSTCL | 60 |  | FEB-25
202 | Addl 100 MVA T/F at 220 kV S/S Majitha (N-1) | 220/66 | PSTCL | 100 |  | JAN-25
203 | 220 kV S/S Gurdaspur (1x100 MVA) (Upgraded from 132 KV to 220 KV) | 220/66 | PSTCL | 100 |  | JUL-24
204 | Aug. of 100 MVA T/F to 160 MVA T/F at 220 kV SS Mandi Gobindgarh G-3 | 220/66 | PSTCL | 60 |  | JUL-24
205 | Aug 100 to 160 MVA at 220 KV S/S Kartarpur | 220/66 | PSTCL | 60 |  | JUN-24
206 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Badhshahpur | 220/66 | PSTCL | 100 |  | MAY-24
207 | Addl 100 MVA 220/66 KV T/F at 220 KV S/S Naraingarh (N-1) | 220/66 | PSTCL | 100 |  | MAY-24
208 | 220 kV S/S Banur (Aug. of 1x100 MVA T/F with 1x160 MVA T/F) | 220/66 | PSTCL | 60 |  | MAY-24
209 | Aug. of 100MVA 220/66kV T/F to 160MVA 220/66kV T/F at 220kV S/Stn Bajakhana | 220/66 | PSTCL | 60 |  | MAY-24
210 | 220 kV SS Sandhaur (late reported, commissioned in October-2024) | 220/66 | PSTCL | 100 |  | NOV-24
211 | 220 kV SS Civil line Amritsar (late reported, commissioned in October-2024) | 220/132 | PSTCL | 100 |  | NOV-24
212 | Addl. 100 MVA 220/66 kV T/F at 220 kV Badni Kalan SS | 220/66 | PSTCL | 100 |  | NOV-24
213 | 220 kV Sandhwan S/s | 220/66 | PSTCL | 100 |  | SEP-24
214 | 220 kV GIS S/s Baram | 220/33 | PTCUL | 50 |  | MAR-25
215 | 220 kV GSS Heerapura (replacement of 100 MVA T/F with 160 MVA) | 220/132 | RVPNL | 60 |  | AUG-24
216 | 220 kV Jhunjhunu GSS (replacement of 100 MVA T/F by 160 MVA) | 220/132 | RVPNL | 60 |  | DEC-24
217 | 220 kV GSS Sayla | 220/132 | RVPNL | 160 |  | FEB-25
218 | 220 kV GSS Udyog Vihar, Sriganganagar (Augmentation) | 220/132 | RVPNL | 160 |  | JAN-25
219 | 220 kV GSS MIA, Alwar (Augmentation) | 220/132 | RVPNL | 100 |  | JAN-25
220 | 220 kV GSS Khinvsar (replacement of 100 MVA T/F with 160 MVA T/F) | 220/132 | RVPNL | 60 |  | JUL-24
221 | 220 kV GSS, Ratangarh | 220/132 | RVPNL | 100 |  | MAR-25
222 | 220 kV GSS, Bhiwadi | 220/132 | RVPNL | 100 |  | MAR-25
223 | 220 kV GSS Aspur | 220/132 | RVPNL | 100 |  | MAR-25
224 | 220 kV GSS, Bansur | 220/132 | RVPNL | 100 |  | MAR-25
225 | 220 kV GSS Suratgarh (160-100) =60 | 220/132 | RVPNL | 60 |  | MAR-25
226 | 220 kV GSS IG Nagar (160-100) =60 | 220/132 | RVPNL | 60 |  | MAR-25
227 | 220kV GSS Bap (Additional T/F) | 220/132 | RVPNL | 160 |  | MAY-24
228 | 220 kV GSS Balotra (replacement of 100 MVA T/F with 160 MVA T/F) | 220/132 | RVPNL | 60 |  | NOV-24
229 | Sawai Madhopur (100 to 160 MVA) | 220/132 | RVPNL | 60 |  | OCT-24
230 | Bharatpur (100 to 160 MVA) | 220/132 | RVPNL | 60 |  | OCT-24
231 | Banar GIS (Distt. Jodhpur) | 220/132 | RVPNL | 200 |  | OCT-24
232 | 220 kV GSS Nimbahera (replacement of existing 100 MVA T/F with 160 MVA T/F) | 220/132 | RVPNL | 60 |  | SEP-24
233 | 220 kV Nirmal SS (160-100 MVA) | 220/132 | TSTRANSCO | 60 |  | FEB-25
234 | Hial SS (50-20 MVA)(Late reported, charged in July 2024) | 220/33 | TSTRANSCO | 30 |  | FEB-25
235 | Narsapur SS (late reported, charged in October-2024) | 220/132 | TSTRANSCO | 160 |  | FEB-25
236 | 220 kV Jurala SS (160-100 MVA) | 220/132 | TSTRANSCO | 60 |  | FEB-25
237 | 220/132/33 kV S/S, Bowrampet | 220/33 | TSTRANSCO | 50 |  | MAR-25
238 | 220 kV Mahabubabad S/S | 220/132 | TSTRANSCO | 100 |  | MAR-25
239 | 220 kV S/s Sangipur (New) 160 MVA T/F-II | 220/132 | UPPTCL | 160 |  | APR-24
240 | 220 kV S/s Kanpur South (Capacity Augmentation 60 MVA T/F-III) | 220/33 | UPPTCL | 60 |  | APR-24
241 | 220 kV S/s Khurja (Capacity Augmentation 160 MVA T/F-III) | 220/132 | UPPTCL | 160 |  | APR-24
242 | 220 kV S/s Sirathu (Capacity Aug. 160 MVA T/F-III) | 220/132 | UPPTCL | 160 |  | APR-24
243 | 220 kV S/s Pahadi Chitrakoot (Capacity Augmentation) | 220/132 | UPPTCL | 160 |  | AUG-24
244 | Sirsaganj Firozabad S/s (Capacity Augmentation) | 220/132 | UPPTCL | 160 |  | DEC-24
245 | 220 kV Kursi Road SS, Lucknow (160-100 MVA) | 220/132 | UPPTCL | 60 |  | FEB-25
246 | 400 kV S/s Sector-148 Noida, GB Nagar (Capacity Augmentation) T/F-II | 220/132 | UPPTCL | 160 |  | JAN-25
247 | 220 kV S/s Sector-129 Noida, GB Nagar (Capacity Augmentation) T/F-IV | 220/132 | UPPTCL | 160 |  | JAN-25
248 | 220 kV S/s Jewar Extn., GB Nagar T/F-I | 220/132 | UPPTCL | 160 |  | JAN-25
249 | 220 kV S/s Hardoi Road, Lucknow (Capacity Augmentation) T/F-III | 220/132 | UPPTCL | 160 |  | JAN-25
250 | 220 kV S/s Metro Depot Gr. Noida GB Nagar (New) T/F-I and T/F-II | 220/132 | UPPTCL | 320 |  | JUL-24
251 | 220 kV S/s Darshan Nagar Ayodhya (New) T/F-I | 220/132 | UPPTCL | 160 |  | JUL-24
252 | 220 kV S/s Kanduni Sitapur (New) T/F-II | 220/132 | UPPTCL | 200 |  | JUL-24
253 | 220 kV S/s Knowledge Park-5 Gr. Noida GB Nagar (New) T/F-II | 220/132 | UPPTCL | 160 |  | JUN-24
254 | 220 kV S/s Faridpur, Bareilly (New T/F-II) | 220/132 | UPPTCL | 100 |  | MAR-25
255 | 220 kV S/s Pratap Vihar, Ghaziabad (Capacity Augmentation) (160-100) | 220/132 | UPPTCL | 60 |  | MAR-25
256 | 220 kV S/s Boner, Aligarh (Capacity Augmentation) (160-100) | 220/132 | UPPTCL | 60 |  | MAR-25
257 | 220 kV S/s Mainpuri (Capacity Augmentation) T/F-III (160-100) | 220/132 | UPPTCL | 60 |  | MAY-24
258 | 220 kV S/s Bhadaura Ghazipur (New) T/F-II | 220/132 | UPPTCL | 100 |  | MAY-24
259 | 220 kV S/s Maharajganj (New) T/F-II | 220/132 | UPPTCL | 160 |  | MAY-24
260 | 220 kV S/s Jahangirabad Bulandshahr (Capacity Augmentation) T/F-III | 220/132 | UPPTCL | 160 |  | MAY-24
261 | 220 kV S/s Hata Kushinagar (Capacity Augmentation) (160-100) | 220/132 | UPPTCL | 60 |  | MAY-24
262 | 220 kV S/s Khorabar Gorakhpur (New) T/F-II | 220/33 | UPPTCL | 60 |  | MAY-24
263 | 220 kV GIS SS Badaun Road Bareilly (T/F-II) | 220/33 | UPPTCL | 60 |  | NOV-24
264 | 220 kV GIS S/s Badaun Road Bareilly (New) GIS | 220/33 | UPPTCL | 60 |  | OCT-24
265 | 220 kV S/s Debai Bulandshaher (Capacity Augmentation) | 220/132 | UPPTCL | 160 |  | SEP-24
266 | Food Park (T/F-I) 220 KV GIS | 220/132 | WBSETCL | 160 |  | AUG-24
267 | Food Park (T/F-II) 220 KV GIS | 220/132 | WBSETCL | 160 |  | AUG-24
268 | AB Zone 220 KV GIS (upgraded to 220 kV from 132 kV) | 220/132 | WBSETCL | 320 |  | NOV-24
| TOTAL STATE SECTOR |  |  | 21013
| TOTAL 220 kV |  |  | 21013
765 kV
PRIVATE SECTOR
269 | Aug. of Khavda PS1 by 2X1500 MVA,765/400kV ICT (MVA:6000) (Late reported-commisioned in Feb 2025) | 765/400 | MEGHA | 3000 |  | MAR-25
| TOTAL PRIVATE SECTOR |  |  | 3000
| TOTAL 765 kV |  |  | 3000
400 kV
PRIVATE SECTOR
270 | ACME Solar Holdings limited PS at Jaisalmer (4x315 MVA) (Late reported, commissioned in Oct-24) | 400/33 | ACME | 1260 |  | MAR-25
271 | Adani Green Energy Limited (PSS-04) at Khavda RE Park Gujarat (Late Reported Comm. Feb-25) | 400/33 | ADANIGREEN | 660 |  | MAR-25
272 | Adani Green Energy Limited (PSS-05) at Khavda RE Park Gujarat (Late Reported Comm. Apr-24) | 400/33 | ADANIGREEN | 660 |  | MAR-25
273 | Adani Green Energy Limited (PSS-13) at Khavda RE Park Gujarat (Late Reported Commissioned Jan-25) | 400/33 | ADANIGREEN | 1320 |  | MAR-25
274 | Adani Renewable Energy Holding Four Limited at Badi Sid,Rajasthan (Late Reported Comm. Sep-24) | 400/33 | AREHFL | 660 |  | MAR-25
275 | Augmentation of transformation capacity 1X500 MVA ICT (3rd ) at patran (GIS) S/s (RTM) | 400/220 | INDIGRID | 500 |  | DEC-24
276 | Aug. of transformation capacity at Kallam PS by 2x500 MVA, 400/220 kV ICTs (3rd & 4th)(ISTS_RTM) | 400/220 | INDIGRID | 1000 |  | JAN-25
277 | Gadag PS (Trans Scheme for Solar Energy Zone in Gadag (1000 MW) Karnataka Part-A Phase-I) | 400/220 | RENEW | 1000 |  | SEP-24
278 | RGESL Pooling S/S at Solapur, Maharashtra (Late Reported Commissioned Jan-25) | 400/33 | Renew Green | 225 |  | MAR-25
279 | Sarjan Realities Private Limited at (PSS-09) Khavda RE Park Gujarat ((Late Reported Comm. Nov-24) | 400/33 | Sarjan Realities | 660 |  | MAR-25
280 | Xeldem New SS (GTTPL - TBCB) | 400/220 | STERLITE | 1000 |  | OCT-24
281 | Vapi -II (Western Region Strengthening Scheme-XIX (WRSS-XIX and NERSS - IX) | 400/220 | STERLITE | 1000 |  | SEP-24
| TOTAL PRIVATE SECTOR |  |  | 9945
| TOTAL 400 kV |  |  | 9945
220 kV
PRIVATE SECTOR
282 | Adani Renewable Energy Holding Four Limited at | 220/33 | AREHFL | 500 |  | MAR-25
Bhimsar, Rajasthan ((Late Reported Comm. Nov-24)
283 | RSJPL Pooling S/S at Jaisalmer | 220/33 | Renew Surya Jyoti | 210 |  | MAR-25
284 | RSRPL Pooling S/S (Late Reported Commissioned May-24) | 220/33 | Renew Surya | 200 |  | MAR-25
285 | RSVPL Pooling S/S at Jaisalmer | 220/33 | Renew Surya | 200 |  | MAR-25
286 | M/s Sembcorp Green Infra Private Limiteds generation (PS) at Koppal (Late Reported Comm. Sep-24) | 220/33 | Sembcorp Green | 320 |  | MAR-25
287 | Serentica Renewables India Private Limited(SRIPL)PS at Bikaner,Rajasthan(Late Reported Apr-24) | 220/33 | Serentica | 550 |  | MAR-25
288 | Serentica Renewables India1 Private Limited(SRI1PL)PS atKoppal,Karnataka (Late Reported Comm.May-24) | 220/33 | Serentica | 300 |  | MAR-25
289 | Nangalbibra 220/132 kV (2x160MVA) | 220/132 | STERLITE | 320 |  | OCT-24
290 | Vena Energy Vidyuth Private Limited PS in Jumlapura Village,Koppal (Late Reported, Comm. Oct-24) | 220/132 | Vena Energy | 160 |  | MAR-25
| TOTAL PRIVATE SECTOR |  |  | 2760
| TOTAL 220 kV |  |  | 2760
| GRAND TOTAL |  |  | 86433