## line_construction_status_test_r
REPORT INDICATING STATUS OF CONSTRUCTION OF TRANSMISSION LINES (220 kV & ABOVE) IN RFD PROGRAMME DURING- 2023-24
As on 31-AUG-2023
Sl No | Name of Transmission Lines | Ckts (S/C) & (D/C) | Voltage Level (kV) | Total Length (cKm) | Progress Status of Transmission |  |  |  | Target Date |  | Tag Names |  | Remarks
[5 empty] | Total Locations (Nos) | Foundation completed (Nos) | Tower Erected (Nos) | Stringing completed (CKm) | Schedule | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |  | 13.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | LILO of CTPS -Kalyaneswari line at RTPS | D/C | 220 | 12 | 72 | 43 | 8 | 0 | JAN-24 | JAN-24 | RFD |  | Scheduled target - Jan'24. Revised Line length = 12.956, Route length= 12.956*4 =51.824CKM
2 | LILO of MTPS-A - Barjora at MTPS -B | D/C | 220 | 43 | 76 | 74 | 70 | 4.25 | JAN-24 | JAN-24 | RFD |  | Scheduled target - Jan'24. Line length = 21.52KM, Route lenth = 21.52*4 = 86CKM
3 | LILO of MTPS-A - Durgapur line at Barjora s/s | S/C | 220 | 4 | 17 | 17 | 15 | 1.29 | JAN-24 | JAN-24 | RFD |  | Scheduled target - Jan'24. Line length = 4.36KM, Route length = 4.36*2 = 8.76CKM
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | Bikaner-II PS-Khetri 400kV line (phase II part F) | M/C | 400 | 1102 | 0 | 0 | 0 | 1102 | MAY-23 | JUL-23 | RFD |  | Commissioned 06/23.
2 | Fatehgar-II - Bhadla-II (2nd) | D/C | 765 | 404 |  |  |  |  | FEB-24 |  | RFD
3 | Khetri-Bhiwadi 400kV line (Twin HTLS) (PHASE II Part F) | D/C | 400 | 251 | 0 | 0 | 0 | 251 | JUL-23 | JUL-23 | RFD |  | Commissioned 06/23.
4 | Lower Subhansiri - Biswanath Chariyali line -II | D/C | 400 | 371 | 515 | 376 | 227 | 0 | SEP-23 | MAR-23 | RFD |  | Initially work was stalled on a/c of local disturbance/ agitation against big dams. Contract was short closed as generation was not coming. Balance work of line awarded in Dec'20. As per communication dated 27.05.21 from NHPC 1st & 2nd Unit schedule preponed from May'23 to Aug'22.
5 | Ramgarh-II -Jaisalmer-II (RVPNL) (Twin HTLS) | D/C | 400 | 100 |  |  |  |  | JUL-23 |  | RFD
6 | Ramgarh-II SEZ PP- Fateharh-II (Twin HTLS) | D/C | 400 | 88 |  |  |  |  | NOV-23 |  | RFD
7 | Re-conductoring of BTPS- Salakati 220kv line with Single HTLS Conductor | D/C | 220 | 8 | 0 | 0 | 0 | 8 | MAY-23 | JUL-23 | RFD |  | Commissioned 06/23.
8 | Removal of LILO of one Ckt. of Bhadla-Bikaner (RVPN) at Bikaner (PG) and Extension of this LILO section from Bikaner (PG) to Bikaner-PS -Bikaner (PG) | D/C | 400 | 68 | 0 | 0 | 0 | 68 | SEP-23 | AUG-23 | RFD |  | Commissioned 07/23.
9 | Simbhavali (400kV) -Muradnagar-II (Gaziabad) 400kV D/C line | D/C | 400 | 142 | 0 | 0 | 0 |  | APR-23 | MAR-23 | RFD
10 | Sitamarhi (POWERGRID) (Quad Moose) - Dhalkebar (Nepal) (Indian Portion) | D/C | 400 | 78 |  |  |  |  | OCT-23 |  | RFD
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | Amnour- Digha | D/C | 220 | 48 | 0 | 0 | 0 |  | APR-23 | JAN-22 | RFD
2 | Bakhtiyarpur (New) - Fatuha (BSPTCL) | D/C | 220 | 45 | 157 | 142 | 107 | 0 | OCT-23 | DEC-22 | RFD |  | Work under progress.
3 | BTPP - Dehri-on-sone (single zebra conductor) | D/C | 220 | 77 | 246 | 177 | 97 |  | OCT-23 | AUG-22 | RFD
4 | BTPP - Dumraon (New) GSS | D/C | 220 | 64 | 215 | 185 | 0 |  | SEP-23 | FEB-23 | RFD
5 | BTPP - Karmnasa GSS line (twin moose conductor) | D/C | 220 | 59 | 185 | 134 | 58 |  | JUN-23 | FEB-23 | RFD
6 | BTPP - Naubatpur line (twin moose conductor) | D/C | 400 | 126 | 339 | 257 | 190 |  | SEP-23 | FEB-23 | RFD
7 | LILO of (Quad) Barh - Patna at Bakhtiyarpur (New) | D/C | 400 | 10 | 61 | 49 | 43 |  | JUL-23 | FEB-23 | RFD |  | ROW issues.
8 | LILO of Sipara (BSPTCL) - Bihta (BSPTCL) at Jakkanpur (New) | D/C | 220 | 47 | 0 | 0 | 0 |  | AUG-23 |  | RFD |  | M/s BGCL
9 | Pusouli (New) - Dehri | D/C | 220 | 62 | 159 | 135 | 110 | 18 | SEP-23 | MAR-23 | RFD |  | work under progress
10 | Tajpur- Goraul line | D/C | 220 | 102 | 0 | 0 | 0 | 102 | MAY-23 | MAY-23 | RFD |  | Commissioned 04/23.
11 | Tajpur- Samastipur (New) Trans. line | D/C | 220 | 37 | 0 | 0 | 0 |  | MAY-23 | MAR-23 | RFD
12 | Thakunganj - Kishanganj (New) Trans. line | D/C | 220 | 52 | 0 | 0 | 0 |  | MAR-24 | DEC-22 | RFD
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | Kuurud - Patan DCDS line | D/C | 220 | 22 |  |  |  |  | MAR-24 |  | RFD
DELHI TRANSCO LIMITED ( DTL )
1 | 220 kV between Park Street to Electric Lane and between Lodhi Road to Electric Lane | S/C | 220 | 17 | 0 | 0 | 0 |  | OCT-23 | JUL-23 | RFD |  | 1. Cable laying work have been completed in all 19 sections. 2. Cable Straight through Jointing work completed in all 17 JBs. 3. Case file for releasing of Advance payment (Rs.6.45 Crore) in favour of M/s. PGCIL have been processed on 14/03/2022. This Case file has been received back from Finance Dept. on 12/05/2022 seeking some clarifications, accordingly the Case file put up for seeking clarification from Planning Deptt on 12/05/2022, 27/05/2022, 14/06/2022, 28/07/2022 and 23/08/2022 and received back on 30.09.2022. Clarification sought from PGCIL as per queries of Planning department on dated 04.10.2022, which is still awaited. A) Electric Lane to Park Street (JB#01):- 4. 220kV GIS end termination work and installation of link boxes has been completed.Termination of OFC is completed. 5. Electrical Inspector clearance has been received on 28-03-2023. 6. Commissioning team meeting/activities held on 27th to 29th March, 2023. 7. As per direction of Dir(Opr), and as i
2 | 220 KV D/C U/G Cable from Kashmiri Gate to Timarpur (2x5) | D/C | 220 | 10 | 0 | 0 | 0 |  | NOV-23 | OCT-23 | RFD |  | 1. Contract Agreement has been executed on 15.10.2019. 2. Cable laying work completed in all 09 sections. 3. Cable Jointing (48) has been completed in all 08 JBs. 4. The sites are handed over to PWD by 26.04.2022 after completion of work on PWD Road. 5. Cable end terminations (6 Nos) work has been completed at Timarpur end. On 10.05.2022. 6. A case file has been forwarded to Project I deptt on 15.06.2022 seeking current status of the availability of GIS bays at 220KV Kashmiri Gate S/Stn. GIS interface drawing for manufacturing of Cable indoor termination has been provided to M/s LSCI on dt. 10.03.2023. 8. A case file was forwarded to Planning wing of DTL seeking information/confirmation about the execution of proposed 220 kV Rajghat  Kashmiri Gate D/C O/H T/L and location of the end tower of the same towards 220 kV Kashmiri Gate S/stn. The case file is received back on dt. 25.01.2023 informing that as per 13th Business plan connectivity from 220kV Rajghat to Kashmiri Gate S/st
3 | LILO of Electric Lane to Park Street at Dev Nagar (U/G Cable) | D/C | 220 | 10 | 0 | 0 | 0 |  | JUL-23 | APR-23 | RFD |  | 1. CPG has been submitted on 20.12.2019. 2. Contract Agreement has been executed on 23.12.2019. 3. L-2 network has been approved on 06.01.2020. 4. Cable laying work has been completed in 12 sections out of 12 sections. 5. Jointing works have been completed at 12 JBs out of 12 JBs. 6. Indoor End Termination work at 220kV GIS bay Devnagar S/stn has been completed. 7. Park Street  Devnagar 220KV U/G cable has energized on 06.12.2022 at 20:58 Hrs. 8. Provisional time extension has been approved from competent authority up to 30.04.2023. 9. The Electric lane-Dev Nagar circuit was test charged on 29.03.2023 at 20:54 hrs but it tripped on differential protection soon after. The repairing work of side cable is in progress.
ENERGY & POWER DEPARTMENT,GOVT. OF SIKKIM ( SPD )
1 | Dikchu -Singhik | D/C | 220 | 22 |  |  |  |  | JUN-23 |  | RFD
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | Balance work of 220kV D/C KALAWAD - KANGASIYALI LINE with AL-59 condu. and OPGW | D/C | 220 | 114 |  |  |  |  | OCT-23 |  | RFD
2 | Bhogat-Kalavad (Twin AL-59) | D/C | 400 | 250 | 409 | 408 | 402 | 198.78 | NOV-23 | SEP-23 | RFD |  | WIP.
3 | Chorania - Salejada line (AL-59) | D/C | 220 | 135 | 217 | 216 | 215 | 126.32 | DEC-23 | DEC-23 | RFD |  | WIP .
4 | LILO of one Ckt. Vadavi- Halvad line at Sanand-II GIDC s/s with Twin AL-59 Cond. and OPDW line | D/C | 400 | 85 | 0 | 0 | 0 |  | FEB-24 | MAR-23 | RFD
5 | Soja -Zerda line (Pkg-2) with Twin AL-59 Conductor | D/C | 400 | 135 | 200 | 200 | 200 | 135.36 | JUL-23 | MAY-23 | RFD |  | RoW issues, court matter and COVID-19 pandemic
6 | Vadavi (Balance Work) - Halvad line (Package-2) (Twin AL-59) | D/C | 400 | 144 |  |  |  |  | DEC-23 |  | RFD
7 | Vadinar (Balance Work) -Amreli line (PKG-III) with ACSR Twin Moose Conductor and Earth Wire | D/C | 400 | 121 | 533 | 533 | 533 | 242 | JAN-24 | JUN-23 | RFD |  | WIP
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | Bhiwani - Isharwal line | D/C | 220 | 100 | 212 | 202 | 190 | 75.66 | DEC-23 | DEC-23 | RFD |  | Work is in progress. Work is held up due to severe RoW problem from farmers. However, matter taken up with District Administration, Bhiwani for resolving the issue. MD, HVPNL, Panchkula to hold a meeting with farmers on dated 12.05.2023 at Shakti Bhawan Panchkula for resolving the issue.
2 | Creation of 220 kV 0.5 sq D/C Mund-IOCL Line Karnal. | D/C | 220 | 34 | 135 | 135 | 135 | 68 | AUG-23 | AUG-23 | RFD
3 | LILO of both Ckts. of 220kV Sector-65-Pali line at Kadarpur line (AL-59) | D/C | 220 | 7 | 45 | 13 | 13 | 0 | DEC-23 | MAR-24 | RFD |  | Work in progress. (Forest Clearance Stage-I received)
4 | LILO of both Ckts. of Pali-Sector-56 at Kadarpur | D/C | 220 | 14 | 80 | 13 | 0 |  | DEC-23 | MAR-24 | RFD |  | Forest clearance pending
5 | LILO of Ckt. no. 04 from 400kV S/S Sector-72 Gurgaon (PGCIL) - Sector- 72 Gurgaon (HVPNL) at Sector-15-II at Gurgaon | D/C | 220 | 5 | 28 | 2 | 2 | 0 | OCT-23 | DEC-23 | RFD |  | Work in progress.
6 | LILO of Mohana - Samalkha line at Jajji (PGCIL) | D/C | 220 | 3 | 24 | 24 | 16 | 1 | DEC-23 | SEP-23 | RFD |  | Work in progress.
7 | LILO of Sector-72- Rangla Raipur at Roj-Ka-Meo | D/C | 220 | 7 | 10 | 9 | 0 |  | NOV-23 | JUN-23 | RFD |  | Short closed.
8 | Mandanpur - Kunihar line at Sector-32 Madanpur - Kunihar line at PGCL Naggal | D/C | 220 | 40 | 73 | 73 | 66 | 28.4 | JUL-23 | DEC-23 | RFD |  | Work in progress.
9 | Panchkula (PGCIL)- Panchkula Sector-32 | D/C | 220 | 40 | 74 | 74 | 67 | 31.4 | AUG-23 | DEC-23 | RFD |  | Work in Progress.
10 | Prithla - Sector-78 Faridabad line | D/C | 220 | 59 | 169 | 125 | 66 | 0 | FEB-24 | MAR-24 | RFD |  | Work in progress.
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | Mazra - Karian | D/C | 220 | 35 | 52 | 30 | 0 | 0 | JUL-23 | MAR-23 | RFD |  | Work is in Progress.
2 | PGCIL (PS) Kala Amb - Andheri s/s | D/C | 220 | 6 | 0 | 0 | 0 |  | SEP-23 | MAR-23 | RFD
3 | Stringing of 2nd Ckts. 220kV line Dehar Power House -Kangoo s/s | D/C | 220 | 4 | 0 | 0 | 0 |  | AUG-23 | MAR-23 | RFD
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | LILO of 220kV D/C Govindpur -TTPS at Jainmore | D/C | 220 | 47 | 92 | 82 | 67 | 24.3 | SEP-23 | MAR-23 | RFD |  | Work in Progress.
2 | PUVNL- Patratu | D/C | 400 | 14 | 0 | 0 | 0 |  | JUL-23 |  | RFD |  | Request letter regarding additional fund as difference of sanctioned cost and offered price of L-1 bidder has been sent to energy dept. Govt of Jharkhand. After sanctioning of requisite fund, work order will be issued.
3 | Quad Essar (Chandwa) - Latehar (JUSNL) TL | D/C | 400 | 83 | 122 | 122 | 120 | 42.58 | SEP-23 | MAR-23 | RFD |  | Work in Progress.
J&K POWER DEVELOPMENT DEPARTMENT ( JKPDD )
1 | LILO-II of Bishnah-Hiranagar Tr. Line from 400/220 kV Grid Station Jatwal(PGCIL) to Loc. No. 203 | D/C | 220 | 4 |  |  |  |  | MAY-23 |  | RFD
2 | (PMDP - Kashmir) Extension of Mirbazar - Alusteng line upto New Wanpoh | D/C | 220 | 12 | 19 | 7 | 0 | 0 | MAY-23 | JUN-23 | RFD |  | Works in progress.
3 | (PMDP - Kashmir) LILO of one ckt. Alusteng - New Wanpoh at Tailbal | D/C | 220 | 7 | 5 | 5 | 4 |  | AUG-23 | MAR-23 | RFD |  | LILO Completed after ROW issue at one location.
4 | Wagoora-Budgam- Zainkote | D/C | 220 | 60 | 123 | 106 | 82 | 17 | JAN-24 | OCT-23 | RFD |  | ROW issues at various locations delaying the project.
5 | Wagoora-Mirbazar | D/C | 220 | 104 | 177 | 175 | 173 | 63 | AUG-23 | JUL-23 | RFD |  | ROW,, compensation issues delaying the project.
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | Ghanagapura - Aaheri line | D/C | 220 | 112 |  |  |  |  | FEB-24 |  | RFD
2 | Ghanagapura - Ferozbad line | D/C | 220 | 72 |  |  |  |  | JAN-24 |  | RFD
3 | Ghanagapura - link Shahpur - Khanapura line | D/C | 220 | 21 |  |  |  |  | DEC-23 |  | RFD
4 | LILO at Bilagi - Kudigi -Vajramatti line | D/C | 220 | 37 |  |  |  |  | JAN-24 |  | RFD
5 | LILO at Keonics (Electronic City)- Mylsandra - Yeradanahalli | S/C | 220 | 21 |  |  |  |  | JAN-24 |  | RFD
6 | LILO at Keonics (Electronic City) - Somanahalli Hoddy | S/C | 220 | 38 |  |  |  |  | JAN-24 |  | RFD
7 | LILO at Somasamudra - Allipura -Rayalpadu line | D/C | 220 | 12 |  |  |  |  | JAN-24 |  | RFD
8 | Somasamudra - BTPS (Kudithini) | D/C | 220 | 41 |  |  |  |  | JAN-24 |  | RFD
9 | Srinivasapura from existing s/s -to the proposed Srinivasapura s/s | D/C | 220 | 48 | 99 | 84 | 70 | 10.2 | OCT-23 | JAN-23 | RFD |  | Work under proress
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kanhirode - Mylatti line | D/C | 220 | 178 | 303 | 220 | 175 | 99 | MAR-24 | MAR-24 | RFD |  | Work in Progress.
2 | Kunnamkulam - Vengallur | D/C | 220 | 84 | 150 | 6 | 0 | 0 | FEB-24 | FEB-24 | RFD |  | Work in Progress.
3 | Mylatti-Vidyanagar | D/C | 220 | 12 | 35 | 20 | 0 | 0 | DEC-23 | MAR-24 | RFD |  | Work in Progress.
4 | Pathanamthitta -Kakkad line | D/C | 220 | 114 | 188 | 131 | 98 | 15.81 | JUN-23 | NOV-23 | RFD |  | Work in Progress.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220kV DC line from 220kV Wani s/s to 132kV Pandharkawda | D/C | 220 | 65 | 189 | 189 | 189 | 65 | DEC-23 | JUL-23 | RFD |  | Commissioned 05/23 (Late Reported).
2 | 220 kV DC line from 400 kV Jejuri Substation to location no. 28 of existing 220 kV Jejuri-Lonand circuit | D/C | 400 | 14 | 24 | 22 | 19 | 4.6 | JUN-23 | SEP-23 | RFD |  | Work in progress.
3 | 220kV DC line from Umred S/stn to Nagbhid s/s | D/C | 220 | 103 | 187 | 180 | 179 | 55.73 | DEC-23 | DEC-23 | RFD |  | Forest involved in PART-II :-3.04 HA(4 Loc;0.88KM). NBWL: Proposal submitted by CCF, Nagpur to APCCF, Wildlife Nagpur on Dt 03.11.2022.NBWL Proposal compliances submitted on dt 27.01.2023. Compliances from DCF Nagpur - CCF Nagpur on dt: 24.02.23. APCCF Wildlife Nagpur - PCCF Wildlife Nagpur on Dt. 21.03.2023.. Matter taken up with Collector, Chandrapur regarding SDO Level Committee meeting on Dt:12.05.2023.
4 | 220kV D/C line from Vishwind- Bhenda | D/C | 220 | 86 | 141 | 138 | 132 | 42.64 | JUN-23 | DEC-23 | RFD |  | Slow work.
5 | 220kV Koradi-II to Butibori-III DCMC line | D/C on M/C | 220 | 106 | 189 | 187 | 180 | 48.58 | NOV-23 | OCT-23 | RFD |  | Work in progress.
6 | 220KV Nagewadi- Bhokardhan line | D/C | 220 | 90 | 151 | 116 | 106 | 0 | DEC-23 | DEC-23 | RFD |  | All Tower Material received at site store. Conductor not received at site.
7 | 400KV Babhaleshwar-Kudus DC line | D/C | 400 | 453 | 719 | 681 | 659 | 272.25 | FEB-24 | FEB-24 | RFD |  | Work in progress.
8 | Jerur- Karjat line | D/C | 220 | 101 | 162 | 146 | 137 | 23.25 | OCT-23 | DEC-23 | RFD |  | Work in progress.
9 | Kumbhargaon (Nanded) - Kurunda | D/C | 220 | 122 | 219 | 206 | 201 | 84.6 | DEC-23 | OCT-23 | RFD |  | Slow work.
10 | LILO of one Ckt. of 220kV Kolshet-Wada line and Padghe-Wada line on M/C towers at 400 kV Kudus S/S | LILO | 220 | 32 | 50 | 29 | 27 | 14.88 | DEC-23 | DEC-23 | RFD |  | Forest proposal : DCF, Thane site visit done on 27.05.2023.  DCF Thane forwarded proposal to CCF Thane on 10.07.2023 and CCF Thane forwarded to APCCF Nagpur on 20.07.2023. All foundation in non-forest area completed.
11 | LILO on 220kV Bhigwan Kurkumb line at 400kV Karjat s/s | LILO | 220 | 36 | 51 | 46 | 43 | 14.26 | JUN-23 | SEP-23 | RFD |  | Work in progress.
12 | LILO on 220kV Kathapur-Lonikand-I line at 220kV Khed City line | D/C | 220 | 11 | 22 | 22 | 22 | 4.57 | APR-23 | OCT-23 | RFD |  | Severe ROW issues, Stringing work to be carried out under police protection.
13 | LILO on 220kV Mhaisal - Jath at 400kV Alkud | LILO | 220 | 45 | 77 | 73 | 56 | 0 | OCT-23 | DEC-23 | RFD |  | Work in Progress.
14 | LILO on 220 kV Nalasopara- Boisar line at Palghar | D/C | 220 | 5 | 4 | 4 | 4 | 5 | APR-23 | JUN-23 | RFD |  | Commissioned 05/23.
15 | LILO on 220kV Tarapur-Borivali and Boisar- Ghodbandar line at 400kV Kudus S/S | LILO | 220 | 117 | 124 | 110 | 101 | 63.21 | OCT-23 | DEC-23 | RFD |  | Forest proposal : Mantralaya raised query to DCF, Nanded on 22.05.2023. DCF, Nanded forwarded compliance to DCF, Dahanu on 12.06.2023. DCF dahanu forwarded compliance to CCF, Thane on 13.06.2023. CCF, Thane has forwarded proposal to APCCF, Nagpur on 22.06.2023. APCCF, Nagpur has forwarded compliance to GoM, Nagpur on 26.06.2023. Proposal is under scrutiny at Mantralaya, GoM. Cases filed under section 16(1) for locs. 11A and 16A at Collector, Palghar. He delegates Powers to SDO Wada, hearing awaited.
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
1 | LILO of Bina - Ganjbasoda 220 KV Line at Bina (MPPTCL) 400KV S/s | DCDS | 220 | 25 | 43 | 43 | 43 | 25 | SEP-23 | JUN-23 | RFD |  | Commissioned 05/23.
2 | LILO of Gwalior - Datiya 220kV line at Gwalior(PGCIL) 765kV S/s | DCDS | 220 | 20 | 13 | 13 | 13 | 5.4 | FEB-24 |  | RFD |  | work under progress.
3 | Rewa UMSP - Sidhi 220kV DCDS line | DCDS | 220 | 126 | 200 | 200 | 200 | 126 | AUG-23 | SEP-23 | RFD |  | Commissioned 08/23.
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | LILO of Bhanjanagar -Meramundali at Daspalla | LILO | 220 | 60 | 113 | 108 | 99 | 45 | SEP-23 | DEC-23 | RFD |  | Forest issue
2 | LILO of Duburi - Balasore at Dhamra | D/C | 220 | 70 | 133 | 133 | 133 | 70 | MAY-23 | APR-23 | RFD |  | Commissioned 04/23.
3 | LILO of Joda -TTPS at Keonjhar (OPTCL) | D/C | 220 | 27 | 52 | 45 | 33 |  | NOV-23 | DEC-23 | RFD |  | The line length may be corrected to 26.8 Ckm. Forest clearance issue
4 | LILO of Narendrapur - Therubali at Aska New S/S | LILO | 220 | 90 | 161 | 162 | 162 | 63 | SEP-23 | NOV-23 | RFD |  | the total no. of Towers are 162 nos.
POWER TRANSMISSION CORP. OF UTTARAKHAND LTD. ( PTCUL )
1 | Baramwari -Srinagar Phase-2 (Single Zebra conductor from Interconnection point of Singoli Bhatwari HEP) at Rudrapur line | D/C | 220 | 31 | 0 | 0 | 0 |  | SEP-23 | MAR-23 | RFD
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | Bhari (proposed) - Daheru Railway TSS line | D/C | 220 | 26 | 50 | 50 | 50 | 26 | APR-23 | JUL-23 | RFD |  | Commissioned 06/23.
2 | LILO of 220kV Mansa -Sunam at Patran | D/C | 220 | 85 | 144 | 144 | 144 | 84.54 | OCT-23 | OCT-23 | RFD |  | Work in progress. Delayed due to paddy season. Likely to be completed by Oct., 2023
3 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | 220 | 16 | 31 | 31 | 31 | 14.8 | JUN-23 | NOV-23 | RFD |  | Line almost completed, but the work of upgradation of 132 kV to 220 kV substation at Gurdaspur is under progress. Work likely to be completed by 30.11.2023.
4 | LILO of one Ckts. of Jamalpur Dhandari Kalan at Sherpur | D/C | 220 | 4 | 5 | 3 | 0 | 0 | DEC-23 |  | RFD |  | Work in progress.
5 | Mansa - Budhlada line | D/C | 220 | 51 | 100 | 89 | 83 | 24.14 | FEB-24 |  | RFD |  | Work in progress.
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED ( RVPNL )
1 | LILO of 220kV Sirohi - Bhinmal line at 220kV GSS Reodar line | D/C | 220 | 50 | 82 | 82 | 82 | 50 | AUG-23 | SEP-23 | RFD |  | Commissioned 08/23.
2 | Suratgarh - Babai | D/C | 400 | 491 | 676 | 676 | 676 | 469 | DEC-23 | MAR-24 | RFD |  | 1. Earlier Work order awarded to M/s Aster Chennai has been withdrawn at risk and cost of the firm. 2. Stay against termination of contract issued by court. 3. Matter is under the jurisdiction of court. Next hearing date is 10.8.23. 4. For balance work revised detailed W.O. issued to M/s Kay Cee Infra & Energy on 8.4.22 .
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | CMRL Central Jail to proposed Mambalam 230kV GIS SS (UG Cable) | S/C | 230 | 9 | 0 | 0 | 0 |  | MAY-23 | MAR-23 | RFD |  | Total sections: 19. Laying 19/19 completed. Joints 54/54 completed. Cable damage by corporation to be rectified. To be taken up after monsoon.
2 | Kilpauk - TNEB HQ | S/C | 230 | 6 |  |  |  |  | JUN-23 |  | RFD
3 | LILO of 230 kV Abishekapatti - Udayathur line at Nanguneri | D/C | 230 | 40 | 0 | 0 | 0 |  | DEC-23 |  | RFD
4 | LILO of 230 kV Mylapore - Tarammani feeder at the proposed Thiruvanmiyur (400 kv GIS) | D/C | 230 | 2 |  |  |  |  | JUN-23 |  | RFD
5 | LILO of Dharmapuri (Palavadi) 400 kV SS to the proposed Tirupattur 230 kV SS | S/C on D/C | 230 | 77 | 299 | 289 | 248 | 32.8 | JAN-24 | MAR-23 | RFD |  | Work to resume after payment of crop compensation.
6 | LILO of existing 230 kV Arni - Sriperumbudur feeder (0.81KM) at the proposed Vembakkam 230 kV S/S | D/C | 230 | 2 |  |  |  |  | DEC-23 |  | RFD
7 | LILO of Karaikudi - Pugalur feeder-I at Vellalaviduthi | D/C | 400 | 167 | 246 | 246 | 246 | 166.71 | APR-23 | MAR-23 | RFD |  | All works completed, PTCC & CEIG approval to be obtained.
8 | LILO of one ckt of Thappagundu - Anaikadavu 400 line at Udumalpet (PGCIL) S/S | D/C | 400 | 40 | 60 | 60 | 60 | 29.09 | NOV-23 | MAR-23 | RFD |  | 5.463 KM of stringing and 20.012 KM OPGW stringing pending.Work will be taken up after payment of Tree /Crop compensatation.
9 | LILO of Pugalur - Kalivanthapattu line at Ariyalur | 2xD/C | 400 | 15 | 15 | 15 | 15 | 14.57 | JUN-23 | JAN-23 | RFD |  | Work completed. Will be energised on commissioning of Ariyalur 765 KV SS
10 | LILO of S. P. Koil - Oragadam at Maraimalai Nagar 230 KV S/S | D/C | 230 | 9 |  |  |  |  | JUN-23 |  | RFD
11 | LILO of the exisiting 230 kV Myvady - Kurukathi - Pugalur feeder at sanctioned Rasipalayam 400 kV SS | D/C | 230 | 46 | 93 | 92 | 92 | 41 | JAN-24 | MAR-24 | RFD |  | Row issues land owners are demanding yield compensation prior to commencement of further works tender floated for supply and erection of 5 nos towers.
12 | NCTPS Stage-III - North Chennai (PS) line | D/C | 765 | 13 | 20 | 19 | 19 | 11.3 | JUN-23 | MAR-23 | RFD |  | ROW issue. Being followed up.
13 | N.T. Kudy - Karaikudi line | S/C on D/C | 230 | 104 | 370 | 367 | 365 | 98.41 | SEP-23 | DEC-22 | RFD |  | Work under progress.Row issues in 2 locations.
14 | Sholinganallur (Ottiyambakkam) - Omega | D/C | 230 | 66 | 150 | 150 | 150 | 66 | AUG-23 | MAY-23 | RFD |  | Commissioned 04/23.
15 | Thervaikandikai - Manali | D/C | 400 | 73 | 113 | 111 | 106 | 58.6 | OCT-23 | MAR-23 | RFD |  | Work under progress. Row issues Enter upon permission awaited.
16 | Udangudi - Ottapidaram (QM ACSR Conductor) line | D/C | 400 | 141 | 206 | 205 | 205 | 132.08 | JUL-23 | JUN-23 | RFD |  | Ottapadiram-Kamudhi line energised on 15.03.2023. Ottapadiram-Udangudi line Work is under progress.
17 | UG Cable from Basin Bridge to TNEB Head Quarters | S/C | 230 | 7 | 0 | 0 | 0 | 0 | APR-23 | FEB-23 | RFD |  | Total section: 15. Laying work for section 15/15 completed. Joints 42/42 completed. Cable damaged during Chennai Corporation contract in 3 sections. Rectification work under progress.
18 | Vellalaviduthi 400 kV SS to Mondipatti 230 kV SS | S/C on D/C | 230 | 90 | 354 | 354 | 354 | 91.75 | APR-23 | MAR-23 | RFD |  | Railway crossing work to be taken up.
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | Brandix-Atchuthapuram | D/C | 220 | 7 | 11 | 11 | 11 | 3 | JUN-23 | DEC-23 | RFD |  | Work in progress
2 | Hindupur (400) - Pampanur Tanda (220)(GEC-I) | D/C | 220 | 140 | 239 | 237 | 237 | 8.3 | APR-23 | MAR-23 | RFD |  | Work in Progress.
3 | Hindupur - Penukonda | D/C | 220 | 54 | 97 | 94 | 92 | 32.26 | JUN-23 | DEC-23 | RFD |  | work is under progress
4 | Jammalamadugu - Betamacherla | D/C | 220 | 152 | 260 | 258 | 258 | 140.94 | JAN-24 | DEC-23 | RFD |  | 96% works completed, after approval from forest department balance works will be taken up
5 | Jammalamadugu - Porumamilla | D/C | 220 | 198 | 133 | 133 | 127 | 71.36 | AUG-23 | AUG-23 | RFD |  | Works are under progress.
6 | Kamavarapukota -Bhimadole line | D/C | 220 | 37 | 69 | 69 | 69 | 37 | APR-23 | AUG-23 | RFD |  | All works completed
7 | LILO of Krishnapatnam - Manubolu (Ckt - I) Quad Moose line to M/s SEIL- P2 400KV GIS Substation | D/C | 400 | 4 | 16 | 12 | 0 | 0 | SEP-23 | OCT-23 | RFD |  | work is under progress
8 | LILO of Nunna- KTPS line at Tiruvru | S/C | 220 | 6 | 16 | 10 | 4 | 0 | JUN-23 | OCT-23 | RFD |  | work is under progress
9 | LILO Pallantla -Pattiseema line at Guddigudem line | D/C | 220 | 23 | 49 | 43 | 41 | 8.9 | JUL-23 | JAN-23 | RFD |  | Works are under progress.
10 | Purushothapatnam - Guddigudem line | D/C | 220 | 31 | 65 | 58 | 47 | 0.48 | OCT-23 | NOV-23 | RFD |  | Works are under progress.
11 | Rachagunneri - Racherla line | D/C | 220 | 107 | 188 | 188 | 188 | 107 | SEP-23 | JAN-24 | RFD |  | Stautary inspection under progress
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | Damaracherla -Huzurnagar line | D/C | 220 | 77 | 137 | 137 | 133 | 73.09 | AUG-23 | DEC-23 | RFD |  | works are hampered due to standing crops( repeated at S.No:32)
2 | Dichpally - Yacharam Thanda line | D/C | 220 | 54 | 97 | 89 | 86 | 36 | DEC-23 | DEC-23 | RFD |  | Forest approval and working permission was obtained on 17.01.2023 for a period of 1 year
3 | Dindi S/s -Yedula s/s | D/C | 400 | 111 | 167 | 167 | 167 | 111 | JUL-23 | JUL-23 | RFD |  | Commissioned 06/23.
4 | Janagon -Husnabad | D/C | 220 | 79 | 139 | 139 | 136 | 60.58 | AUG-23 | NOV-23 | RFD |  | Works under progress.
5 | Jangaon -Devannapet line | D/C | 220 | 109 | 198 | 198 | 198 | 109 | MAY-23 | MAY-23 | RFD |  | Commissioned 04/23.
6 | LILO of Mahabubabad-Warangal line at Ammavaripet | D/C | 220 | 64 | 111 | 111 | 111 | 64 | APR-23 | JUL-23 | RFD |  | Works under progress.
7 | LILO of Pulukurthy- Bheemghanpur line to KTPP SS | D/C | 220 | 46 | 88 | 88 | 88 | 46 | SEP-23 | JUL-23 | RFD |  | Commissioned 06/23.
8 | LILO of Salivagu- Bheemghanpur line to KTPP SS | D/C | 220 | 42 | 83 | 83 | 82 | 41 | JUN-23 | JUN-23 | RFD |  | Works completed. Statutory remarks being attended. Ready for charging .Connected SS works are under progress
9 | Narlapur SS - Yedula SS | D/C | 400 | 56 | 94 | 94 | 94 | 55.47 | DEC-23 | DEC-23 | RFD |  | All works completed. Ready for charging.
10 | Narsapur to Bowrampet line (lattice structure) | M/C | 220 | 136 | 136 | 136 | 134 | 131 | AUG-23 | MAR-24 | RFD |  | work completed
11 | Narsapur to Bowrampet (Monopole towers) | D/C | 220 | 7 | 23 | 11 | 0 |  | AUG-23 | MAR-24 | RFD |  | Survey work under progress. Monopole structure revised design approval under process.
12 | Narsapur to Bowrampet (XLPE UG Cable ) | D/C | 220 | 7 | 1 | 0 | 0 | 6.49 | AUG-23 | MAR-24 | RFD |  | cable laying works under progress. Cable Jointing works completed.
13 | Pulakurthy - Kakatiya Mega Textile Park | D/C | 220 | 30 | 110 | 93 | 61 | 0 | MAR-24 | MAR-24 | RFD
14 | Veltoor SS - Yedula SS | D/C | 400 | 94 | 139 | 139 | 139 | 94 | AUG-23 | AUG-23 | RFD |  | All works completed. Ready for charging.
15 | Yadadri TPP Switchyard - Choutuppal S/S | D/C | 400 | 185 | 259 | 259 | 253 | 66.3 | SEP-23 | AUG-23 | RFD |  | Tower Foundation, Erection and Stringing works are under progress.
16 | Yadadri TPP Switchyard - Dindi s/s | D/C | 400 | 208 | 290 | 290 | 289 | 168.8 | AUG-23 | AUG-23 | RFD |  | Tower foundation,Erection & Stringing works are under progress.
17 | Yadadri TPP switchyard - Jangaon S/S | D/C | 400 | 268 | 402 | 367 | 283 | 44 | FEB-24 | FEB-24 | RFD |  | Works under progress.
18 | Yedula SS - Vattem SS | D/C | 400 | 61 | 90 | 90 | 90 | 60.54 | AUG-23 | AUG-23 | RFD |  | All works completed except gantry connections.
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | Aligarh - Shamli Line | D/C | 400 | 478 | 739 | 729 | 658 | 290.78 | JUL-23 | DEC-23 | RFD |  | Work in progress.
2 | Aurai - Mizapur | S/C | 220 | 43 | 152 | 129 | 77 | 0 | JUL-23 | DEC-23 | RFD |  | Work alloted to M/s Rama Power on debitable basis. Due to non availability of tower parts, conductor and financial constrains of firm, work is delayed and likely to be completed in Dec-23.
3 | Aurai - Phoolpur | S/C | 220 | 71 | 223 | 202 | 178 | 41 | JUL-23 | DEC-23 | RFD |  | Work alloted to M/s Gayatri Ganga on debitable basis. Due to non availibility of tower parts, conductor and financial constrains of firm, work is delayed and likely to be completed in Dec-23.
4 | Badhaikalan (Muzaffarnagar) - Shamli line | D/C | 220 | 66 | 113 | 113 | 104 | 12.2 | JUN-23 | DEC-23 | RFD |  | Work in progress.
5 | Jehta (400) - Mallawaan line | D/C | 220 | 160 | 266 | 265 | 263 | 114.46 | JUN-23 | OCT-23 | RFD |  | Work is likely to be completed in Oct-23
6 | Kursi Rd (PG) - Kanduni line | D/C | 220 | 91 | 151 | 151 | 151 | 87.2 | AUG-23 |  | RFD |  | Likely to be charged in September-2023
7 | LILO of 220kV Gr. Noida -RC Green/Metro Depot line at Jalpura | D/C | 220 | 42 | 80 | 70 | 45 | 10 | AUG-23 | SEP-23 | RFD |  | Work is in progress, last lot of monopole will be delivered in Sept-23. Line is likely to be completed and charged in Sept-23.
8 | LILO of 220kV Parichha (TPS) - Orai Ckt.II at Moth line | D/C | 220 | 12 | 20 | 20 | 20 | 11.42 | APR-23 | OCT-23 | RFD |  | Line will be charged in Oct-2023.
9 | LILO of 220kV Sec.-148 - RC Green/Metro Depot at Knowledge Park-5 | D/C | 220 | 28 | 80 | 70 | 45 | 10 | AUG-23 |  | RFD |  | Work is in progress, last lot of monopole will be delivered in Sept-23. Line is likely to be completed and charged in Sept-23.
10 | LILO of Ckt.-I and Ckt. -II (Quad) Thathra- Biharsharif at Sahupuri | D/C | 220 | 54 | 157 | 157 | 123 | 27.17 | JUL-23 | NOV-23 | RFD |  | 400kV line Work alloted to M/s R.S. Infra after re-tendering for leftover work with completion period of 9 months. Work is likely to be completed in Dec-2023
11 | LILO of Modipuram- Faridnagar at Modipuram-II line | D/C | 220 | 12 | 22 | 21 | 21 | 6.86 | APR-23 | SEP-23 | RFD |  | Work in progress.
12 | LILO of Motiram Adda (400) - Barahuan line at Khorabar (2km Monopole 2km Cable) | D/C | 220 | 8 | 9 | 9 | 9 | 2 | SEP-23 |  | RFD |  | Work in progress.
13 | Maharajganj - Gorakhpur PG (400) line | D/C | 220 | 174 | 274 | 274 | 274 | 172 | APR-23 | SEP-23 | RFD |  | Work in progress. Likely to be completed in September-2023.
14 | Modipuram-II-Shamli Line | D/C | 220 | 148 | 261 | 261 | 258 | 146 | APR-23 | SEP-23 | RFD |  | Work in progress. It is expected to complete the line in Oct-23.
15 | Raebareli (400) -Bachhrawan line | D/C | 220 | 160 | 273 | 259 | 156 | 28 | JUL-23 | FEB-24 | RFD |  | Foundation work is in progress.
16 | Saharanpur PG (400) - Deoband line | D/C | 220 | 50 | 87 | 87 | 87 | 50 | APR-23 | MAY-23 | RFD |  | Commissioned 04/23.
17 | Shamli (400) - Deoband line | D/C | 220 | 93 | 150 | 150 | 149 | 32.24 | JUN-23 | NOV-23 | RFD |  | Due to price variations, REC scheme is exhausted. Proposal is under process of BoD's approval. Due to above reasons work is delayed. It is expected to complete the line in Nov-23.
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
1 | Diversion of existing STPS-Asansol Transmission line | D/C | 220 | 5 | 122 | 122 | 122 | 5 | JUN-23 | AUG-23 | RFD |  | Commissioned 07/23.
2 | Jeerat - Krishnanagar | D/C | 220 | 114 | 0 | 0 | 0 |  | JUL-23 | DEC-22 | RFD
3 | LILO of Birpara -Alipurduar line (PGCIL) at proposed line at Falakata s/s | D/C | 220 | 17 | 0 | 0 | 0 |  | DEC-23 | MAR-23 | RFD
4 | LILO of Durgapur - Asansole Tr. Line at proposed Mongalpur 220kV GIS | M/C | 220 | 9 | 0 | 0 | 0 | 9 | JUN-23 | AUG-23 | RFD |  | Commissioned 07/23.
5 | LILO of Durgapur -DPL at Durgapur AB Zone (for Upgradation of Durgapur AB Zone S/S | D/C | 220 | 8 |  |  |  |  | OCT-23 |  | RFD
6 | LILO of Existing STPS - JK Nagar 220kV line at Asansol 220kV S/S | D/C | 220 | 65 | 0 | 0 | 0 |  | AUG-23 | DEC-22 | RFD
7 | LILO of Howarh-KTPP at Jangalpur 220 kV GIS | D/C | 220 | 1 | 0 | 0 | 0 | 1 | MAY-23 | JUN-23 | RFD |  | Commissioned 05/23.
PRIVATE SECTOR
ADANI POWER LTD. ( APL )
1 | Hyderabad - Kurnool | D/C | 765 | 335 | 0 | 0 | 0 | 335 | JUL-23 | AUG-23 | RFD |  | Commissioned 07/23.
2 | LILO of both Ckts. of Pugalur-Pugalur (HVDC) (with Quad Moose ACSR conductor) at Karur PS | D/C | 400 | 4 |  |  |  |  | JUL-23 |  | RFD
3 | Warangal (New) - Chilakaluripeta | D/C | 765 | 390 |  |  |  |  | MAY-23 |  | RFD
4 | Warangal (New) - Hyderabad | D/C | 765 | 268 |  |  |  |  | JUN-23 |  | RFD
5 | Warangal(New)- Warangal(Existing) | D/C | 400 | 95 | 0 | 0 | 0 | 95 | APR-23 | JUL-23 | RFD |  | Commissioned 06/23.
6 | Warora (Pool) - Warangal (New) | D/C | 765 | 664 |  |  |  |  | MAY-23 |  | RFD
G R Infraprojects Limited ( GRINFRA )
1 | Pachora SEZ PP - Bhopal (Sterlite) line (Quad/HTLS) | D/C | 400 | 288 |  |  |  |  | NOV-23 |  | RFD
Indigrid Ltd ( INDIGRID )
1 | LILO of both Ckts. of Parli (PG) -Pune (GIS) line at Kallam (PS) | M/C | 400 | 68 | 47 | 30 | 12 | 0 | OCT-23 | OCT-23 | RFD |  | 1) Work has been resumed in Month of May-23, after 3 months of complete stoppage due to severe RoW . The resolution has been for partial location of Beed district, we are resolving RoW location by location which is taking time to achieve monthly targets. We are getting continuous support from both district administration and need to have similar support in next couple of months. 2) Onset of timely monsoon and continuous rain are making approaching the location difficult and further for execution.
ReNew Transmission Ventures Private Limited ( RTVPL )
1 | Gadag (PS) - Narendra (New) Trans. Ltd. | D/C | 400 | 187 | 232 | 160 | 83 | 13 | SEP-23 | SEP-23 | RFD |  | Bagalkot Forest Division : DFO, Bagalkote has recommended the proposal on 03.03.2023 and forwarded to CCF, Belgaum. Gadag Forest Division : Reply against DFO, Gadag queries dated 20.02.2023 was submitted on 02.03.2023. Proposal is pending with DFO, Gadag & PCCF, Karnataka for acceptance and further processing of proposal & ROW compensation fixation order have been issued for Bagalkote, Gadag & Vijayapura Districts (except Koppal district) by the respective DCs on 27.10.2022, 04.03.2023 & 06.03.2023 respectively.
2 | Koppal PS - Narendra (New) Trans. Ltd. | D/C | 400 | 275 | 352 | 345 | 316 | 186.7 | JUN-23 | JUN-23 | RFD |  | Proposal has been approved by PCCF, Karnataka and Additional Chief Secretary (Forest), Govt. of Karnataka on 03.03.2023 and 14.03.2023. Currently proposal is pending with State Forest Minister (Honble Chief Minister) for their recommendation & Severe RoW (Issue ID : 4048-11306 to 11309) Total Foundation Locations : 2 Nos.
STERLITE GRID LTD. ( SGL )
1 | Bongaigaon (POWERGRID) - Nangalbibra | D/C | 400 | 245 |  |  |  |  | DEC-23 |  | RFD
2 | LILO of Apta-Kalwa/Taloja at Navi Mumbai(PG) | M/C | 220 | 5 |  |  |  |  | SEP-23 |  | RFD
Tata Power Ltd ( TATAPOWER )
1 | Babai-Bhiwani (NRSS XXXVI Element II) | D/C | 400 | 111 | 299 | 265 | 215 | 1.12 | MAY-23 | MAR-23 | RFD |  | Details of Tr. Line Falling under Forest: 3.37 Km ,Forest area: 12.90 Ha (2.80 Kms) of Rajsthan + 3.46 Ha (0.57 Kms) of Haryana. Forest proposals submitted on : 15.05.2017 for Haryana and on 11.08.2017 for Rajasthan. Stage I approval from Haryana Forest Deptt. received on 27.03.2018 and Stage I approval from Rajasthan Forest Deptt. received on 06.07.2018. Wildlife Clearance : Wildlife area(ha) : 7.452 Ha (2.80 Kms) Khetri Bansyal Conversion Reserve Wildlife proposals submitted on : 16.02.2018 and at present, Proposal recommended by NBWL and currently recommendations forwarded to State Govt. (Rajasthan). Severe RoW issues: 52/1, 52/3, 53/0, 54/0, 54/1, 54/2 & 54A/0 of Tehsil Dadri and loc. No. 17/0 & 18/0 of Tehsil Khetri.