## State_trans_utility_wise_prt1
REPORT INDICATING STATUS OF CONSTRUCTION OF TRANSMISSION LINES (220 kV & ABOVE) DURING- 2024-25
As on 31-DEC-2024
Sl No | Name of Transmission Lines | Ckts (S/C) & (D/C) | Voltage Level (kV) | Total Length (cKm) | Progress Status of Transmission |  |  |  | Target Date |  | Remarks
[5 empty] | Total Locations (Nos) | Foundation completed (Nos) | Tower Erected (Nos) | Stringing completed (CKm) | Schedule | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12.
DAMODAR VALLEY CORPORATION(DVC)
1 | LILO of CTPS (A) - Kalyaneswari line at RTPS | D/C | 220 | 52 | 72 | 72 | 72 | 52 | APR-24 | JUL-24 | Commissioned 06/24.
2 | LILO of MTPS (A) - Borjora line at MTPS (B) | D/C | 220 | 84 | 76 | 76 | 76 | 84 | MAY-24 | JAN-25 | Delay due to severe ROW problem and non-obtaining of Forest clearance. Stage I Clerance received. FRA received. Application for Stage 2 submitted and is in process, clearance awaited. Tree cutting in presence of Forest Department completed. Foundation, erection and stringing completed. CEA inspection done and clearance awaited. Revised date of completion changed to January'2025.
NHPC LIMITED(NHPC)
1 | LILO of Lakhwar HEP- Muzaffarnagar at Vyasi HEP | D/C | 220 | [5 empty] | JAN-17
POWERGRID (Consultancy Work)(PGCONSULTANCY)
1 | (J&K) LILO of Leh - Kharu line | S/C | 66 | 16.19 | 97 | 55 | 16 | 1 | MAY-17 | MAY-17
2 | (J&K) LILO of Leh - Nimmo line | S/C | 66 | 2.15 | 13 | 13 | 9 | 1 | MAY-17 | MAY-17
3 | (Sikkim) Chungthang - Lachen line | D/C | 66 | 44 | 126 |  |  |  | DEC-18 | APR-19
4 | (Sikkim) Chungthang - LILO point of Rabon - Malting line | D/C | 66 | 8 | 23 |  |  |  | DEC-18 | SEP-17
5 | (Sikkim) Dikchu Pool - Makha line | D/C | 66 | 18 | 114 |  |  |  | DEC-18 | MAR-19
6 | (Sikkim) Khamdong - Makha line | S/C | 66 | 4 | 86 |  |  |  | DEC-18 | MAR-19
7 | (Sikkim) Khamdong - Temi line | S/C | 66 | 8 | 69 |  |  |  | DEC-18 | MAR-19
8 | (Sikkim) Kumrek - Rorathang line | D/C | 66 | 10 | 103 |  |  |  | DEC-18 | MAR-19
9 | (Sikkim) Parbing - Pangthang line | D/C | 66 | 14 | 86 |  |  |  | DEC-18 | MAR-19
10 | (Sikkim) Parbing - Sichey line | S/C | 66 | 6 | 40 |  |  |  | DEC-18 | MAR-19
11 | (Sikkim) Parbing - Tadong line | S/C | 66 | 4 | 67 |  |  |  | DEC-18 | MAR-19
12 | (Sikkim) Rorathang - LILO point on Pakyong - Rongli line | D/C | 66 | 10 | 29 |  |  |  | DEC-18 | MAR-19
13 | (Sikkim) Samardong - Kumrek line | D/C | 66 | 22 | 103 |  |  |  | DEC-18 | MAR-19
14 | (Sikkim) Samardong - Mamring line | S/C | 66 | 10 | 45 |  |  |  | DEC-18 | MAR-19
15 | (Sikkim) Samardong - Namthong line | S/C | 66 | 7 | 86 |  |  |  | DEC-18 | MAR-19
16 | (Sikkim) Singhik - Mangan line | S/C | 66 | 10 | 57 |  |  |  | DEC-18 | MAY-18
17 | (Sikkim) Singhik - Passidong line | S/C | 66 | 20 | 114 |  |  |  | DEC-18 | MAR-19
18 | (Maghalaya) Byrnihat (Killing) - Mawngap - New Shillong line | D/C | 220 | 244 | 369 |  |  |  | DEC-18 | SEP-19
19 | (PMDP - Jammu) LILO of Hiranagar - Gladni at Chowadhi | S/C | 220 | 16 | 0 | 0 | 0 |  | MAR-19 | NOV-19 |  Contract awarded. Chowadhi Substation land yet to be handed over to POWERGRID.
20 | (PMDP - Jammu) LILO of Thein - Hiranagar at Kathua-II (Ghatti) | D/C | 220 | 12 | 14 | 8 | 0 |  | MAR-19 | NOV-19 |  Tower foundation work in progress and 08/14 locations completed. Land acquisition matter taken up with concerned revenue authorities & JKPDD regarding framing of land papers of all 14 locations.
21 | (PMDP - Jammu) Samba(JK) - Jatwal(PG) | D/C | 220 | 11 | 25 | 15 | 0 |  | MAR-19 | NOV-19 |  Tower foundation work in progress and 15/25 locations completed. Land acquisition matter taken up with concerned revenue authorities & JKPDD. Preparation of land papers yet to start.
22 | (Sikkim) Dikchu Pool - Rangpo (Samardong) (twin) | D/C | 220 | 50 |  |  |  |  | DEC-18 | SEP-18
23 | (Sikkim) Dikchu Pool - Singhik | D/C | 220 | 46 |  |  |  |  | DEC-18 | JUN-19
24 | (Sikkim) Singhik - Chungthang | D/C | 220 | 44 | 83 |  |  |  | DEC-18 | APR-19
25 | (Arunachal Pradesh) Along - Kambang line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
26 | (Arunachal Pradesh) Along - Yingkiong line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
27 | (Arunachal Pradesh) Changlang - Jairampur line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
28 | (Arunachal Pradesh) Chimpu (Itanagar) - Holongi line | S/C on D/C | 132 | 20 |  |  |  |  | DEC-18 |  | Yet to be awarded.
29 | (Arunachal Pradesh) Daporijo - Nacho line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
30 | (Arunachal Pradesh) Deomali - Khonsa line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
31 | (Arunachal Pradesh) Gerukamukh - Likabali line | S/C on D/C | 132 | 60 | 0 | 0 | 0 |  | DEC-18 |  | Yet to be awarded.
32 | (Arunachal Pradesh) Jairampur - Miao line | S/C | 132 | 40 |  |  |  |  | DEC-18
33 | (Arunachal Pradesh) Kambang - Mechuka line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
34 | (Arunachal Pradesh) Khonsa - Changlang line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
35 | (Arunachal Pradesh) Khonsa - Longding line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
36 | (Arunachal Pradesh) Khupi - Seppa line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
37 | (Arunachal Pradesh) Likabali - Niglok line | S/C on D/C | 132 | 75 | 293 | 0 | 0 |  | DEC-18 | NOV-19 | Yet to be awarded.
38 | (Arunachal Pradesh) LILO of Daporijo - Along 132 KV S/C at Basar | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
39 | (Arunachal Pradesh) Miao - Namsai (PG) line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
40 | (Arunachal Pradesh) Naharlagun - Banderdewa line | S/C on D/C | 132 | 25 |  |  |  |  | DEC-18 |  | Yet to be awarded.
41 | (Arunachal Pradesh) Naharlagun - Gerukamukh line | S/C on D/C | 132 | 90 |  |  |  |  | DEC-18 |  | Yet to be awarded.
42 | (Arunachal Pradesh) Niglok - Pasighat New (Napit) | S/C on D/C | 132 | 30 |  |  |  |  | DEC-18 |  | Yet to be awarded.
43 | (Arunachal Pradesh) Palin - Koloriang line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
44 | (Arunachal Pradesh) Pasighat New (Napit) - Pasighat Old | S/C on D/C | 132 | 15 |  |  |  |  | DEC-18
45 | (Arunachal Pradesh) Pasighat Old - Mariyang line | S/C on D/C | 132 | 80 |  |  |  |  | DEC-18 |  | Yet to be awarded.
46 | (Arunachal Pradesh) Rilo - Sagali line | S/C on D/C | 132 | 55 |  |  |  |  | DEC-18 |  | Yet to be awarded.
47 | (Arunachal Pradesh) Rilo - Seijosa line | S/C on D/C | 132 | 85 |  |  |  |  | DEC-18 |  | Yet to be awarded.
48 | (Arunachal Pradesh) Roing (PG) - Anini line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
49 | (Arunachal Pradesh) Roing (PG) - Dambuk line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
50 | (Arunachal Pradesh) Sagali - Naharlagun line | S/C on D/C | 132 | 45 |  |  |  |  | DEC-18 |  | Yet to be awarded.
51 | (Arunachal Pradesh) Seppa - Rilo line | S/C on D/C | 132 | 55 |  |  |  |  | DEC-18 |  | Yet to be awarded.
52 | (Arunachal Pradesh) Tawang - Lumla line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
53 | (Arunachal Pradesh) Tezu (PG) - Halaipani line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
54 | (Arunachal Pradesh) Yingkiong - Tuting line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
55 | (Arunachal Pradesh) Ziro (PG) - Palin line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
56 | (Arunachal Pradesh) Ziro (PG) - Ziro New line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
57 | (Arunachal Prades) Seppa - Bameng line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
58 | (Assam) Amingaon - Hazo line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
59 | (Assam) Dhemaji - Silapathar line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
60 | (Assam) Kahilipara - Guwahati Medical college ( Including 2 km cable) | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
61 | (Assam) Kamakhya - Paltan Bazar | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Awarded.
62 | (Assam) LILO of Golaghat - Bokajan line at Sarupathar | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
63 | (Assam) LILO of Jorhat (Gormur) - Nazira at Teok. | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
64 | (Assam) LILO of Kamalpur - Sishugram line at Amingaon S/S | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
65 | (Assam) LILO of one circuit of Rangia - Rowta line at Tangla | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
66 | (Assam) Rupai - Chapakhowa line (including 2 km cable) | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
67 | (Assam) Sonabil - Tezpur (New) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
68 | (Maghalaya) LILO of both circuits of MLHEP - Khliehriat line at Mynkre | D/C | 132 | 34 | 99 |  |  |  | DEC-18 | SEP-19
69 | (Maghalaya) Phulbari - Ampati line | D/C | 132 | 138 | 239 |  |  |  | DEC-18 | SEP-19
70 | (Manipur) Imphal (PG) - Ningthoukhong line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
71 | (Manipur) Kakching - Churachandpur (2nd ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
72 | (Manipur) Kakching - Kongba (2nd Ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
73 | (Manipur) LILO of one circuit of Kongba - Kakching line at Thoubal S/S | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
74 | (Manipur) LILO of Yurembam (Imphal-State) - Karong line at Gamphajol | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
75 | (Manipur) Rengpang - Tamenlong line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
76 | (Manipur) Yaingangpokpi - Kongba (2nd Ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
77 | (Manipur) Yuremum - Karong - Mao (Manipur - Nagaland border) section of Yuremum-Karong-Kohima line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
78 | (Mizoram) Chawngte - S. Bungtlang line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
79 | (Mizoram) Lungsen - Chawngte line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
80 | (Mizoram) W. Phaileng - Marpara line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
81 | (Nagaland) LILO of Kohima - Meluri (Kiphire) at New Kohima | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
82 | (Nagaland) LILO of Kohima - Wokha line at New Kohima | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
83 | (Nagaland) LILO of Mokokchung (Nagaland) - Mariani (Assam) line at Longnak | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
84 | (Nagaland) New Kohima (Zadima) - New Secretariat Complex Kohima line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
85 | (Nagaland) Tuensang - Longleng line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
86 | (Nagaland) Wokha (Doyang River) - Zunheboto - Mokokchung (Nagaland) | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
87 | (PMDP - Kashmir) Waganpora - Khanyar (Cable) | D/C | 132 | 10 | 0 | 0 | 0 |  | MAR-20 | NOV-19 | Route survey completed and report approved. Cable received at site.
88 | (Sikkim) Dikchu Pool - Parbing line | D/C | 132 | 42 | 96 |  |  |  | DEC-18 | MAR-19
89 | (Sikkim) LILO of Rangit - Melli (Power Deptt. Sikkim) 132 kV S/C at Manpur line | D/C | 132 | 4 |  |  |  |  | DEC-18 |  | Yet to be awarded.
90 | (Sikkim) LILO of Rangit - Melli (Power Deptt. Sikkim) 132 kV S/C at Namchi line | D/C | 132 | 4 |  |  |  |  | DEC-18 |  | Yet to be awarded.
91 | (Tripura) Bagafa - Belonia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
92 | (Tripura) Bagafa - Satchand (utilizing the corridor of existing Bagafa - Satchanda 66 kV line) | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
93 | (Tripura) Belonia - Sabroom line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
94 | (Tripura) Kailasahar - Dharmanagar line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
95 | (Tripura) LILO of Agartala (79 Tilla) - Dhalabil (Khowai) line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
96 | (Tripura) LILO of Ambassa - P.K. Bari at Manu | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
97 | (Tripura) LILO of one circuit of Surajmaninagar - Rokhia line at Gokulnagar | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
98 | (Tripura) Rabindra Nagar - Belonia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
99 | (Tripura) Rabindra Nagar - Rokhia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
100 | (Tripura) Udaipur - Amarpur line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
101 | (Tripura) Udaipur - Bagafa line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
102 | (Assam) LILO of Kamalpur - Kamakhya line at Amingaon S/S | S/C | 120 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
POWER GRID CORPORATION OF INDIA LIMITED(PGCIL)
1 | 765kV D/C Ahemdabad- South Gujrat (New Navsari ) line | D/C | 765 | 577 | 807 | 231 | 52 |  | MAR-25 |  | RoW Issues are being faced at 32 locs. in Navsari Dist., 68 locs. in Bharuch Dist., 14 Locs. in Vadodara Dist., 119 Locs. in Surat Dist., 59 Locs. in Ahmedabad dist., 60 locs. in Anand dist. & 7 Locs. in Kheda dist.
2 | 765kV Dc/KPS2-KPS3 line | D/C | 765 | 30 | 40 | 17 | 0 |  | MAR-25 |  | Stone piling work in progress.
3 | 765kV D/C Lakadia PS- Ahmedabad line | D/C | 765 | 368 | 474 | 115 | 21 |  | MAR-25 |  | RoW Issues are being faced at 113 locs. in Morbi Dist., 43 locs. in Surendranagar Dist.
4 | Aurangabad - III - Aurangabad (PG) | 2xS/C | 765
5 | Banskantha-Ahemadabad line | D/C | 765 | 269 | 362 | 143 | 45 |  | MAR-25 |  | Patan Dist.: Section 16 (1) Orders awaited: 30 locs. Mehsana: Orders awaited: 04 locs. Ahmedabad: Orders awaited: 29 locs.
6 | Bhadla II - Sikar II 765 kV D/C line (2nd) Rajasthan (8.1 GW) under Phase-II Part-E | D/C | 765 | 600 | 816 | 469 | 175 |  | DEC-24 |  | RoW issues at 7 loc. in Sikar, 37 loc. in Didwana Kuchman . Forest (0.77 Ha): Proposal submitted on 23.10.23. Stage-I clearance accorded on 10.04.24. Working permission Awaited.
7 | Bhadla II - Sikar II 765 kV D/C line (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 765 | 618 | 808 | 808 | 808 | 618 | DEC-24 | JAN-25 | Commissioned 12/24.
8 | Fatehgarh II- Bhadla II 765kV D/C Line ( 2nd) Under Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part B | D/C | 765 | 405 | 529 | 529 | 529 | 405 | MAY-24 | SEP-24 | Commissioned 08/24.
9 | Fatehgar-II - Bhadla-II (2nd) | D/C | 765 | 404 | 529 | 529 | 527 | 384 | FEB-24 | JUL-24 | Transmission System falling under GIB potential area. Supreme Court committee on 18.07.22 has suggested diverted route for the transmission line. Transmission license from CERC received in Nov'22. Shutdown constraints in Jaisalmer area for strining works due to wind developer. Intermitant sand storm. Intermitant RoW in Phalodi district.
10 | Khetri-Narela 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part G) | D/C | 765 | 340 | 463 | 366 | 320 | 60 | JUL-24 | SEP-24 | 1. RoW at 88 loc. in Jhajjar district in Haryana. 2. RoW at 8 loc. in North Delhi district
11 | Kurnool-III-Kurnool (New) (PGCIL)-RTM) (AP) - Part-A and Part-B | D/C | 765 | 225 | 299 | 175 | 35 |  | MAR-25 |  | Length of the line is to be provided.
12 | Kurnool - III - Maheshwaram (PG) (PGCIL-RTM) | D/C | 765 | 504 | 673 | 345 | 48 |  | MAR-25 | DEC-19 | Forest: 26.993 Ha: Stage-I Approval Pending
13 | LILO of 765kV S/C Meerut -Bhiwani line at Narela | S/C | 765 | 68 | 97 | 58 | 24 |  | JUL-24 | SEP-24 | 1. RoW at 27 loc. in Sonipat district in Haryana. 2. RoW at 12 loc. in North Delhi district
14 | LILO of Mainpuri -Gr. Noida S/C line at Jawaharpur TPS (J-FTL-TBCB) | S/C | 765 | 0
15 | LILO of Tilaiya - Balia line at Gaya | D/C | 765
16 | Navsari (New (South Gujarat) (GIS) - Padghe (GIS) 765 kV D/C line | D/C | 765 | 453 | 616 | 331 | 136 | 5.57 | DEC-24 |  | Navsari Dist.: Section 16 (1) Orders awaited: 24 locs. Valsad: Orders awaited: 01 loc. ROW issues are being faced in 13 locations in Palghar & 29 locatrions in Thane district in construction of 765 kV D/C Navsari (New) - Padghe (GIS) TL of Maharashtrafor portion. Farmers/landowners are demanding high compensation.
17 | Sikar II - Aligarh 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part D) | D/C | 765 | 513 | 679 | 679 | 679 | 513 | DEC-24 | NOV-24 | Commissioned 10/24.
18 | Vindhyanchal PS - Varanasi line ( WR-NR PTL -TBCB) | D/C | 765 | 379 | 521 | 521 | 520 | 368 | JUL-21 | JUL-21 | Stage -I forest clearance of UP portion obtained on 14.09.20. Working permission for Mirzapur division received on 29.10.20. Wildlife proposal cleared by NBWL. NBWL in their clearance advised to cross river using 765 kV U/G Cable. Technology is not available world wide. Matter was taken up with SBWL/ NBWL and clarification in this regard issued on 17th June'20. In MP portion, delay in tree felling by forest deptt. also affected foundation works. Presently tree felling in stringing stretches are in progress.
19 | Leh-Kharu (And LILO of Leh-Nimmo) | D/C | 66 | 17 | 0 | 0 | 0
20 | 2nd Circuit of Kishenpur - Dulhasti 400kV D/c (Q) line (Kishtwar - Kishenpur Section) | S/C | 400 | 130 | 29 | 21 | 17 | 73.15 | MAR-25
21 | 400kV D/C Banaskantha- Sankhari line (2nd ckt. ) | D/C | 400 | 45 | 59 | 44 | 13 |  | JUN-23 | MAR-25 | Patan dist.: Section 16 (1) Orders awaited: 1 loc.
22 | 400kV D/C Jeypore (POWERGRID) - Jagdalpur (CSPTCL) line | D/C | 400 | 137 | 172 | 112 | 1 |  | MAR-25 |  | 1) Forest Chhatisgarh (4.48 Ha): Forest proposal for Chhattisgarh submitted on 09.06.23, Revised Proposal Submitted on 09/11/2023​.Stage-I Awaited.2) Forest Odisha (18.1 Ha): Forest proposal for Jeypore (Odisha) side initially submitted in Oct 2023 which got rejected. Stage-I Awaited.
23 | Farakka - Malda (Reconductoring) | D/C | 400 | 86 | 0 |  |  | 86 | NOV-16 | MAR-16 | Line charged in Mar'16.
24 | Jawaharpur TPS-Firozabad 400kV D/C (Q) line (J-FTL-TBCB) | D/C | 400 | 0
25 | Kishenpur - Ratle, (Dulhasti- Kishenpur Second Ckt stringing extending up to Ratle HP) | S/C | 400 |  | 0 | 0 | 0
26 | LILO of both Ckt. Kishanganj - Patna (Q) line Saharsa (ERSS XXITL - TBCB) | D/C | 400 | 150 | 211 | 211 | 211 | 149.4 | AUG-21 | OCT-21 | One ckt charged in 11.09.2021, 2nd ckt expected in October'21.
27 | LILO of Both Ckt of Bawana - Mandola at Rajghat | D/C | 400 | 116 |  |  |  |  | MAY-17 |  | Rajgath S/s annulled. Bays now constructed at Maharanibagh
28 | LILO of both Ckt. of RAPP - Shujalpur at Jeerapur PS (GEC-II) | D/C | 400 | 0
29 | LILO of Gaya-Chandwa(existing) at North Karanpura STPP (Interim) | M/C | 400 | 38 |  |  |  |  | DEC-18
30 | LILO of Jeerat (WBSETCL)  Subhasgram (PG) | D/C | 400 | 1 |  |  |  |  | JUL-20
31 | LILO of Jeerat (WBSETCL) - Subhasgram (PG) 400kV at Rajarhat (PM-JTL-TBCB) | D/C | 400 | 24 | 37 | 0 | 0 |  |  | JUL-20 | Line deleted from scope.
32 | LILO of one circuit of Dulhasti - Kishenpur at Ratle HEP. | D/C | 400
33 | LILOof one Ckt. of Agra South-Fatehabad (765kV) D/C line at 400kV at Firozabad (J-FTL-TBCB) | D/C | 400 | 0
34 | LILO of Palatama-Surajmaninagar (ISTS) line at Surajmaninaga (TSECL) | D/C | 400 | 12 | 0 | 0 | 0 |  | MAY-22 | OCT-22
35 | LILO OUT of Teesta-III - Kishanganj at Rangpo | D/C | 400 | 15 | 35 | 35 | 35 | 23 | JUN-20 | AUG-21 | Work affected due to RoW in stringing at one section due to Tashi Choling trust. Progress also affected due to COVID-19 restrictions. Lockdown extended upto 14.07.2021.
36 | Magarwada (GIS) - Kala (GIS) 400 kV D/C line | D/C | 400 | 89 | 149 | 71 | 13 |  | DEC-24 |  | Gujarat: Valsad Dist. Orders awaited: 01 loc. Maharashtra: RoW are being faced at 30 locs. in palghar Dist. Farmers/landowners are demanding rate revision of land compensation.
37 | Navsari (New) (South Gujurat) (GIS) - Magarwada (GIS)400kV D/C line | M/C | 400 | 385 | 266 | 235 | 115 |  | DEC-24 |  | Daman: Section 16(1) Orders awaited: 04 locs. Navsari Dist.: Section 16 (1) Orders awaited: 3 locs. Valsad Dist. Section 16(1) Orders awaited: 06 locs.
38 | Neyveli TS-II - Neyveli TS-I | D/C | 400 | 14 | 0 | 0 | 0 |  | JUL-15
39 | Raipur Pool - Dhamtari 400kVD/C line (Q) | D/C | 400 | 176 | 232 | 149 | 11 |  | DEC-24
40 | Rajarhat - Purnea (excl. Farakka-Gokarna portion) | D/C | 400 | 645 | 1219 | 1219 | 1219 | 645 | APR-16 | JUL-20 | 400 KV S/C New Purnea-Gokarna line & 400 KV S/C New Purnea-Farakka line charged on 10.11.19 (both lines are section of 400 KV D/C Rajarhat-Purnea line). Farakka - Gokarna portion of 400KV D/C Rajarhat - Purnea line (236 Ckm) including both LILO's at Farakka & Gokarna commissioned in Mar'17. Balance portion of line is commissioned on 12.07.20.
41 | Ramgarh-II -Jaisalmer-II (RVPNL) (Twin HTLS) | D/C | 400 | 100 |  |  |  |  | JUL-23
42 | Ramgarh-II SEZ PP- Fateharh-II (Twin HTLS) | D/C | 400 | 88 |  |  |  |  | NOV-23
43 | Reconductoring Dulhasti Ratle LILO tap point of Dulhasti- Kishenpur 400kV line implemented through twin moose conductor to Quad moose conductor | S/C | 400 | 13 | 0 | 0 | 0 | 4 | APR-25 |  | Shutdown Constraint: Shutdown disallowed by Grid Controller due to high hydro generation.
44 | Reconductoring of Jharsuguda/Sundargarh(PG) Rourkela(PG) 400 kV twin moose line with twin HTLS | D/C | 400 | 1404 | 0 | 0 | 0 | 284 | NOV-25 |  | Awarded in Mar'23. .Ckt-1 completed in March 2024 (142 CKM). 105.354 CKm of Ckt-3 completed . 8 Ckm of Ckt-4 completed.
45 | Removal of LILO of Bawana- Mandola 400kv D/C line at Maharanibagh s/s and Extension of above LILO section from Maharanibagh upto Narela s/s so as to from 2x400 kV D/C Maharanibagh- Narela line on Mult | D/C | 400 | 57 | 123 | 63 | 38 | 4 | JUL-24 | SEP-24 | Work affected due to RoW Issue at 30 locations in Delhi
46 | Sikar II - Neemrana 400kV D/C line (Twin HTLS) (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 400 | 270 | 368 | 368 | 368 | 270 | DEC-24 | NOV-24 | Commissioned 10/24.
47 | Siliguri - Purnea | D/C | 400 |  | 0 | 0 | 0 |  | SEP-13 | MAY-20
48 | Tirunelveli PS - Tuitcorin PS (Quad) line-1 and 2 line | D/C | 400 | 48 | 33 | 33 | 33 | 24 | APR-17 | MAR-18 | Erection completed. Work has been slowed-down to match with Generation (ant. by Mar'18).
49 | Chandigarh S/s - Panchkula (PG) (incl. 10 KMs underground cable). | D/C | 220 | 48 | 56 | 53 | 51 | 43 | SEP-22 | DEC-22 | Work of downstream system (66 KV Cable) under progress by UT Chandigarh. 220 KV Underground cable laying completed. Work held up at 5 locations due to ROW issues. DM, SAS NAGAR issued orders u/s 16 of Indian telegraph act for removal of ROW on 09.11.2020. High Court stayed works on 16.11.2020. Next hearing on 20.08.2021 after repeated adjournments.
50 | Kathalguri (NEEPCO) - NAmsai (POWERGRID) 220kV D/C line | D/C | 220 | 139 | 221 | 125 | 58 |  | OCT-25
51 | Laying of cable between Minamarg and Zojilla top section of Alusteng- Drass 220kV Section | S/C | 220 | 12 | 0 | 0 | 0 |  | DEC-24 |  | Present Status: Cable Trench-Excavation Work under progress (5.0 Km completed).PCC --3.685 km Completed HDPE Pipe-2.65/12 Km laying along with jointing completed. Note:- Work is at halt due to extreme weather conditions
52 | LILO of 220kV Firozabad (220kV)- Agra (765kV PG) line at 400kV Firozabad (J-FTL-TBCB) | D/C | 220 | 0
53 | Purnea - Purnea (New) | D/C | 220 | 2 | 0 | 0 | 0 | 2 | MAY-20 | DEC-19 | Re-conductoring work completed & charged.
54 | 132kV D/C Roing (PG) -Chapakhowa (AEGCL) line | D/C | 132 | 66 |  |  |  |  | MAY-22
55 | 132kV Firozabad (400kV)- Narkhi D/C line (J-FTL-TBCB) | D/C | 132 | 0 | 0 | 0 | 0
56 | LILO of 132kV Atmadpur -Barhan S/C line at 400kV Firozabad (J-FTL-TBCB) | S/C | 132 | 0
57 | LILO of Aizwol (PG) - Zemabawk at Melriat (PG) | D/C | 132 | 30 | 17 | 17 | 17 | 10 | DEC-12 | NOV-18 | Line commissioned in Nov'18.
58 | LILO of Gangtok - Melli at Rangpo | S/C | 132 | 19
59 | LILO of Ranganadi - Nirjuli at Pare HEP | D/C | 132 | 3 | 10 | 10 | 10 | 3 |  | FEB-18 | Line work completed. Test charged on 03.03.2018.
60 | Melriat (New) - Sihmui line | D/C | 132 | 12 | 20 | 20 | 20 | 12 | DEC-12 | NOV-18 | Line commissioned in Nov'18.
61 | Pasighat - Roing line. | S/C on D/C | 132 | 102 | 347 | 347 | 347 | 104 | DEC-12 | JUN-17 | Line commissioned in Jun'17.
62 | Reconductoing of existing Single AAAC Panther Khandong (NEEPCO) | S/C | 132 | 40 |  |  |  |  | NOV-24
63 | Re-conductoring of Agartala GBPP - Agartala (State) with HTLS conductor | D/C | 132 | 16 | 0 | 0 | 0 | 16 | MAY-18 | FEB-18 | Line commissioned in Feb'18.
64 | Reconductoring of Aizawal (POWERGRID) - Luangmual (Mizoram 132kV ACSR Panther S/C line with Single HTLS Conductor of 800A (at nominal Voltage Level ) | S/C | 132 | 1 | 0 | 0 | 0 |  | APR-25 |  | Reconductoring works completed by Dept. of Power, Mizoram, Informed/requested to CTUIL for scope deletion
65 | Reconductoring of existing Single AAAC Panther Khliehriat (POWERGRID) | S/C | 132 | 73 | 0 | 0 | 0 | 7.34 | NOV-24
66 | Reconductoring of existing Single ACSR Panther Khandong (NEEPCO) | S/C | 132 | 42 | 0 | 0 | 0 | 42.48 | NOV-24 | MAR-24 | Work completed & charged on 30.03.2024.
67 | Reconductoring of existing Single ACSR Panther Kopili (NEEPCO) | S/C | 132 | 10 | 0 | 0 | 0 | 11.03 | NOV-24 | MAY-24 | Line commissioned on 09.05.2024
68 | Reconductoring of exiting Single ACSR Panther Khliehriat (POWERGRID) | S/C | 132 | 7 | 0 | 0 | 0 | 7.8 | NOV-24
69 | Re-conductoring of Imphal (PG) - Yurembam with HTLS conduuctor. | S/C | 132 | 1 | 0 | 0 | 0 | 1 | JUL-18 | APR-18 | Line commissioned in Apr'18.
70 | Reconductoring of Melriat (GIS) (POWERGRID) - Zuangtui (Mizoram) 132kV ACSR Panther S/C line with Single HTLS conductor of 900A (at nominal voltage level) | S/C | 132 | 10 |  |  |  |  | APR-25
71 | Reconductoring of Rangpo-Gangtok 132kV D/c line with single HTLS conductor of 800A (at nominal voltage level) | D/C | 132 | 54 | 0 | 0 | 0 | 5 | NOV-24 |  | Shutdown constraint from Sikkim. S/D denied by Sikkim Power Department.
72 | Roing - Tezu line | S/C on D/C | 132 | 73 | 244 | 244 | 244 | 72 | APR-12 | JUN-17 | Line commissioned in Jun'17.
73 | Shifting of Melriat (GIS) (POWERGRID) - Zuangtui (Mizoram) 132kV HTLS line from existing bay and termination of the HTLS line in the new bay | S/C | 132 | 1 |  |  |  |  | APR-25
74 | Silchar - Hailakandi (Contingency arrangement) | D/C | 132 | 60 | 110 | 110 | 110 | 60 |  | NOV-17 | Part line commissioned (35Ckm) through contingency in Jun'12. Balance line commissioned in Nov'17.
75 | Tezu - Namsai line. | S/C on D/C | 132 | 96 | 332 | 332 | 332 | 95 | DEC-12 | JUL-18 | Line commissioned in Jul'18.
REC Transmission Projects Company limited(RECTPCL)
1 | (PMDP - Jammu) LILO of Barn - Kishanpur at Nagrota | S/C | 220 | 10 | 0 | 0 | 0 |  | MAR-19 |  | Due to non-availability of land, work could not commence though agency is ready for mobilization.
2 | (PMDP - Leh) Drass - Padum (Zanaskar) line | S/C | 220 | 207 | 0 | 0 | 0 |  | MAR-19 |  | Tender shall be published immediately after getting clearance from the JKPDD/PGCIL & sanction of additional fund requirement by MoP.
3 | (PMDP - Leh) Phyang (PGCIL) - Diskit (Nubrai) line | S/C | 220 | 100 | 0 | 0 | 0 |  | MAR-19 |  | Tender shall be published immediately after getting clearance from the JKPDD/PGCIL & sanction of additional fund requirement by MoP.
ASSAM ELECTRICITY GRID CORP. LIMITED(AEGCL)
1 | Sonabil - Biswanath Chariali | S/C | 220 | 40 | 136 | 133 | 62 | 0.2 | MAR-21 | MAR-21 | RoW issues at many locations.
2 | Agia-Sonapur (Hatchingmari) S/C line D/C tower | S/C | 132 | 102.51 | 387 | 363 | 284 | 0 |  | NOV-19 | RoW issues many locations. Change in scope of work due to technical issues.
3 | Amguri solar park - Mariani line (GEC-II) | D/C | 132 | 0 | 5 | 0 | 0 |  |  | MAR-20 | Re-survey done due to requirement of additional tower, additional financial implication involved which was submitted to APGCL for deposit
4 | Barnagar-Barpeta line on D/C tower | D/C | 132 | 68 | 0 | 0 | 0 | 0 |  | AUG-19 | The scope was changed to LILO of Shaligaon- Nalbari line at Barpeta GSS.
5 | BTPS - Kokrajhar line | S/C on D/C | 132 | 10 | 39 | 39 | 39 | 10 | DEC-13 | JUN-16 | Line charged on 30.06.2016.
6 | BTPS (salakati)-APM line S/C on D/C tower | S/C | 132 | 42 | 163 | 115 | 84 | 0 |  | MAR-20 | RoW issues at many locations. Change in scope of work due to technical issues.
7 | Hailakandi-Karimganj line on D/C tower | S/C | 132 | 26 | 93 | 13 | 0 | 0 |  | DEC-20 | 1. Contract agreement cancelled due to contractual failure. 2. Work order issued for supply of stub, superstructure,
8 | Kokrajhar - Bilashipara - Gauripur | S/C on D/C | 132 | 63 | 203 | 203 | 203 | 63 | SEP-13 | NOV-19 | Kokrajhar to Bilashipara charged on 24.06.16 and Bilashipara to Gauripur charged on 14.06.2016
9 | Kukurmara - Azara line | S/C on D/C | 132 | 5 | 29 | 29 | 29 | 6 | DEC-11 | NOV-19 | Court case pending at Loc-19. Stringing of Railway and Highway crossing left to be done.
10 | Kukurmara(Mirza)-Boko | S/C on D/C | 132 | 6 | 0 | 0 | 0 |  |  |  | Proposal was dropped.
11 | LILO of both ckt of Depota - Gohapur at Sonabil S/S | 2xD/C | 132 | 3 | 6 | 6 | 6 | 3 | NOV-13 | JUN-16 | Charged on 31.08.2015.
12 | LILO of Dhaligaon- Bornagar line at Barpeta GSS (Package-A) | D/C | 132 | 23.6 | 96 | 63 | 33 | 0 |  | APR-20 | ROW issues at many locations. change in scope of work due to technical issues. (LILO to Barpeta GSS is from Dhaligaon- Nalbari line, not from Dhaligaon-Barnagar line)
13 | LILO of one ckt of Rowta-Depota at Dhekiajuli | S/C | 132 | 2.07 | 8 | 0 | 0 | 0 |  | JUL-17 | One tower excavation work completed
14 | LILO of one ckt. of Rowta-Depota line-1 at Dhekiajuli (Pkg B) | D/C | 132 | 2 | 8 | 8 | 8 | 2 |  | MAY-18 | Test Charged on 30.01.18.
15 | LILO to Barpeta GSS from 132 kV Dhaligaon-Bornagar line | D/C | 132 | 23.6
16 | Sonapur - Chandrapur line | D/C | 132 | 28 | 55 | 53 | 51 | 20 | NOV-13 | MAR-18 | Completed and Charged on 10.03.2018.
17 | Sonapur - Jagirod line | D/C | 132 | 52 | 107 | 107 | 107 | 24 | NOV-13 | DEC-20 | Due to ROW issues stringing is not completed. (Forest clearance issues).
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED(BSPTCL)
1 | LILO of (Quad) Barh - Patna at Bakhtiyarpur (New) | D/C | 400 | 41 | 61 | 49 | 43 |  | OCT-24 | FEB-23 | ROW issues.
2 | Bakhtiyarpur (New) - Fatuha (BSPTCL) | D/C | 220 | 92 | 157 | 142 | 107 | 0 | OCT-24 | DEC-22 | Work under progress.
3 | Banka(PG)-Goradih Transmission line | D/C | 220 | 65 | 0 | 0 | 0 | 65 | SEP-24 | DEC-24 | Commissioned 11/24.
4 | BTPP - Dumraon (New) GSS | D/C | 220 | 129 | 215 | 215 | 215 | 129 | MAY-24 | JUN-24 | Commissioned 05/24. (ANTITHEFT CHARGED on 13-05-2024)
5 | BTPP - Karmnasa GSS line (twin moose conductor) | D/C | 220 | 59 | 185 | 185 | 185 | 59 | JUN-23 | MAY-24 | Commissioned 02/24. (Charged on no load from Karamnasa (New) end on 24-02-2024)
6 | LILO of Purnea (PG) - Khagaria (New) at Korha (New) | D/C | 220 | 28 | 0 | 0 | 0 |  | JAN-20 | JUN-22 | land not finalised yet
7 | LILO of Sipara (BSPTCL) - Bihta (BSPTCL) at Jakkanpur (New) | D/C | 220 | 47 | 0 | 0 | 0 |  | JUN-24 |  | M/s BGCL
8 | Pusouli (New) - Dehri | D/C | 220 | 125 | 159 | 159 | 159 | 125 | MAY-24 | JUL-24 | Commissioned 06/24.
9 | Sitamarhi (New) - Motihari (New) | D/C | 220 | 120 | 0 | 0 | 0 |  |  |  | This is the Same line as mentioned in Sr. no.34-Sitamarhi(New)-Raxual
10 | Tajpur- Samastipur (New) Trans. line | D/C | 220 | 37 | 0 | 0 | 0 |  | MAY-23 | MAR-23
11 | Thakunganj - Kishanganj (New) Trans. line | D/C | 220 | 52 | 0 | 0 | 0 |  |  | DEC-22
12 | Betia-Raxaul (2nd circuiting) | D/C | 132 |  | 0 | 0 | 0 |  |  |  | Completed
13 | Motihari-Bettia | D/C | 132 | 79 | 143 | 143 | 143 | 79 |  | MAY-17 | completed
14 | Motihari-Motihari | D/C | 132 | 78 | 142 | 142 | 142 | 78 |  | JUL-17 | Completed
15 | Motihari-Raxaul | D/C | 132 | 119 | 215 | 215 | 215 | 119 |  | OCT-17 | Completed
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD.(CSPTCL)
1 | LILO of 400kV Raita-Jagdalpur line at 400kV Kurud (Dhamtari) s/s | D/C | 400 | 3 |  |  |  |  | SEP-24
2 | Raipur (PGCIL Kumhari) - Raita | D/C | 400 | 6
3 | 2nd circuiting of 220 Khedamara- Bemetara line from 220kV s.s Ahiwara to 220kV s/s Bemetara line | S/C | 220 | 38
4 | Bilaspur - Mopka DCDS line | D/C | 220 | 80 | 0 | 0 | 0 |  | MAR-22 |  | This line was re-planned as LILO of 220 KV Mopka -Bhatapara circuit & 220 KV Mopka- Siltara circuit on multi circuit tower at 220 KV S/s Dhardehi (Bilaspur) and these line were charged on dtd 25.09.2019
5 | Bilaspur - Suhela DCDS line | D/C | 220 | 220 | 0 | 0 | 0 |  | MAR-22 |  | This line was re-planned as LILO of 220 KV Mopka -Bhatapara circuit & 220 KV Mopka- Siltara circuit on multi circuit tower at 220 KV S/s Dhardehi (Bilaspur) and these line were charged on dtd 25.09.2019
6 | DCDS Raita - Parsada | D/C | 220 | 110 | 0 | 0 | 0 |  | MAR-20 |  | land for substation not finalized
7 | Dhamtari - Gurur DCDS line | D/C | 220 | 50 | 0 | 0 | 0 |  | MAR-19 | AUG-19 | This line is re-planned as Gurur-Kurud(Bangoli) , S.No. 7
8 | Janjgir Champa Ps - Mopka (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | work not approved till date
9 | Kurud-Gurur line | D/C | 220 | 74 |  |  |  |  | DEC-24
10 | Kurud -Rajim line | D/C | 220 | 66 |  |  |  |  | FEB-25
11 | Kuurud - Patan DCDS line | D/C | 220 | 22 |  |  |  |  | MAR-24
12 | LILO of Bhatapara - Doma at Rita ( 400kV S/s) | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-22 |  | Estimate sanctioned
13 | LILO of Khedamara-Thelkadih at Semariya | D/C | 220 | 3 |  |  |  |  | DEC-24
14 | LILO of Mopka - Siltara line at Raita. | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-22 |  | Estimate sanctioned
15 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | D/C | 220 | 45 | 0 | 0 | 0 | 44 | APR-24 | JUL-24 | Commissioned 06/24.
16 | Raita - Rakhi DCDS line on multi ckt tower | D/C | 220 | 140 | 0 | 0 | 0 |  | MAR-22 |  | work not approved till date
17 | Rajnandgaon Ps - Bhilai (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | work not approved till date
DELHI TRANSCO LIMITED(DTL)
1 | 220kV between Park Street-Electric Lane and Between Lodhi Road to Electric Lane s/s under MOU-II (U/G XLPE cable link) 220kV | S/C | 220 | 17 | 0 | 0 | 0 |  | OCT-23 | JUL-23 | 1. Cable laying work have been completed in all 19 sections. 2. Cable Straight through Jointing work completed in all 17 JBs. 3. Case file for releasing of Advance payment (Rs.6.45 Crore) in favour of M/s. PGCIL have been processed on 14/03/2022. This Case file has been received back from Finance Dept. on 12/05/2022 seeking some clarifications, accordingly the Case file put up for seeking clarification from Planning Deptt on 12/05/2022, 27/05/2022, 14/06/2022, 28/07/2022 and 23/08/2022 and received back on 30.09.2022. Clarification sought from PGCIL as per queries of Planning department on dated 04.10.2022, which is still awaited. A) Electric Lane to Park Street (JB#01):- 4. 220kV GIS end termination work and installation of link boxes has been completed.Termination of OFC is completed. 5. Electrical Inspector clearance has been received on 28-03-2023. 6. Commissioning team meeting/activities held on 27th to 29th March, 2023. 7. As per direction of Dir(Opr), and as i
2 | 220kV D/C underground cable from IP -New Rajghat GIS | D/C | 220 | 4 |  |  |  |  | MAR-25
3 | 220 kV U/G cable from Kashmiri Gate SS to 220 kV Timarpur (GIS) SS | D/C | 220 | 10 | 0 | 0 | 0 | 10 | JUN-24 | DEC-24 | Commissioned 11/24.
4 | Bawana - Kanjhawala at Barwala | D/C | 220 | 1 | [5 empty] | MAR-23
5 | Budella - Zakhira | D/C | 220 | 20 |  |  |  |  | MAR-20
6 | Dev Nagar - Subzi Mandi (U/G Cable) | D/C | 220 | 10 | 0 | 0 | 0 |  | MAR-22 | OCT-22
7 | Harsh Vihar - Preet Vihar | D/C | 220 |  | 0 | 0 | 0 |  | FEB-16
8 | IP-Park Street-Electric Lane (Cable) | S/C | 220 | 18 | 0 | 0 | 0 |  | MAR-22 | MAR-22 | Work in Progress.
9 | Kashmiri Gate - Rajghat line | D/C | 220 | 10 | 0 | 0 | 0 |  |  |  | PGCIL yet to start the work.
10 | LILO of 2nd Ckt Kanjhawala - Njafgarh at Mundka | D/C | 220 | 7 | [5 empty] | MAR-21
11 | LILO of AIIMS - Ridge Valley at R.K.Puram | D/C | 220 | 5 | 0 | 0 | 0 |  |  | NOV-21 | 1. Preliminary Joint Survey has been carried out on 18.12.19. 2. CPG has been submitted on 20.12.2019. 3. Contract Agreement has been executed on 23.12.19. 4. L-2 network has been approved on 07.01.2020. 5. Drum length has been approved for all eight sections. 6. R.K.Puram-AIIMS Ckt-II (Bay No 206) has been charged on 29.03.2021 and thereafter R.K.Puram Ridge Valley Ckt-II (Bay No-212) has been charged on 30.03.2021 7. R.K.Puram-AIIMS Ckt-I (Bay no 207) has been charged on 31.03.2021 and thereafter R.K.Puram Ridge Valley Ckt-I (Bay No 211) has been charged on 31.03.2021. 8. Installation of Route markers has been completed.
12 | LILO of Bamnauli to DIAL D/C at Bhartal | D/C | 220 | 4 |  |  |  |  | MAR-20
13 | LILO of Electric Lane to Park Street at Dev Nagar (U/G Cable) (remaining portion) | S/C | 220 | 10 | 0 | 0 | 0 |  | MAY-24 | APR-23 | 1. CPG has been submitted on 20.12.2019. 2. Contract Agreement has been executed on 23.12.2019. 3. L-2 network has been approved on 06.01.2020. 4. Cable laying work has been completed in 12 sections out of 12 sections. 5. Jointing works have been completed at 12 JBs out of 12 JBs. 6. Indoor End Termination work at 220kV GIS bay Devnagar S/stn has been completed. 7. Park Street  Devnagar 220KV U/G cable has energized on 06.12.2022 at 20:58 Hrs. 8. Provisional time extension has been approved from competent authority up to 30.04.2023. 9. The Electric lane-Dev Nagar circuit was test charged on 29.03.2023 at 20:54 hrs but it tripped on differential protection soon after. The repairing work of side cable is in progress.
14 | LILO of first ckt of double ckt of Pragati - Sarita Vihar at maharani Bagh | D/C | 220 | [5 empty] | MAR-15
15 | LILO of Maharanibagh - Gazipur at Mayur Vihar | D/C | 220 | 0.2 | [5 empty] | MAR-22
16 | LILO of Maharanibagh - Masjid Moth at Nehru Place | D/C | 220 | 0.2 | [5 empty] | MAR-21
17 | LILO of Mandola - Gopalpur at Budhpur/Nathupura | D/C | 220 | 2 | [5 empty] | MAR-22
18 | LILO of Narela - Mandola at Tikri Khurd | D/C | 220 | 3 | 10 | 5 | 5 |  | JUN-19 | MAR-19
19 | LILO of one ckt of Bamnauli - Naraina Ckt-I at Pappankalan-I | S/C | 220 |  | 2 | 2 | 2 | 0.2 | MAR-15 | NOV-17 | Work completed
20 | LILO of Pragati - Sarita Vihar at Maharanibagh | D/C | 220 | 1
21 | Zakhira - Devnagar D/C U/G | D/C | 220 | 10 |  |  |  |  | MAR-21
DEPARTMENT OF POWER ARUNACHAL PRADESH(null)
1 | LILO of Ranganadi - Itanagar at Pare HEP | D/C | 132 | 5 | 12 | 12 | 12 | 5 |  | MAR-18 | Line work completed. a) RHEP Section: Charged on 06.07.2018. b) Itanagar Section: Charged on 07.07.2018.
2 | Pasighat-Roing -Tezu - Namsai 132kV S/c line (2nd ckt. stringing) (GEC-II) | S/C | 132 | 0
3 | Tezu pool - Tezu line (GEC-II) | D/C | 132 | 0
ELECTRICITY DEPARTMENT, GOVT. OF MANIPUR(ED, Manipur)
1 | Kakching - Churachandpur | S/C on D/C | 132 | 35 | 0 | 0 | 0 |  | OCT-17 |  | Work almost completed except two spans of 700 m due to forest clearance.
2 | Leimatak PH (NHPC) - Ningthoukhong 132 s/s 2nd ckt | S/C on D/C | 132 | 11 | 0 | 0 | 0 |  | NOV-17 |  | 35% work completed
3 | Moreh Line | S/C | 132 | 45 | 181 | 158 | 70 | 3 | SEP-17
4 | Thanlon line | S/C | 132 | 66 | 242 | 234 | 224 | 52 | SEP-17 | SEP-17
5 | Thoubal 400kV s/s - Kongba Yaingangpokpi , Hundung | D/C | 132 | 22 | 44 | 43 | 34 | 9 | AUG-17 | SEP-17
6 | Thoubal 4ookV s/s - Moreh 132kV s/s | D/C | 132 | 170 | 0 | 0 | 0 |  | MAR-18 |  | WIP
7 | Tipaimukh Line | S/C | 132 | 10 | 24 | 12 | 0 |  | DEC-17
8 | Yurembam S/S (State) 132kV- YurembamS/S(PGCIL) 132kVS/S 3rd ckt | S/C on D/C | 132 | 2 | 0 | 0 | 0 |  | NOV-17 |  | 35% work completed
ENERGY & POWER DEPARTMENT,GOVT. OF SIKKIM(SPD)
1 | Dikchu -Singhik | D/C | 220 | 22 |  |  |  |  | JUN-23
2 | (Sikkim) Singhik-Chungthang line | D/C | 220 | 30 |  |  |  |  | SEP-22
GOA ELECTRICITY DEPARTMENT(ED-GOA)
1 | Colvale - Kadamba - Verna - Cuncolim line | D/C | 220 | 120 | [5 empty] | MAR-19 | Proposals have been forwarded to Government. The approcal is awaited from Finance Department.
2 | Colvale-Saligao | D/C | 220 | 80 |  |  |  |  | JUL-19
3 | Colvale - Tuem | D/C | 220 | 20 | [5 empty] | MAR-19 | Letter of Intent will be issued to RECTPCL shortly, who has been appointed as Project Management consultant(PMC). Necessary approvals have been obtatined from the Government.
4 | Ponda - Verna | M/C | 220 | 84 |  | 0 | 0 | 0 |  | MAR-19 | Proposals have been forwarded to Government. The approcal is awaited from Finance Department.
GUJARAT ENERGY TRANSMISSION CORP. LIMITED(GETCO)
1 | Dhuvaran-Chharodi Line | D/C | 765 | 240 | 0 | 0 | 0 |  |  | MAR-22
2 | 400kV D/C Shapar-Pachcham (Fedra) Line with Twin AL-59 cond. and 1 OPGW and 1 Earth Wire | D/C | 400 | 197 | 301 | 289 | 279 | 114.16 | JUN-24 | DEC-24 | WIP
3 | 400kV D/C Varsana-Halvad (PACKAGE-1) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 144 |  |  |  |  | DEC-24
4 | 400kV D/C Varsana-Halvad (PACKAGE-2) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 94 |  |  |  |  | DEC-24
5 | Amreli - Kasor line | D/C | 400 | 460 | 680 | 633 | 591 | 224.43 |  | MAR-25 | W I P / Severe RoW problems
6 | Balance work of 400kV D/C Vadavi -Halvad Line (PACKAGE-2) (AP-41 to Halvad) with Twin AL-59 Condu. and 1 and OPGW and 1 Earth Wire | D/C | 400 | 149 |  |  |  |  | JUN-24
7 | Bhachunda - Bhuj Pool (PG) line | D/C | 400 | 220 | 0 | 0 | 0 |  |  | MAR-21 | Yet to award.
8 | Bhachunda - Varsana line (Twin AL-59) | D/C | 400 | 280 | 431 | 314 | 266 | 31.57 |  | DEC-24 | WIP
9 | dhuvaran - Fedra (Quad) line | D/C | 400 | 140 | [5 empty] | MAR-22
10 | Kosamba- Achhalia | D/C | 400 | 140 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
11 | LILO of both ckt. Kakrapar - Vapi (PG) line at Chikhli S/s (Twin Moose) | D/C | 400 | 80 | [5 empty] | MAR-22
12 | LILO of Kasor-Amerli line at Fedra | D/C | 400 | 80 | [5 empty] | OCT-22
13 | LILO of one ckt Halvad - Vadavi line at Chharodi S/s (ACSR Twin Moose) | D/C | 400 | 60 | 411 | 336 | 225 | 139.89 |  | MAR-21 | WIP
14 | LILO of one ckt Kosamba-Chorania line at Fedra | D/C | 400 | 46 | 66 | 55 | 48 | 0 |  | MAR-19 | WIP
15 | LILO of one ckt. of planned Ukai - Kosamba line at new s/s near Chikhli | D/C | 400 | 120 | [5 empty] | MAR-22
16 | LILO of SSP- Asoj & SSP -Kasor lines at Achhalia S/S | D/C | 400 | 80 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
17 | Mundra (Adani) - Zerda line 1 | D/C | 400 | 640 | 997 | 491 | 293 | 120.94 |  | MAR-25 | W I P / Severe RoW problems
18 | Pipavav-Amreli | D/C | 400 | 150 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
19 | Sankhari-Prantij | D/C | 400 | 200 |  | 0 | 0 | 0 |  | MAR-21 | Yet to award
20 | Shapoorji Pallonji generating station | D/C | 400 | 220 | 0 | 0 | 0 | 0 |  | DEC-16 | Generation not coming
21 | Vadavi (Balance Work) - Halvad line (Package-2) (Twin AL-59) | D/C | 400 | 144 |  |  |  |  | DEC-23
22 | Varsana-halvad | D/C | 400 | 237 | 360 | 343 | 332 | 110.51 |  | SEP-24 | Tender to be invited at Risk & Cost of EPC Contractor.
23 | Wanakbori TPS-Soja | D/C | 400 | 212 | 343 | 272 | 271 | 144.09 | DEC-19 | MAR-19 | WIP
24 | 220 kV D/C Choraniya - Salejada line | D/C | 220 | 136 | 221 | 221 | 221 | 136 | MAY-24 | AUG-24 | Commissioned 07/24.
25 | 220kV D/C Motigop Babarzar line (AP-7-Motigop gantry) | D/C | 220 | 32 |  |  |  |  | SEP-24
26 | 220kV D/C Motigop Babarzar line (Babarzar gantry to AP-7) -under stopgap | D/C | 220 | 5 |  |  |  |  | SEP-24
27 | 220kV D/C Shapar- Ghiyavad line with AL-59 Conductor | D/C | 220 | 85 | 168 | 116 | 108 | 36.47 | SEP-24 | SEP-24
28 | 220kV S/C Dhama-Bechraji line on 220kV D/C towers (Tap location of existing220kV Bechraji-Surel line to 220kV Dhama S/S | D/C | 220 | 23 |  |  |  |  | JAN-25
29 | Amreli - Maglana line | D/C | 220 | 400 | 0 | 0 | 0 |  |  | MAR-21 | Tender to be done
30 | Babara - Gondal - II line | D/C | 220 | 320 | 0 | 0 | 0 |  |  | MAR-20 | Tender to be done
31 | BECL (Padva) - Botad line | D/C | 220 | 188 | 310 | 254 | 217 | 33.79 |  | DEC-24 | Tender on website and last date is 10.12.2018. (Risk & cost for Balance work).
32 | Bhachau - Radhanpur | D/C | 220 | 340 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award.
33 | Bhatia - Kalavad line | D/C | 220 | 238 | 373 | 176 | 127 | 10.51 |  | MAR-25 | Tender on website and last date is 17.12.2018. (Risk & cost for Balance work).
34 | Bhogat - Moti Gop line (AL-59) | D/C | 220 | 140 | 226 | 177 | 169 | 67.92 |  | SEP-24 | WIP
35 | Bhogat - Ranavav line (AL-59) | D/C | 220 | 150 | 216 | 154 | 119 | 0 |  | DEC-24 | WIP.
36 | Chhatral - Dhanaj | D/C | 220 | 40 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
37 | Chikhli - Bhilad | D/C | 220 | 170 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
38 | Chorania - Botad | D/C | 220 | 104 | 170 | 166 | 151 | 64.56 |  | SEP-24 | WIP
39 | Gavasad - Salejada line with AL-59 conductor and Earth Wire | D/C | 220 | 194 | 327 | 305 | 289 | 146.93 | JUN-24 | SEP-24 | W I P / Severe RoW problems
40 | Hadala - Rajkot-II | D/C | 220 | 25 | 0 | 0 | 0 | 0 |  | MAR-23 | Yet to award
41 | Hazaira (GSEC) - Mota | D/C | 220 | 111 | 182 | 111 | 96 | 41.82 |  | JUN-19 | Inter connection of Utran-Kosamba charged under stop gap arrangement (Kosamba-Mota & Utran-Mota) on 16.06.2018 as per system requirement.
42 | Jasdan - Gondal | D/C | 220 | 100 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
43 | Kalavad - Kangasiali line | D/C | 220 | 112 | 196 | 196 | 196 | 113.73 |  | SEP-23 | Tender under acceptance.
44 | Keshod - Keshod | D/C | 220 | 60 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
45 | Keshod - Veraval line | D/C | 220 | 180 | [5 empty] | MAR-21
46 | Keshod - Visavadar | D/C | 220 | 120 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet toaward
47 | LILO f one ckt. Chandrapura - Godhara line at Halol | D/C | 220 | 20 | [5 empty] | MAR-20
48 | LILO of 220kV GSEG - Mora - Kim line at 220kV Velanja | M/C | 220 | 7 | 14 | 13 | 5 | 0 | JAN-18 | SEP-24 | WIP.
49 | LILO of Achhaliya-Jambuva line at Vyankatpura (Jarod) S/S | D/C | 220 | 125 | 130 | 130 | 130 | 72 |  | AUG-20
50 | LILO of Bhatia - Kalav ad - Kangasiyali at Khambhalia - II | D/C | 220 | 50 | 57 | 34 | 21 | 0 |  | DEC-24 | Yet to award
51 | LILO of both circuits of 220 kV D/C Jambuva - Karamsad line at Dhuvaran CCPP | D/C | 220 | 18 | 0 | 0 | 0 | 18 |  | JAN-25 | Commissioned 12/24.
52 | LILO of both circuits of 220kV D/C Mota - Ambheta (Chikhli) line at proposed 220kV Mahuva | M/C | 220 | 44 | 0 | 0 | 0 | 44 |  | MAY-24 | Commissioned 04/24.
53 | LILO of both ckt. Kawas - Navsari (PG) line at Vesu S/s (2220kVu/g cable) | D/C | 220 | 5 | 0 | 0 | 0 |  |  | MAR-25
54 | LILO of both ckt Kawas - Nvasari (PG) line at Khajod S/s | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-21
55 | LILO of both Ckts. of 220kV D/C Kalawad-Kangasiyali line at Siddheshwar s/s | D/C | 220 | 10 |  |  |  |  | JUL-24
56 | LILO of both ckt. Visavadar- Timbdi line at Keshod S/s | D/C | 220 | 100 | [5 empty] | MAR-21
57 | LILO of Chorania - Gondal at Rajkot-II | D/C | 220 | 25 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
58 | LILO of Chorania - Gondal at Shapar | D/C | 220 | 40 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
59 | LILO of Gavasad - Salejda line at Bil | D/C | 220 | 120 | [5 empty] | MAR-20
60 | LILO of Godhra -Kadana line at Lunawada | D/C | 220 | 5 | 223 | 223 | 214 | 80.09 |  | DEC-18 | WIP
61 | LILO of Jamnagar - Jetpur line-I at Sikka | D/C | 220 | 116 | 178 | 0 | 0 | 0 |  | MAR-21 | Yet to be awarded.
62 | LILO of Jetpur - Rajkot at Metoda | D/C | 220 | 5 | 0 | 0 | 0 | 0 |  | MAR-21 | yet to award
63 | LILO of Keshod - Timbdi line at Veraval | S/C | 220 | 8 | [5 empty] | MAR-20
64 | LILo of Morbi - Hadala line at Makansar S/s | D/C | 220 | 20 | [5 empty] | MAR-21
65 | LILO of of both ckt. GSEG - Kosamba line at Olpad S/s | D/C | 220 | 16 | [5 empty] | MAR-21
66 | LILO of one ckt Kasor - Gavasad line at Gotri S/s | D/C | 220 | 44 | 85 | 73 | 73 | 85.77 |  | MAR-25 | WIP
67 | LILO of one ckt. Wanakbori - Asoj line at Balsinor | D/C | 220 | 40 | [5 empty] | MAR-21
68 | LILO of pm ckt. GPPC- Savarkumdla line at Rajula S/s (ACSR Zerba) | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-23
69 | LILO of pne ckt GPEC - Karamsad lani at Bil | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-21
70 | LILO of Sartanpar - Wankaner line at Makansar S/s | D/C | 220 | 2 | [5 empty] | MAR-22
71 | LILO of Savarkundla - Visavadar at Bagasara S/s | D/C | 220 | 16 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
72 | LILo of Tarapur - Bhilad line at Umargaon | D/C | 220 | 10 | 33 | 12 | 6 | 0 |  | SEP-19 | WIP
73 | LILO of Tarapur - Vapi line at Umargaon | S/C | 220 | 10 | [5 empty] | MAR-20
74 | LILo of Ukai (Thermal) -Achhalia line - III at Virpore | D/C | 220 | 15 | 0 | 0 | 0 |  |  | MAR-21
75 | LILO of Ukat (Th) - Achhalia at Achhalia | D/C | 220 | 10 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
76 | LILO of Vadavi -Chatral at Santej (Dhanaj) | D/C | 220 | 51 | 91 | 91 | 91 | 51.28 |  | AUG-21 | Line Commissioned
77 | LILO of Vadavi - Chhatral & Vadavi - Ganndhinagar TPS at Dhanaj S/s | D/C | 220 | 60 | [5 empty] | MAR-21
78 | LILo of Vapi - Bhilad line at Chikhli s/s | D/C | 220 | 150 | 0 | 0 | 0 |  |  | MAR-21
79 | LILO of Vapi - Chikhli & Bhilad - Chikhli lines at Chikhli | D/C | 220 | 150 | [5 empty] | MAR-20
80 | LILO of Wanakbori TPS - Zalod line at Savdasna Muvada | D/C | 220 | 270 | [5 empty] | MAR-22
81 | LLO of 220 kv Vadavi - Chhatral line at Santej S/s | D/C | 220 | 43 | 91 | 91 | 91 | 50 | MAR-14 | SEP-21 | Commissioned 08/21.
82 | Pipava - Bagasara line | D/C | 220 | 160 | [5 empty] | MAR-21
83 | Pipavav - Otha line | D/C | 220 | 100 | [5 empty] | MAR-21
84 | Pipavav - Rajula line | D/C | 220 | 80 | [5 empty] | MAR-21
85 | Pirana (PG) - Gatrad | D/C | 220 | 50 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
86 | Prantij - Agiyol | D/C | 220 | 60 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
87 | Prantij - Dhansura | D/C | 220 | 70 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
88 | Suva - Achhalia | D/C | 220 | 140 | 0 | 0 | 0 | 0 |  | MAR-23 | Yet to award
89 | Termination of GPEC - Haldarva at Achhalia | D/C | 220 | 90 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
90 | Utran - Kosamba Line-II | D/C | 220 | 86 |  |  |  |  | DEC-09
91 | Vadodara (PG) - Vyankatpura line | D/C | 220 | 30 | 60 | 57 | 57 | 28 |  | FEB-18 | WIP
92 | Vataman (PG) - Bagodara line | D/C | 220 | 160 | [5 empty] | MAR-21
93 | Virpore - Chikhli line | D/C | 220 | 120 | [5 empty] | MAR-20
94 | Vondh - Radhanpur line | D/C | 220 | 340 | [5 empty] | MAR-21
95 | Vyankatpura - Halol line | D/C | 220 | 100 | [5 empty] | MAR-20
96 | LILO of both circuits Sitac WF - Jasdan at Babara (GEC-I) | 2xD/C | 132 | 0 | 0 | 0 | 0 |  |  | JUN-20 | Price Bid Opened & amp; under approval
HARYANA VIDYUT PRASARAN NIGAM LIMITED(HVPNL)
1 | 220kV D/C line from 220kv Meerpur Kurali to TSS Rundhi as a deposit work of Indian Railway | D/C | 220 | 25 | 47 | 47 | 47 | 25 | MAY-24 | NOV-24 | Commissioned 10/24.
2 | 220 kV D/C Line from 220KV S/S Sonipat - 220KV Sector-6 Sonipat | D/C | 220 | 6 | 14 | 1 | 0 | 0 | MAR-25 | MAR-25 | Route approved work started from 03.09.2024.
3 | 220kV D/C line from 400kV PGCIL Panchkula to 220kV Sadhaura | D/C | 220 | 76 | 163 | 127 | 25 | 0 | AUG-24 | MAR-25 | ROW issue TL no. 14 to 33 due to farmer agitation.
4 | 220kV D/C line from 400kV S/Stn. Panchgaon (PGCIL) - 220kV S/S Panchgaon | M/C | 220 | 48 | 2 | 2 | 2 | 10 |  | SEP-22 | commissioned on 05.09.2022
5 | 220kV D/C line from 765kV S/stn. PGCIL Bhiwani to 220kV S/stn. Isherwal | D/C | 220 | 100 | 212 | 209 | 193 | 38 | JUL-24 | DEC-24 | Work is in progress. Work is held up due to severe RoW problem from farmers. However, matter taken up with District Administration, Bhiwani for resolving the issue. MD, HVPNL, Panchkula to hold a meeting with farmers on dated 12.05.2023 at Shakti Bhawan Panchkula for resolving the issue.
6 | 220kV D/C line on M/C towers from 400kV S/S Prithla - 220kV S/Stn. Sector 78 FBD | D/C | 220 | 59 | 169 | 152 | 89 | 0 | SEP-24 | DEC-24 | Work in progress
7 | 220kV D/C overhead line on M/C and D/C towers from 400kV ISTS Prithla to 220kV Harfali with LILO of one ckt at 220kV Meerpur Kurali on M/C and D/C tower | D/C | 220 | 118 | 226 | 25 | 0 |  | MAR-25 | MAR-25 | Work in progress.
8 | 220KV KV D/C Line from 400KV S/Stn PGCIL Bahadurgarh to IMT Pocket-B Kharkhoda | D/C | 220 | 56 | 106 | 38 | 0 |  | MAR-25 | MAR-25 | ROW issue
9 | 220KV KV D/C Line from 400KV S/Stn PGCIL Sonipat to IMT Pocket-A Kharkhoda | D/C | 220 | 44 | 89 | 63 | 0 |  | MAR-25 | MAR-25 | ROW issue
10 | Bagun - Hisar (IA) line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
11 | Barula - Mahindergarh line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
12 | Daukhera - Rewari line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
13 | LILO of 1 ckt of 220kV D/C Samaypur-Palwal at 220kV Harfali | D/C | 220 | 1 | 4 | 4 | 4 | 0 | MAR-25 | OCT-24 | Will be commissioned with commissioning of 220kV substation Harfali.
14 | LILO of 220kV D/C PTPS-Jind line at 220kV S/S Nain | M/C | 220 | 33 | 39 | 39 | 37 | 33 | FEB-25 | FEB-25 | Work held up due to paddy crop.
15 | LILO of 220KV D/C PTPS Jind line at 400KV PGCIL Khatkar (Jind) | M/C | 220 | 18 | 46 | 46 | 44 | 4 | MAR-25 | MAR-25 | Work in progress.
16 | LILO of 220KV Mohana- Samalkha D/C line at 400KV S/S Jhajji (PGCIL) on M/C towers | M/C | 220 | 13 | 24 | 24 | 23 | 3 | JUN-24 | DEC-24 | Forest clearance is pending.
17 | LILO of Both Circuits of 220kV PGCIL Hisar- Fatehabad D/C line at 220kV Chikanwas (Hisar) with 0.4 sq. inch ACSR | M/C | 220 | 19 | 25 | 25 | 23 | 5 | MAR-25 | MAR-25 | Work in progress.
18 | LILO of both ckt. Narwana-Mund line at Khatkar (Jind) PGCIL S/s | D/C | 220 | 44 | 130 | 130 | 128 | 41.5 |  | FEB-21 | Commissioned on 01.02.2021
19 | LILO of both Ckts of 220kV Pali-Sector-65 D/C Line at 400kV S/S Kadarpur | M/C | 220 | 26 | 45 | 45 | 39 | 4 | MAY-24 | OCT-24 | Work held due to delay forest clearance and farmer agitation.
20 | LILO of both Ckts. of Pali-Sector-56 at Kadarpur | D/C | 220 | 14 | 80 | 13 | 0 |  | DEC-23 | MAR-24 | Forest clearance pending
21 | LILO of Ckt. no. 04 from 400kV S/S Sector-72 Gurgaon (PGCIL) - Sector- 72 Gurgaon (HVPNL) at Sector-15-II at Gurgaon | D/C | 220 | 5 | 28 | 2 | 2 | 0 | OCT-23 | JUL-24 | Work in progress.
22 | LILO of Dhanoda - Daultabad line at Farukhnagar S/s | D/C | 220 | 10 | 0 | 0 | 0 |  |  | DEC-23 | Principally approved but possession of land is still pending.
23 | LILO of gurgaon Sec -72 - Sector 52 (A) at Sector 57 | D/C | 220 | 1 | 1 | 1 | 0 |  |  | APR-18 | Commissioned.
24 | LILO of Kunihar - PGCIL Naggal line at Pinjore S/s | M/C | 220 | 5.5 | 46 | 46 | 46 | 5 |  | NOV-22 | Work completed
25 | LILO of Madnpur - Kunihar line at Panchkula sector-32 | D/C | 220 | 5 | 1 | 1 | 1 | 4.5 |  | NOV-22 | Work completed
26 | LILO of one ckt. Badshapur - IMT Manesar line at Gurgaon Sector- 77 S/s | D/C | 220 |  | 4 | 4 | 4 |  |  | NOV-18 | Line Commissioned on 01.11.2018
27 | LILO of Sec -72 Gurugram (PGCIL 400 kV SS) to Sec -72 Gurugram (HVPNL 220 kV SS) ckt - IV at 220 kV Sec 15-II Gurugram220kV Sec 15-II Gurugram | D/C | 220 | 16 | 28 | 28 | 28 | 16 | MAY-24 | DEC-24 | Commissioned in Dec-2024
28 | LILO of Sector-72- Rangla Raipur at Roj-Ka-Meo | D/C | 220 | 7 | 10 | 9 | 0 |  | NOV-23 | JUN-23 | Short closed.
29 | LILO of Tepla (220kV) - Madanpur (220kV) line at 220kV Sadhaura S/S and LILO of Tepla (220kV) to Rajwali (220kV) at 220kV Sadhaura S/S | M/C | 220 | 103 | 128 | 121 | 62 | 16 | AUG-24 | DEC-24 | ROW issue due to court case at location no. 2
30 | Nuna Majra - Nuna Majra | D/C | 220 | 2 | 0 | 0 | 0 |  |  | DEC-23 | NIT yet to be floated
31 | Singhani - Mahindergarh line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
32 | Sonepat to GIS Rai line (late reported commissioned in May-2024) | D/C | 220 | 51 | 0 | 0 | 0 | 51 |  | DEC-24 | Commissioned 05/24 (Late Reported).
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD.(HPPTCL)
1 | Sunda - Andhra Line (GEC-I) | D/C | 66 | 0
2 | LILO of 400kV Lahal Rajera Transmission line at Kuther (240 MW) HEP | D/C | 400 | 1 |  |  |  |  | JUN-24
3 | LILO of Wangtoo - Abdullapur line at Wangtoo | D/C | 400 | 1 | 8 | 8 | 8 | 1 |  | SEP-19 | Line Commissioned
4 | Nalagarh -Kunihar | S/C | 400 | 33 | [5 empty] | MAR-17
5 | Shongtong Karcham HEP - Wangtoo (Quad) | D/C | 400 | 18 |  | 0 | 0 |  |  | DEC-21 | Preliminert Survey has been carried out and is under tendering process for the detailed Survey of the route.
6 | Palchan-Prini line (GEC-I) | N/A | 33 | 0 | 60 | 23 | 9 | 0 |  | JUN-20
7 | 220/132kV MCT Transmission Line from Kala Amb to T-19 of Jamta Kala Amb Line | M/C | 220 | 36 |  |  |  | 36 | JUL-24 | OCT-24 | Commissioned 09/24.
8 | 400/220 kV GIS of POWERGRID at Airendwala to 220/132/33 kV AIS of HPPTCL at Andheri Kala Amb Distt. Sirmaur | D/C | 220 | 11 | 0 | 0 | 0 | 11 | APR-24 | JUN-24 | Commissioned 05/24.
9 | Hatkoti-Pragati Nagar | D/C | 220 | 56 | 100 | 100 | 100 | 56 | MAR-17 | MAR-20 | Line commissioned
10 | Kashang - Jangi Pooling Station | D/C | 220 |  | 0 | 0 | 0 |  |  |  | power of kashang and other generating projects in vicinity was planned to be pooled at Jangi pooling station, since other generating projects have withdrawn LTA therefore the construction of Jangi pooling station has been dropped for the time being.
11 | Koti-Karian | S/C | 220 | 35 | 0 | 0 | 0 |  |  | MAR-19 | Delay FCA approval.
12 | LILO of 220 kV D/C Bajoli Holi to Lahal Transmission Line at 220/66 kV Heiling S/S | D/C | 220 | 1 | 0 | 0 | 0 | 1 | JUL-24 | JAN-25 | Commissioned 12/24.
13 | LILO of both ckt of Kashang -Bhaba line at Wangtoo GIS | D/C | 220 |  | 0 | 0 | 0 |  |  | DEC-18 | Work in Progress
14 | LILO of Nalagarh-Baddi at Mandhala S/S | D/C | 220 | 8 | [5 empty] | MAR-17
15 | Rauri-Kunihar | D/C | 220 | 28 | [5 empty] | MAR-17
16 | Stringing of 2nd Circuit from Dehar HEP of BBMB to Kangoo S/S | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-24 | MAR-23
17 | Chanju-I - Chanju-II | D/C | 132 | 12
18 | Chanju-II - Chanju-III | D/C | 132 | 8
19 | Chanju - Nakrot line | D/C | 132 | 12 | 30 | 29 | 27 | 10 |  | MAY-16 | commissioned.
20 | LILO of Both Ckt 132 kV D/C Kurthala - Bathri at 220/132 Mazra GIS | 2xD/C | 132 | 1 | 0 | 0 | 0 |  |  |  | Forest Clearance Case is under Progress
21 | Rupin HEP - Sunda (GEC-I) | D/C | 132 | 0
22 | Tangnu Romai-I HEP - 220/132 kV Sunda S/S | D/C | 132 | 24 | 37 | 25 | 17 | 5 |  | DEC-21 | work is progress and all efforts have been made to complete the work by Dec-21.
HIMACHAL PRADESH STATE ELECTRICITY BOARD LIMITED(HPSEBL)
1 | Ghanvi-II - Kotla with HTLS Line (GEC-I) | D/C | 66 | 8
2 | Hatkoti - Samoli Line (GEC-I) | N/A | 66 | 0
3 | Kotla- Nogli-Samoli Line (GEC-I) | N/A | 66 | 120
4 | Nathpa - Wangtoo Line (GEC-I) | N/A | 66 | 0
5 | Bajaura - Naggar Line at Kullu (GEC-I) | S/C + D/C | 33 | 0
6 | Baner Power House - Dehan (Dharmshala) line (GEC-I) | S/C | 33 | 0
7 | Darkata (Ranital) - Lunj Line (GEC-I) | S/C | 33 | 0
8 | Dunkhra (Jari) - Manikaran Line (GEC-I) | D/C | 33 | 0
9 | Gaj Powerhouse - Kangra Line (GEC-I ) | N/A | 33 | 37
10 | LILO from Gaj - Shahpur at Chambi Line (GEC-I) | S/C | 33 | 0
11 | LILO of Bharmour-Gharola line at Lahal (GEC-I) | N/A | 33 | 0
12 | LILO of one Ckt. Shahpur - Kangra at Chambi (GEC-I) | D/C | 33 | 0
13 | LILO of Pandoh - Bijni line at Pandph (GEC-I) | N/A | 33 | 0
14 | LILO point Gharola - Chamba at Karian (GEC-I) | N/A | 33 | 96
15 | Naggar - Bajaira Line at Kullu (GEC-I) | N/A | 33 | 0
16 | Padhar (Gwali) - Bijni Line at Mandi (GEC-I) | S/C | 33 | 0
17 | Pandoh - Bijni Line (GEC-I) | D/C | 33 | 0
18 | Pirini - AD Hydro HEP XLPE Cable Pirini (GEC-I) | N/A | 33 | 0
19 | Pirini - AD Hydro HEP XLPE Cable Pirini (GEC-I) | N/A | 33 | 0
20 | Reconductoring of Gaj-Shahpur line (New reconductoring ) (GEC-I) | S/C | 33 | 19
21 | Salooni - Koti Line (GEC-I) | D/C | 33 | 0
22 | Gumma - Andhra (GEC-I) | D/C | 22 | 12
23 | Jhakri - Rampur line (GEC-I) | D/C | 22 | 0
24 | Karcham - Bhoktoo line (GEC-I) | D/C | 22 | 0
25 | Rampur - Nagli line (GEC-I) | S/C | 22 | 0
26 | Rukti - Shaung line (GEC-I) | D/C | 22 | 8
27 | Gondpur (Paonta) - Sataun line (GEC-I) | D/C | 132 | 0
28 | Uhl-III - Hamir Pur (By BVPCL) | D/C | 132 | 71 | 0 | 0 | 0 |  |  |  | completed on Mar-14
JHARKHAND URJA SANCHAR NIGAM LTD.(JUSNL)
1 | Chandil - Chaibasa (PGCIL) | D/C | 400 | 65 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
2 | Chandil - Dhanbad GSS | D/C | 400 | 125 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
3 | Chandil New - Chaibasa (PG) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
4 | Chandwa - Latehar (JUSNL) line | D/C | 400 | 83 | 122 | 122 | 122 | 83 | OCT-24 | JAN-25 | Commissioned 12/24.
5 | Dumka - Jasidih | D/C | 400 | 70 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
6 | Koderma - Jasidih | D/C | 400 | 130 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
7 | LILO of Bero- Patratu at GSS Mander | D/C | 400 | 15 | 0 | 0 | 0 |  |  | MAR-24 | "The RFQ & RFP floted by M/s RECTPCL has been cancelled. The decision for mode of execution of this project will be taken after getting approval of 1st phase projects i.e Project related to PUVNL evacuation."
8 | LILO of one ckt QM Kahalgaon - Maithon at GSS Dumka | D/C | 400 | 20 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
9 | OM Jasidih - Koderna GSS | D/C | 400 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
10 | Patratu - Chandil GSS | D/C | 400 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
11 | Patratu (JSUNL) - Latehar(JUSNL) | D/C | 400 | 215 | 304 | 275 | 260 | 81.55 |  | FEB-23 | Stage-I clearances awaited.
12 | Patratu New - Chandil New line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
13 | Patratu New - Kodarma (JUSNL) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
14 | Patratu New - Patratu line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Project is being implemented by JUSNL. Tender is likely to be floated in Jul 20. Length of line is 8ckm.
15 | PUVNL- Patratu | D/C | 400 | 14 | 0 | 0 | 0 |  | JUN-24 |  | Request letter regarding additional fund as difference of sanctioned cost and offered price of L-1 bidder has been sent to energy dept. Govt of Jharkhand. After sanctioning of requisite fund, work order will be issued.
16 | PVUNL-Chandil | D/C | 400 | 270 | 0 | 0 | 0 |  |  |  | Technical evaluation under progress.
17 | PVUNL-Koderma | D/C | 400 | 300 | 0 | 0 | 0 |  |  |  | Technical evaluation under progress.
18 | QM Koderma - Daltonganj | D/C | 400 | 200 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
19 | QM Koderma DVC TPS - Koderma JUSNL | D/C | 400 | 15 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
20 | QM North Karanpura - Latehar | D/C | 400 | 100 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
21 | QM Patratu - Koderma GSS | D/C | 400 | 150 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
22 | Quad Essar (Latehar) - Chandwa TL | D/C | 400 | 2 | 7 | 4 | 0 |  |  | FEB-22 | Work in Progress.
23 | TTPS - Dumka GSS | D/C | 400 | 236 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
24 | TTPS-PTPS (Modification and upgradation) to provide startup power to PVUNL) | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | LOA placed on 15.07.22. Schedule completion 14.10.22.
25 | 3 Ph. Baliyapur - Topchanchi | D/C | 220 | 50 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
26 | 3 Ph. Giridih - Domchanch | D/C | 220 | 90 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
27 | 3 Ph. Giridih - Topchanchi | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
28 | 3 Ph. Khunti - Mander (400kV GSS) | D/C | 220 | 60 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
29 | 3 Ph. Khunti - Simdega | D/C | 220 | 120 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
30 | 3 Ph. Koderma - Domchanch | D/C | 220 | 16 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
31 | Chaibasa - Gua TL | D/C | 220 | 168 | 278 | 127 | 110 | 0 |  | JAN-22 | Wildlife clearance issue.
32 | Chandil (4ookV GSS) - Jadugoda | D/C | 220 | 80 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
33 | Chandil GSS - Chandil | D/C | 220 | 10 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018.
34 | Chandil GSS - Tamar | D/C | 220 | 25 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
35 | Chandrapura DVC - Chandrapura | D/C | 220 | 8 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
36 | Chatra - PBCMP (Barkagaon) TL | D/C | 220 | 117 | 185 | 158 | 125 | 20 |  | MAR-23 | Work in Progress.
37 | Giridih - Jamua | D/C | 220 | 160 | 0 | 0 | 0 |  | MAY-18 |  | This line actually constructing at 132kV volatge level instead of 220kV voltage level
38 | Govindpur - Govindpur | D/C | 220 | 7 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
39 | Hazaribagh - Barkatta | D/C | 220 | 18 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
40 | Koderma (JSEB) - Koderma(DVC) | D/C | 220 | 21 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 31.01.2018
41 | Koderma - Giridih | D/C | 220 | 140 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
42 | LILO of 220kV D/C Govindpur -TTPS at Jainmore | D/C | 220 | 47 | 92 | 82 | 67 | 24.3 | OCT-24 | MAR-23 | Work in Progress.
43 | LILO of both ckts Dumka - Govindpur at Palojori GSS | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
44 | LILO of Chandil - Ranchi (PG) at Tamar | M/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
45 | LILO of Hatia - Lohardaga at GSS Mander | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
46 | LILO of Patratu - Hatia at PTPS by MC Tower | D/C | 220 |  | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
47 | Link Line Daltonganj - Garhwa TL (Bhagodih END) | D/C | 220 | 82 | 159 | 159 | 159 | 89 | MAR-22 | AUG-20 | Link Line Daltonganj-Garhwa (both end Bhagodih end and Daltonganj end) has been commissioned on 18.08.2020.
48 | Mander - Tamar | D/C | 220 | 56 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
49 | Noamundi - Chaibasa (PG) | D/C | 220 | 130 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
50 | Noamundi - Jadugoda | D/C | 220 | 80 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
51 | P.T.P.S. - Ratu | D/C | 220 | 70 | 124 | 122 | 121 | 49.25 | MAY-18 | OCT-20 | Tree Cutting Permission awaited for Hapua-Katia Proposal from DFO, Ramgarh.
52 | Ratu - Mander | D/C | 220 | 15 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
53 | Simdega - Chaibasa | D/C | 220 | 165 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
54 | Tenughat - Chandrapura | D/C | 220 | 55 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
55 | Tenughat - Gomia | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
56 | Tenughat - Hazaribagh | D/C | 220 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
J&K POWER DEVELOPMENT DEPARTMENT(JKPDD)
1 | Kharu S/S - Himya S/S | S/C | 66 | 51 | 242 | 239 | 204 | 36 |  | DEC-16 | Slow progress.
2 | Leh III (Army base) - Leh | S/C | 66 | 10 | 53 | 29 | 8 | 2 |  | DEC-16 | Rerouting of line and ganglas s/s droped. Leh Army S/S shall be connected with Leh S/S.
3 | Kiru HEP - Kishtwar Pooling Station (Triple HLTS Conductor) | D/C | 400 | 0 | 0 | 0 | 0 |  |  | DEC-21 | work under planning stage.
4 | LILO of one Ckt. of Kiru HEP - Kishtwar PS at Kwar HEP and Pakal Dul HEP | D/C | 400 | 0 | 0 | 0 | 0 |  |  | DEC-21 | Work under planning stage.
5 | Delina - Wahipora-Kishanganga | D/C | 220 | 80 | [6 empty] | Fund yet to be tied up.
6 | LILO-II of Bishnah-Hiranagar Tr. Line from 400/220 kV Grid Station Jatwal(PGCIL) to Loc. No. 203 | D/C | 220 | 4 |  |  |  |  | MAY-23
7 | (PMDP - Kashmir) LILO of Wagoora - Mirbazar line at Lassipora | D/C | 220 | 11 | 22 | 21 | 20 | 0 |  | JUN-22 | Works under progress. Delayed due to severe ROW issue.
8 | Thein (RSD)-Hiranagar (2nd ckt) | S/C | 220 | 40 | 117 | 117 | 117 | 40 | MAR-08 | DEC-19 | E-NIT floated by PGCIL for the three works on 09-10-2017.
9 | Wagoora-Budgam- Zainkote | D/C | 220 | 60 | 123 | 106 | 82 | 17 | JAN-24 | OCT-23 | ROW issues at various locations delaying the project.
10 | Wagoora-Mirbazar | D/C | 220 | 104 | 177 | 175 | 173 | 63 | AUG-23 | JUL-23 | ROW,, compensation issues delaying the project.
11 | Zainkote-Alusteng-Mirbazar | D/C | 220 | 254 | 444 | 436 | 371 | 114 | MAY-19 | MAR-23 | Section I-- Zainakote-Alusteng completed and commissioned in Feb 20. Erection works on Section-II Alusteng-Mirbazar section held up due to non-availability of funds.
12 | Lower Kalnai - Thathri S/s (existing) line | D/C | 132 | 6
13 | Parnai HEP - Parnai (JKPDD) | D/C | 132 | 30
14 | (PMDP - Jammu) Hiranagar - Kathua line (Reconductoring) | D/C | 132 | 152 | 0 | 0 | 0 |  | MAR-19 | DEC-19 | CC-I meeting held on 3rd and 4th of June 2019 and minutes of meeting yet to be issued.
15 | (PMDP - Jammu) LILO of Canal - Miran Sahib at Chatha | D/C | 132 | 16 | 3 | 0 | 0 |  | MAR-19 | MAR-20 | Out of 40 Kanals of land 20Kanals land has been acquired. Preliminary works (soil testing and demarcation) are under progress. Layout also approved.
16 | (PMDP - Kashmir) LILO of Budgam - Bemina at Tengpora (Power Cable) | D/C | 132 | 8 | 0 | 0 | 0 |  | MAR-20 | SEP-21 | Completed
17 | (PMDP - Kashmir) Replacement of Conductor in Pampore - Cheshmashahi | D/C | 132 | 28 | 0 | 0 | 0 |  | MAR-19 | JAN-21 | Completed.
18 | Solar Park - Samba line (GEC-II) | D/C | 132 | 0
J&K STATE POWER DEVELOPMENT CORPORATION(JKSPDC)
1 | Udhampur- Gladni | S/C | 220 | 48 | 165 | 165 | 165 | 48 | APR-08 | SEP-14 | Severe RoW and Court case.
KARNATAKA POWER TRANSMISSION CORP. LIMITED(KPTCL)
1 | Bellary (PS) - C.N. Hally | D/C | 400 |  | 0 | 0 | 0 |  |  | MAR-18
2 | Bellary (TPS) - Bellary (PS) | D/C | 400 | 5 | 0 | 0 | 0 |  |  | MAR-18 | This work is not in planned works.
3 | Hiriyur - Mysore (GEC-II) | D/C | 400 | 390 | 0 | 0 | 0 |  |  |  | Pertains to PGCIL
4 | Kalburgi - YTPS | D/C | 400 |  | 331 | 331 | 331 | 226.95 | SEP-18 | JAN-23 | Commissioned
5 | LILO of Bellary PS - Chikkanayakanahalli at Jagalur (Common Point at Rampura) | M/C | 400 | 130 | 187 | 187 | 187 | 130 | SEP-18 | AUG-18 | commissioned
6 | LILO of both ckt. of Bellary Pool - Madhugiri at Tumkur (Pavagada ) PS (GEC-II) | M/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Commissioned
7 | LILO of Both ckt of Nelamangala - Talaguppa at CN Halli | D/C | 400 |  | 0 | 0 | 0 |  |  | MAR-18 | S/S Land to be Acquired
8 | Tumkur (Pavagada) PS - Devanahally (KPTCL) (GEC-II) | D/C | 400 | 170 | 0 | 0 | 0 |  |  |  | Pertains to PGCIL
9 | Tumkur PS - Hiriyur (GEC-II) | D/C | 400 | 218
10 | Yermarus TPS - Gulbarga | D/C | 400 |  | 331 | 331 | 331 | 234.11 |  | MAR-23 | Repeated work. Commissioned
11 | 220kV CB Pura I/A -Work-A Construction of 220kV DC LILO line from proposed 220 kV Chintamani-Mittemari D/ C line (both Ckts.) at proposed 220kV CTT | D/C | 220 | 111 | 101 | 75 | 70 | 32 | NOV-24 |  | Work under progress
12 | 220kV DC line from the existing 220/110 kV Halabarga s/s to the proposed Santhpur S/S | D/C | 220 | 57 | 103 | 103 | 103 | 54.74 | AUG-24 | DEC-24 | Work under progress
13 | Beerenahalli - Thallak (Chitradurga) (Balance portion) | D/C | 220 | 41 | 73 | 72 | 63 | 17 | MAR-18 | DEC-24 | ROW issues at Talvatti and Berenahalli limits.
14 | Bidadi (PGCIL) - Magadi S/S | D/C | 220 | 64 | 127 | 91 | 84 | 42.23 | FEB-17 | MAR-25 | ROW issues.
15 | Bidadi - Kothipura (Channapatna) | D/C | 220 | 174 | 91 | 91 | 91 | 72.75 | FEB-08 | NOV-22 | Commissioned on 18.11.2023.
16 | Bijapur - Sindagi | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | SEP-19
17 | Chikkabettahalli limits (8 Pole Structure) - Sahakarinagar GIS s/s | M/C | 220 | 19 | 29 | 29 | 29 | 19 |  | DEC-21 | Commissioned
18 | Conversion of 220 kV Bidnal-Soundatti-Mahalingapura S/C line - 220 kV Bidnal - Mahalingapur D/C line | D/C | 220 | 125 | 457 | 457 | 457 | 125 | JUL-24 | AUG-24 | Commissioned 07/24.
19 | Devanahalli Hardware Park (WORK-A) from 400 kV DWHP to CTT for Double LILO of 220 kV Nelamanagal -Hoody DC line (Vidyanagar 66kV line corridor) | M/C | 220 | 21 | 4 | 4 | 4 | 21 | SEP-19 | SEP-24 | Commissioned 08/24.
20 | Devanhalli -(Hardware Park 2nd ckt) and Doddaballapura (2nd ckt) | M/C | 220 | 100 | 94 | 88 | 73 | 64.4 |  | DEC-24 | ROW issues in the line. ROW issues resolving under progress.
21 | Ghanagapura - Aaheri line | D/C | 220 | 112 | 215 | 214 | 212 | 88.72 | SEP-24 | DEC-24 | Work under progress
22 | Ghanagapura - link Shahpur - Khanapura line | D/C | 220 | 21 | 32 | 17 | 14 |  | SEP-24 | MAR-25 | Tower no. 6 to 22(7.161km) is under SEW by Shree cements ltd. Hence the work will be completed 3months from the date of LOI of SEW.
23 | Gulbarga - Afzalpur (Ganagapura) | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | SEP-19 | Work tendered
24 | Hangal Construction of 220kV DC line on DC towers from 220 kV Hiremallanahole (Jagalur) to Hangal D/C Line | D/C | 220 | 73 | 140 | 87 | 59 | 0.85 | FEB-25 | FEB-25 | WUP
25 | Hiriyur (PG) - Hiriyur S/S | S/C | 220 | 16 | 28 | 25 | 25 | 15.16 | APR-19 | DEC-19 | Commissioned on 30.03.2022
26 | Hoondy 200 kv - EPIP GIS 200 kv staion (UG Cable) | S/C | 220 |  | 0 | 0 | 0 |  |  | MAR-19 | Commissioned
27 | Hosadurga - CN Halli line | D/C | 220 |  | 0 | 0 | 0 |  |  | DEC-18 | Included in CN Halli Work
28 | Jagalur (Hiremallanahole) - Kudligi line | D/C | 220 | 83 | 159 | 159 | 159 | 83 | JUL-19 | MAY-20 | Commissioned 05/20.
29 | Kolar - Malur at Somanahalli | D/C | 220 | 180 | 13 | 4 | 4 | 1.2 | MAR-18 | DEC-19 | Work shortclosed. For balance work :LOI issued to M/s Sagar Steel Pvt Ltd on 15.09.17. Cases pending in Court
30 | Kudligi (Badeladaku) line from existing 220 kV Itagi SS to the proposed Station at Kudligi | D/C | 220 | 65 | 118 | 118 | 118 | 65 | AUG-19 | JUN-24 | Commissioned 05/24.
31 | LILO from Shimoga - Mysore at Hassan (220 kV Re-orientation and shifting lines) | D/C | 220 | 35 | 68 | 65 | 64 | 22 |  | MAR-20 | As per decision of 132nd Board meeting pertaining to the subject work , M/s KSIIDC Ltd. Bengaluru has paid Rs.17.96 Crs towards the shifting of Line and hence the work now comes under the purview of deposit contribution (DCW) head.
32 | LILO line from 220kV Varahi-Kemar S/C line at Heggunje (Mabdarthi Line) | M/C | 220 | 2 | 9 | 9 | 9 | 2 |  |  | Commissioned on 28.03.2021
33 | LILO of 220 kV Allipura-Ragalapadu line at Somasamudra SS | D/C | 220 | 12 | 28 | 28 | 28 | 12 | AUG-24 | DEC-24 | Commissioned 11/24.
34 | LILO of 220kV Kudigi-Vajramatti DC line at proposed 220/110kV Bilagi S/S | D/C | 220 | 74 | 73 | 62 | 35 | 25.99 | OCT-24 |  | Some of the towers are coming under Krishna Back water area.
35 | LILO of 2nd circuit of 220kV Bidnal -Mahalinapur DC Line at Soundatti SS | D/C | 220 | 21 | 0 | 0 | 0 | 21 |  | AUG-24 | Commissioned 07/24.
36 | LILO of Gadag - Lingapur at Koppal | D/C | 220 | 1 | 2 | 2 | 2 | 1 |  | OCT-19 | Commissioned
37 | LILO of Hoody-Kolar at Hoskote | D/C | 220 | 27 | 55 | 35 | 31 | 0.35 | MAR-18 | MAR-20 | Work to be dropped
38 | LILO of Hoody - Nelamangala to proposed 220/66 kv Manyatha S/s | M/C | 220 |  | 0 | 0 | 0 |  |  |  | Commissioned
39 | LILO of HSR- NIMHANS to proposed at Koramangala | S/C | 220 | 5 | 0 | 0 | 0 |  | SEP-17 | OCT-19 | Cable charged on 20.05.19.
40 | LILO of Mylasandra - Malur to proposed 220/66 kV EXORA S/s | S/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | MAR-20 | Commissioned on 28.03.2022(4/4 sec Cable laying completed)
41 | LILO of Mylasandra to the 220kV Somanhalli-Malur | M/C | 220 |  | 0 | 0 | 0 |  | SEP-17 | SEP-19 | Proposal Dropped
42 | LILO of Mylsandra-Yeradanahalli at Keonics (Electronic City) | D/C | 220 | 7 | 7 | 7 | 7 | 7 | MAY-24 | OCT-24 | Commissioned 09/24.
43 | LILO of Shimoga - Mysore at Dandiganahally | D/C | 220 | 35 | 68 | 68 | 68 | 35 | JAN-18 | JAN-19 | Commissioned on 14.03.2022
44 | LILO of Somanahalli-hoody line at Keonics (Electronic City) | D/C | 220 | 14 | 0 | 0 | 0 | 14 | MAY-24 | DEC-24 | Commissioned 11/24.
45 | LILO of Thubinkere - Ramnagara to Maddur | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | MAR-20 | Approved in TCCM
46 | Mylasandra - Somanahalli line | S/C | 220 | 1 | 0 | 0 | 0 | 1 |  | DEC-19 | Commissioned on 12.02.2022
47 | Nagamangala-Tubinkere | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | MAR-20 | Proposal Dropped
48 | Nelamangala - Peenya S/s | M/C | 220 | [5 empty] | SEP-18 | MAR-19
49 | Nelmangala - Brindavan Alloys | D/C | 220 | 1 | 7 | 7 | 7 | 1 | SEP-17 | OCT-19 | commissioned
50 | Peenya - A Station UG Cable | S/C | 220 | 0 | 24 | 0 | 0 |  | SEP-18 | JAN-24 | 1/24 sec cable laying completed. Work under progress
51 | PGCIL Station at Beerennahalli (Hiriyour) to existing 220/66/11kV Hiriyour s/s | S/C | 220 | 15 | 0 | 0 | 0 | 15 |  | APR-22 | Commissioned 03/22.
52 | Shanthigrama - B4 line ( near Hedanahalli limits) | D/C | 220 | 16 | 34 | 34 | 32 | 12.42 | MAR-18 | DEC-24 | Contract terminated on 12.05.2016. DWA issued for balance portion of work on 29.07.2019. Row issues.
53 | Somanahalli - Malur I and II lines - Yarandanahally S/s Sommanahally-SingarpetSC line Corridor | M/C | 220 | 27 | 0 | 0 | 0 |  | SEP-18 | MAR-19 | Proposal Dropped
54 | Somanahalli- Subramanyapura (M/C M/V) | M/C | 220 |  | 0 | 0 | 0 |  | SEP-18 | MAR-19 | Proposal Dropped
55 | Somanahalli - T.K. Halli SC line to DC | D/C | 220 |  | 236 | 227 | 151 | 72.32 | SEP-17 | DEC-24 | Work under progress.
56 | Somananahalli Malur I & II lines - Jigani | D/C | 220 | 23 | 34 | 6 | 4 | 0 | MAR-18 | MAR-18 | Termination issued to agency on 22.03.2017. Jigani station commissioned on 04.03.2018
57 | Somasamudra - BTPS (Bellary Thermal Power plant) (Kudithini) | D/C | 220 | 41 | 64 | 64 | 60 | 34.4 | AUG-24 |  | Work under progress
58 | Srinivasapura from existing s/s -to the proposed Srinivasapura s/s | D/C | 220 | 48 | 99 | 99 | 99 | 48 | OCT-23 | NOV-23 | Commissioned 10/23.
59 | Tubinakere - Ramnagar (Kothipura) line | D/C | 220 | 142 | 290 | 290 | 290 | 142 | JUN-09 | MAY-20 | Commissioned on 07.04.2020
60 | Vajamangala - Kadakola | D/C | 220 | 40 | 83 | 83 | 83 | 14.46 | MAR-18 | DEC-24 | LOI issued on 18.04.2022 to PVR Constructions, Bangalore for balance work. Row issues
61 | Vajamangala -Kodakola and Vajamangala-Varun M/C lines | M/C | 220 | 9 | 23 | 23 | 23 | 10 |  | OCT-19 | Commissioned. Physically and financially closed
62 | Yelanhanka(KPTCL)- Yelanhanka(PG) | D/C | 220 | 6 | 0 | 0 | 0 | 11.6 |  | AUG-18 | Commissioned on 14.09.2018.
63 | Yelburga from the existing 220/110/11kV Kushtagi S/S- the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 68 | 68 | 59 | 1 | 0 | AUG-24 |  | Work under progress
64 | Yelburga from the existing 220/110/11kV Kushtagi S/S -to the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 57 | 113 | 97 | 84 | 24 | AUG-24 |  | Work under progress
KERALA STATE ELECTRICITY BOARD(KSEB)
1 | Kasaragod - Wayanad | D/C | 400 | 250 | 359 | 108 | 71 | 0 | JUN-25 | DEC-25 | Very low progress due to protests from public demanding very high compensation
2 | Kanhirode-Mylatty 220 kV DC line | D/C | 220 | 168 | 273 | 268 | 263 | 149.36 | JUN-24 | MAR-25 | Work in Progress.
3 | Kunnamkulam - Vengallur | D/C | 220 | 84 | 145 | 35 | 30 | 145 | FEB-24 | DEC-25 | Work in Progress.
4 | Mylatty-Vidyanagar 220kV DC line | D/C | 220 | 12 | 35 | 22 | 11 | 5.9 | DEC-24 | DEC-25 | Work in Progress.
5 | Pathanamthitta - Kakkad s/s | D/C | 220 | 114 | 197 | 177 | 168 | 82.59 | MAY-24 | JAN-25 | In the case of lines to Pathanamthitta SS, one stay order is prevailing at one location (EA05) against construction of tower. In the case of lines to kakkad S/s lines are to be drawn through land allotted by Forest Dept under 'Grow moreFoord Scheme'. Since the occupants don't have documents validating their possession compensation disbursement is not possible. Opposition from occupants leads to stoppage of works.
6 | Powerloom metta to Parambayi | M/C | 220 | 1 | 0 | 0 | 0 | 1 |  | JAN-25 | Commissioned 12/24.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD.(MSETCL)
1 | Jejuri - Hinjewadi - I and II | D/C | 400 | 207 | 277 | 204 | 187 | 69.54 |  |  | Pkg-I: ROW :dtd 03-06-16 : SDO Bhor- revised Lr. dt 15.06.16:SDO Haveli: 2 nos (loc 86,87). Agency went into Arbitration . Tender on Risk & cost is under process.
2 | JPGPL TPS Switchyard - Warora PS (JPGPL-TBCB) | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Not in STU Plan.
3 | LILO of Bhusawal-II to Aurangabad-I ckt-II at Thaptitanda | D/C | 400 | 176 | 273 | 270 | 248 | 135.3 |  | MAR-25 | Severe ROW issue, Police Protection required.
4 | LILO of one ckt Dhule - Sardar Sarovar at Balsane (PS) | D/C | 400 | 36 |  |  |  |  | MAR-20
5 | LILO of Talegaon -Kalwa at Vikroli (Intra State TBCB) | D/C | 400 | 24 | 0 | 0 | 0 | 24 |  |  | Commissioned 10/24. (Constructed by Adani in State TBCB.)
6 | LILO of two ckts Bhadravati - Chandrapur- I at Chandrapur -II | D/C | 400 | 5 |  |  |  |  | MAR-19
7 | LILO om Solapur ( PG) - Karad at Tembhurni | S/C | 400 | 20 |  |  |  |  | MAR-22
8 | LILO on Chandrapur I - Parli 3rd Ckt at Warora | D/C | 400 | 50 |  |  |  |  | MAR-22
9 | Shevgaon / Pathardi - Tapti Thanda | D/C | 400 | 120 | 198 | 198 | 198 | 144.9 | MAR-22 | AUG-22 | Commissioned on 28.07.2022.
10 | 220kV DC Kalmeshwar-Warud (PhaseI and II ) (from Kalmeshwar s/s to loc no 90) | D/C | 220 | 53 | 75 | 75 | 75 | 43.34 | DEC-23 | MAR-25 | Commissioned 03/24 (Partially Charged (Package -III Shifted to FY -2024-25). Balance phase III to be included in Target. Only stringing between 3 spans( 1Km) in forest balance, forest approval awaited. NBWL: Proposal approved by MoEF & CC subject to use of insulated conductors. Meeting held on 21.12.2024 with MoEFCC, Delhi, minutes awaited.
11 | 220kV D/C line from Vishwind- Bhenda | D/C | 220 | 86 | 141 | 140 | 139 | 64.19 | JUN-24 | MAR-25 | 1. Severe ROW in Saundala, Vaiju Babhulgaon & Lohsar village. 2. Police protection in Saundala availed but could not be utilized due to Local political interference, FIR lodged. 3. 3 towers collapsed on 30.07.2024 out of which 2 foundations re-casted. Rework is also creating ROW.
12 | 220 kV Koradi-II to Butibori-III DCMC line | D/C | 220 | 109 | 189 | 189 | 189 | 109 | JUN-24 | AUG-24 | Commissioned 07/24.
13 | 220 kV Kumbhargaon (Nanded)- Kurunda line (Pkg-B) | D/C | 220 | 55 | 107 | 107 | 107 | 38.04 | JUN-24 | FEB-25 | i) Work delayed due to delay in supply of Conductor and tower material by agency. ii) SDM order (loc 212) received on 04.12.2024. iii) Mango tree valuation (loc 212) awaited. Hearing done with SAO, Hingoli on 17.12.2024, he referred to Director (Horticulture), Pune. iv) After receipt of Order, stringing will be completed for span 208-214.
14 | 220KV Nagewadi- Bhokardhan line | D/C | 220 | 90 | 151 | 142 | 135 | 59.55 | JUN-24 | MAR-25 | 1) Severe ROW issues. Order under section 16 awaited from Collector Jalna for 3 locs. 2) Valuation awaited from concerned SDOs. 3) Supply of narrow base towers -6 nos awaited. Stringing work is in progress.
15 | 220kV Wani -Pandharkawada D/C line (Phase-II) Phase-I (65Ckm) Commissioned 05/23 | D/C | 220 | 51 | 0 | 0 | 0 | 51 |  | APR-24 | Commissioned 03/24.
16 | 2nd ckt Dodaicha - Shahada | S/C + D/C | 220 | 27 | 0 | 0 | 0 |  | MAR-18 |  | Tenderization under process.
17 | 2nd Ckt. Stringing of Gangapur - Valve at Jamde (GEC-I) | S/C on D/C | 220 | 13 | 0 | 0 | 0 |  | MAR-21
18 | 2nd Ckt. Stringing of Miraj - (Tilawani) Ichalkaranji | S/C + D/C | 220 | 35 | 0 | 0 | 0 | 21.92 | MAR-23 | FEB-21 | Balance line charged on 09.02.2021.
19 | Ambazari - Mankapur (UG) | M/C | 220 | 36 |  |  |  |  | MAR-23
20 | Aurangabad (PG) - Bidkin | D/C | 220 | 40 |  |  |  |  | MAR-22
21 | Babhaleshwar - Kopargaon LILO Point | M/C | 220 | 36 | 118 | 90 | 2 | 0 | MAR-18 |  | ROW at 13 nos loc. Railway crossings involved.
22 | Babhaleshwar-Kudus DC line | D/C | 220 | 457 | 719 | 690 | 675 | 308.78 | DEC-24 | MAR-25 | i) Severe RoW issues at Ale village for 22 locations. Ii) And fresh ROW are being faced due to delay in providing police protection and help from revenue Authorities.Police Protection received on 09.09.24 but work could not started due to strong oppose from cultivators and intervention from leaders. Negotiation with cultivators is under progress. Meeting was scheduled at Honble Collector Pune on 02.01.2025, which is rescheduled on 07.01.2024.
23 | Balsane (Shivajinagar) (T Conductor) - Shivanjinagar | D/C | 220 | 36 |  |  |  |  | MAR-20
24 | Boisar (PG)-Wada | S/C on D/C | 220 | 50 | 211 | 173 | 165 | 28.05 | MAR-22 | MAR-19 | The work stopped due to 1) Severe RoW2) Forest issue.The existing contract closure proposal is approved by C.O.The balance work shall be executed by placing new contract.
25 | Butibori - III - Addl. Butibori | D/C | 220 | 20 |  |  |  |  | MAR-23
26 | Chinchwad - II for reorientation of existing line at Chinchwad - II | D/C | 220 | 12 | 4 | 4 | 2 | 0 | DEC-19 | MAR-20 | Work in progress.
27 | Colourchem - Kolshet | D/C | 220 | 8 |  |  |  |  | MAR-21
28 | Deoli (PGCIL) upto LILO point for 220 kV Yavatmal ss | D/C | 220 | 100 | 173 | 173 | 173 | 99 | OCT-22 | OCT-23 | Line commissioned on 07.10.2023.
29 | Dondaicha - Nandurbar | D/C | 220 | 80 |  |  |  |  | MAR-23
30 | Indapur MIDC (Loni Deokar) - Tembhurni | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-18 |  | Scheme under revision.
31 | Jerur- Karjat line | D/C | 220 | 101 | 163 | 163 | 163 | 101 | MAY-24 | NOV-24 | Commissioned 10/24.
32 | Kalmeshwar-Warud line (Phase III) | D/C | 220 | 45 | 75 | 75 | 75 | 43.34 | JUN-24 | JAN-25 | Only stringing between 3 spans( 1Km) in forest is balance. Target subject to forest approval. NBWL proposal was taken in meeting dtd 31-07-2024, MoM received, compliances are submitted on 26.09.2024.
33 | Kandalgaon - Dasturi SCDC line | S/C on D/C | 220 | 75 | 236 | 92 | 0 | 0 |  | MAR-19 | Severe ROW problem. Work stopped since June-2016. Short closure is approved. Balance work is to be carried out on Risk & cost basis.
34 | Khapakheda - Uppalwadi | D/C | 220 | 7 |  |  |  |  | MAR-19
35 | Kopargaon tap - Babhaleshwar | M/C | 220 | 144 | 118 | 90 | 2 | 0 |  | DEC-20 | ROW cases filed, order awaited [13].Railway crossing loc no 12-13 and 55-56. Proposal submitted to railway authority. New LOA issued to M/s Precious Infra services on Risk & Cost.
36 | Koradi II - Butibori | D/C on M/C | 220 | 106 | 189 | 189 | 189 | 109.21 | MAR-11 | JUL-24 | Commissioned on 04.07.2024
37 | Lamboti - Karkamb | D/C | 220 | 60 |  |  |  |  | MAR-20
38 | LILO of 220 kV Jalna - Chikhali line at 220 kV Nagewadi S/s | D/C | 220 | 3 | 0 | 0 | 0 | 3 |  | JAN-25 | Commissioned 12/24.
39 | LILO of 220kV Kalwa- Bapgaon line at Mankoli s/s | D/C | 220 | 1 | 4 | 4 | 3 | 0.48 |  | MAR-25 | 1) Substation work delayed due to modification in technical specifications of 220kV GIS modules and cable size. 2)Line work completed except LILO point. Outage proposed on 24th, 25th & 26th January-2025.
40 | LILO of 220 kV Shendra- Chitepimpalgaon line at 220 kV Shendra DMIC GIS s/s (UG cable) | D/C | 220 | 12 |  |  |  | 12 | JUN-24 | OCT-24 | Commissioned 09/24.
41 | LILO of Aaret (RINFRAT) - Borivalli (MSETCL) (Proposed cable ) at Goregaon Filmcity - 5 (UG Cable) | D/C | 220 | 5 |  |  |  |  | MAR-23
42 | LILO of Aarey (RINFRAT) - Borivalli (RINFRAT) at Goregaon Filmcity - 5 (UG Cable) | D/C | 220 | 5 |  |  |  |  | MAR-23
43 | LILO of Dhule - Dondaicha at 400 kV Balsane PS (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Not yet tenderised.
44 | LILO of one Ckt. Ahmednagar Bhose at Supa | D/C | 220 | 40 | 0 | 0 | 0 |  | MAR-22
45 | LILO of one Ckt. Aurangabad (PG) - Shendra at Shendra (AURIC) (DMIC Project) | D/C | 220 | 16 | 0 | 0 | 0 | 12 | MAR-19 | SEP-24 | Commissioned on 11.09.2024
46 | LILO of one Ckt. borivali - Boisar at Boisar (PG) | D/C | 220 | 5 |  |  |  |  | MAR-20
47 | LILO of one Ckt. of 220kV Kolshet-Wada line and Padghe-Wada line on M/C towers at 400 kV Kudus S/S | LILO | 220 | 32 | 50 | 29 | 27 | 14.88 | DEC-23 | MAR-25 | 1) All works except forest area completed. 2) PCCF, Wild life permission received on 08.10.2024. 3) APCCF Nagpur forwarded proposal to IRO Nagpur on 11.11.2024. As all works except forest area completed, work can be scheduled on receipt of forest approval.
48 | LILO of one Ckt. Padegaon - Paithan line at Chitegaon | D/C | 220 | 5 |  |  |  |  | MAR-19
49 | LILO of Tarapur-Borivli at Boisar II | D/C | 220 | 16 | 15 | 15 | 12 | 11 | MAR-07 |  | The work is stopped due to1) Severe ROW. Forest of 0.49 Ha involved forest Clearance proposal is pending at DCF, Dahanu.
50 | LILO on 220kV Bhigwan Kurkumb line at 400kV Karjat s/s | D/C | 220 | 34 | 52 | 52 | 52 | 34 | MAY-24 | SEP-24 | Commissioned 08/24.
51 | LILO on 220kV Mhaisal - Jath at 400kV Alkud | LILO | 220 | 45 | 78 | 76 | 67 | 6.23 | DEC-24 | MAR-25 | Work in progress.
52 | LILO on 220kV Tarapur-Borivali and Boisar- Ghodbandar line at 400kV Kudus S/S | LILO | 220 | 118 | 120 | 112 | 110 | 100.6 | NOV-24 | MAR-25 | Severe RoW. Forest working permission awaited from CCF, Thane. 1) Stage -1 approval received on 08.07.2024. 2) Stage II compliances forwarded by GoM to MoEF & CC Delhi on 30.09.2024. Queries raised on 11.12.2024. Compliance under scrutiny. 3) FRA certificate received on 12.12.2024.
53 | LILO on Babhaleshwar - Nashik at Sinnar | D/C | 220 | 20 |  |  |  |  | MAR-20
54 | LILO on Boisar (M) - Versova at Boisar | S/C + D/C | 220 | 1 |  |  |  |  | MAR-20
55 | LILO on Boisar - Kopri at Chikhal Dongri | D/C | 220 | 4 |  |  |  |  | MAR-19
56 | LILO on Boisar - Nalasopara at Palghar | D/C | 220 | 20 | 4 | 4 | 4 | 4.8 | MAR-19 | MAR-23 | Line commissioned on 31.03.2023.
57 | LILO on Boisar - Varsova at Virar | D/C | 220 | 4 | 0 | 0 | 0 |  | MAR-20 |  | Not in STU Plan.
58 | LILO on Boisar - Vasai Loc No. A | D/C | 220 | 7 |  |  |  |  | MAR-20
59 | LILO on both ckts. of Uran-Kharghar Ulwe Node | D/C | 220 | 18 | 0 | 0 | 0 |  | DEC-22 | JAN-23 | Ist ckt charged on 03.09.2021 & second ckt charged on 24-09-2021.
60 | LILO on Kandalgaon -Lanand at Kesurdi | S/C | 220 | 10 |  |  |  |  | MAR-22
61 | LILO on Kolshet-Wada and Padghe-Wada line at 400kV Kudus S/s | M/C | 220 | 36 | 50 | 29 | 27 | 14.8 | DEC-24 | MAR-25 | 1) All works except forest area completed. 2) PCCF, Wild life permission received on 08.10.2024. 3) APCCF Nagpur forwarded proposal to IRO Nagpur on 11.11.2024. As all works except forest area completed, work can be scheduled on receipt of forest approval.
62 | LILO on Kolshet-Wada and Padghe-Wada line at 400kV Kudus S/s | M/C | 220 | 32 | 50 | 29 | 27 | 14.88 |  | MAR-25 | 1) All works except forest area completed. 2) PCCF, Wild life permission received on 08.10.2024. 3) APCCF Nagpur forwarded proposal to IRO Nagpur on 11.11.2024. As all works except forest area completed, work can be scheduled on receipt of forest approval.
63 | LILO on Loc No. A (MC Towers ) - Kopri (Virar E) | M/C | 220 | 5 |  |  |  |  | MAR-20
64 | LILO on narrow base towers Boisar - Varsova Loc No. A | 2xD/C | 220 | 2 |  |  |  |  | MAR-20
65 | LILO on one Ckt. of Bhusawal (Khadka) - Chalisgaon at Jamner | D/C | 220 | 1 | 2 | 2 | 2 | 0.36 | MAR-19 | APR-19 | Line commissioned on 25-03-2019.
66 | LILO on one Ckt. of Eklahare - Navsari at Girnare | D/C | 220 | 10 |  |  |  |  | MAR-22
67 | LILO on Padghe - Wada at Kudus | D/C | 220 | 10 | 50 | 29 | 27 | 14.88 | MAR-18 | MAR-25 | 1) All works except forest area completed. 2) PCCF, Wild life permission received on 08.10.2024. 3) APCCF Nagpur forwarded proposal to IRO Nagpur on 11.11.2024. As all works except forest area completed, work can be scheduled on receipt of forest approval.
68 | LILO on Padghe-wada line at Loc.no. 98 at Abitghar s/s (NBDC) line | D/C | 220 | 17 | 31 | 2 | 0 | 0 | MAR-23 | MAR-25 | This line comes under Eco- sensitive zone of forest. therefore, work will be restarted after forest approval. Forest status: (12.7435 Ha) : APCCF Nagpur raised queries on compliance report Dtd. 11.10.2024 and compliance submitted by MSETCL to DCF Jawhar Dtd. 15.10.2024.
69 | LILO on two ckts Boisar (M) - Borivalli at Kudus | D/C on M/C | 220 | 100 | 120 | 112 | 110 | 100.6 | MAR-19 | MAR-25 | Severe RoW. Forest working permission awaited from CCF, Thane. 1) Stage -1 approval received on 08.07.2024. 2) Stage II compliances forwarded by GoM to MoEF & CC Delhi on 30.09.2024. Queries raised on 11.12.2024. Compliance under scrutiny. 3) FRA certificate received on 12.12.2024.
70 | LILO on two ckts Boisar - borivalli at Boisar | M/C | 220 | 1 | 7 | 7 | 7 | 3.6 | MAR-20 | JUL-20 | Line commissioned on 16/07/2020.
71 | LILO on Vita - Miraj at Kupwad s/s | S/C | 220 | 1 |  |  |  |  | MAR-22
72 | Mangaon CCPP(Vile)- Bhagad | D/C | 220 | 4 | 0 | 0 | 0 |  |  |  | commissioned 03/16
73 | Nagothane - Wadkhal | D/C | 220 | 30 | 104 | 56 | 44 | 52 |  |  | Work was stopped by agency due to severe ROW problem on 18/05/2008. Later the line is charged on 11/03/2016 by JSW under ORC using the corridor of existing 220kV DC IPCL-Wadkhal line from loc no 9.
74 | Raymonds - Girnare | D/C | 220 | 30 |  |  |  |  | MAR-22
75 | Umred S/stn to Nagbhid s/s (Part-II) | D/C | 220 | 49 | 94 | 90 | 90 | 31.97 | NOV-24 | MAR-25 | i) Last 4 locations in forest balance, Forest approval awaited. ii) FCA: Compliance report to queries submitted by APCCF to GoM on 05.12.2024. iii) NBWL: Proposal approved by MoEF & CC on 21.10.2024 subject to use of insulated conductors. Meeting is scheduled on 21.12.2024 with MoEFCC, Delhi.
76 | Uppalwadi - Mankapur | M/C | 220 | 32 |  |  |  | 0 |  |  | Scope revised O/H - 7.5 Km U/ G - 2.5 Km To be considered in Ph. III, if necessary as per BR 112/12 .
77 | Uppalwadi - New Pardi | M/C | 220 | 54 | 0 | 0 | 0 | 0
78 | Uppalwadi-Pardi UG Cable | D/C | 220 | 26 | 0 | 0 | 0 | 24.21 | JUN-24 | FEB-25 | Involvement of 4 bridges & HDD (Horizontal Directional Drilling) work for which permission from Nagpur Municipal Corporation and Railways received late. HDD work at Railway crossing is in progress.
79 | Vairag - Paranda | S/C + D/C | 220 | 40 | 0 | 0 | 0 |  | MAR-20 |  | Not in STU Plan.
80 | Vashi - Pawane | D/C | 220 | 3 |  |  |  |  | MAR-22
81 | Wardha (PGCIL) - Ghatodi | D/C | 220 | 322 | 551 | 461 | 346 | 99 |  |  | For balance works, revised BR sanctioned on 22.07.2024.
82 | Yavatmal Tap - Ghatodi Line | D/C | 220 | 25 |  |  |  |  | MAR-21
83 | 2nd Ckt. Stringing of Aundh - Dahiwadi line (GEC-I) | S/C + D/C | 132 | 0 | 2 | 2 | 1 | 28.3 |  | OCT-20 | Line commissioned on 30/09/2020.
84 | 2nd Ckt. Stringing of Georai - Beed (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 | 31.8 |  | NOV-19 | Line commissioned on 28/11/2019.
85 | 2nd Ckt. Stringing of Kale (T) - Warna line (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line under GEC-I cancelled. MBR sanctioned for MSETCL scheme.
86 | 2nd Ckt stringing of Kharda - Bhairavnath (GEC-II) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Space is not available at 132kV Kharda S/s,and alternate sources are available at Kharda S/s, Hence 2nd ckt stringing is not required.
87 | 2nd Ckt. Stringing of Manmad - Yeola line (GEC-I) | S/C + D/C | 132 | 0 | 1 | 1 | 1 | 28.78 |  | JUL-19 | Line commissioned on 03/06/2019.
88 | 2nd Ckt. Stringing of Nandurbar - Visarwadi line (GEC-I) | D/C | 132 | 0 | 3 | 3 | 3 | 43.75 |  | MAR-20 | Line commissioned on 08/03/2020.
89 | 2nd Ckt. Stringing of Shevgaon - Ghodegaon line (GEC-I) | S/C + D/C | 132 | 0 | 2 | 2 | 2 | 39.95 |  | MAR-20 | Line commissioned on 07/03/2020.
90 | 2nd Ckt. Stringing of Shevgaon - Pathardi line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 | 22.6 |  | DEC-19 | Line commissioned on 16/11/2019.
91 | 2nd Ckt. Stringing Shevgaon - Benda line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 | 25.68 |  | MAR-19 | Line commissioned on 18.03.2019.
92 | Ahmednagar - Ahmednagar MIDC line (GEC-I) | D/C | 132 | 0 | 25 | 25 | 11 | 1.93 |  | DEC-23 | Instead of Ahmednagar- Ahmednagar(MIDC) line new 132 kV Ahmednagar - Nimblak - Ahmednagar MIDC line- 9.3 km is proposed and work in progress.
93 | Ahmednagar - Supa line (GEC-I) | D/C | 132 | 0 | 65 | 65 | 65 | 38.78 |  | MAR-22 | Line charged on 07.03.2022.
94 | Babhaleshwar - Rahuri at Ahmendnagar MIDC line (GEC-I) | D/C | 132 | 0 | 186 | 181 | 90 | 52.32 |  | DEC-24 | Continuous Outage required on existing 132kV Babhaleshwar Rahuri line for inline tower erection and stringing work. No gang available at site.
95 | Kadegon - Kirloskawadi line (GEC-I) | S/C + D/C | 132 | 0 | 56 | 56 | 56 | 28.64 |  | DEC-20 | Line commissioned on 19.10.20
96 | Kavthemahankal - Jath line (GEC-I) | D/C | 132 | 0 | 108 | 108 | 108 | 63.84 |  | JUN-21 | Line charged on 28.05.2021.
97 | Kavthemahankal - Savlaj line (GEC-I) | S/C + D/C | 132 | 0 | 96 | 96 | 96 | 25 |  | JUN-19 | Commissioned on 31.03.2019.
98 | Kharda - Ashta (D/C partly on M/C Tower (GEC-I) | D/C | 132 | 0 | 168 | 168 | 168 | 91.2 |  | SEP-23 | Line commissioned on 07.09.2023.
99 | LILO of Ashti - Kharda at Patoda (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0
100 | LILO of Lonand - Phaltan line at Phaltan MIDC GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line cancelled.
101 | LILO of Mul Ashti at - Chamorashi | D/C on M/C | 132 | 30 | 56 | 56 | 56 | 13.99 | MAR-20 | DEC-19 | Line commissioned on dtd. 30.12.2019
102 | LILO of Myani - Dighnchi line at Mhaswad (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line cancelled.
103 | LILO of Padegaon -s Sillod at Phulambri line (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | The lines are not required as revised necessity is verified by STU.
104 | LILO of Sawangi - Pishor at Phulambri line (GEC-I) | N/A | 132 | 0 | 0 | 0 | 0 |  |  |  | The line is not required as revised necessity is verified by STU.
105 | LILO on Kalwan - Dindori at Lakhampur | D/C | 132 | 20 |  |  |  |  | MAR-23
106 | LILO on Markal - Kharadi at Eon Kharadi (Using U/G Cable) | D/C | 132 | 4 |  |  |  |  | MAR-19
107 | LILO on Ozar - Kalwan line at Pimpalgaon (GEC-I) | S/C | 132 | 0 | 24 | 24 | 24 | 10.4 |  | JUN-20 | Line LILO on Ozar - Chandwad line at Pimpalgaon (GEC-I) commissioned on 05/05/2020.
108 | Patoda - Raimoha (GEC-II) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Yet to be tenderized.
109 | Sawantwadi - Kudal line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | The line is not required as revised necessity is verified by STU.
110 | Vish Wind - Bhenda (GEC-I) | D/C | 132 | 0 | 141 | 140 | 139 | 64.19 | MAR-21 | MAR-25 | 1. Severe ROW in Saundala, Vaiju Babhulgaon & Lohsar village. 2. Police protection in Saundala availed but could not be utilized due to Local political interference, FIR lodged. 3. 3 towers collapsed on 30.07.2024 out of which 2 foundations re-casted. Rework is also creating ROW.
111 | LILO on Padghe - Vasai | UG Cable | 110 | 42 |  |  |  |  | MAR-19
MEGHALAYA ENERGY CORP. LTD.(MeECL)
1 | 2nd Ckts. of 132 kV Nagalbibra-Agia line | D/C | 132 | 92 | 316 | 316 | 316 | 92.15 |  | FEB-18 | 1.Date of award of contract is 20.01.2014. 2.Schedule date of completion was 30.01.2016. 3.Actual date of completion was 20.01.2018. 4. The line was commissioned on 25.11.2021 5. Reason for delay: a) ROW issues for compensation of crop damage b) Ground clearance in some sections c) Bay construction at Agia S/s was delayed by AEGCL d) Delay in obtaining clearance from PTCC
2 | Killing (Byrnihat)-EPIP-I | M/C | 132 | 17 | 19 | 19 | 19 | 21.75 |  | MAY-17 | 1. Date of award of contract is 18.03.2011. 2. Schedule date of completion was 18.03.2012. 3. The line was completed on 11.02.2016 and commissioned on 12.05.2017. 4. Delay was due to RoW issue, all of which have been resolved and also due to delay in commissioning of SAS at 400/220/132 kV Killing sub-station.
3 | LILO of Agia - Nangal at Mendipathar | D/C | 132 | 5 | 9 | 9 | 9 | 4.57 |  | DEC-15 | 1. Date of award of contract is 11.02.2011. 2. Schedule date of completion was 11.08.2011. 3. Actual date of completion was 28.01.2014. The line was kept charged w.e.f 28.01.2014, but was commissioned with its connected 132/33 kV sub-station at Mendipathar on 22.12.2015. 4. Delay in completion of the line was due to RoW problem. 5. No issue of forest clearance.
4 | LILO of Mawlai - Cherra at Mawngap. | D/C | 132 | 10 | 16 | 15 | 15 | 5 |  | DEC-19 | 1. Date of award of contract is 19.01.2011. 2. Schedule date of completion was 19.07.2011. 3. Anticipated date of completion is March 2020. 4. Delay is due to RoW issues. Work held up due to ROW problem. The PHED, GOMe has complained and filed an FIR against Loc No. 3 to 8. 5. The matter has been taken up with the District Administration for solving the RoW issues. 6. Overall status is 90% completed.
5 | LILO of NEHU - Khliehriat line at Mustem | D/C | 132 | 1 | 4 | 4 | 4 | 1.1 |  | NOV-15 | 1. Date of award of contract is 12.02.2015. 2. Schedule date of completion was 12.05.2015. 3. The LILO was completed and test charged in 7th August, 2015 but was commissioned along with the 132/33 kV Mustem sub-station on 20.11.2015. 4. Delay in completion of the line was due to sub-station was not ready. 5. No issue of forest clearance or RoW issues.
6 | LILO of NEIGRIHMS - Khliehriat at Lad Nongkrem | D/C | 132 | 6 | 7 | 7 | 7 | 3.2 |  | DEC-19 | 1. Date of award of contract is 26.02.2016. 2. Schedule date of completion was 26.02.2017. 3. Anticipated date of completion is December 2019. 4. Delay is due to delay in supply of materials for line by the vendor. 5. No issues on forest clearance and RoW issues. Commissioned on 9th December, 2019
7 | LILO of Rongkhon - Ampati at Praharinagar | D/C | 132 | 20 | 30 | 0 | 0 | 0 |  | MAR-20 | Survey works for 132 kV LILO is completed. Materials procurement is under process. Tendering for the LILO is under process.
8 | Mawngap - Sumer | D/C | 132 | 66 | 102 | 102 | 102 | 66.15 |  | DEC-11 | 1. Date of award of contract is 20.07.2009. 2. Schedule date of completion was 20.07.2010. 3. Actual date of completion was 21.12.2011. 4. No issue of forest clearance, and the RoW issues that were there were resolved. 5. The line was commissioned on 21.12.2011.
9 | Nangalbibra - Agia | S/C | 132 | 92 | 316 | 316 | 316 | 92.15 |  | AUG-13 | 1. Date of award of contract is 14.12.2007. 2. Schedule date of completion was 14.12.2009. 3. Actual date of completion was 24.05.2013 but the line was commissioned on 06.08.2013. 4. Delay in completion was due to RoW issues and due to fund flow constraints. 5. The line was commissioned on 06.08.2013.
10 | New Umtru HEP - Norbong (EPIP-II) | D/C | 132 | 1.21 | 7 | 7 | 7 | 1.21 |  | MAR-17 | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion was 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm, 132 kV S/C line - 1.07 ckm 7. The total expenditure incurred is Rs.471.87 Lakhs and is inclusive of 132 kV New Umtru - Umtru HEP line.
11 | New Umtru - Umtru HEP | S/C | 132 | 0.5 | 1 | 1 | 1 | 0.5 |  | MAR-17 | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion work 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm and 132 kV S/C line - 0.36 ckm 7. The total expenditure incurred is Rs. 448.76 Lakhs and is inclusive of the cost of 132 kV New Umtru HEP - Norbong -EPIP-II line.
12 | Rongkhon S/S - Ampati | D/C | 132 | 33 | 102 | 102 | 102 | 32.14 |  | DEC-18 | 1. Date of award of contract is 29.07.2011. 2. Schedule date of completion was 29.07.2012. 3. Anticipated date of completion is December, 2018. 4. Delay is due to heavy flood damage in Garo Hills in September 2014, and also due to fund flow constraint and RoW issues. 5. No issues on forest clearance and no court cases. 6. The line has been charged on 20th November'2018.
M. P. POWER GENERATING CORPORATION LIMITED(MPPGCL)
1 | Sailana - Ratlam | D/C | 220
M.P. POWER TRANSMISSION CORPORATION LIMITED(MPPTCL)
1 | Ashta - Ujjian (GEC-I) | DCDS | 400 | 179 | 258 | 258 | 258 | 179.91 | JUN-21 | JUN-22 | Line charged on dated 16.06.2022
2 | Dada Dhuniwale TPP - Moondi Pooling Point | D/C | 400 | 80
3 | DBTPS - Vindhyachal PS (Quad) line | D/C | 400 | 0
4 | Handia - Ashta(2nd stage) | D/C | 400 | 180
5 | LILO of both circuit of Itarsi (PGCIL) - Bhopal 400kV line (on Twin Moose) at Mandideep 400kV S/s | D/C | 400 | 20 | 7 | 7 | 0 | 0 |  |  | TBCB work
6 | LILO of Indira Sagar - Satpura at Handia | D/C | 400 | 40
7 | LILO of Indore - Itarsi at Handia | D/C | 400 | 40
8 | LILO of one circuit of 400KV Damoh(PGCIL) - Bhopal line at Sagar 400KV S/S | D/C | 400 | 38 | 58 | 56 | 24 | 0 | MAR-25 | MAR-25 | work under progress.
9 | LILO of one ckt of Vindhychal - Satna at Nigrie | D/C | 400
10 | Moondi Pooling Point - Handia | D/C | 400 | 240
11 | Pithampur - Moondi Pooling Point | D/C | 400 | 280
12 | REVA TPP - Moondi Pooling Point | D/C | 400 | 70
13 | Shri Singaji TPP - Moondi Pooling Point | D/C | 400 | 40
14 | Ashta - Shajapur | D/C | 220 | 95 | 0 | 0 | 0 |  |  |  | In previously, line already charged on 28.02.2015
15 | Badod - Nipaniya line PS | D/C | 220 | 8.813 | 0 | 0 | 0 |  |  | MAR-19
16 | Badod - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry . Already reported line charged on 28.12.2020
17 | Badwar PS - PGCIL S/s | D/C | 220 | 4 | 4 | 4 | 4 | 2.26 |  | MAR-19 | CKT -I Charged on 28.03.2019 Ckt-II charged on 4.07.2019
18 | DCDS Barsitadesh PS - PGCIL S/s | D/C | 220 | 2 | 7 | 7 | 7 | 2 |  | DEC-18 | Ckt. - I charged on 17.06.2018 & 2nd ckt charged on 23.07.2018
19 | DCDS Ramnagar pahad PS - PGCIL S/s | D/C | 220 | 5 | 13 | 13 | 13 | 5.14 |  | DEC-18 | Line work completed. Ckt-I charged on 22.07.2018 & 2nd ckt charged on 10.10.2018
20 | Katni - Damoh | D/C | 220 | 220
21 | LILO of both circuits of Chhegaon - Nimrani 220kV line at Khargone 220kV S/s | D/C | 220 | 60 | 48 | 0 | 0 | 0 |  |  | TBCB work
22 | LILO of both circuits of Hoshangabad - Mandideep - Adampur 220kV line at Mandideep 400kV S/s | D/C | 220 | 40 | 6 | 0 | 0 | 0 | JAN-25 |  | TBCB work
23 | LILO of both circuits of Satna-Chhatarpur 220kV line at Ajaygarh (TBCB) | D/C | 220 | 14 | 0 | 0 | 0 | 14 | DEC-24 | JUL-24 | Commissioned 06/24.
24 | LILO of both circuits of Satpura-Itarsi-Handiya 220kV line at Bisonikala 220 kV S/s | D/C | 220 | 20 | 15 | 0 | 0 |  | JAN-25 |  | TBCB work
25 | LILO of both circuits of Sidhi - Hindalco 220 kV line at Bargawan (220 kV) S/s (TBCB)(late reported commissioned in Nov-2024) | D/C | 220 | 8 | 21 | 21 | 21 | 8 | DEC-24 | JAN-25 | Commissioned 12/24.
26 | LILO of both ckt Indore - Pithampur at Indore | D/C | 220 | 8
27 | LILO of both ckt of Ratlam - Badnagar at Badnawar | D/C | 220 | 40 | 0 | 0 | 0 |  |  |  | double entry. In previously, already reported line charged on 11.11.2019
28 | LILO of Handia - Barwaha at Handia | D/C | 220 | 40
29 | LILO of Indore-II - Ashta at Shankargarh | D/C | 220 | 20
30 | LILO of one circuit of Satpura TPS-Itarsi 220 kV line at Shahpur 220 kV S/s | D/C | 220 | 10 | 23 | 0 | 0 | 0 | JAN-25 |  | TBCB work
31 | LILO of one ckt of Bansagar (Tons) - Satna at Sirmour | D/C | 220 | 2 | 0 | 0 | 0 |  |  |  | LILO of 220kv Rewa-Tons line at 220Kv S/s Sirmour charged on 12.10.2015.
32 | LILO of one ckt of Bina - Gwalior at Datia | D/C | 220 | 10 | 0 | 0 | 0 | 0.18 |  |  | line charged on 29.03.2022.
33 | LILO of one ckt of Bina - Sagar at Bina | D/C | 220 | 10
34 | LILO of one ckt of Indore - Barwaha at Simrol | D/C | 220 | 13
35 | LILO of one ckt of Pithampur - Rajgarh (PGCIL) at Dhar | D/C | 220 | 4 | 0 | 0 | 0 |  |  |  | Line already charged on 17.10.2015
36 | LILO of second ckt of Auraiya - Malanpur at Mehgaon | D/C | 220 | 6
37 | LILO of second ckt of Damoh - Tikamgarh at Damoh | D/C | 220 | 10
38 | Maheshwar (HEP) - Rajgarh (Dhar) | D/C | 220 | 230
39 | Morena - Malapur | D/C | 220 | 80 | 0 | 0 | 0 |  |  |  | In previously line charged already. Line 2x29.765 Ckm charged on 16.02.2017.
40 | Morena SP - Morena s/s (ISTS) line (GEC-II) | D/C | 220 | 0
41 | Pithampur - Gandhinagar | D/C | 220 | 60
42 | Rajgarh - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry . In previously , reported already line charged on 24.06.2021.
43 | Sagar - Begamganj 220 kV line (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | D/C | 220 | 125 | 0 | 0 | 0 | 125 | DEC-24 | AUG-24 | Commissioned 04/24 (Late Reported).
44 | Ujjain - Dewas | D/C | 220 | 90
45 | Ujjain - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry. In previously reported in June'2021 already. 2x79.763 CKM charged on 17.06.2021 (2nd ckt) & 21.06.2021 (1st ckt)
46 | 2nd Circuiting of Mahidpur - Zarda (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 | 23.1 |  |  | Line Charged on 31.03.2019
47 | Kanwan (220) - Kanwan (132) (GEC-I) | D/C | 132 | 26 | 42 | 42 | 42 | 29.63 |  | MAR-19 | 2x13.115 + 3.4 Kms (second circuit) line charged on 30.03.2019
48 | Kanwan (220) - Teesgaon (GEC-I) | D/C | 132 | 24 | 44 | 44 | 44 | 24.65 |  | MAR-19 | Line Charged on 26.03.2019
49 | Sendhwa (220) - Sendhwa (132) (GEC-I) | D/C | 132 | 12 | 15 | 15 | 15 | 9.61 |  | MAR-19 | 1x2.538 + 7.071 Km (second Circuit) Line charged on 29.03.2019
ORISSA POWER TRANSMISSION CORPORATION LTD.(OPTCL)
1 | Cuttack (OPTCL) - Pratapsasan | D/C | 220 | 96 | 177 | 177 | 174 | 83.4 |  | DEC-24 | Total location shall be corrected as 177 nos.
2 | Kaonjhar (PG) - Turumunga S/s | D/C | 220 | 35 | 66 | 57 | 51 | 0 |  | MAR-25 | Due to forest issue 220kV line could not be completed. However, The 220kV GSS is charged from 132kV side. One 160 MVA, 220/132kV and 1 no. 220/33kV Power Transformer was back charged on 22.07.24. This may be taken as achievement.
3 | Katapalli-Kiakata | D/C | 220 | 250 | 447 | 348 | 323 | 82.4 | JAN-20 | JUN-25 | The no. of Towers may be revised to 447nos.
4 | Kesinga - Baliguda | D/C | 220 | 200 | 388 | 326 | 299 |  | JUN-17 | JUN-25 | Delayed due to forest clearance issue. The total locations may be revised to 388 due to site requirement.
5 | Kesinga - Baliguda GSS | D/C | 220 | 202 |  |  |  |  | MAR-25
6 | LILO of 220 KV Balimela Jayanagar Circuit III at 220/33 KV GSS Govindpali | D/C | 220 | 2 | 0 | 0 | 0 | 2 |  | JUN-24 | Commissioned 05/24.
7 | LILO of 220 kV line New Duburi - Paradeep Circuit I at 220/33 KV GSS Balichandrapur Palei | D/C | 220 | 2 | 0 | 0 | 0 | 2 |  | JUN-24 | Commissioned 05/24.
8 | LILO of 220 kV Nuapada Pratapsasan Line at Balianta GSS | D/C | 220 | 20 | 48 | 47 | 44 | 14 | JUN-24 | MAR-25
9 | LILO of 220 KV TTPS -Joda DC Line at 220/33 KV GIS Keonjhar (Ranki) | D/C | 220 | 27 | 0 | 0 | 0 |  | JUN-24 |  | Repeat may be deleted
10 | LILO of Balimela-Malkangiri line at Govindpalli | D/C | 220 | 80 | 146 | 146 | 146 | 21.37 |  | JUN-25 | The S/s charged through "T"connection. The line is delayed due Forest clearance issue.
11 | LILO of Bhanjanagar-Meramundali line at Daspalla | D/C | 220 | 59 | 113 | 108 | 99 | 45 | JUN-24 | MAR-25 | Forest issue
12 | LILO of Joda -TTPS at Keonjhar (OPTCL) | D/C | 220 | 27 | 52 | 45 | 33 | 0 | NOV-23 | DEC-24 | The line length may be corrected to 26.8 Ckm. Forest clearance issue
13 | LILO of one ckt of Rengali - Tarkera at Deogarh | S/C | 220 | 24 |  |  |  |  | MAR-21
14 | PGCIL Keonjhar - Turumunga GS | D/C | 220 | 34 | 0 | 0 | 0 |  | JUN-24 |  | Repeat may be deleted
15 | LILO of Aska - Bhanjanagar at Aska line | S/C | 132 | 12 | 0 | 0 | 0 |  | MAR-18 |  | May be deleted as it is 132kV voltge level
POWER AND ELECTRICITY DEPARTMENT, MIZORAM(PEDMIZO)
1 | 2nd evacuation line : Tuirial HEP to Sihhmui via Bawktlang | S/C | 132 | 105 | [6 empty] | Concept Note is being submitted
2 | Bairabi to W.Phaileng via Mamit | D/C | 132 | 74 | 0 | 0 | 0 |  |  |  | Sanction received from NEC. Preliminary survey started
3 | Bawktlang (Kolasib) S/S - Sihhmui S/S | D/C | 132 | 47 | 135 | 135 | 135 | 46.67 |  | DEC-16 | The 132KV Sihhmui substation was constructed by P&E, Govt. of Manipur and completed on 31.03.2016. Line has completed.
4 | LILO of 2nd ckt of Tuirial-Aizwal at Kolasib | D/C | 132 | 105 | 0 | 0 | 0 |  |  |  | Funding of project is yet to be identified
5 | LILO of Zemabawk - W.Phaileng at Sihhmui | S/C | 132 | 5 | 0 | 0 | 0 | 0 |  | DEC-13 | Approval from State Govt. obtained
6 | Luangmual to Sihhmui | D/C | 132 | 16 | [6 empty] | Work progress is 28 percent due to ROW problem since the line is to be constructed through city area
7 | Melriat to Khumtung | D/C | 132 | 25 | [6 empty] | Proposal stage
8 | Sihhmui s/s to Airport road Sihhmui(to re-align existing W.Phaileng line | S/C | 132 | 11 | [6 empty] | Proposal stage. Fund will be sought from NEC/DoNER
9 | Tuirial HEP - Bawktlang (Kolasib) S/S | S/C | 132 | 42 | 85 | 85 | 85 | 42 |  | FEB-17 | Line completed on Mar-17.
POWER TRANSMISSION CORP. OF UTTARAKHAND LTD.(PTCUL)
1 | Kuwari Pass (Pipalkoti)-Karanprayag -Srinagar(Khandukhal) | D/C | 400 | 184 | 220 | 45 | 0 | 0 |  | DEC-21 | Contract awarded in 03 no. packages in Sep 2017. Forest proposal had been submitted on dated 24.11.2018 for Package-I, on dated 23/10/2018 for Package-II and on dated 23/02/2019 for Package-III. Stage-I clearance of forest case for Package I, II and III is expected by Oct'19, Oct'19 and Nov'19 resp. Construction work of line will be started after approval of stage-I clearance of forest.
2 | LILO of Loharinagpala - Koteshwar at Pala - Maneri | D/C | 400 | 10 | 0 | 0 | 0 | 0 |  |  | The work at Pala Maneri HEP stopped as per GOI order.
3 | LILO of Vishnu Prayag - Muzaffarnagar at Tapovan Vishnugarh HEP | D/C | 400 | 2 | 0 | 0 | 0 |  |  |  | Approval is pending in Standing Committee, CEA. Construction of Transmission line will be planned after due approval from competent authority.
4 | Loharinagpala-Koteshwar line | D/C | 400 | 180 | 0 | 0 | 0 | 0 |  |  | The work at Loharinagpala HEP stopped as per GOI order.
5 | Pipalkoti HEP (THDC) - Pipalkoti (Kuwari Pass) Switching Substation T/line | D/C | 400 | 2 | 0 | 0 | 0 |  | SEP-19 | DEC-21 | Construction of line shall be planned as per schedule of Pipalkoti HEP (THDC) after signing of Implementation Agreement with PTCUL.
6 | Srinagar(Khandukhal)-Kashipur(Rampura) | D/C | 400 | 362 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line to be taken up under central sector as an ISTS scheme with the matching timeframe of commissioning of Vishnugad -Pipalkoti(HEP) of THDC i.e June 2023 or Tapovan-Vishnugad HEP of NTPC whichever is earlier as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21.
7 | Tapovan (Vishnugad) - Pipalkoti | D/C | 400 | 36 | 48 | 13 | 4 |  | MAR-23 | MAR-23 | Final approval on forest proposal was accorded on dt 21.07.2020. Natural calamity happened on dt.07.02.2021in Joshimath,Dist Chamoli at Rishi Ganga, which also affected the NTPC HEP. Revised commissioning schedule of Tapovan-Vishnugad HEP is awaited from NTPC.
8 | Vishnugad - Kuwari Pass (Pipalkoti) | D/C | 400 | 40 | 62 | 0 | 0 | 0 |  | DEC-18 | Construction of 400 KV DC Vishnugad-Pipalkoti line & LILO of 400 KV DC Vishnuprayag-Muzaffarnagar at Piapalkoti is under progress. Rroute alignment, profile has been finalized and forest case preparation is under process. Completion period of line as amended is 02 years from 26.09.2016.
9 | Almora-Pithoragarh | D/C | 220 | 146 | 0 | 0 | 0 | 0 |  | DEC-20 | Revised DPR under preperation.
10 | Arakot -Mori and LILO of Arakot -Mori at Hanol Tuni | D/C | 220 | 94 | 0 | 0 | 0 | 0 |  | MAR-20 | Land for construction of S/s is being searched. Construction of line will be planned as per Connectivity Schedule of Generators in Yamuna Valley.
11 | Baramwari -Srinagar Phase-2 (Single Zebra conductor from Interconnection point of Singoli Bhatwari HEP) at Rudrapur line | D/C | 220 | 31 | 0 | 0 | 0 |  | SEP-23 | MAR-23
12 | Devsari-Karanprayag | D/C | 220 | 52 | 0 | 0 | 0 | 0 |  |  | Construction of Transmission line will be planned as per Connectivity Schedule of Devsari HEP (SJVNL) in Alaknanda Valley.
13 | Jakhol -Sankri -Mori and LILO of Jakhol -Sankri -Mori at Natwar Mori | D/C | 220 | 76 | 0 | 0 | 0 | 0 |  | MAR-18 | Construction of line as per Conectivity Schedule of Generators in Yamuna Valley.
14 | Joshimath - Kunwari Pass (Pipalkoti) | D/C | 220 | 40 | 0 | 0 | 0 |  |  | DEC-21 | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
15 | Lakhwar- Dehradun | D/C | 220 | 60 | 110 | 57 | 52 | 0 |  | JUN-20 | Foundation Completed : 57Nos. Tower erection : 52 Nos. Stringing :0.000 Kms
16 | Lata Tapovan- Joshimath | D/C | 220 | 24 | 36 | 0 | 0 | 0 |  | DEC-21 | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
17 | LILO of Baramwari - Srinagar at Singoli Bhatwari | D/C | 220 | 5 | 0 | 0 | 0 | 0 | DEC-19 | MAY-21 | Work held up due to COVID-19.
18 | LILO of Dhauliganga - Pithoragarh (PGCIL) line at proposed 220/33 kV S/s Baram (Jauljivi) | D/C | 220 | 22 | 0 | 0 | 0 |  | MAR-23 | MAR-23 | Work is under progress. Physical Progress is 36%. Excavation done for 6 nos. tower locations out of 39 tower locations.
19 | LILO of Kashipur - Pantnagar line at Jaffarpur | D/C | 220 | 8 | 17 | 17 | 17 | 8 | MAY-20 | APR-21 | Commissioned 03/21.
20 | LILO of Mori - Dehradun line at Nogaon | D/C | 220 | 10 | 39 | 1 | 0 | 0 |  | MAY-20 | Target date of Completion 31.05.2020.
21 | LILO of Nandprayag -Karanprayag at Langrasu | D/C | 220 | 16 | 0 | 0 | 0 | 0 |  |  | Construction of Transmission line will be planned as per Connectivity Schedule of Langrasu HEP (UJVNL) in Alaknanda Valley.
22 | LILO of Vyasi HEP - Dehradun at Dehradun (PG) S/S | D/C | 220 | 70 | 0 | 0 | 0 | 0 |  | DEC-18 | Route Survey has been completed. Tower schedule and profile of line has been approved. Principal approval obtained from MOEF on dated 11/09/2017. Proposal for transfer of land (73.36 Hect.) for compensatory afforestation was submitted to DM, Dehradun on dated 14/09/2017. SDM directed to Tehsildar on 03/10/2017 for further necessary action. Total Progress 12%
23 | Mori -Dehradun | D/C | 220 | 200 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
24 | Naitwar Mori HEP - Mori SS | D/C | 220 | 0 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
25 | Phata HEP-Baramwari (Rudrpur) | D/C | 220 | 8 | 8 | 0 | 0 |  |  | DEC-22 | Pertains with L&T HEP.
26 | Pipalkoti -Srinagar Trans. Line | D/C | 220 | 176 |  |  |  |  | MAR-23
27 | Puhana - Imlikhera (Pirankaliyar) line | D/C | 220 | 14 |  |  |  |  | NOV-19
PUNJAB STATE TRANSMISSION CORPORATION LIMITED(PSTCL)
1 | LILO of both ckts. Rajpura Thermal s/s to Nakodar s/s at Doraha | 2xD/C | 400 | 22 |  |  |  |  | MAR-18
2 | LILO of both lines Rajpura s/s- Lalru s/s at Mohali | D/C | 400 | 14 |  |  |  |  | MAR-18
3 | LILO of one Ckt. of 400kV Ludhiana PGCIL-Koldam at proposed 400kV s/s Ropar | D/C | 400 | 14 | 0 | 0 | 0 | 14 | JUN-24 | AUG-24 | Commissioned 07/24.
4 | 220 KV D/C line from 400 KV S/S Dhanansu to Tata Steel plant Kadiana Khurd (Contributory work) | D/C | 220 | 5 | 30 | 11 | 9 | 0 | MAR-25 | MAR-25 | Work in progress.
5 | Bhateri-TSS Mehmadpur line | D/C | 220 | 53 | 103 | 38 | 10 | 0 | SEP-22 | MAR-26 | ROW issues. Help of District Administration has been sought to resolve ROW issue.
6 | Connecting 220 kV PGCIL Ludhiana-Doraha SC line with 220 kV Lalton Kalan-Dhandari Kalan forming PGCIL Ludhiana- Dhandari Kalan SC line (charged in June-2024 however late reported by PSTCL) | S/C | 220 | 10 | 0 | 0 | 0 | 10 |  | AUG-24 | Commissioned 06/24 (Late Reported).
7 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | 220 | 16 | 31 | 31 | 31 | 16 | MAY-24 | MAY-24 | Commissioned 04/24.
8 | LILO of 220 kV S/Stn Mansa - Sunam at 400 kV S/Stn Patran | D/C | 220 | 85 | 144 | 144 | 144 | 85 | APR-24 | JUL-24 | Commissioned 06/24.
9 | LILO of one ckt of 220 KV Ganguwal-Jamalpur at 400 KV S/S Dhanansu | D/C | 220 | 9 | 33 | 5 | 5 | 0 | MAR-25 | MAR-25 | Work in progress.
10 | Lilo of one ckt of 220 KV Jamalpur-Dhandari Kalan-1 line at 220 Kv Sherpur S/S | D/C | 220 | 4 | 5 | 5 | 3 | 0.79 | JUN-24 | OCT-24 | Work in progress, likely to be completed by Oct'24.
11 | Makhu - Taran ¦Tarn | D/C | 220 | 60
12 | Mansa - Budhlada line | D/C | 220 | 52 | 100 | 99 | 95 | 38.67 | JUL-24 | NOV-24 | Work in progress. Due to water logging, work will be completed after Paddy season, likely to be completed by Nov'24.
13 | Rajpura s/s to 220 kv Rajpura s/s D/C on D/C towers | D/C | 220 | 3 | 14 | 6 | 0 | 0 | SEP-24 | DEC-24 | ROW issue by Kisan Union.
14 | Shifting of 220 KV S/C Patti-Verpal line from 220 KV Verpal to 400 KV S/S Amritsar | D/C | 220 | 2 | 8 | 8 | 8 | 1.7 | APR-24 | OCT-24 | Work Completed Line yet to be energised.
15 | Work for connecting 400kV Rajpura -220kV Mohali-1 (one ckt direct one via 220 kV Banur) | D/C | 220 | 4 | 19 | 1 | 0 |  | JUL-24 | DEC-24 | ROW issue by kisan union.
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED(RVPNL)
1 | LILO of 400 kV Rajwest-Kankani line at 400 kV Pachpadra GSS | D/C | 400 | 72 | 0 | 0 | 0 | 72 |  | JAN-25 | Commissioned 12/24 (Deposit work of M/s HPCL Rajasthan Refinery Limited)
2 | Suratgarh - Babai | D/C | 400 | 491 | 676 | 676 | 676 | 469 | DEC-23 | DEC-24 | 1. Earlier Work order awarded to M/s Aster Chennai has been withdrawn at risk and cost of the firm. 2. Stay against termination of contract issued by court. 3. Matter is under the jurisdiction of court. IA Cancelled in hearing on 11.09.23. 4. For balance work revised detailed W.O. issued to M/s Kay Cee Infra & Energy on 8.4.22 W.O. short closed. 5. For balance work, W.O. issued on 15.06.24 to JV of M/s Navdurga
3 | Suratgarh TPS- Babai (Jhunjhunu)(Quad Moose) Line | D/C | 400 | 491 | 0 | 0 | 0 | 472 | MAR-25 | MAR-25 | 1. For balance work W.O. issued to JV of M/s Navdurga, and M/s Man on 15.06.24. Work in progress.
4 | 220 kV D/C Surpura-Banar line (late reported commissioned in October-2024) | D/C | 220 | 20 | 0 | 0 | 0 | 20 |  | DEC-24 | Commissioned 10/24 (LAte Reported).
5 | Jodhpur CHB - Soorsagar | D/C | 220 | 16 | 32 | 32 | 32 | 15.46 |  | DEC-21 | Charged on dated 10.03.2022 at 132 KV Voltage level.
6 | LILO of 220 kV Balotra-Boranada line at 400 kV Pachpadra GSS | D/C | 220 | 18 | 0 | 0 | 0 | 18 |  | JAN-25 | Commissioned 12/24 (Deposit work of M/s Hindustan Rajasthan Refinery Limited)
7 | LILO of 220 kV S/C Ramgarh (400 kV GSS)-Dechu Line | S/C | 220 | 8 | 0 | 0 | 0 |  | AUG-24 | NOV-24 | Work order issued to M/s Hi-Tech on 04.10.2023. Line Survey completed. Line lies in GIB Arc. GIB Case for approval of Supreme Court submitted on 31.04.2024. Approval pending.
8 | LILO of existing 220 kV S/C Bhilwara (220 kV GSS)-Beawer line at 220 kV GSS Rayla | S/C | 220 | 28 | 46 | 20 | 0 |  | JUN-24 |  | Work Order to M/s Geetanjali enterprises on 06.10.23. Survey completed & Profile approved on 14.05.2024. Work started, S/S:10/46
SIKKIM POWER DEVELOPMENT CORPORATION LTD.(SIKKIM)
1 | LILO of Teesta III - Rangpo 400 kv line at Dikchu (Interim connectivity) | D/C | 400 | 1 | 2 | 2 | 12 | 1 |  | FEB-17 | Completed.
2 | Dikchu HEP - Dikchu Pool | D/C | 132 |  | 0 | 0 | 0 |  |  |  | Yet to award
TAMILNADU TRANSMISSION CORPORATION LTD.(TANTRANSCO)
1 | Uppur SCTPP - Virudhunagar | D/C | 765 | 204 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated.
2 | Virudhnagar - Coimbatore | D/C | 765 | 498 | 725 | 556 | 527 | 200 | MAR-21 | MAR-24 | Work in progress in all the 3 reaches awarded.
3 | 400 KV UG Cable laying work from UG common point near Pallikarunai to O.H U.G common point near Perambakkam | S/C | 400 | 10 |  |  |  |  | MAR-25
4 | Ennore SEZ - North Chennai Pooling Station | D/C | 400 | 33 | 51 | 40 | 36 | 15.18 | SEP-23 | MAR-24 | Work under progress.ROW issues involved . PWD approval awaited
5 | ETPS exp.- Ennore SEZ | D/C | 400 | 24 | 22 | 21 | 19 | 9.72 | APR-19 | MAR-25 | Work under progress.line stringing pending for want LC
6 | ETPS exp. - North Chennai Pooling Station | D/C | 400 | 24 | 9 | 8 | 8 | 3.78 | SEP-18 |  | Work under progress.
7 | ETPS to Tondiarpet point ATS | D/C | 400 | 18 | 5 | 5 | 5 | 1.73 | SEP-17 | MAR-23 | Work is under progress. Line stringing pending for want of LC.
8 | Laying of 400KV UG Cable from OH and UG common point at Manjambakkam to the proposed Korattur 400KV SS | S/C | 400 | 12 |  |  |  |  | JUN-24
9 | LILO of Kayathar - Thennampatti 400 kV line Virudhunagar 765/400 KV SS | D/C | 400 | 140 | 201 | 201 | 201 | 140 | MAR-21 | SEP-24 | Commissioned 08/24.
10 | LILO of one ckt of Thappagundu - Anaikadavu 400 line at Udumalpet (PGCIL) S/S | D/C | 400 | 40 | 60 | 60 | 60 | 16.76 | NOV-23 | MAR-24 | 3.252 KM of stringing and 20.012 KM OPGW stringing pending.Work will be taken up after payment of Tree /Crop compensatation.
11 | LILO of Ottiyambakkam Guiny 400 KV SC feeder at Tharamani 400 KV GIS UG Cable -3.925 KM | D/C | 400 | 8 |  |  |  |  | MAR-25
12 | LILO of Sunguvarchatram - Alamathy at Vellavedu (Guindy) | D/C | 400 | 16 | 44 | 44 | 44 | 28.08 |  | FEB-22 | Work completed. Will be energised after completion of 400 KV UG Cable from Parivakkam to Guindy.
13 | LILO of Thappagundu - Anaikadavu at Udumalpet (PGCIL SS) | D/C | 400 | 40 |  |  |  |  | JUN-24
14 | Manali - Pulianthoppe | D/C | 400 | 9 | 64 | 64 | 64 | 18.72 | JUN-22 | MAR-23 | Line energised on 02.03.2023
15 | Manjakuppam - Korattur | D/C | 400 | 22 | 0 | 0 | 0 | 0 | APR-17 | JAN-24 | Laying completed in 22/27 sections and Joining 18/26 completed. Work under progress.
16 | Parali - Karamadai line | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Parali - Karamadai 400 kV D/C line is to run on D/C tower up to location no. 57 (Hilly terrain area) and subsequently on 400 kV M/C tower (with four circuits) upto Karamadai 400/230 kV S/S (S/S (in Plains area ), which will also accommodate existing Parali-Karamadai 400 kV D/C line utilizing the corridor of existing Kundah PH-II-ARasur 230 kV S/C line. the lines will have HTLS conductor.
17 | Parivakkam (Vellavedu) - Guindy 400 KV Substation 400KV UG Cable | D/C | 400 | 33 |  |  |  |  | MAR-25
18 | Sholinganallur 400 kV S/S (Perumbakkam) - Guindy 400 kV S/S | D/C | 400 | 40 | 19 | 19 | 19 | 5.7 |  | MAR-24 | 400KV UG Cable in lieu of erection of 400KV OH line in the portion of line invloved in Marsh Land.(9.5 KM) awarded on24.02.2023.OH Line 5.70 Km completed.
19 | Sholinganallur - Guindy | D/C | 400 | 12 | 0 | 0 | 0 |  |  | MAY-22 | UG cable work from Perumbakkam Jn to Guindy Work awarded on 27.05.20. As per field route length is 9 Kms.
20 | Thervaikandigai - Korattur | D/C | 400 | 5 | 9 | 9 | 9 |  | APR-15 | OCT-17 | line Energised on 23.07.17.
21 | Thervaikandikai - Manali | D/C | 400 | 73 | 113 | 111 | 106 | 58.6 | JUN-24 | MAR-23 | Work under progress. Row issues Enter upon permission awaited.
22 | Udangudi - Samugarengapuram (QM ACSR Conductor) line | D/C | 400 | 154 | 154 | 0 | 0 |  |  |  | Estimate approval under process.
23 | Udangundi - Virudhunagar (QM ACSR Condutor) line | D/C | 400 | 0 | 0 | 0 | 0
24 | Vellavedu - Guindy 400 kV S/S (U/G Cable) | D/C | 400 | 40 | 0 | 0 | 0 |  |  | MAR-24 | Laying completed in 10/33 Sections. Work under progress.
25 | Virudhnagar - Kamuthi | D/C | 400 | 114 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated. Revised estimate under preparation.
26 | Virudhnagar - Thappagundu | D/C | 400 | 160 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated.
27 | CMRL Central 230 kV SS to Pulianthope 400 kV SS (UG Cable) | S/C | 230 | 3.4 | 0 | 0 | 0 |  | SEP-17 | JUN-21 | Tender to be floated.
28 | CMRL Central Jail to proposed Mambalam 230kV GIS SS (UG Cable) | S/C | 230 | 9 | 0 | 0 | 0 |  | JUN-24 | JAN-24 | Total sections: 19. Laying 19/19 completed. Joints 54/54 completed. Sheath fault rectification work under progress.
29 | Extension of Shoolagiri Karimangalam line (from location no. 6 of Shoolagiri Karimangalam line) to Udanapally 230 KV SS | S/C | 230 | 2 | 0 | 0 | 0 | 2 | APR-24 | MAY-24 | Commissioned 04/24.
30 | Kilpauk - TNEB HQ | S/C | 230 | 6 | 0 | 0 | 0 |  | JUN-24 | MAR-24 | Total: 13 sections. Total:36 joints.Cable Laying 13/13 Completed. Joints 36/36 completed. Cable fault rectification work under progress.
31 | KPSHEP - Parali lines on M/C towers | S/C | 230 | 0 | 114 | 40 | 22 | 0 |  | MAR-24 | Work under progress
32 | Laying of UG cable by making LILO in the existing 230 KV Korattur- Kilpauk water works at Ganesh Nagar 230 KV SS | D/C | 230 | 3 |  |  |  |  | JUN-24
33 | Laying of UG cable by making LILO in the proposed 230 KV Alamathy-Srperumbudur feeder at the proposed Avadi 230/110 KV SS | D/C | 230 | 9 |  |  |  |  | JUN-24
34 | LILO in 230 kV Othakalmandapam - Ponnapuram at the proposed Edayarapalayam 400 kV SS | D/C | 230 | 50 | 42 | 42 | 41 | 15 | SEP-18 | MAR-24 | land compensation issue being followed up
35 | LILO in the existing 230 kV Shoolagiri - Karimangalam at the propsosed Uddanapally 230kV SS | D/C | 230 | 30 | 3 | 3 | 3 | 1.02 |  | JUL-18 | Energised 0n 26.07.18
36 | LILO in the existing Dharmapuri (Palavadi) 400 kV SS to the proposed Uddanapally 230 kV SS | D/C | 230 | 136 | 247 | 247 | 247 | 114.36 | SEP-18 | MAR-22 | Energised on 03.07.2021
37 | LILO of 230 kV Abishekapatti - Udayathur line at Nanguneri | D/C | 230 | 40 | 84 | 84 | 84 | 40.35 | SEP-24 |  | Line work completed. Will be energised on energisation of Nanguneri 230KV Substation.
38 | LILO of 230 kV Basin Bridge -TNEB Head Quarters feeder at Pulianthope 400 KV GIS SS (230KV UG Cable) | D/C | 230 | 1 | 0 | 0 | 0 | 1 |  | AUG-24 | Commissioned 07/24.
39 | LILO of 230 kV Mylapore - Tarammani feeder at the proposed Thiruvanmiyur (400 kv GIS) | D/C | 230 | 2 | 0 | 0 | 0 |  | DEC-24 | DEC-23 | Cable laying work completed.Cable will be energised during commissioning of SS.
40 | LILO of 230 KV Ottiyambakkam - Omega Feeder II at the proposed Mambakkam 230/110 KV SS | D/C | 230 | 68 |  |  |  |  | SEP-24
41 | LILO of Arasur- Ingur 230kV line at Kalivelampatty 230kV s/s | D/C | 230 | 31 |  |  |  |  | NOV-24
42 | LILO of Dharmapuri (Palavadi) 400 kV SS to the proposed Tirupattur 230 kV SS | S/C on D/C | 230 | 77 | 299 | 289 | 248 | 32.8 | JAN-24 | MAR-24 | Work to resume after payment of crop compensation.
43 | LILO of existing 230 kV Arni - Sriperumbudur feeder (0.81KM) at the proposed Vembakkam 230 kV S/S | D/C | 230 | 2 |  |  |  |  | JUN-24
44 | LILO of KPSHEP - Kundah PH-III at Parali (400/230 kV S/S) | D/C | 230 | 0 | 0 | 0 | 0 |  |  |  | The existing LILO of KPSHEP - Kundah PH-III, 230 kv D/C line to Parali 400/230 kV S/S . And utilizing the existing 230kV corridor upto Parli.
45 | LILO of Pudhansandhai - Pugalur 230 KV Feeder at Nallur SS | M/C | 230 | 24 |  |  |  |  | MAR-25
46 | LILO of S. P. Koil - Oragadam at Maraimalai Nagar 230 KV S/S | D/C | 230 | 9 |  |  |  |  | SEP-24
47 | LILOof Sriperumbudur-Kadapperi at Porur 230KV SS (UG) Kadapperi to Porur (OH+UG) | D/C | 230 | 28 | 0 | 0 | 0 |  | MAR-18 | DEC-20 | UG cable work awarded to M/s Universal cable on 16.02.17.Total section 12 nos. Cable laying in the section completed. Joints 27/33 completed.
48 | LILO of the exisiting 230 kV Ingur - Kurukathi - Palladam feeder at sanctioned Rasipalayam 400 kV S/S | D/C | 230 | 46 | 59 | 59 | 51 | 6.7 | AUG-22 | MAR-24 | ROW issues. Land owners are demanding yield compensation of further works tender floated for 8 nos towers.
49 | LILO of the exisiting 230 kV Myvady - Kurukathi - Pugalur feeder at sanctioned Rasipalayam 400 kV SS | D/C | 230 | 46 | 93 | 92 | 92 | 41 | SEP-24 | MAR-24 | Row issues land owners are demanding yield compensation prior to commencement of further works tender floated for supply and erection of 5 nos towers.
50 | LILO of Thiruvalam - Singarapet 230 KV Feeder at Sathumadurai 230KV SS (OH- 1.75 Kms and UG -0.800 Kms.) | D/C | 230 | 5 |  |  |  |  | MAR-25
51 | LILO of Tonidapet - Mylapore at TNEB HQ (UG Cable) | D/C | 230 | 1 | 0 | 0 | 0 | 0 |  | SEP-20 | Dropped. Scheme will be completed while making LILO of CMRL Central to Mylapore feeder at TNEB HQ
52 | LILO the existing 230 kV P.P Nallur - Thanjavur at proposed Narimanam 230 kV SS | D/C | 230 | 30.4 | 0 | 0 | 0 |  | SEP-18 | MAR-24 | Revised administrative approval is under process.
53 | LILO the existing 230 kV P.P.Nallur - Thiruvarur at the proposed Narimanam 230 kV SS | D/C | 230 | 30.8 | 0 | 0 | 0 |  | SEP-18 | MAR-24 | Revised administrative approved is under process.
54 | Neyveli - TS-II to the proposed Neyveli 230/110 kV SS | D/C | 230 | 2 | 20 | 20 | 20 | 9.5 | SEP-18 | JUN-21 | Work completed. Energised on 26.12.19
55 | N.T. Kudy - Karaikudi line | S/C on D/C | 230 | 104 | 370 | 370 | 370 | 104.12 | SEP-23 | DEC-23 | Work completed. LC awaited for energisation.
56 | Ottiyambakkam (Sholinganallur) - KITS | D/C | 230 | 21 | 35 | 33 | 33 | 12.8 | SEP-24 | MAR-24 | OH line work completed for 33/35 locations (6.40/7.30 KM ) for balance 2 Nos loc Alternate route tender under process. UG cable laying for 3.04 KM proposed in lieu of OH line in marsh land.Tender awarded. Route survey under progress.
57 | Palavady - Thirupathur line | D/C | 230 | 75 | 299 | 289 | 248 | 32.84 |  | MAR-24 | Work to resume after payment of making crop compensation.
58 | Palladam - Ingur | S/C on D/C | 230 | 62 | 249 | 236 | 209 | 40.7 | APR-13 | MAR-24 | Line energised from Palladam to Kurukkathi tapping points ie up to loc 160. Severe RoW issue between Loc no 160 - 190.
59 | Sholinganallur - KITS | D/C | 230 | 24 | 50 | 47 | 44 | 20.8 |  | MAR-23 | "Proposal for laying of UG Cable to avoid OH line in 4 locations in Marsh Land is submitted and approval is in Process. Proposal submitted for Reserve Forest clearance in 2 locations.
60 | Sriperumbudur -Korattur (Changing of conductor) | S/C | 230 | 20 | 70 | 0 | 0 | 12 | SEP-06 | DEC-20 | Line work is under modification. Revised administrative approval is under process.
61 | UG Cable from Basin Bridge to TNEB Head Quarters | S/C | 230 | 6 | 0 | 0 | 0 | 6 | JUN-24 | MAY-24 | Commissioned 04/24.
62 | Vellalaviduthi 400 kV SS to Mondipatti 230 kV SS | S/C on D/C | 230 | 90 | 354 | 354 | 354 | 91.9 | APR-23 | OCT-23 | Line energised on 04.10.23
63 | Villupuram - Ulundurpet | S/C | 230 | 55 | 183 | 181 | 117 | 20 |  | MAR-25 | Work could not be taken up further due to issues invloved and revised route is under study.
64 | Common Point (from Karamadai) - Thudialur (2nd Circuit) | S/C | 220 | 20 | 68 | 68 | 68 | 38.67 | AUG-15 | JUN-21 | Both the Ckts energised on 19.12.16 and 06.02.17
65 | Kilpauk - CMRL Central Jail | S/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-24
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED(APTRANSCO)
1 | 400kV QMDC line from 400kv Polavaram SS - 400/220/11kV Guddigudem | D/C | 400 | 49 | 72 | 68 | 67 | 33.68 | MAY-24 | DEC-24 | Works are under progress. 3 Locations (Loc.Nos. 7,8,11) are in forest area.Loc.No.7 and 8: CA land allotted. Permission from Forest authorities awaited.Loc.No. 11: CA land yet to be allotted by Revenue authorities.
2 | Chilakaluripeta (PG) to Chilakaluripeta (AP) | D/C | 400 | 64 | 0 | 0 | 0 |  | AUG-19 |  | work cancelled
3 | Elluru-Gudivada (Q) | D/C | 400 | 160 | 0 | 0 | 0 |  | AUG-19 |  | work cancelled
4 | Gudivada-Chilakaluripeata (Q) | D/C | 400 | 206 | 0 | 0 | 0 |  | AUG-19 |  | The line is cancelled as the contract for construction of 400kV SS at Chilakaluripeta is rescinded.
5 | Jammalamdugu-Gani (QM) | D/C | 400 | 240 | 0 | 0 | 0 |  | AUG-19 |  | work cancelled
6 | LILO of 400kV HNPCL- Kamavarapukota TMDC line to proposed 400/220/11 kV Guddigudem S/S | D/C | 400 | 41 | 0 | 0 | 0 |  |  |  | Charged
7 | LILO of 400kV Kalpaka-Vemagiri at Kallpaka | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-20 |  | The scheme not yet formulated
8 | LILO of 400kV Vemagiri-Sattenapalli TMDC lineat 400kV s/s Gudiwada | D/C | 400 | 51 | 90 | 66 | 14 | 0 |  | MAR-25 | work under progress
9 | LILO of 400kV VTS-IV Sattenapalli TMDC line at Thallayapalem and Temporary diversion of PGCIL VTS/Nunna-Nellore 3 and 4 Ckts. to avoid aerial passage over 400/220kV GIS Thallayapalem | D/C | 400 | 2 | 7 | 7 | 7 | 3 | JUN-24 | NOV-24 | Commissioned 10/24.
10 | LILO of 400kV VTS-Sattenapalli at CRDA Amaravathi SS-I | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-20 |  | work cancelled
11 | LILO of 400kV VTS-Sattenapalli at CRDA Amaravathi SS-II | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-21 |  | work cancelled
12 | LILO of existing VTS-Sattenapalli at proposed Inavolu/Thullurs SS | D/C | 400 | 20 | 7 | 4 | 3 | 2.41 | JUN-22 | JUN-24 | work under progress
13 | LILO of Hindupur - Kadapa (Cuddapah) at NP Kunta PS (GEC-II) | D/C | 400 | 18 | 0 | 0 | 0 |  |  |  | Not pertains to APTRANSCO
14 | LILO of Kadapa (Cuddapah) - Kolar S/C line at NP Kunta PS (GEC-II) | D/C | 400 | 14 | 0 | 0 | 0 |  |  |  | Not pertains to APTRANSCO
15 | LILO of - Manubolu (Ckt-I Quad Moose line - M/s SEIL - P2 400kV GIS s/s | D/C | 400 | 4
16 | LILO of Vemagiri-I Sattenpali at Eluru | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-18 |  | work cancelled
17 | MAilavaram - Kondapura (Jammalamadugu) (GEC-II) | D/C | 400 | 21 | 0 | 0 | 0 |  | JUL-20 |  | The line is cancelled as the scheme is modified by laying 220kV lines from pooling stations at Mylavaram Ultra Mega Solar Park (1000MW ) at kadapa dist. of AP to the existing 400kV Jammamalamadugu in a Cost effective manner instead of constructing separate 400kV Substation at Mylavaram.
18 | Mylavaram-Jammalamdugu QMDC Line | D/C | 400 | 21 | 0 | 0 | 0 |  | JUL-20 | JUL-20 | The line is cancelled as the scheme is modified by laying 220kV lines from pooling stations at Mylavaram Ultra Mega Solar Park (1000MW ) at kadapa dist. of AP to the existing 400kV Jammamalamadugu in a Cost effective manner instead of constructing separate 400kV Substation at Mylavaram.
19 | Narnoor-Aspiri (QM) | D/C | 400 | 180 | 0 | 0 | 0 |  | AUG-19 |  | The scheme is cancelled as the uncommissioned RE connectivities which are proposed to connect Aspiri scheme are envisaged in 10,000MW Solar Power establishment Scheme at other Substations.
20 | NTTPS, Vijayawada TPS-existing Sattenapalli SS | D/C | 400 | 120 | 0 | 0 | 0 |  | AUG-18 |  | work cancelled , not taken up as per system studies
21 | Polavaram-Kamavarapukota (QM) | D/C | 400 | 140 | 0 | 0 | 0 |  | AUG-19 |  | The scope of the work revised due to site constraints. 400kV QMDC Line from 400kV Polavaram SS to 400/22/11 kV Guddigudem SS is proposed in place of earlier approved 400kV Polavaram-K.Kota QMDC Line.Tenders floated with revised scope of work on 28.01.2019.Tenders finalized and LOI placed on 29,04.2019 .Line survey works completed. Works will be taken up after finalization of award of contract of Polavaram Hydro Electric Project by APGENCO.
22 | Rasipalayam -Dharmapuri (Palavadi) | D/C | 400 | 379 | 0 | 0 | 0 |  |  |  | does not pertains to APTRANSCO
23 | Urvakonda-Uravkonda-II | D/C | 400 | 100 | 0 | 0 | 0 |  | AUG-18 |  | May be deleted that CEA , during 42nd standing committe meeting recommended to take up 400/220kV Uravakonda  2 Substation with 3 x 500MVA PTRs + 1 x 125 MVAR Bus Reactor in the existing 400/220KV Uravakonda - 1 Sub-station of APTRANSCO duly extending the 400 KV Bus without constructing a new 400/220kV Sub-station.
24 | Vemagiri - Kamavarapukota | D/C | 400 | 116 | 268 | 268 | 268 | 116 | DEC-22 | NOV-24 | Commissioned 09/24 (Late Reported).
25 | 220 kV Brandix - Atchuthapuram | D/C | 220 | 7 | 11 | 11 | 11 | 7 | JUN-24 | AUG-24 | Commissioned 07/24.
26 | 220KV DC line from 220KV Gunadala S/S - 220KV Nunna S/s | D/C | 220 | 13 | 34 | 34 | 34 | 12.32 | MAY-24 | DEC-24
27 | 220kV DC line from 400kV Kamavarapukota to 220kV SS Bhimadole SS | D/C | 220 | 37 | 69 | 69 | 69 | 37 | MAY-24 | AUG-24 | Commissioned 07/24.
28 | 220 kV Krishnagiri- Nansuralla Line | S/C | 220 | 24 | 0 | 0 | 0 | 24 |  | DEC-24 | Commissioned 11/24.
29 | 220kV multi circuit line for making Double LILO of 220kV Gudivada-Akiveedu-Bhimavaram DC line at Proposed 400/220kV S/S Gudivada | M/C | 220 | 38 | 63 | 40 | 0 | 0 |  | DEC-24 | work under progress
30 | 220kV SMDC line converted to TMDC from 400kV Hindupur - 220kV Pampanurthanda | D/C | 220 | 148 | 268 | 235 | 220 | 52.42 | JUN-24 | DEC-24 | work under progress
31 | Chittoor 400 kV SS-Mananapalli | D/C | 220 | 130 | 0 | 0 | 0 |  |  |  | Work not taken up
32 | Garividi-Bobbili | D/C | 220 | 75 | 130 | 130 | 130 | 75 |  |  | charged
33 | Garividi - Garividi | D/C | 220 | 70 | 0 | 0 | 0 |  |  |  | Work not taken up
34 | Garividi - Pydibhimavaram | D/C | 220 | 100 | 169 | 169 | 169 | 100 |  | MAY-21 | charged on 14.05.21
35 | Jammalamadugu (400 kV SS) to proposed Bethamcherla (220 kV SS) in Kurnool District | D/C | 220 | 151 | 260 | 260 | 260 | 151 | JUN-24 | DEC-24 | Commissioned 11/24.
36 | Jammalamadugu (400) - Tadipatri (220) (GEC-I) | D/C | 220 | 80 | 0 | 0 | 0 |  |  |  | work cancelled
37 | Jammalamadugu - Betamacherla | D/C | 220 | 152 | 260 | 259 | 259 | 140.94 | JAN-24 | DEC-24 | Work permit received from Forest CF/Kurnool on 16.04.2024. Work under Progress
38 | Kalyandurg-Anantapur | S/C | 220 | 61 | 0 | 0 | 0 |  |  |  | work cancelled
39 | Kamavarapukota - Kamavarapukota | D/C | 220 | 30 | 69 | 69 | 69 | 36.9 |  | SEP-24 | All works completed
40 | LILO of 220 kv ongole-Racherlpadu line at 220 kv ss Kandukur | D/C | 220 | 7 | 13 | 13 | 13 | 7 | MAY-24 | SEP-24 | Commissioned 08/24.
41 | LILO of 220kV VTS-Tallapally-1 at 220/132 kV SS Rentachintala | D/C | 220 | 3 | 5 | 5 | 4 | 3 | APR-24 | JUN-24 | Commissioned 05/24.
42 | LILO of existing 220kV Gooty -Shapuram line at proposed 220kV Dharmavaram S/S | D/C | 220 | 3 | 8 | 8 | 8 | 3.28 | JUN-24 | JUN-24 | works completed
43 | LILO of existing 220 kV Madanapalli-Palamaner line to 220 kV Punganur S/S | D/C | 220 | 5 | 13 | 13 | 13 | 5 | JUN-24 | DEC-24 | Commissioned 12/24.
44 | LILO of existing 220 KV Nunna - KTPS Single Ckt. line at 220kV SS Tiruvuru | D/C | 220 | 2 | 16 | 10 | 4 | 0 | JUL-24 | JUL-24 | work is under progress
45 | LILO of existing one circuit of 220kV VTS-Kamavarapukota line at 400/220kV S/S Kamavarapukota | D/C | 220 | 3 | 9 | 9 | 8 | 0 | MAY-24 | JUN-24 | work under progress
46 | LILO of Uravakonda - Kalyandurga at Borampalli | D/C | 220 | 22 | 0 | 0 | 0 |  |  |  | Charged on 19.09.2020
47 | LILO of VSS - Kakinada line and Anrak-Samakota line at Chandanada line | D/C | 220 | 11 | 60 | 53 | 26 | 1.03 |  | DEC-24
48 | LILO of VTS -3 and 4 at Pidugguralla line | D/C | 220 | 4 | 8 | 8 | 8 | 3.73 |  | MAR-23 | Charged on 06.01.2023
49 | Muddanur-Anantapur (3rd line) | S/C on D/C | 220 | 100 | 0 | 0 | 0 |  |  | DEC-16 | commissioned on Dec-16
50 | Muddanur (RTPP) - Dharmavaram | D/C | 220 | 200 | 0 | 0 | 0 |  |  |  | work cancelled
51 | Narketpally_Suryapet | S/C on D/C | 220 | 60 | 0 | 0 | 0 |  |  | DEC-16 | work does not pertains to APTRANSCO
52 | Narsapur-Doultabad | S/C | 220 | 15 | 0 | 0 | 0 |  |  | DEC-16 | does not pertains to APTRANSCO
53 | Narsapur-Manoharabad | S/C | 220 | 15 | 0 | 0 | 0 |  |  | DEC-16 | does not pertains to APTRANSCO
54 | Nirmal-Nandipeta | S/C | 220 | 20 | 0 | 0 | 0 |  |  | DEC-16 | does not pertains to APTRANSCO
55 | Nizamabad-Janakampeta | S/C | 220 | 10 | 0 | 0 | 0 |  |  | DEC-16 | does not pertains to APTRANSCO
56 | Oddugudem-Koyagudem | D/C | 220 | 20 | 0 | 0 | 0 |  |  | DEC-16 | does not pertains to APTRANSCO
57 | Oglapur(Warangal 400 kV SS)-Warangal 220 kV SS | D/C | 220 | 36 | 0 | 0 | 0 |  |  |  | does not pertains to APTRANSCO
58 | Peddapuram-Koruprolu | D/C | 220 | 130 | 0 | 0 | 0 |  |  | MAR-17 | Charged on March-17
59 | ppannadorapalem - Bobbili (Ckt-II) | D/C | 220 | 84 | 0 | 0 | 0 |  |  |  | Charged on 29.03.2017
60 | Somayajulapalli - Gani/Panyam S/S | D/C | 220 | 20 | 0 | 0 | 0 |  |  |  | Work not taken up
61 | Uravakonda - Kalyanduring | D/C | 220 | 100 | 160 | 160 | 160 | 100 | NOV-14 |  | Charged
62 | Badvel-Porumamilla (2nd Ckt) (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Charged on 21.08.2018
63 | LILO of Both Circuits of Badvel-Porumamilla at Porumamilla(GEC-I) | M/C | 132 | 4 | 0 | 0 | 0 |  |  |  | line charged on 28.8.19
64 | LILO of both circuits of Suzlon Wind-Jammalamadugu(132) at Jammalamadugu(400) (GEC-I) | M/C | 132 | 24 |  |  |  |  | MAR-18 | JUL-24 | Work in Progress.
65 | Penukonda(220) - Penukonda (132) | D/C | 132 | 20 | 0 | 0 | 0 |  |  |  | work cancelled
Transmission Corporation of Telangana Limited(TSTRANSCO)
1 | Vadarevu - Amangal | S/C | 765 | 240 | 0 | 0 | 0 | 0 |  | AUG-16
2 | 400kV QMDC line from 400kV Kachapur Switching STation -400/11kV Velgatoor S/S | D/C | 400 | 52 | 76 | 66 | 63 |  | JAN-23 | APR-24 | Works under progress.
3 | 400kV QMDC line from 400kV Kachapur Switchng station - 400/11kV Namapur (Pegadapally) S/S of line | D/C | 400 | 30 | 46 | 35 | 0 |  | JAN-23 | DEC-23 | Works under progress.
4 | 400kV QMDC line from 400kV Kachapur (Vadkapur) Swtiching Station - -400/220kV Gajwel S/S in Karimnagar (old) district | D/C | 400 | 14 | 23 | 14 | 0 |  | FEB-23 | DEC-23 | Works under progress.
5 | 400kV QMDC line from 400kV Velgatoor Switchyard -400/11kV Namapur (Pegadapally) s/s | D/C | 400 | 42 | 70 | 58 | 0 |  | JAN-23 | DEC-23 | Works under progress.
6 | 400kV QMDC line from existing 400/11kV Tippapur S/S - proposed 400/11kV Veljipur S/S | D/C | 400 | 5 | 18 | 17 | 16 | 0 | JAN-23 | MAR-24 | It is requested to update the line Ckt KM as 10.05 KM ( instead of 5 kM )
7 | 400kV QMDC line from Existing 400/13.8/11kV Chandiapur s/s -proposed Yellaipally 400/11kV S/S | D/C | 400 | 10 | 30 | 30 | 30 | 9.55 | NOV-23 | JUN-24 | Works under progress.
8 | 400KV QMDC line from exsiting 765/4000kV Nizamabad s/s (PGCIL) - Existing 400/13.8/11 Chandulapur S/S | D/C | 400 | 188 | 278 | 211 | 0 |  | FEB-23 | DEC-24 | Works under progress.
9 | 400kV QMDC line from STPP (Jaipur) - proposed 400kV S/S at Annaram pump house | D/C | 400 | 40 | 63 | 62 | 0 |  | NOV-22 | DEC-23 | Works under progress.
10 | Chandlapur SS to Tukkapur SS (TMDC) | D/C | 400 | 60 | 70 | 70 | 70 | 48.77 | SEP-17 | SEP-19 | 400kV TMDC Chandulapur - Tukkapur Line charged on 19.09.2019
11 | Damacherla TPP - Choutuppal | D/C | 400 | 300 |  |  |  |  | SEP-18
12 | Damacherla TPP - Dindi | D/C | 400 | 280 |  |  |  |  | SEP-18
13 | Damaracherla TPP - Jangaon | D/C | 400 | 310 |  |  |  |  | SEP-18
14 | Damaracherla TPP - Maheswaram (TS) | D/C | 400 | 310 |  |  |  |  | SEP-18
15 | Kethiredypally - AP-41 line (Twin HTLS Quad Conventional Towers) | D/C | 400 | 53 | 79 | 79 | 79 | 54.5 |  | DEC-21 | charged on 13.01.2022
16 | LILO of 400kV QMDC line from STPP Jaipur- Ramadugu 400/220/132kV s/s - Kachapur Switching Station line | D/C | 400 | 20 | 30 | 18 | 0 |  | FEB-23 | DEC-23 | Works under progress.
17 | LILO of 400kv QMDC line from Telegana STPP ntpc (2X800mw)-400/220/32kV Narsappur SS- Kachapur Switching Station | D/C | 400 | 8 | 13 | 7 | 0 |  | FEB-23 | DEC-23 | Works under progress.
18 | LILO of both Ckt. KTPP - Gajwel line to Chandlapur SS (TMDC) | M/C | 400 | 164 | 160 | 160 | 160 | 108.42 | SEP-17 | MAY-19 | Line Length was revised to 108.42 CKM and Commissioned on 16.05.2019
19 | LILO of both Ckt. of Nedunuru - Telangana STPP line to Yellampalli | M/C | 400 | 40 |  |  |  |  | SEP-17
20 | LILO of both Ckt. of SCCL - Gajwel line to Ramadugu SS (QMDC) | D/C | 400 | 72 | 97 | 97 | 97 | 72 | SEP-17 | MAY-18 | Commissioned on 06.05.2018
21 | LILO of both ckt. of SCCL - Ramadugu QMDC line to Yellampalli SS | M/C | 400 | 32 | 20 | 20 | 20 | 5.94 | SEP-17 | SEP-18 | Due to Change in Connectivity And Change in Name of Substation the line route was changed as LILO of both Ckts of SCCL-Nirmal QMDC line to 400/220/11 kV Sundilla SS.CKT-I Commissioned on 18.07.2018 and CKT-II Commissioned on 25.09.2018
22 | LILO of suryapet - Kethireddypalli (Manikonda) line to Uddandapur SS | D/C | 400 | 120 | 0 | 0 | 0 |  | SEP-18 |  | The connectivity was revised as per the Revised Administrative Approval.
23 | Narsapur SS to Tukkapur SS (TMDC) | D/C | 400 | 140 | 159 | 159 | 159 | 110.25 | SEP-17 | MAR-20 | 400kV TMDC Narsapur - Tukkapur Line charged on 21.03.2020
24 | NTPC - Ramadugu (QMDC) line | D/C | 400 | 104 | 161 | 161 | 161 | 98.23 | AUG-19 | JAN-20
25 | Ramadugu SS to Tippapur SS (QMDC) | D/C | 400 | 40 | 133 | 133 | 133 | 92.23 | SEP-17 | APR-19 | Line Length was revised to 92.23 CKM and Commissioned on 29.04.2019
26 | Ramdugu SS - Medaram SS (QMDC) | D/C | 400 | 42 | 59 | 59 | 59 | 40.7 | SEP-17 | AUG-18 | Line Length was revised to 40.70 CKM and Commissioned on 28.08.2018
27 | Sirichilla (NTPC) Common Point ) - Narsapur | D/C | 400 | 171 | 492 | 492 | 492 | 346.9 | FEB-19 | JAN-20
28 | Tippapur SS to Chandlapur SS (QMDC) | D/C | 400 | 42 | 59 | 59 | 59 | 40 | SEP-17 | MAY-19 | Line Length was revised to 40 CKM and Commissioned on 06.05.2019
29 | Vattem SS - Uddandapur SS | D/C | 400 | 100 | 103 | 103 | 103 | 67.84 | SEP-18 | DEC-23 | All works completed except gantry connections against the line length of 68.278 (ckm).
30 | Veltoor SS - Yedula SS | D/C | 400 | 94 | 139 | 139 | 139 | 94 | JUN-24 | OCT-23 | All works completed. Ready for charging. Statutory inspection is under progress
31 | Yadadri TPP Switchyard - Choutuppal S/S | D/C | 400 | 185 | 259 | 259 | 258 | 66.3 | JUN-24 | MAR-24 | Standing crops issue
32 | Yadadri TPP switchyard - Jangaon S/S | D/C | 400 | 278 | 402 | 367 | 283 | 44 | DEC-19 | FEB-24 | Works under progress.
33 | Yedula SS - Maheswaram SS | D/C | 400 | 260 | 0 | 0 | 0 |  | SEP-18 |  | The connectivity was revised as per the Revised Administrative Approval.
34 | YTPP Switchyard - 400kV Dindi SS | D/C | 400 | 208 | 290 | 290 | 290 | 208 | APR-24 | JUL-24 | Commissioned 06/24.
35 | Erection of 230 kV S/C line on D/C tower from Vellalaviduthi 400kV S/S - Nemmeli Thippayakudy 230 kV S/S | S/C | 230 | 23
36 | 220kV LILO line (2KM) -Proposed Mentrajpally from one of the circuit of under construction 220 KVDC line from 400/220kV S/S Dichpally to 220/11kV Manchippa s/s | S/C | 220 | 4 | 7 | 7 | 7 | 4 |  | SEP-23 | Commissioned on31.03.2022.
37 | 220KV Pulakurthy - Kakatiya Mega Textile Park | D/C | 220 | 60 | 110 | 99 | 89 | 18 | DEC-24 | DEC-24 | Works under progress. Foundations are pending due to Severe ROW
38 | 220kV Twin Moose D/C line from proposed 400/200kV s/s at Annaram Pump House - Existing 200/11kV s/s at Medigadda Pump House-48 KM | D/C | 220 | 41 | 155 | 129 | 118 |  | NOV-22 | JUN-24 | Original line length -40.494. Therefore, line CKM is 80.988Works under progress.
39 | Chilakallu - Narketpally | D/C | 220 | 25 | 42 | 42 | 42 | 25 |  | JUL-19 | It is 220kV LILO of Chilakallu - Narketpally to the 220kV Huzurnagar SS. This Line charged on 05.12.2018.
40 | Damaracherla -Huzurnagar line | D/C | 220 | 77 | 137 | 137 | 137 | 76.06 | MAY-24 | JUL-24 | Line commissioned on 26-08-2024
41 | Dichpally - Yacharam Thanda line | D/C | 220 | 54 | 97 | 97 | 97 | 54 | JUL-24 | JUL-24 | Works under progress.
42 | Existing 220kV from Proposed Damaracharla -Huzurnagar | D/C | 220 | 77 | 137 | 125 | 122 | 65 | JAN-22 | MAR-23 | This May be deleted as it is covered at SlNO 15.
43 | Ghanapur s/s -CPRI (220kV Monopole DC/SC line) | D/C+S/C | 220 | 9 | 0 | 0 | 0 |  | NOV-21 | MAY-22 | Permission from National highways, HGCL,Forest Authority under process
44 | Janagon -Husnabad | D/C | 220 | 79 | 139 | 139 | 139 | 73 | AUG-24 | JUL-24 | Works under progress.
45 | Kalwakurthy-Dindi 3rd line | S/C | 220 | 24 | 0 | 0 | 0 |  |  | DEC-16 | Proposal cancelled
46 | Kamareddy-Bhumpally | S/C | 220 | 15 | 0 | 0 | 0 |  |  | DEC-16 | Proposal cancelled
47 | Kethireddypalli (Manikonda) - Kanakamamidi DC line | D/C | 220 | 10 | 22 | 22 | 22 | 10 | JUN-17 |  | Line charged on 13.12.2018
48 | Kethireddypalli (Manikonda) SS to Kanakamamidi SS | M/C | 220 | 5 | 16 | 16 | 16 | 5 | SEP-17 |  | Line charged on 14.11.2018.
49 | LILO of 220kV XLPE UG cable Chandrayangutta - Imlibun to the proposed Chanchalguda | S/C | 220 | 1 | 0 | 0 | 0 | 1 | SEP-18 |  | Line charged on 26.02.2020
50 | LILO of Bhoothpur - Kalwakurthy at Thimmajipet | D/C | 220 | 2 | 4 | 4 | 4 | 1 |  | OCT-18 | Line charged on 07.06.2017
51 | LILO of Bhoothpur - Kalwakurthy at Thimmajipet (Ckt-II) | D/C | 220 | 2 | 4 | 4 | 4 | 1 |  | OCT-18 | Line charged on 07.06.2017
52 | LILO of both Ckts. of Dindi - Bonguluru to Madugula and Maheshwaram | D/C | 220 | 18 | 0 | 0 | 0 |  | SEP-17 |  | commissioned in 2017
53 | LILO of Budidampadu - Bhongiri at Waddekothapally | D/C | 220 | 14 |  |  |  |  | DEC-13
54 | LILO of Durshed - Seddipet at Nadunuru line | D/C | 220 | 20 |  |  |  |  | SEP-17
55 | LILO of existing RSS (Malayalapalli) - Bheemgal proposed line at Ramadugu (Karimnagar District) | S/C | 220 | 24 | 0 | 0 | 0 |  | SEP-19 |  | Work cancelled as new 220/11kV Rampur is taken up
56 | LILO of Ghanapur - Chandrayan Gutta to Kachavani Singaram | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-18 |  | Works yet to be taken up
57 | LILO of Ghanapur - Hayathnagar to Kachavani Singaram DC line | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-18 |  | Works yet to be taken up
58 | LILO to Mahabubabad from Existing 220kV at Budidampadu - Warangal DC line | M/C | 220 | 24 | 20 | 20 | 20 | 24 | JUN-17 |  | Line charged on 29.01.2018
59 | Marripally common point- Hayatnagar S/S XLPE cable | DC UG cable | 220 | 14 | 0 | 0 | 0 | 7.5 |  | MAY-19 | Works are under progress.13/14 Nos Cable joints completed and remaining works are under progress
60 | Narsapur to Bowrampet line (lattice structure) | M/C | 220 | 134 | 136 | 136 | 136 | 134.26 | SEP-24 | JUN-24 | work under progress
61 | Narsapur to Bowrampet (Monopole towers) | D/C | 220 | 7 | 23 | 15 | 14 |  | SEP-24 | JUN-24 | Works under progress.
62 | Narsapur to Bowrampet (XLPE UG Cable ) | D/C | 220 | 7 | 1 | 0 | 0 | 7 | SEP-24 | JUN-24 | Works under progress.
63 | Narsapur to Toopran & LILO of Gajwel - Minpur to Toopran line | D/C | 220 | 79 | 0 | 0 | 0 |  | DEC-17 |  | Works yet to be taken up
64 | Nirmal Upgraded 220/132kV Ranjal SS | D/C | 220 | 136 | 228 | 228 | 228 | 136 | NOV-17 |  | Line charged on 15.02.2020
65 | Parigi SS to Lakshmidevipalli | D/C | 220 | 20 |  |  |  |  | SEP-17
66 | RC Puram 400kV to Raidurg 220kV | D/C | 220 | 10 |  |  |  |  | SEP-17
67 | Thimmajipet to Jadcherla DC line | D/C | 220 | 40 | 0 | 0 | 0 |  | SEP-17 |  | As per the field condition, not yet taken up.
68 | Timmajipet - Balanagar | D/C | 220 | 60 | 0 | 0 | 0 |  | SEP-17 |  | Proposal cancelled
69 | Yeddumailram - Pargi | D/C | 220 | 135 | 137 | 137 | 137 | 90 |  | MAR-19 | Works are in progress
70 | Yellampalli - Goliwada | D/C | 220 | 1 | 0 | 0 | 0 | 0 | SEP-17 |  | Does not exist. Removed due to change in Pump House location
71 | Yellampalli - Sundla | D/C | 220 | 30 | 106 | 106 | 106 | 56 | SEP-17 | SEP-18 | Due to Change in Pump House Location the Connectivity is Revised as 220 kV TMDC Line from 400/220/11kV Sundilla(Yellampally ) to 220/11 kV Annaram SS.(Sundilla is renamed as annaram)
72 | Yellampalli to Kaleshwaram | D/C | 220 | 60 | 260 | 260 | 260 | 152 | SEP-17 | SEP-18 | Yellampally SS was renamed as 400/220/11 kV Sundilla SS and Kaleshwaram was renamed as 220/11 kV Medigadda SS,Hence 220 kV Line from 400/220/11 kV sundilla to 220/11 kV Medigadda was Commissioned on 29.09.2018 and total line length was revised to 152 CKM
TRIPURA STATE ELECTRICITY CORPORATION LIMITED(TSECL)
1 | Surajmani nagar-P.K.Bari | D/C | 400 | 260 | 0 | 0 | 0 | 0 |  | MAR-17 | Fund not yet tied up. Proposed under World Bank Financing /SPA/NEC.
2 | AGTP - Agartala line | D/C | 132
3 | AGTP - Kumarghat line | S/C | 132
4 | Gamai Tilla - Dhalabil | S/C | 132 | 31 | 107 | 101 | 78 | 17 |  | SEP-13 | ROW problems affected the work
5 | LILO of Rokia - Udaipur at Melaghat for connection to Monoarchak | D/C | 132 | 20 | 40 | 0 | 0 | 0 |  | JUN-15
6 | Monarchak - Surajmani Nagar | D/C | 132 | 43 | 154 | 145 | 128 | 15 |  | AUG-20 | RoW issues. TSECL has connected a portion of the said D/C line splitting the existing Rokhia - Udaipur 132 KV S/C line near Melaghar (12.178 Km distance from Monarchak) thereby connecting Monarchak with Rokhia and Udaipur sub-stations. The said arrangement has already been commissioned and is in operation w.e.f January 2015 for evacuation of Monarchak Power.
7 | P.K. Bari - Kanchanpur | S/C | 132 | 47 | 113 | 109 | 99 | 17 |  | MAR-15 | All works completed in non forest land. Stage- I clearance received and compliance for conditions completed.
8 | Surajmani Nagar - Badarghat | D/C | 132 | 6 | 0 | 0 | 0 | 0 |  | AUG-16 | Fund proposed in World Bank.
9 | Surajmani Nagar - Rokhia | D/C | 132 | 20 | 80 | 68 | 56 | 7 |  | DEC-18 | RoW issue
10 | Surajmani Nagar - Udaipur | D/C | 132 | 50 | 50 | 0 | 0 | 0 |  | JUN-15 | Proposed under NEC.
U.P. POWER TRANSMISSION CORPORATION LTD.(UPPTCL)
1 | Agra - Gr. Noida line | S/C | 765 | 200 | 411 | 411 | 411 | 159 |  |  | Line energized on 18.03.2021. To be deleted.
2 | Agra (UP) - Greater Noida (UP) | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | To be deleted
3 | Ghatampur TPS-Agra line | S/C | 765 | 240 | 579 | 579 | 579 | 229 |  |  | Line energised on 23.09.2024. To be deleted.
4 | Ghatampur TPS - Agra (UP) | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | Commissioned in Mar'2021
5 | Ghatampur TPS - Hapur | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | Line energized on 18.06.2022.
6 | Ghatampur TPS-Hapur Line | S/C | 765 | 400 | 1052 | 1052 | 1052 | 411 |  |  | Line Energized on 18.06.2022. To be deleted.
7 | LILO of Anpara D-Unnao line at Obra | S/C | 765 | 40 | 28 | 28 | 28 | 18 |  |  | Line energised on 20.04.2023
8 | LILO of Mainpuri - G Noida at Jawaharpur TPS | S/C | 765 | 30 | 66 | 66 | 66 | 25.84 |  |  | Line charged on 10.04.2023. Being constructed in TBCB mode by PGCIL.
9 | 400kV Shamli - Aligarh Line | D/C | 400 | 482 | 737 | 737 | 736 | 482 | MAY-24 | AUG-24 | Commissioned 07/24.
10 | Ballia (PG)-Rasra Line | S/C | 400 | 35 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
11 | Ghatampur TPS - Kanpur (PG) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Commissioned in Jan'2020
12 | Ghatampur TPS-Kanpur PG Line | D/C | 400 | 120 | 138 | 138 | 138 | 98 |  |  | Line Antitheft energized on 28.02.2020.
13 | Gonda - Shahjehanpur (PG) | D/C | 400 | 460 | 543 | 296 | 140 | 0 |  |  | To being constructed in TBCB mode
14 | Jawahapur TPS-Firozabad Line | D/C | 400 | 80 | 204 | 204 | 204 | 140.98 |  |  | Energized on 07,08.07.2021 . Being constructed in TBCB mode by PGCIL. To be deleted
15 | LILO of Aligarh - Shamli Line at Kurja (Power Plant) | D/C | 400 | 21 | 38 | 37 | 23 | 0 | JUL-24 | MAR-25 | Line Construction is in TBCB Mode.
16 | LILO of Ckt.II of 400 KV DC Quad Varanasi (PG) (Thathra) -Biharsharif at 400 kV Sahupuri SS (charged on 18-05-2024 however late reported by UPPTCL) | D/C | 400 | 53 | 0 | 0 | 0 | 53 |  | JUL-24 | Commissioned 06/24 (Late Reported).
17 | LILO of Ckt-I of 400kV Varanasi (PG (Thathra) - Biharshariff DC Line at 400kV Sahupuri | D/C | 400 | 52 | 92 | 92 | 92 | 52 | APR-24 | MAY-24 | Commissioned 04/24.
18 | LILO of one Ckt. 400kV (Twin Moose) Shamli -Aligarh line at THDC Khujra Power Plant | D/C | 400 | 26 | 38 | 37 | 23 | 0 |  |  | To be constructed in TBCB mode.
19 | Mathura - Jawaharpuram | D/C | 400 | 220 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . To be deleted.
20 | Obra-C-Jaunpur Line | D/C | 400 | 400 | 459 | 459 | 459 | 334 |  |  | Charged on 03.09.2023. To be deleted.
21 | Panki TPS - Panki s/s | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Please To be deleted.
22 | Roza TPS-Badaun Line | D/C | 400 | 90 | 221 | 221 | 221 | 85 |  |  | Line charged on 02.04.2021. Being constructed in TBCB mode by M/s Adani Transmission Ltd. To be deleted..
23 | Sambhal-Moradabad Line | D/C | 400 | 100 | 0 | 0 | 0 |  |  |  | There is no such line. Please remove this from the list.
24 | Simbholi-Meerut Line | D/C | 400 | 40 | 80 | 80 | 80 | 57.54 |  |  | Line energised on 25.03.2023. To be deleted.
25 | Simbholi-Muradnagar-II Line | D/C | 400 | 50 | 213 | 213 | 213 | 142.2 |  |  | Line charged on 03.11.2023. Being constructed in TBCB mode.
26 | Simbholi-Simbholi Line | D/C | 400 | 15 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted.
27 | Tanda TPS Extn- Basti (Q) | S/C | 400 | 43 | 137 | 137 | 137 | 87.72 | OCT-19 |  | Line energised on 14/03/2021. To be deleted.
28 | 220 kV Modipuram-II - Shamli Line | D/C | 220 | 150 | 262 | 262 | 262 | 150 | APR-24 | SEP-24 | Commissioned 08/24.
29 | Anandnagar-Maharajganj Line | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
30 | Aurai - Mizapur | S/C | 220 | 43 | 160 | 160 | 75 | 0 |  | SEP-25 | Due to blacklisting of M/s Isolux, 400kV Aurai S/s could no be feasible. The line from Mirzaput to Aurai extended by 06 km route length up to 220 kV S/s Bhadohi. Hence, the new name of this line will be 220kV Bhadohi- Mirzapur Line having 43 ckm length. The work is held up due to variation in fund availibility and approval of the same.
31 | Aurai - Phoolpur | S/C | 220 | 71 | 229 | 229 | 175 | 42 |  | OCT-25 | Due to blacklisting of M/s Isolux, 400kV Aurai S/s could no be feasible. The line from Phoolpur to Aurai extended by 08 km route length up to 220 kV S/s Bhadohi. Hence, the new name of this line will be 220kV Bhadohi- Phoolpur Line having 69 ckm length. The work is held up due to variation in fund availibility and approval of the same.
32 | Badhaikalan (Muzaffarnagar) - Shamli line | D/C | 220 | 66 | 113 | 113 | 105 | 56 | AUG-24 | FEB-25 | Supply of Tower parts is pending and ROW issues,being resolved with the help of District Administration..
33 | Bah (Agra) - Sirsaganj (Firozabad) line (GEC-II) | S/C | 220 | 0 | 140 | 68 | 15 | 0 |  |  | Will be constructed in deposit scheme after receipt of fund from UPNEDA/LSPDCL.
34 | Bhadrekhi (Orai) - Bah (Agra) line (GEC-II) | S/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Line has been cancelled by UPPTCL as per decision in TWC meeting on 09.11.2022.
35 | Bhadrekhi (Orai) - Sikandera (Kanpur dehat) line (GEC-II) | S/C | 220 | 0 | 182 | 93 | 83 | 0 |  |  | Will be constructed in deposit scheme after receipt of fund from UPNEDA/LSPDCL.
36 | Bhopal Road-Khatauli Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
37 | Darshan Nagar GIS to Sohawal (Tower NO. 152 of Gonda line) | S/C | 220 | 1 | 2 | 2 | 2 | 1 | MAY-24 | AUG-24 | Commissioned 07/24.
38 | Firozabad (400)-Tundla | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
39 | Gorakhpur-Anandnagar Line | D/C | 220 | 100 | 0 | 0 | 0 |  |  |  | Line Cancelled by TWC on dt. 09.09.2020. To be deleted.
40 | Hamirppur-Banda Line | D/C | 220 | 140 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
41 | Hamirpur-Sarh Line | D/C | 220 | 140 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
42 | Hardoi Road-Lucknow Line | D/C | 220 | 20 | 20 | 39 | 39 | 19.8 |  |  | Commissioned in March-2022. To be deleted.
43 | Hardoi Road-Sandila Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
44 | Indirapuram - Pratap Vihar | D/C | 220 | 16 | 38 | 33 | 0 | 9.6 |  | DEC-24 | Rerouting of line is under process.
45 | Indrapuram (400 kV)- Sector-62 DC line (Under Ground Cable) | D/C | 220 | 5 | 0 | 0 | 0 |  | DEC-24 | JAN-25 | Cable laying for NHAI crossing is under progress.
46 | Jehta (400) - Mallawaan line | D/C | 220 | 160 | 266 | 266 | 266 | 157.82 | JUN-23 |  | Line charged on 06.01.2024. To be deleted.
47 | LILO of 220 kV C.B. Ganj (220)- Budaun (220) line | D/C | 220 | 2 | 4 | 4 | 4 | 2 | MAR-21 |  | Commissioned in March-2021. To be deleted.
48 | LILO of 220 kV Nara- Jansath line at Meerut(765) | D/C | 220 | 95 | 150 | 150 | 148 | 80 | JUN-24 | FEB-25 | RoW at location no. 8/3. Matter is being resolved with the help of District Administration.
49 | LILO of 220 kV Pura Chandausi (220) - Budaun (220) line at Budaun | D/C | 220 | 31 | 58 | 58 | 58 | 36.79 | MAR-21 |  | Commissioned in March-2021. To be deleted.
50 | LILO of 220kV Rasra (220) - Gaipur S/C line at Rasra | D/C | 220 | 26 | 49 | 49 | 49 | 26.49 | APR-22 |  | Commissioned in March-2021. To be deleted.
51 | LILO of Agra-Bharatpur Line | D/C | 220 | 20 | 0 | 0 | 0 |  |  |  | PGCIL scope. Line is energised.
52 | LILO of Badaun(400 kV)- C.B. Ganj line at Badaun Road | D/C | 220 | 1 | 3 | 3 | 3 | 1 | JUN-24 | NOV-24 | Commissioned 10/24.
53 | LILO of Banda-Karvi at Chittrakoot Line | S/C | 220 | 8 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
54 | LILO of Nibkarori-Mainpuri PG Fatehgarh Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | There is no line as such a this name . Please to be deleted .
55 | LILO of One ckt Laitpur TPS -Dunara line at Babina | D/C | 220 | 15 | 25 | 25 | 25 | 14.54 | MAR-21 |  | Commissioned in August-2019. To be deleted.
56 | LILO of one Ckt. of Chhata (Mathura) - Manth (400) at Vrindawan | D/C | 220 | 46 | 74 | 74 | 74 | 44 | MAR-21 |  | Commissioned in August-2020. To be deleted.
57 | LILO of Saharanpur-Nakur Line | S/C | 220 | 10 | 13 | 13 | 13 | 6.7 |  |  | Commissioned in May-2018. To be deleted.
58 | LILO of Unnao(400 kV)- Bithoor line at Trans Ganga city (220 kV) | D/C | 220 | 9 | 19 | 19 | 17 | 2 | AUG-24 | JAN-25 | RoW issue resolved with NHAI and survey for diverted route completed and approval for additional supply and work is in process.
59 | Mallawan (220) - Hardoi(220) | D/C | 220 | 81 | 143 | 143 | 143 | 86.29 | MAY-22 |  | Energised on 04/08/2022. To be deleted.
60 | Meerut by pass-Modipuram Line | D/C | 220 | 70 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. To be deleted.
61 | Meerut-Gr. Noida-II Line | D/C | 220 | 200 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. To be deleted.
62 | Modipura-II-Bagpat PG Line | D/C | 220 | 70 | 133 | 133 | 133 | 76.6 |  |  | Commissioned in 30.09.2022. To be deleted.
63 | Modipuram-II-Modipuram Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted.
64 | Muradabad-Tajpur Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted.
65 | Nehtaur-Tajpur Line | D/C | 220 | 100 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted.
66 | Nighasan-Lakhimpur Line | D/C | 220 | 120 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted.
67 | Rae Bareli (400)-(Amethi (220) | D/C | 220 | 89 | 147 | 147 | 147 | 89.35 | OCT-22 |  | Line Antitheft charged on 28.10.2021.
68 | Raebareli (400) -Bachhrawan line | D/C | 220 | 162 | 273 | 273 | 273 | 162 | JUN-24 | JAN-25 | Line will be anti theft charged after getting statutory clearances as bay is not ready at Raebareli end.
69 | Shamli (400) - Deoband line | D/C | 220 | 93 | 150 | 150 | 149 | 79 | MAY-24 | FEB-25 | ROW issue at 34/0,35/0,36/0, being resolved with the help of District Administration.
70 | Shamli-Khatauli Line | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | There is no line as such a this name. Please To be deleted
71 | 132 kV D/C Agra cantt. - 400 kV Agra(South) | D/C | 132 | 24.08 | 44 | 44 | 44 | 24.32 |  |  | Line energised on 25/07/2017. To be deleted
72 | Barkhera (Bajaj) - Dohna | D/C | 132 |  | 203 | 203 | 203 | 128.96 |  |  | Line energised on 13.09.2017. To be deleted.
73 | Bhadrekhi (Orai) - Jalaun line (GEC-II) | S/C | 132 | 0 | 108 | 108 | 108 | 36.65 |  |  | Commissioned in June-2021. To be deleted.
74 | Dakore (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 105 | 105 | 105 | 69.68 |  |  | Commissioned in April-2018. To be deleted.
75 | Dumariaganj- - Utraula | S/C | 132 |  | 114 | 114 | 114 | 40 |  |  | Commissioned in January-2019. To be deleted.
76 | Gujrai (Solar Plant) - Pukhraya line (GEC-II) | D/C | 132 | 0 | 72 | 72 | 72 | 38.4 |  |  | Line energised on 22.02.2024. To be deleted.
77 | Gurrah (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 30 | 30 | 30 | 16.76 |  |  | Line energised on 02.08.2023. To be deleted.
78 | Jigna - Dadar Vijaypur (Solar plant) Mirzapur line (GEC-II) | D/C | 132 | 0 | 38 | 38 | 38 | 14.9 |  |  | Commissioned in March-2018. To be deleted.
79 | LILO of 132 kV Bodla - Kheragarh at 400 kV Agra (South) | D/C | 132 | 11.9 | 19 | 19 | 19 | 11.9 |  |  | Commissioned in July-2017. To be deleted.
80 | LILO of 132 kV Kirawaki-Mathura at 400 kV Agra (South) | D/C | 132 | 11.5 | 25 | 25 | 25 | 5.6 |  |  | Commissioned in November-2017. To be deleted.
81 | LILO of 132 kV Shamshabad-Kheragarh at 400 kV Agra(South) | D/C | 132 | 11.95 | 22 | 22 | 22 | 11.95 |  |  | Commissioned in July-2017. To be deleted.
82 | LILO of Makreccha (Solar plant) - Bhadrekhi (Orai) line at Baghauli (Solar Plant) (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Will be constructed in deposit scheme after receipt of fund from UPNEDA/LSPDCL.
83 | Makreccha (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | LOI issued on 05.05.2022. Line will be alloted after reciept of fund from UPNEDA/ LSPDCL.
84 | Meja - Kosda Kala (Solar plant) Meja line (GEC-II) | D/C | 132 | 0 | 132 | 132 | 132 | 30 |  |  | Commissioned in February-2018. To be deleted.
85 | Parasan (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 | 18.15 |  |  | Commissioned on 14.09.2022. To be deleted.
UTTARAKHAND POWER CORPORATION LIMITED(UKPCL)
1 | Pipalkoti-Srinagar Line | D/C | 400 | 173 |  |  |  |  | SEP-24
2 | Vishnugad-Pipalkoti Line | D/C | 400 | 36 |  |  |  |  | DEC-24
3 | Balance work of Baramwari -Srinagar line (Single Zebra conductor from Interconnection point of Singoli Bhatwari HEP to Baramwari) | D/C | 220 | 31 |  |  |  |  | JUN-24
4 | Baramwari (GIS)-Srinagar S/S | D/C | 220 | 180 | 228 | 210 | 182 | 72 | DEC-19 | DEC-19 | Baramwari  Srinagar 220 kV D/C line and LILO of this line at Singoli Bhatwari HEP are required for transfer of power from Singoli Bhatwari HEP up to Srinagar pooling station.But after the works of Phata Byung (2x38 MW) being severely affected due to flash floods in June, 2013 and all works being stalled since July, 2017 due to Funds constraints with the developer , this Baramwari switching station is not being constructed, therefore currently above line is being constructed from 400kV S/s Srinagar to interconnection point of 99MW Singoli Bhatwari HEP.This line is of 150 Ckm out of which 72 Ckm stringing have been completed. Also out of 220 tower locations, 210 fdns have been completed and 182 towers have been erected
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED(WBSETCL)
1 | LILO of Gokarna-New Chanditala Transmission Line at proposed Satgachia 400 KV GIS S/S | D/C | 400 | 11 | 22 | 19 | 17 | 0 | JAN-25 | JAN-25
2 | Bankura - New Bishnupur line (GEC-II) | D/C | 220 | 0
3 | Bhangar (UG Cable ) (PGCIL) -New Town-IIC (GIS) S/S | D/C | 220 | 18 | 0 | 0 | 0 |  | OCT-22 | MAR-23
4 | Connectivity between New Bishnupur - Raghunathpur New Bishnupur-Hura Hura-Raghunathpur and connectivity between STPS and Hura 220kV s/s | S/C | 220 | 1 | 2 | 2 | 0 | 0 | OCT-24 | MAR-25 | Online tower erection and stringing activity may be taken up after receiving shutdown of the following existing lines: 220 KV D/C STPS to New Bishnupur T/L and 220 KV Raghunathpur to Hura T/L
5 | East Mednipur - Kharagpur line (GEC-II) | D/C | 220 | 0
6 | Establishment of Barasat - Rajarhat (PG) utilising Barasat - Kasba | D/C | 220 | 62 | [5 empty] | MAR-18
7 | Establishment of Rajarhat (PG) - New Town-IIIutilishing Barasat - Kasba | D/C | 220 | 2 | [5 empty] | MAR-18
8 | LILO of 220 kV Durgapur -DPL unit-8 line at AB Zone 220 kV Substation. | D/C | 220 | 8 | 14 | 14 | 14 | 8 | JUL-24 | DEC-24 | Commissioned 11/24.
9 | LILO of 229kV Domjur-Arambagh line at proposed Khanakul 220kV GIS | D/C | 220 | 11 | 47 | 45 | 45 | 14.82 | MAR-25 | MAR-25 | Loc. Nos.- 9/0; 9D/0- Severe hindrance from Landowners.
10 | LILO of Arambag - Domjur at Mayapur | D/C | 220 | 36 | [5 empty] | MAR-20
11 | LILO of Birpara -Alipurduar line (PGCIL) at proposed line at Falakata s/s | D/C | 220 | 17 | 39 | 39 | 37 | 14.06 | SEP-24 | MAR-25 | All tower foundations are completed only 2 Nos. online tower erection at AP 15/0 & 21A/0 are pending for want of S/D of existing PGCIL 220 KV Line. Falakata Substation is not ready.
12 | LILO of BKTPP - Satgachia at Mahachhanda | D/C | 220 | 14 | [5 empty] | MAR-19
13 | LILO ofc arambag - Midnapur at C.K.Road | D/C | 220 | 232 | [5 empty] | MAR-21
14 | LILO of Existing STPS - JK Nagar 220kV line at Asansol 220kV S/S | D/C | 220 | 62 | 124 | 120 | 112 | 46.42 | JUL-24 | DEC-24 | Severe ROW issue in loc- 46/0, 50/0, 49/2.
15 | LILO of KTPP-Howrah 220 kV D/C Line at Proposed Food Park 220/132 KV GIS S/S | M/C | 220 | 2 | 0 | 0 | 0 | 2 |  | SEP-24 | Commissioned 08/24.
16 | LILO of KTPP- Jangalpur 220 kV D/C line at Food Park 220 kV Substation | D/C | 220 | 2 | 0 | 0 | 0 | 2 |  | AUG-24 | Commissioned 07/24.
17 | LILO of Sadaipur - Gokarna at Kotasur | D/C | 220 | 8 | [5 empty] | MAR-20
18 | Rajarhat (PG) - New Town-II | D/C on M/C | 220 | 56 | 58 | 2 | 2 | 1.09 |  | MAR-19 | Work of main line yet to be commenced due to mass resistance by the villagers
19 | STPS - Raghunathpur | D/C | 220 | 45 | 94 | 94 | 94 | 46.3 | MAR-25 | MAR-25 | Awaiting approval for hotline power line crossing for AP-9/0 to AP-10/0.
20 | West Mednipur - Kharagpur line (GEC-II) | D/C | 220 | 0
21 | LILO of 132 kV One Ckt of Rammam-II - NBU at Rammam -III HEP | D/C | 132 | 20 | 0 | 0 | 0 |  | APR-19 | DEC-21 | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
22 | Rammam III - Chalsa | D/C | 132 | 130 | 0 | 0 | 0 |  | APR-19 | DEC-21 | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
ADANI Energy solution Limited(ADANI)
1 | KPS2 (GIS) - Lakadia | D/C | 765 | 0
2 | Narendra New (GIS) - Pune (GIS) (line with 1x330MVA r switchable line reactor (SLR) on each ckt. at both ends) | D/C | 765 | 636 |  |  |  |  | DEC-24
3 | North Karanpura - Gaya line (NKTL - TBCB) | D/C | 400 | 196 | 286 | 140 | 132 | 37 |  |  | Work in progress.
Adani Renewable Energy Park Rajasthan Limited(AREPRL)
1 | Bhadla IV SP - Bhadla Pooling station line (GEC-II) | D/C | 220 | 0
2 | Fatehgarh Solar Park - Fatehgarh Pooling Station line (GEC-II) | D/C | 220 | 0
3 | SPP - Bhadla (PS) (GEC-II) | D/C | 220 | 0
Apraava Energy Pvt. Ltd.(APRAAVA)
1 | Fatehgarh-3- Bhadla-3 400kV D.C line (Quad) line | D/C | 400 | 446 |  |  |  |  | FEB-25
2 | Fatehgarh-4 - Fatehgarh-3 PS 400kV D/c | D/C | 400 | 42
ATHENA CHHATTISGARH POWER LIMITED(ACPL)
1 | LILO of one ckt of MSCTL - Chandrapur at Singhitrai | D/C | 400
BAJAJ ENERGY PVT. LTD.(BEPL)
1 | Balrampur-Utraula line | D/C | 132 | [7 empty] | Existing line.
CORPORATE POWER LTD.(CPL)
1 | Corporate TPP - Jharkhand Pooling Station | D/C | 400 | 6 | 11 |  |  |  |  | AUG-16
2 | Latehar - Namkum | D/C | 400 | 216 | 320 | 293 | 274 | 132 |  | AUG-16
D.B. POWER CORP. LTD.(DBPCL)
1 | LILO of Raigarh - Raipur (3rd Ckt) at Baradhara TPP ( Interim arrangement) | D/C | 400 | 30 | 44 | 44 | 44 | 30 |  | MAY-13 | Line completed. (Interim)
DIRANG ENERGY PVT. LTD.(DEPL)
1 | Gongri - Dinchang Pooling Station | D/C | 220
ESSAR POWER TRANSMISSION CO. LTD.(EPTCL)
1 | Navbharat TPP - Angul P.S. (PG) | D/C | 400
2 | Tori - Jhharkhand Pooling Station | D/C | 400
Essel Infraprojects Ltd.(ESSEL)
1 | Hyderabad - Kurnool (WKTL- TBCB) | D/C | 765 | 332 | 422 | 337 | 183 |  | FEB-20 | FEB-20 | Work hampered due to severe RoW issue in the stretch of AP 27  AP 29, AP 60 A AP 60 B and AP 66  AP 67.
2 | Warangal (New) - Chilakaluripeta (WKTL - TBCB) | D/C | 765 | 395 | 565 | 446 | 341 |  | FEB-20 | FEB-20 | Severe RoW issue existing in the stretch of AP 10  AP 11, AP 14- AP 15, AP 25  AP 28, AP 52- AP 53, AP 55  AP 56, AP 63  63/12, AP 76  AP 77, AP 84- AP 85 and AP 89  AP 90. Court Case: 04 no. of tower locations has been traversing though the proposed land area of M/s Emami Cement Ltd., out of which the 04 no. of foundations and 03 nos of erections are already completed. At this point of time, M/s Emami Cement Ltd. moved to High Court of Hyderabad for seeking Order to remove WKTL transmission towers along with direction to re-route the transmission line. At present this matter is under consideration of Honble High Court, Hyderabad and next date is yet to schedule. Forest Details of Tr. Line Falling under Forest: Forest area affected (ha):18.442 ha (2.75 Kms) in Andhra pradesh .Forest proposals sub on :23.08.2017. Stage I forest approval granted on 28.11.18.
3 | Warangal (New) - Hyderabad (WKTL - TBCB) | D/C | 765 | 265 | 344 | 312 | 247 |  | DEC-19 | DEC-19 |  RoW issue: In the stretch of AP 34 - AP 35, AP 37- AP 38, AP 41- AP 42, AP 46/0, AP 54/2, AP 17/3 and AP 21/6. At loc. nos. 47/2 and 47/3, locals have removed the stubs by using JCB. A FIR in this regard has been lodged with local Police Station. Court Case:  Land Owner of location no. 2/6 has approached High Court of Telangana. The Court has granted the stay on work. Further on hearing held on 07th June 2018, the Court adjourned and as on date the matter is still pending for scrutiny.  Land owner for the stretch between the location no. 30 to 31 has approached the District Court (Nalgonda) to accord permanent injunction. On the hearing held on 14.03.2019, , the Court scheduled next date of hearing on 01.05.2019 in this matter. In such situation, the work is at stand still at this location effectively from 20th Mar 2018.
4 | Warora (Pool) - Warangal (New) (WKTL - TBCB) | D/C | 765 | 645 | 827 | 773 | 423 | 58.6 | DEC-19 | NOV-19 |  Severe RoW issues.; Forest area affected (ha): 19.793 ha (2.954 Kms) in Maharastra and 47.592 ha (7.103 Kms) in Telangana. Forest proposals submitted on 4th Aug 17 for Maharashtra and on 23 Aug 17 for Telangana. Current status: Maharashtra Stage I received on 05.02.18. The Telangana stage I approval received on 13.12.2018 ; WIld life approval : Proposal forwarded by State Government to Member Secretary (NBWL) on 20.11.2018. Proposal forwarded to NTCA for their recommendation and MoEF&CC asked State Govt. to submit SBWL MoM, which is still awaited for further processing & consideration in next NBWL meeting.The work execution in under Maharashtra is severely affected due to farmer agitation demanding higher compensation for the construction of transmission line at their fields. Court Case- at loc. no. 89/8 in terms of stay order granted by Bombay High Court. The matter is listed on 15.01.2020.
5 | Koteshwar (PS) - Rishikesh (HTLS) (NRSS-XXXVITL-TBCB) | D/C | 400 | 81 | 106 | 16 | 0 |  | DEC-19 | DEC-19 | 1. Consent from Indian Drug and Pharmaceuticals Ltd. (IDPL) , Rishikesh for traversing 400 kV D/C Koteshwar-Rishikesh line through IDPL premises is awaited.Pending NOC from IDP (Rishikesh), the Forest Deptt. is not ready to accept the forest diversion proposal because all 16 no. of tower locations are falling inside the IDPL lease hold area, which belongs to the forest deptt.2. DFO-Tehri directed us to divert from our existing transmission line route, which was earlier approved and confirmed by Forest Range officer through verification of land schedule and DGPS survey in Jan-2018. 3) Severe RoW issues are existing at loc. No. 1/0, 2/0, 3/0, 4/0, 13/0, 14/0, 14/1, 15/0, 16/0, 42/0, 43/0, 44/0, 48/0, 48/1 and 49/0 .
6 | Sohwal - Lucknow (TTL -TBCB) | D/C | 400 | 240 | 0 | 0 | 0 |  |  |  | MoP has already dropped the project.
7 | Tanda - Sohwal (TTL - TBCB) | D/C | 400 | 186 | 0 | 0 | 0 |  |  |  | MoP has already dropped the project.
8 | Warangal (New) - Warangal (Existing) (Q) (WKTL - TBCB) | D/C | 400 | 95 | 130 | 9 | 0 |  | FEB-20 | FEB-20 | Forest : Nil
GATI INFRASTRUCTURE PRIVATE LIMITED(GIPL)
1 | LILO of one circuit of Chujachen - Rangpo line at Bhasmay | 2xS/C | 220 | 10 | [5 empty] | MAY-18 | Work yet to be awarded.
GMR ENERGY LIMITED(GMR ENERG)
1 | LILO of Talchar -Meramundli at Kamalanga TPP | D/C | 400 | 1 | 3 | 3 | 3 | 1 |  | MAY-12 | For start up power,work completed 5/12.
2 | Alaknanda HEP - Joshimath | D/C | 220
GUPTA ENERGY PVT. LTD.(GEPL)
1 | LILO of one ckt of Bhadrawati -Parli at GEPL TPS | D/C | 400
IDEAL ENERGY PROJECTS LTD.(IEPL)
1 | LILO of Mouda - Wardha at Bela | D/C | 400 | 0.3 | 2 | 2 | 2 | 0.3 |  | NOV-12 | Completed (Interim)
IND BHARATH POWER INFRA LIMITED(IBPIL)
1 | Ind Barath TPP - Tuticorin (PS) | D/C | 400 | 200
2 | LILO of Rouekila - Raigarh at Ind Barath | D/C | 400 | 47 | 72 | 72 | 72 | 47 |  | JUN-15
ISPAT ENERGY LTD(ISPAT)
1 | Haldia TPP - Egra | D/C | 220 | 180 | [6 empty] | Under planning stage by WBSETCL.
JAIN ENERGY TRADING LTD(JAIN ETL)
1 | Jain Energy TPS - Dharamjaygarh Korba Pooling station | D/C | 400 | [6 empty] | MAR-17
JAL POWER CORP. LTD.(JPCL)
1 | Rangit IV - New Melli line | D/C | 220 | 6.6 | 15 |  |  |  |  | MAR-19 | Work of 220kV line has been awarded to M/s. Ashish Infratech and completion period is 8 months from start of work. Generation project will take about 2? years for completion as against 8 months for completion of associated transmission line, there will be no mismatch for evacuation of power. It may also be mentioned that route survey of transmission line has been completed and design work of transmission system including towers (15 nos.) has also been completed. 220kV GIS bays at PGCIL substation at New Melli have also been awarded to M/s. PGCIL as deposit work. Line length is 3.3 KM. Associated transmission system comprises of 220kV GIS in PH building, 3.3 km long 220kV D/C line from PH to PGCIL pooling station at New Melli. Work for 220kV GIS substation at PH has been awarded to M/s. Siemens and GIS equipment has already been delivered at site.
KALPATARU POWER TRANSMISSION LIMITED(KPTL)
1 | LILO from Kothipura - Tubinakere at Channapatna | D/C | 220 | 7
KORBA WEST POWER COMPANY LIMITED(KWPCL)
1 | LILO of on Ckt of Raigarh - Raipur at Avantha Bhandar (Korba west ) TPS | D/C | 400 | 10 | 22 | 22 | 22 | 10 |  | DEC-13 | Interim arrangement.
KVK ENERGY PVT. LTD.(KVK)
1 | LILO of Mendasal - Baripada at Nilanchal TPP | D/C | 400 | 16 | 0 | 0 | 0 | 0 |  | JUN-16 | Work yet to Start.
LANCO ENERGY (P) LTD,.(LEPP)
1 | LILO of Seoni - Wardha at Lanco Vidarbha TPS | D/C | 765 | 15 | 16 |  |  |  |  | MAR-17
2 | Babandh TPP - Angul Pooling Station | D/C | 400 | 48 | 72 | 0 | 0 | 0 |  | DEC-16 | Work yet to start.
3 | Lanco Amarkantak - Champa Pooling Station | D/C | 400 | 95 | 158 | 96 | 12 | 0 |  | JUN-16
4 | Phata HEP-Baramwari (Rudrpur) | D/C | 220 | 8 | 20 | 0 | 0 | 0 |  | DEC-16
5 | Routing of one circuit of Jorthong - New Melli via Rangit - IV | D/C | 220 | [6 empty] | MAR-19 | Work in generation project is stopped for since 2013.
6 | Teesta VI HEP - Rangpo Pooling Station | D/C | 220 | 25 | [6 empty] | Detail survey completed section 164 approval received. Work yet to started.
MALANA POWER COMPANY LIMITED(MPCL)
1 | Ka Dogri - Jangi Pooling Station | D/C | 400
2 | Chango Yangthang - Ka Dogri Pooling Station | D/C | 220
Megha Engineering & Infrastructures Limited(MEGHA)
1 | KPS1-Khavda PS GIS (KPS2) 765kV D/C line | D/C | 765 | 42 |  |  |  |  | FEB-25
2 | 400kV Khandhukal -Rampura Transmission line | D/C | 400 | 384 |  |  |  |  | SEP-24
3 | Khandkha (Srinagar) - Rampura (Kashipur ) line (Twin HTLS) | D/C | 400 | 384
MONNET POWER COMPANY LIMITED(MPCL)
1 | Malibrahmani - Angul | D/C | 400 | 62 | 108 | 100 | 80 | 20 |  | JUL-16
NORTH KARANPURA TRANSMISSION CO. LTD.(NKTCL)
1 | Bareilly - Meerut (NKTL - TBCB) | S/C | 765 | 240 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
2 | Lucknow - Bareilly (NKTL - TBCB) | S/C | 765 | 220 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
3 | Agra - Gurgaon (NKTL - TBCB) | D/C | 400 | 220 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
4 | Gurgaon - Gurgaon (PG) (NKTL - TBCB) | D/C | 400 | 20 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
5 | Sipat/Korba (PS)  Seoni (NKTL - TBCB) | S/C | 400 | 334 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
NSL NAGAPATNAM POWER PVT. LTD.(NSLNPPL)
1 | NSL TPP - Angul | D/C | 400 | 46 | 0 | 0 | 0 | 0 |  |  | Project Authority intimated that PGCIL yet to award construction of work.
2 | LILO of Kasang - Bhbaba at Tidong-I | D/C | 220 | 32 | 57 | 44 | 40 |  |  | DEC-23 | Being Executed by M/s Statkraft. St-II clearance obtained for 17 locations in Nov-22.
RELIANCE POWER TRANSMISSION LTD.(RPTL)
1 | Moti Khavdi TPP - Jam Nagar | D/C | 400
2 | Sohwal - Lucknow Line (TBCB-TTCL) | D/C | 400 | 176
3 | Tanda - Sohwal Line (TBCB-TTCL) | D/C | 400 | 173
Renew Surya Vihaan Private Limited (Renew Surya Vihaan)
1 | ReNew Surya Aayan Private Limited solar power plant - Fatehgarh-III PS 220 kV S/C line on D/c Tower | S/C | 220 | 9
ReNew Transmission Ventures Private Limited(RENEW)
1 | 400 kV D/C Gadag PS-Narendra (New) line (Trans. Scheme for Solar Energy Zone in Gadag (1000MW) Karnataka-Part-A Phase-I) | D/C | 400 | 187 | 232 | 232 | 232 | 187 | MAY-24 | OCT-24 | Commissioned 09/24.
2 | Gadag PS- Koppal (PS) line | D/C | 400 | 100 |  |  |  |  | AUG-23
RKM POWERGEN PVT. LIMITED(RKMPPL)
1 | LILO of Raigarh (Kotra) - Raipur at Uchpinda (Interim Arrangement) | D/C | 400 |  | 73 | 73 | 73 | 38.99 |  |  | Commissioned (Interim Arrangement). De-LILO activity completed.
Saurya Urja Company of Rajasthan Ltd(SUCRL)
1 | SUCRL Solar Park - Bhadla | D/C | 220 | 18 | 0 | 0 | 0 | 18 |  | APR-23 | Commissioned 03/23.
Shekhawati Transmission Service Company Limited(SKHWTTSCL)
1 | Jhunjhunu - Nawalgarh line | S/C | 220 | 32 | 108 | 77 | 73 | 0 | FEB-15 | DEC-20 | court case pending, severe ROW problem, Railway crossing pending.Funds problem from PFC.
2 | Sikar - Nawalgarh line | S/C | 220 | 22 | 76 | 55 | 48 | 0 | FEB-15 | DEC-20 | court case pending, severe ROW problem, Railway crossing pending.Fund problem from PFC.
SIKKIM HYDRO POWER LIMITED(SHPL)
1 | LILO of one ckt of Legship - New Melli at Rangit-II | D/C | 220
South East UP Power Transmission Company Limited(SEUPPTCL)
1 | Mainpuri - Bara Ckt-I | S/C | 765 | 375 | 889 | 613 | 346 | 0 |  | JUN-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
2 | Mainpuri - Unnao (Quad) | S/C | 765 | 188 | 449 | 380 | 274 | 0 |  | JUL-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
3 | Bara - Karchana | D/C | 400 | 80 | 124 | 0 | 0 | 0 |  | JUN-16 | Karchana gantry not finalised. The project is at stand still pending of a time extension requested to UPPTCL in June 2015
4 | Gonda - Shahjanpur | D/C | 400 | 442 | 542 | 295 | 140 | 0 |  | DEC-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
5 | LILO of Obra - Sultanpur at Aurai | S/C | 400 | 1 | 5 | 0 | 0 | 0 |  | JUN-16 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
6 | LILO of Sarojini Nagar - Kursi RD at Sultanpur RD | D/C | 400 | 14 | 18 | 0 | 0 |  |  | JUL-16 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
7 | Rewa Road - Karchana | D/C | 400 | 58 | 102 | 0 | 0 |  |  | OCT-16 | Karchana gantry not defined. The project is at stand still pending of a time extension requested to UPPTCL in June 2015
8 | Tanda TPS Extn - Gonda | S/C | 400 | 100 | 241 | 97 | 54 | 0 |  | OCT-18 | "Work is standstill for more than a year due to poor financial health of SEUPPTCL, the transmission service provider, owned by M/s Isolux. The line is a part of TBCB project awarded to M/s Isolux. UPPTCL representative informed that GoUP is considering to take over transmission project and evaluation of completed work is under progress. Bids for valuers have been invited by M/s PFC. Valuation is under progress. Final decision will be taken after valuation."
STERLITE GRID LTD.(STERLITE)
1 | Fatehgarh-III PS - Beawar 765 kV D/C line (Rajasthan (20GW) under Phase-III Part F) | D/C | 765 | 635 |  |  |  |  | MAR-25
2 | Fatehgar III - Beawar 765kV line (Rajasthan (20GW) under Phase-III Part -G) | D/C | 765 | 630 |  |  |  |  | MAR-25
3 | LILO of both Ckts. of Ajmer - Chittorgarh 765kV D/C at Beawar (Rajasthan (20GW) under Phase-III Part F) | D/C | 765 | 136
4 | Bongaigaon (POWERGRID) - Nangalbibra (Twin ACSR Moose) line | D/C | 400 | 246 | 311 | 311 | 311 | 246 | JUN-24 |  | Ready for commissioning on Oct-2024.
5 | LILO of 400kV Kota- Merta line at Beawar (Rajasthan (20GW) under Phase-III Part F) | D/C | 400 | 64
6 | LILO of KAPP - Vapi 400 kV D/C line at Vapi II | D/C | 400 | 1 |  |  |  |  | APR-23
7 | LILO of one Ckt. of Kishenpur -Dulhasti (Quad) line at Kishtwar | D/C | 400 | 5 |  |  |  |  | APR-25
8 | LILO of one ckt. of Narendra (existing) - Narendra (New) quad line at Xeldem (G-TTPL-TBCB) | D/C | 400 | 196 | 233 | 2 | 0 |  | MAR-23 | JUL-22 | 1.Delay in getting forest and wildlife clearances. State Govt had returned the proposal to nodal officer seeking the details that whether the user agency is utilizing the corridor of existing defunct 110kV Ambewadi  Ponda line or not at possible extent. The user agency confirmed that they are utilizing the corridor of defunct 110kV line at the maximum possible extent. Therefore, support is required from PCCF / Nodal officer and Chief Wildlife Warden, Karnataka to recommend the proposal with mitigation measures 2. The progress is suffered due to petition filed by Goa Foundation in CEC constituted by Supreme court and High Court of Mumbai and Goa 3. The introduction of Guidelines being issued by District Collector, North Goa vide letter dated 06-11-2020 for payment of Additional Compensation towards damages in regards of Right of Way for transmission Line has consequently led to an escalation in the cost of the project and the same is covered under Article 12 of the TSA as CIL event
9 | LILO of Padghe (PG)-Ghatkopar/Vikroli 400 kV S/C line at Navi Mumbai GIS(PG) (WRSS-XIX and NERS-IX) | S/C | 400 | 38 | 0 | 0 | 0 | 38 | JUN-24 | OCT-24 | Commissioned 09/24.
10 | Mangalore (Udupi PCL) - Kasargode (Quad) line | D/C | 400 | 231 |  |  |  |  | JUL-23
11 | Padghe (PG) - Kharghar 400 kV D/C (Quad) line (WRSS-XIX and NERSS-IX) | D/C | 400 | 140 | 0 | 0 | 0 | 140 | JUN-24 | OCT-24 | Commissioned 09/24.
12 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | 400 | 106 | 142 | 142 | 142 | 106 | JUN-24 | JAN-23 | Ready for commissioning on Oct-2024.
13 | LILO of Apta-Kalwa/Taloja at Navi Mumbai (PG) | D/C | 220 | 5 | 0 | 0 | 0 | 5 | MAY-24 | NOV-24 | Commissioned 10/24.
14 | Vapi-II-Sayali 220 kV D/C line (WRSS-XIX and NERSS-IX) | D/C | 220 | 45 | 0 | 0 | 0 | 45 | MAY-24 |  | Commissioned 09/24.
15 | Xeldem (Existing) - Xeldem (New) Transmission line | D/C | 220 | 45 | 66 | 66 | 66 | 45 | JUN-24 |  | Ready for commissioning on Oct-2024.
16 | AGTPP (NEEPCO) - P.K. Bari (TSECL) line (NER-II TL-TBCB) | D/C | 132 | 167 | 236 | 236 | 236 | 166.8 | MAR-20 | FEB-21 | Commissioned and declared under Commercial Operation (DOCO) w.e.f. 00:00 Hrs of 21-02-2021
17 | Biswanath Chariyalli (PG) - Itanagar (Zebra) line (NER-II TL-TBCB) | D/C | 132 | 134 | 211 | 211 | 207 | 126 | MAR-20 | MAR-21 | 1.The proposal for PLCC Carrier frequency has been submitted to Ministry of Communication (WPC Wing) and the approval is still awaited. Support required to expedite the same. The WPC Wing has informed that the Frequency allotment has been temporarily closed by MOC, therefore in the interest of timely completion of the project we have requested CEA to grant an approval for use of proposed frequenices otherwise the line cant be charged 2. The Additional Compensation has been paid for forest Land in the state of Arunachal Pradesh as being directed by Deputy commissioner, Papum Pare and Itanagar Districts. This is an additional cost to the project and the same is entitled to be covered under Article 12 of the TSA as Change in Law event
18 | Hatsinghmari (Assam)- Ampati (Meghalaya) (Single ACSR Panther) | D/C | 132 | 57 |  |  |  |  | DEC-23
19 | LILO of one Ckt. of Biswanath Chariyalli (PG)- Itanagar (Zebra) line at Gohpur (AEGCL) (NER-II TL-TBCB) | D/C | 132 | 17 | 30 | 30 | 30 | 16 | MAR-20 | MAR-21 | 1.Non-finalization of terminal bays at Gohpur S/s by AEGCL for the termination of LILO line 2. The proposal for PLCC Carrier frequency has been submitted to Ministry of Communication (WPC Wing) and the approval is still awaited. Support required to expedite the same. The WPC Wing has informed that the Frequency allotment has been temporarily closed by MOC, therefore in the interest of timely completion of the project we have requested CEA to grant an approval for use of proposed frequenices otherwise the line cant be charged 3. The Additional Compensation has been paid for forest Land in the state of Arunachal Pradesh as being directed by Deputy commissioner, Papum Pare and Itanagar Districts. This is an additional cost to the project and the same is entitled to be covered under Article 12 of the TSA as Change in Law event
20 | LILO of one Ckt. of Pare HEP - North Lakhimpur (AEGCL) (With ACSR Zebra)at Nirjuli (POWERGRID) | D/C | 132 | 33 |  |  |  |  | JUN-23
21 | Pare HEP (NEEPCO) (From near LILO Point) - North Lakhimpur (AEGCL) (With ACSR Zebra Conductor) along with 2 no. 132 kV line bays at North Lakhimpur | D/C | 132 | 62 |  |  |  |  | JUN-23
TALCHER TRANSMISSION CO. LTD.(TTCL)
1 | Behrampur - Gazuwaka (T-II TL -TBCB) | D/C | 400 | 290 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
2 | Talcher II - Behrampur (T-II TL - TBCB) | D/C | 400 | 220 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
3 | Talcher II - Rourkela (T-II TL - TBCB) | D/C | 400 | 161 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
Tata Power Ltd(TATAPOWER)
1 | 400kV D/C Koteshwar - Rishikesh line | D/C | 400 | 77
TEESTA URJA LTD.(TUL)
1 | Teesta III - Kishanganj | D/C | 400 | 427 | 590 | 586 | 581 | 391.8 |  | OCT-18 | Teesta III  Rangpo (CKT-II) and Teesta III  Dikchu (Ckt 1(a)) Lines are in commercial operation from 16.01.2017 & 14.04.2017 respectively. Dikchu- Rangpo (Ckt 1 (b)) is energized on 30.06.2018 (i.e. trial operation for 24 hours) and could successfully complete the trial operation on 1st July 2018. 46.1 Kms line from Kishanganj Substation has been successfully energized for antitheft purpose. Re-Stringing works, in last span of 290-291 is under progress and back charging would be extended stretch by stretch on completion of re-stringing. RoW and Forest issues faced in Darjeeling distt.
TORRENT POWER LTD(TOR. POW. (UNOSUGEN))
1 | DGEN TPS - Bharuch/Dahej Pooling Station | D/C | 400
2 | DGEN - Vadodara (DGEN TL - TBCB) | D/C | 400 | [7 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
3 | Sandila TPP - ATS not defind | D/C | 400
4 | Navseri - Bhasten (DGEN TL - TBCB) | D/C | 220 | [7 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
VANDANA VIDYUT LTD.(VVL)
1 | Salora TPS - Dharamjaigarh (Korba) (PGCIL) Pooling Station | D/C | 400 | 60 | 84 |  |  |  |  | MAR-17 | Target Commissioning date will be provided after approval/receipet of loan from lenders.
VEDANTA LIMITED(VEDANTA)
1 | Sterlite TPP - Jharsuguda (LILO-II to Jharsuguda) | D/C | 400 | 40 | 0 | 0 | 0 |  | NOV-16 |  | Transmission work not started yet. SEL will approach CEA for approval of continuing the LILO-II.
VEMAGIRI TRANSMISSION SYSTEM LIMITED(VTSL)
1 | Khammam-Hyderabad Line-1 | D/C | 765 | 772 | [5 empty] | MAR-15
2 | Khammam - Hyderabad line -I | D/C | 765 | 410 |  |  |  |  | APR-15 |  | Bidding process to be taken up
3 | Vemagiri Pooling Station -Khammam Line -1 | D/C | 765 | 852 | [5 empty] | MAR-15
4 | Vemagiri Pooling Station - Khammam line -I | D/C | 765 | 455 |  |  |  |  | APR-15 |  | Bidding process to be taken up
VISA POWER LTD(VISA)
1 | Visa Power TPP - Raigarh Pooling Station | D/C | 400 | 26 | 37 | 33 | 26 | 0 |  | JUN-15 | Work is under Construction.