## line_construction_status_test_r
REPORT INDICATING STATUS OF CONSTRUCTION OF TRANSMISSION LINES (220 kV & ABOVE) IN RFD PROGRAMME DURING- 2024-25
As on 31-JUL-2024
Sl No | Name of Transmission Lines | Ckts (S/C) & (D/C) | Voltage Level (kV) | Total Length (cKm) | Progress Status of Transmission |  |  |  | Target Date |  | Tag Names |  | Remarks
[5 empty] | Total Locations (Nos) | Foundation completed (Nos) | Tower Erected (Nos) | Stringing completed (CKm) | Schedule | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |  | 13.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | LILO of CTPS (A) - Kalyaneswari line at RTPS | D/C | 220 | 52 | 72 | 72 | 72 | 52 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
2 | LILO of MTPS (A) - Borjora line at MTPS (B) | D/C | 220 | 84 | 76 | 75 | 75 | 78.55 | MAY-24 | SEP-24 | RFD |  | Line length = 21.52KM, Route lenth = 21.52*4 = 86CKM . Stringing completed: 19.637*4=78.548CKM. Due to severe ROW problem and non-obtaining of Forest clearance. FRA received but stage I awaited. Revised date of completion changed to September'2024.
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | 2nd Circuit of Kishenpur - Dulhasti 400kV D/c (Q) line (Kishtwar - Kishenpur Section) | S/C | 400 | 130 | 29 | 21 | 17 | 73.15 | MAR-25 |  | RFD
2 | 400kV D/C Jeypore (POWERGRID) - Jagdalpur (CSPTCL) line | D/C | 400 | 137 | 172 | 112 | 1 |  | MAR-25 |  | RFD |  | 1) Forest Chhatisgarh (4.48 Ha): Forest proposal for Chhattisgarh submitted on 09.06.23, Revised Proposal Submitted on 09/11/2023​.Stage-I Awaited.2) Forest Odisha (18.1 Ha): Forest proposal for Jeypore (Odisha) side initially submitted in Oct 2023 which got rejected. Stage-I Awaited.
3 | 765kV Dc/KPS2-KPS3 line | D/C | 765 | 30 | 40 | 17 | 0 |  | MAR-25 |  | RFD |  | Stone piling work in progress.
4 | Banskantha-Ahemadabad line | D/C | 765 | 269 | 362 | 143 | 45 |  | MAR-25 |  | RFD |  | Patan Dist.: Section 16 (1) Orders awaited: 30 locs. Mehsana: Orders awaited: 04 locs. Ahmedabad: Orders awaited: 29 locs.
5 | Bhadla II - Sikar II 765 kV D/C line (2nd) Rajasthan (8.1 GW) under Phase-II Part-E | D/C | 765 | 600 | 816 | 469 | 175 |  | DEC-24 |  | RFD |  | RoW issues at 7 loc. in Sikar, 37 loc. in Didwana Kuchman . Forest (0.77 Ha): Proposal submitted on 23.10.23. Stage-I clearance accorded on 10.04.24. Working permission Awaited.
6 | Bhadla II - Sikar II 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 765 | 618 | 808 | 753 | 656 | 356.4 | DEC-24 |  | RFD |  | RoW at 26 loc. in Sikar district. Forest (0.25 HA): Online proposal submitted on 02.12.2023. Stage-I issued on 18.04.24.Working Permission Awaited.
7 | Fatehgarh- II -Bhadla-II 765kV D/C Line (2nd) | D/C | 765 | 405 | 529 | 529 | 511 | 327 | MAY-24 | JUL-24 | RFD |  | Shutdown constraints in Jaisalmer area for stringing works due to wind developer.
8 | Khetri-Narela 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part G) | D/C | 765 | 340 | 463 | 366 | 320 | 60 | JUL-24 | SEP-24 | RFD |  | 1. RoW at 88 loc. in Jhajjar district in Haryana. 2. RoW at 8 loc. in North Delhi district
9 | Kurnool-III-Kurnool (New) (PGCIL)-RTM) (AP) - Part-A and Part-B | D/C | 765 | 225 | 299 | 175 | 35 |  | MAR-25 |  | RFD |  | Length of the line is to be provided.
10 | Kurnool - III - Maheshwaram (PG) (PGCIL-RTM) | D/C | 765 | 504 | 673 | 345 | 48 |  | MAR-25 | DEC-19 | RFD |  | Forest: 26.993 Ha: Stage-I Approval Pending
11 | Laying of cable between Minamarg and Zojilla top section of Alusteng- Drass 220kV Section | S/C | 220 | 12 | 0 | 0 | 0 |  | DEC-24 |  | RFD |  | Present Status: Cable Trench-Excavation Work under progress (5.0 Km completed).PCC --3.685 km Completed HDPE Pipe-2.65/12 Km laying along with jointing completed. Note:- Work is at halt due to extreme weather conditions
12 | LILO of 765kV S/C Meerut -Bhiwani line at Narela | S/C | 765 | 68 | 97 | 58 | 24 |  | JUL-24 | SEP-24 | RFD |  | 1. RoW at 27 loc. in Sonipat district in Haryana. 2. RoW at 12 loc. in North Delhi district
13 | Magarwada (GIS) - Kala (GIS) 400 kV D/C line | D/C | 400 | 89 | 149 | 71 | 13 |  | DEC-24 |  | RFD |  | Gujarat: Valsad Dist. Orders awaited: 01 loc. Maharashtra: RoW are being faced at 30 locs. in palghar Dist. Farmers/landowners are demanding rate revision of land compensation.
14 | Navsari (New (South Gujarat) (GIS) - Padghe (GIS) 765 kV D/C line | D/C | 765 | 453 | 616 | 331 | 136 | 5.57 | DEC-24 |  | RFD |  | Navsari Dist.: Section 16 (1) Orders awaited: 24 locs. Valsad: Orders awaited: 01 loc. ROW issues are being faced in 13 locations in Palghar & 29 locatrions in Thane district in construction of 765 kV D/C Navsari (New) - Padghe (GIS) TL of Maharashtrafor portion. Farmers/landowners are demanding high compensation.
15 | Navsari (New) (South Gujurat) (GIS) - Magarwada (GIS)400kV D/C line | M/C | 400 | 385 | 266 | 235 | 115 |  | DEC-24 |  | RFD |  | Daman: Section 16(1) Orders awaited: 04 locs. Navsari Dist.: Section 16 (1) Orders awaited: 3 locs. Valsad Dist. Section 16(1) Orders awaited: 06 locs.
16 | Raipur Pool - Dhamtari 400kVD/C line (Q) | D/C | 400 | 176 | 232 | 149 | 11 |  | DEC-24 |  | RFD
17 | Removal of LILO of Bawana- Mandola 400kv D/C line at Maharanibagh s/s and Extension of above LILO section from Maharanibagh upto Narela s/s so as to from 2x400 kV D/C Maharanibagh- Narela line on Mult | D/C | 400 | 57 | 123 | 63 | 38 | 4 | JUL-24 | SEP-24 | RFD |  | Work affected due to RoW Issue at 30 locations in Delhi
18 | Sikar II - Aligarh 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part D) | D/C | 765 | 513 | 679 | 673 | 668 | 485.6 | DEC-24 |  | RFD |  | Forest (15.6043 Ha, Rajasthan): Online proposal submitted on 26.07.2021 & accepted by Nodal on 03.09.2021. Stage-I issued on 10.08.23. Stage-II Awaited
19 | Sikar II - Neemrana 400kV D/C line (Twin HTLS) (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 400 | 270 | 368 | 354 | 312 | 102 | DEC-24 |  | RFD |  | Forest (13.013 Ha, Rajasthan): Stage-I clearance accorded on 22.12.2022. Payment submitted on 30.03.23. On 13.07.23, Nodal Officer, Jaipur has requested to furnish FRA certificate. FRA: FRA obtained for Sikar & Alwar is under process.
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | 220kV D/C Banka (PG) -Goradih Transmission line | D/C | 220 | 78 |  |  |  |  | SEP-24 |  | RFD
2 | Bakhtiyarpur (New) - Fatuha (BSPTCL) | D/C | 220 | 92 | 157 | 142 | 107 | 0 | OCT-24 | DEC-22 | RFD |  | Work under progress.
3 | BTPP - Dumraon (New) GSS | D/C | 220 | 129 | 215 | 215 | 215 | 129 | MAY-24 | JUN-24 | RFD |  | Commissioned 05/24. (ANTITHEFT CHARGED on 13-05-2024)
4 | LILO of (Quad) Barh - Patna at Bakhtiyarpur (New) | D/C | 400 | 41 | 61 | 49 | 43 |  | OCT-24 | FEB-23 | RFD |  | ROW issues.
5 | LILO of Sipara (BSPTCL) - Bihta (BSPTCL) at Jakkanpur (New) | D/C | 220 | 47 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | M/s BGCL
6 | Pusouli (New) - Dehri | D/C | 220 | 125 | 159 | 159 | 159 | 125 | MAY-24 | JUL-24 | RFD |  | Commissioned 06/24.
7 | Thakunganj - Kishanganj (New) Trans. line | D/C | 220 | 52 | 0 | 0 | 0 |  | MAY-24 | DEC-22 | RFD
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | 2nd circuiting of 220 Khedamara- Bemetara line from 220kV s.s Ahiwara to 220kV s/s Bemetara line | S/C | 220 | 38 |  |  |  |  | APR-24 |  | RFD
2 | Kurud-Gurur line | D/C | 220 | 74 |  |  |  |  | DEC-24 |  | RFD
3 | Kurud -Rajim line | D/C | 220 | 66 |  |  |  |  | FEB-25 |  | RFD
4 | LILO of 400kV Raita-Jagdalpur line at 400kV Kurud (Dhamtari) s/s | D/C | 400 | 3 |  |  |  |  | SEP-24 |  | RFD
5 | LILO of Khedamara-Thelkadih at Semariya | D/C | 220 | 3 |  |  |  |  | DEC-24 |  | RFD
6 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | D/C | 220 | 45 | 0 | 0 | 0 | 44 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
7 | Raipur (PGCIL Kumhari) - Raita | D/C | 400 | 6 |  |  |  |  | DEC-24 |  | RFD
DELHI TRANSCO LIMITED ( DTL )
1 | 220 KV D/C U/G Cable from Kashmiri Gate to Timarpur (2x5) | D/C | 220 | 10 | 0 | 0 | 0 |  | JUN-24 | OCT-23 | RFD |  | 1. Contract Agreement has been executed on 15.10.2019. 2. Cable laying work completed in all 09 sections. 3. Cable Jointing (48) has been completed in all 08 JBs. 4. The sites are handed over to PWD by 26.04.2022 after completion of work on PWD Road. 5. Cable end terminations (6 Nos) work has been completed at Timarpur end. On 10.05.2022. 6. A case file has been forwarded to Project I deptt on 15.06.2022 seeking current status of the availability of GIS bays at 220KV Kashmiri Gate S/Stn. GIS interface drawing for manufacturing of Cable indoor termination has been provided to M/s LSCI on dt. 10.03.2023. 8. A case file was forwarded to Planning wing of DTL seeking information/confirmation about the execution of proposed 220 kV Rajghat  Kashmiri Gate D/C O/H T/L and location of the end tower of the same towards 220 kV Kashmiri Gate S/stn. The case file is received back on dt. 25.01.2023 informing that as per 13th Business plan connectivity from 220kV Rajghat to Kashmiri Gate S/st
2 | 220kV D/C underground cable from IP -New Rajghat GIS | D/C | 220 | 4 |  |  |  |  | MAR-25 |  | RFD
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | 220 kV D/C Choraniya - Salejada line | D/C | 220 | 136 | 221 | 221 | 221 | 136 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
2 | 220kV D/C Motigop Babarzar line (AP-7-Motigop gantry) | D/C | 220 | 32 |  |  |  |  | SEP-24 |  | RFD
3 | 220kV D/C Motigop Babarzar line (Babarzar gantry to AP-7) -under stopgap | D/C | 220 | 5 |  |  |  |  | SEP-24 |  | RFD
4 | 220kV D/C Shapar- Ghiyavad line with AL-59 Conductor | D/C | 220 | 85 | 168 | 116 | 108 | 36.47 | SEP-24 | SEP-24 | RFD
5 | 220kV S/C Dhama-Bechraji line on 220kV D/C towers (Tap location of existing220kV Bechraji-Surel line to 220kV Dhama S/S | D/C | 220 | 23 |  |  |  |  | JAN-25 |  | RFD
6 | 400kV D/C Shapar-Pachcham (Fedra) Line with Twin AL-59 cond. and 1 OPGW and 1 Earth Wire | D/C | 400 | 197 | 301 | 289 | 279 | 114.16 | JUN-24 | DEC-24 | RFD |  | WIP
7 | 400kV D/C Varsana-Halvad (PACKAGE-1) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 144 |  |  |  |  | DEC-24 |  | RFD
8 | 400kV D/C Varsana-Halvad (PACKAGE-2) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 94 |  |  |  |  | DEC-24 |  | RFD
9 | Balance work of 400kV D/C Vadavi -Halvad Line (PACKAGE-2) (AP-41 to Halvad) with Twin AL-59 Condu. and 1 and OPGW and 1 Earth Wire | D/C | 400 | 149 |  |  |  |  | JUN-24 |  | RFD
10 | Gavasad - Salejada line with AL-59 conductor and Earth Wire | D/C | 220 | 194 | 327 | 305 | 289 | 146.93 | JUN-24 | SEP-24 | RFD |  | W I P / Severe RoW problems
11 | LILO of both Ckts. of 220kV D/C Kalawad-Kangasiyali line at Siddheshwar s/s | D/C | 220 | 10 |  |  |  |  | JUL-24 |  | RFD
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | 220kV D/C line from 220kv Meerpur Kurali to TSS Rundhi as a deposit work of Indian Railway | D/C | 220 | 25 | 0 | 0 | 0 |  | MAY-24 | JUN-24 | RFD
2 | 220 kV D/C Line from 220KV S/S Sonipat - 220KV Sector-6 Sonipat | D/C | 220 | 6 | 0 | 0 | 0 |  | MAR-25 |  | RFD
3 | 220kV D/C line from 400kV PGCIL Panchkula to 220kV Sadhaura | D/C | 220 | 76 | 0 | 0 | 0 |  | AUG-24 |  | RFD
4 | 220kV D/C line from 400kV S/Stn. Panchgaon (PGCIL) - 220kV S/S Panchgaon | M/C | 220 | 48 | 2 | 2 | 2 | 10 | APR-24 | SEP-22 | RFD |  | commissioned on 05.09.2022
5 | 220kV D/C line from 765kV S/stn. PGCIL Bhiwani to 220kV S/stn. Isherwal | D/C | 220 | 100 | 212 | 202 | 190 | 75.66 | JUL-24 | JUL-24 | RFD |  | Work is in progress. Work is held up due to severe RoW problem from farmers. However, matter taken up with District Administration, Bhiwani for resolving the issue. MD, HVPNL, Panchkula to hold a meeting with farmers on dated 12.05.2023 at Shakti Bhawan Panchkula for resolving the issue.
6 | 220kV D/C line on M/C towers from 400kV S/S Prithla - 220kV S/Stn. Sector 78 FBD | D/C | 220 | 59 | 169 | 125 | 66 | 0 | SEP-24 | SEP-24 | RFD |  | Work in progress.
7 | 220KV KV D/C Line from 400KV S/Stn PGCIL Bahadurgarh to IMT Pocket-B Kharkhoda | D/C | 220 | 56 | 0 | 0 | 0 |  | MAR-25 |  | RFD
8 | 220KV KV D/C Line from 400KV S/Stn PGCIL Sonipat to IMT Pocket-A Kharkhoda | D/C | 220 | 44 | 0 | 0 | 0 |  | MAR-25 |  | RFD
9 | LILO of 1 ckt of 220kV D/C Samaypur-Palwal at 220kV Harfali | D/C | 220 | 1 | 0 | 0 | 0 |  | MAR-25 |  | RFD
10 | LILO of 220kV D/C PTPS-Jind line at 220kV S/S Nain | M/C | 220 | 33 | 0 | 0 | 0 |  | FEB-25 |  | RFD
11 | LILO of 220KV D/C PTPS Jind line at 400KV PGCIL Khatkar (Jind) | M/C | 220 | 18 | 0 | 0 | 0 |  | MAR-25 |  | RFD
12 | LILO of 220KV Mohana- Samalkha D/C line at 400KV S/S Jhajji (PGCIL) on M/C towers | M/C | 220 | 13 | 24 | 24 | 16 | 1 | JUN-24 | JUN-24 | RFD |  | Work in progress.
13 | LILO of 400kV Sec -72 Gurugram (PGCIL) to 220kV Sec -72 Gurugram (HVPNL) at 220kV Sec 15-II Gurugram | D/C | 220 | 10 | 0 | 0 | 0 |  | MAY-24 | JUL-24 | RFD
14 | LILO of Both Circuits of 220kV PGCIL Hisar- Fatehabad D/C line at 220kV Chikanwas (Hisar) with 0.4 sq. inch ACSR | M/C | 220 | 19 | 0 | 0 | 0 |  | MAR-25 |  | RFD
15 | LILO of both Ckts of 220kV Pali-Sector-65 D/C Line at 400kV S/S Kadarpur | M/C | 220 | 26 | 45 | 13 | 13 | 0 | MAY-24 | JUL-24 | RFD |  | Work in progress. (Forest Clearance Stage-I received)
16 | LILO of Tepla (220kV) - Madanpur (220kV) line at 220kV Sadhaura S/S and LILO of Tepla (220kV) to Rajwali (220kV) at 220kV Sadhaura S/S | M/C | 220 | 103 | 0 | 0 | 0 |  | AUG-24 |  | RFD
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | 220/132kV MCT Transmission Line from Kala Amb to T-19 of Jamta Kala Amb Line | M/C | 220 | 36 |  |  |  |  | JUL-24 |  | RFD
2 | 400/220 kV GIS of POWERGRID at Airendwala to 220/132/33 kV AIS of HPPTCL at Andheri Kala Amb Distt. Sirmaur | D/C | 220 | 11 | 0 | 0 | 0 | 11 | APR-24 | JUN-24 | RFD |  | Commissioned 05/24.
3 | LILO of 220kV D/C Bajoli Holi to Lahal Transmission Line at 220/66 kV Heiling S/S | D/C | 220 | 1 | 0 | 0 | 0 |  | JUL-24 | SEP-21 | RFD |  | Forest Clearance Case is under Process
4 | LILO of 400kV Lahal Rajera Transmission line at Kuther (240 MW) HEP | D/C | 400 | 1 |  |  |  |  | JUN-24 |  | RFD
5 | Stringing of 2nd Circuit from Dehar HEP of BBMB to Kangoo S/S | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-24 | MAR-23 | RFD
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | LILO of 220kV D/C Govindpur -TTPS at Jainmore | D/C | 220 | 47 | 92 | 82 | 67 | 24.3 | OCT-24 | MAR-23 | RFD |  | Work in Progress.
2 | Patratu (JSUNL) - Latehar(JUSNL) | D/C | 400 | 215 | 304 | 275 | 260 | 81.55 | OCT-24 | FEB-23 | RFD |  | Stage-I clearances awaited.
3 | PUVNL- Patratu | D/C | 400 | 14 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Request letter regarding additional fund as difference of sanctioned cost and offered price of L-1 bidder has been sent to energy dept. Govt of Jharkhand. After sanctioning of requisite fund, work order will be issued.
4 | Quad Essar (Chandwa) - Latehar (JUSNL) TL | D/C | 400 | 80 | 122 | 122 | 120 | 42.58 | OCT-24 | MAR-23 | RFD |  | Work in Progress.
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | 220kV CB Pura I/A -Work-A Construction of 220kV DC LILO line from proposed 220 kV Chintamani-Mittemari D/ C line (both Ckts.) at proposed 220kV CTT | D/C | 220 | 111 | 101 | 75 | 69 | 32 | NOV-24 |  | RFD |  | Work under progress
2 | 220kV DC line from the existing 220/110 kV Halabarga s/s to the proposed Santhpur S/S | D/C | 220 | 57 | 103 | 97 | 95 | 32.59 | AUG-24 |  | RFD |  | Work under progress
3 | Conversion of 220 kV Bidnal-Soundatti-Mahalingapura S/C line - 220 kV Bidnal - Mahalingapur D/C line | D/C | 220 | 125 | 457 | 457 | 457 | 125 | JUL-24 | AUG-24 | RFD |  | Commissioned 07/24.
4 | Ghanagapura - Aaheri line | D/C | 220 | 112 | 215 | 208 | 202 | 66.45 | SEP-24 | SEP-24 | RFD |  | Work under progress
5 | Ghanagapura - link Shahpur - Khanapura line | D/C | 220 | 21 | 32 | 17 | 14 |  | SEP-24 | JUN-24 | RFD |  | WUP
6 | Hangal Construction of 220kV DC line on DC towers from 220 kV Hiremallanahole (Jagalur) to Hangal D/C Line | D/C | 220 | 73 | 140 | 82 | 55 | 0.75 | FEB-25 |  | RFD |  | WUP
7 | LILO at Keonics (Electronic City)- Mylsandra - Yeradanahalli | S/C | 220 | 7 | 7 | 0 | 0 |  | MAY-24 |  | RFD |  | 9/9 Sec cable laying completed
8 | LILO at Keonics (Electronic City) - Somanahalli Hoddy | S/C | 220 | 13 | 0 | 0 | 0 | 6.35 | MAY-24 |  | RFD |  | 15/15 cable laying completed.
9 | LILO at Somasamudra - Allipura -Rayalpadu line | D/C | 220 | 12 | 28 | 28 | 25 | 12.24 | AUG-24 |  | RFD |  | WUP
10 | LILO of 220kV Kudigi-Vajramatti DC line at proposed 220/110kV Bilagi S/S | D/C | 220 | 74 | 73 | 61 | 23 | 25.9 | OCT-24 |  | RFD |  | Some of the towers are coming under Krishna Back water area.
11 | Somasamudra - BTPS (Bellary Thermal Power plant) (Kudithini) | D/C | 220 | 41 | 64 | 58 | 49 | 27.11 | AUG-24 |  | RFD |  | Work under progress
12 | Srinivasapura from existing s/s -to the proposed Srinivasapura s/s | D/C | 220 | 48 | 99 | 99 | 99 | 48 | OCT-23 | NOV-23 | RFD |  | Commissioned 10/23.
13 | Yelburga from the existing 220/110/11kV Kushtagi S/S- the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 68 | 113 | 94 | 94 | 2.18 | AUG-24 |  | RFD |  | Work under progress
14 | Yelburga from the existing 220/110/11kV Kushtagi S/S -to the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 57 | 68 | 57 | 1 |  | AUG-24 |  | RFD |  | Work under progress
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kanhirode-Mylatty 220 kV DC line | D/C | 220 | 168 | 273 | 255 | 251 | 135.32 | JUN-24 | NOV-24 | RFD |  | Work in Progress.
2 | Pathanamthitta - Kakkad s/s | D/C | 220 | 114 | 197 | 169 | 156 | 75.4 | MAY-24 | NOV-24 | RFD |  | Work in Progress.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220kV DC Kalmeshwar-Warud (PhaseI and II ) (from Kalmeshwar s/s to loc no 90) | D/C | 220 | 53 | 75 | 75 | 75 | 43.34 | DEC-23 | SEP-24 | RFD |  | Commissioned 03/24 (Partially Charged (Package -III Shifted to FY -2024-25). Balance phase III to be included in Target. Only stringing between 3 spans( 1Km) in forest balance, forest approval awaited.
2 | 220kV D/C line from Vishwind- Bhenda | D/C | 220 | 86 | 141 | 140 | 139 | 64.19 | JUN-24 | DEC-24 | RFD |  | Outage issue. Severe RoW issues. Police protection availed for foundation work of Loc. no. 135. However work could not be carried out due to farmers opposition. The FIR was launched in Newasa Police Station.
3 | 220 kV Koradi-II to Butibori-III DCMC line | D/C | 220 | 109 | 189 | 189 | 189 | 109 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
4 | 220 kV Kumbhargaon (Nanded)- Kurunda line (Pkg-B) | D/C | 220 | 55 | 107 | 107 | 105 | 30.7 | JUN-24 | SEP-24 | RFD |  | Work in progress.
5 | 220KV Nagewadi- Bhokardhan line | D/C | 220 | 90 | 151 | 140 | 122 | 52.57 | JUN-24 | DEC-24 | RFD |  | ) Severe ROW issue. Valuation awaited from concerned SDOs.
6 | Babhaleshwar-Kudus DC line | D/C | 220 | 457 | 719 | 689 | 673 | 293.2 | DEC-24 | DEC-24 | RFD |  | i) Severe RoW issues at Ale village for 22 locations. Ii) And fresh ROW are being faced due to delay in providing police protection and help from revenue Authorities.
7 | Jerur- Karjat line | D/C | 220 | 101 | 163 | 162 | 162 | 84.72 | MAY-24 | AUG-24 | RFD |  | Row issues. Row are being resolved with the help of revenue & police authorities.
8 | Kalmeshwar-Warud line (Phase III) | D/C | 220 | 45 | 75 | 75 | 75 | 43.34 | JUN-24 | SEP-24 | RFD |  | Only stringing between 3 spans( 1Km) in forest is balance. Target subject to forest approval.
9 | LILO of 220kV Kalwa- Bapgaon line at Mankoli s/s | D/C | 220 | 1 | 4 | 4 | 3 | 0 |  | MAR-25 | RFD |  | Work in progress. Outage required for erection of inline tower
10 | LILO on 220kV Bhigwan Kurkumb line at 400kV Karjat s/s | D/C | 220 | 36 | 52 | 52 | 51 | 31.48 | MAY-24 | AUG-24 | RFD |  | RoW issues, Row are being resolved with the help of revenue & police authorities.
11 | LILO on 220kV Shendra- Chitepimpalgaon line at 220kV Shendra DMIC GIS s/s | D/C | 220 | 6 | 0 | 0 | 0 | 6 | JUN-24 | AUG-24 | RFD |  | Work of 3 nos JB jointing is balance which in progress. Work delayed due to cable theft (85 m).
12 | LILO on 220kV Tarapur-Borivali and Boisar- Ghodbandar line at 400kV Kudus S/S | LILO | 220 | 118 | 120 | 110 | 108 | 89.51 | NOV-24 | NOV-24 | RFD |  | Severe RoW. Forest proposal Status: Stage -1 approval received on 08.07.2024. Demand note awaited from DCF Dahanu.
13 | LILO on Kolshet-Wada and Padghe-Wada line at 400kV Kudus S/s | M/C | 220 | 36 | 50 | 29 | 27 | 14.8 | DEC-24 | DEC-24 | RFD |  | 1) All works except forest area completed. 2) SBWL proposal approved on 27.06.2024. 3) NBWL proposal was taken in meeting dtd 31-07-2024.4) DCF Thane conducted meeting on 01.08.2024, MSETCL requested to forward FCA proposal to CCF Thane.
14 | Umred S/stn to Nagbhid s/s (Part-II) | D/C | 220 | 49 | 94 | 90 | 90 | 25.25 | NOV-24 | NOV-24 | RFD |  | i) 4 locations in forest balance, Forest approval awaited. ii) NBWL proposal was taken in meeting dtd 31-07-2024.
15 | Uppalwadi-Pardi UG Cable | D/C | 220 | 26 | 0 | 0 | 0 | 23.16 | JUN-24 | NOV-24 | RFD |  | Involvement of 4 bridges & HDD (Horizontal Directional Drilling) work. i) Fabrication on Nag River crossing NMC (Nagpur Municipal corporation) water pipeline for passing 6 nos. of 220 kV single core cable and 1 number of Railway crossing with cathodic coating on 14 mm thick MS pipe to be done for railway crossing.
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
1 | LILO of both circuit of Itarsi (PGCIL) - Bhopal 400kV line (on Twin Moose) at Mandideep 400kV S/s | D/C | 400 | 20 | 7 | 7 | 0 | 0 |  |  | RFD |  | TBCB work
2 | LILO of both circuits of Chhegaon - Nimrani 220kV line at Khargone 220kV S/s | D/C | 220 | 60 | 48 | 0 | 0 |  | JAN-25 |  | RFD |  | TBCB work
3 | LILO of both circuits of Hoshangabad - Mandideep - Adampur 220kV line at Mandideep 400kV S/s | D/C | 220 | 40 | 6 | 0 | 0 |  | JAN-25 |  | RFD |  | TBCB work
4 | LILO of both circuits of Satna-Chhatarpur 220kV line at Ajaygarh (TBCB) | D/C | 220 | 14 | 0 | 0 | 0 | 14 | DEC-24 | JUL-24 | RFD |  | Commissioned 06/24.
5 | LILO of both circuits of Satpura-Itarsi-Handiya 220kV line at Bisonikala 220 kV S/s | D/C | 220 | 20 | 15 | 0 | 0 |  | JAN-25 |  | RFD |  | TBCB work
6 | LILO of both circuits of Sidhi - Hindalco 220kV line at Bargawan 220kV S/s | D/C | 220 | 40 | 21 | 21 | 12 | 0 | DEC-24 |  | RFD |  | TBCB work
7 | LILO of one circuit of 400KV Damoh(PGCIL) - Bhopal line at Sagar 400KV S/S | D/C | 400 | 38 | 58 | 55 | 8 | 0 | MAR-25 | MAR-25 | RFD |  | work under progress.
8 | LILO of one circuit of Satpura TPS-Itarsi 220 kV line at Shahpur 220 kV S/s | D/C | 220 | 10 | 23 | 0 | 0 | 0 | JAN-25 |  | RFD |  | TBCB work
9 | Sagar - Begamganj 220 kV line (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | D/C | 220 | 125 | 0 | 0 | 0 | 125 | DEC-24 | AUG-24 | RFD |  | Commissioned 04/24 (Late Reported).
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | Kesinga - Baliguda GSS | D/C | 220 | 202 |  |  |  |  | MAR-25 |  | RFD
2 | LILO of 220 kV Nuapada Pratapsasan Line at Balianta GSS | D/C | 220 | 20 | 48 | 44 | 42 | 12 | JUN-24 | DEC-24 | RFD
3 | LILO of 220 KV TTPS -Joda DC Line at 220/33 KV GIS Keonjhar (Ranki) | D/C | 220 | 27 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Repeat may be deleted
4 | LILO of Balimela-Malkangiri line at Govindpalli | D/C | 220 | 80 | 146 | 146 | 146 | 21.37 | DEC-24 | JUN-25 | RFD |  | The S/s charged through "T"connection. The line is delayed due Forest clearance issue.
5 | LILO of Bhanjanagar-Meramundali line at Daspalla | D/C | 220 | 59 | 113 | 108 | 99 | 45 | JUN-24 | MAR-25 | RFD |  | Forest issue
6 | PGCIL Keonjhar - Turumunga GS | D/C | 220 | 34 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Repeat may be deleted
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | 220 KV D/C line from 400 KV S/S Dhanansu to Tata Steel plant Kadiana Khurd (Contributory work) | D/C | 220 | 5 | 30 | 5 | 2 | 0 | MAR-25 |  | RFD |  | Work in progress.
2 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | 220 | 16 | 31 | 31 | 31 | 16 | MAY-24 | MAY-24 | RFD |  | Commissioned 04/24.
3 | LILO of 220 kV S/Stn Mansa - Sunam at 400 kV S/Stn Patran | D/C | 220 | 85 | 144 | 144 | 144 | 85 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
4 | LILO of one ckt of 220 KV Ganguwal-Jamalpur at 400 KV S/S Dhanansu | D/C | 220 | 9 |  |  |  |  | MAR-25 |  | RFD
5 | Lilo of one ckt of 220 KV Jamalpur-Dhandari Kalan-1 line at 220 Kv Sherpur S/S | D/C | 220 | 4 | 5 | 3 | 0 | 0 | JUN-24 |  | RFD |  | Work in progress.
6 | LILO of one Ckt. of 400kV Ludhiana PGCIL-Koldam at proposed 400kV s/s Ropar | D/C | 400 | 14 | 0 | 0 | 0 | 14 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
7 | Mansa - Budhlada line | D/C | 220 | 52 | 100 | 89 | 83 | 24.14 | JUL-24 |  | RFD |  | Work in progress.
8 | Rajpura s/s to 220 kv Rajpura s/s D/C on D/C towers | D/C | 220 | 3 |  |  |  |  | SEP-24 |  | RFD
9 | Shifting of 220 KV S/C Patti-Verpal line from 220 KV Verpal to 400 KV S/S Amritsar | D/C | 220 | 4 |  |  |  |  | APR-24 |  | RFD
10 | Work for connecting 400kV Rajpura -220kV Mohali-1 (one ckt direct one via 220 kV Banur) | D/C | 220 | 4 |  |  |  |  | JUL-24 |  | RFD
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | 400 KV UG Cable laying work from UG common point near Pallikarunai to O.H U.G common point near Perambakkam | S/C | 400 | 10 |  |  |  |  | MAR-25 |  | RFD
2 | CMRL Central Jail to proposed Mambalam 230kV GIS SS (UG Cable) | S/C | 230 | 9 | 0 | 0 | 0 |  | JUN-24 | JAN-24 | RFD |  | Total sections: 19. Laying 19/19 completed. Joints 54/54 completed. Sheath fault rectification work under progress.
3 | Extension of Shoolagiri Karimangalam line (from location no. 6 of Shoolagiri Karimangalam line) to Udanapally 230 KV SS | S/C | 230 | 2 | 0 | 0 | 0 | 2 | APR-24 | MAY-24 | RFD |  | Commissioned 04/24.
4 | Kilpauk - TNEB HQ | S/C | 230 | 6 | 0 | 0 | 0 |  | JUN-24 | MAR-24 | RFD |  | Total: 13 sections. Total:36 joints.Cable Laying 13/13 Completed. Joints 36/36 completed. Cable fault rectification work under progress.
5 | Laying of 400KV UG Cable from OH and UG common point at Manjambakkam to the proposed Korattur 400KV SS | S/C | 400 | 12 |  |  |  |  | JUN-24 |  | RFD
6 | Laying of UG cable by making LILO in the existing 230 KV Korattur- Kilpauk water works at Ganesh Nagar 230 KV SS | D/C | 230 | 3 |  |  |  |  | JUN-24 |  | RFD
7 | Laying of UG cable by making LILO in the proposed 230 KV Alamathy-Srperumbudur feeder at the proposed Avadi 230/110 KV SS | D/C | 230 | 9 |  |  |  |  | JUN-24 |  | RFD
8 | LILO of 230 kV Abishekapatti - Udayathur line at Nanguneri | D/C | 230 | 40 | 84 | 84 | 84 | 40.35 | SEP-24 |  | RFD |  | Line work completed. Will be energised on energisation of Nanguneri 230KV Substation.
9 | LILO of 230 kV Mylapore - Tarammani feeder at the proposed Thiruvanmiyur (400 kv GIS) | D/C | 230 | 2 | 0 | 0 | 0 |  | DEC-24 | DEC-23 | RFD |  | Cable laying work completed.Cable will be energised during commissioning of SS.
10 | LILO of 230 KV Ottiyambakkam - Omega Feeder II at the proposed Mambakkam 230/110 KV SS | D/C | 230 | 68 |  |  |  |  | SEP-24 |  | RFD
11 | LILO of Arasur- Ingur 230kV line at Kalivelampatty 230kV s/s | D/C | 230 | 31 |  |  |  |  | NOV-24 |  | RFD
12 | LILO of existing 230 kV Arni - Sriperumbudur feeder (0.81KM) at the proposed Vembakkam 230 kV S/S | D/C | 230 | 2 |  |  |  |  | JUN-24 |  | RFD
13 | LILO of Ottiyambakkam Guiny 400 KV SC feeder at Tharamani 400 KV GIS UG Cable -3.925 KM | D/C | 400 | 8 |  |  |  |  | MAR-25 |  | RFD
14 | LILO of Pudhansandhai - Pugalur 230 KV Feeder at Nallur SS | M/C | 230 | 24 |  |  |  |  | MAR-25 |  | RFD
15 | LILO of S. P. Koil - Oragadam at Maraimalai Nagar 230 KV S/S | D/C | 230 | 9 |  |  |  |  | SEP-24 |  | RFD
16 | LILO of Thappagundu - Anaikadavu at Udumalpet (PGCIL SS) | D/C | 400 | 40 |  |  |  |  | JUN-24 |  | RFD
17 | LILO of the exisiting 230 kV Myvady - Kurukathi - Pugalur feeder at sanctioned Rasipalayam 400 kV SS | D/C | 230 | 46 | 93 | 92 | 92 | 41 | SEP-24 | MAR-24 | RFD |  | Row issues land owners are demanding yield compensation prior to commencement of further works tender floated for supply and erection of 5 nos towers.
18 | LILO of Thiruvalam - Singarapet 230 KV Feeder at Sathumadurai 230KV SS (OH- 1.75 Kms and UG -0.800 Kms.) | D/C | 230 | 5 |  |  |  |  | MAR-25 |  | RFD
19 | Ottiyambakkam (Sholinganallur) - KITS | D/C | 230 | 21 | 35 | 33 | 33 | 12.8 | SEP-24 | MAR-24 | RFD |  | OH line work completed for 33/35 locations (6.40/7.30 KM ) for balance 2 Nos loc Alternate route tender under process. UG cable laying for 3.04 KM proposed in lieu of OH line in marsh land.Tender awarded. Route survey under progress.
20 | Thervaikandikai - Manali | D/C | 400 | 73 | 113 | 111 | 106 | 58.6 | JUN-24 | MAR-23 | RFD |  | Work under progress. Row issues Enter upon permission awaited.
21 | UG Cable from Basin Bridge to TNEB Head Quarters | S/C | 230 | 6 | 0 | 0 | 0 | 6 | JUN-24 | MAY-24 | RFD |  | Commissioned 04/24.
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | 220 kV Brandix - Atchuthapuram | D/C | 220 | 7 | 11 | 11 | 11 | 7 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
2 | 220KV DC line from 220KV Gunadala S/S - 220KV Nunna S/s | D/C | 220 | 13 | 34 | 34 | 34 | 12.32 | MAY-24 | DEC-24 | RFD
3 | 220kV DC line from 400kV Kamavarapukota to 220kV SS Bhimadole SS | D/C | 220 | 37 | 69 | 69 | 69 | 37 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
4 | 220kV DC line from 400kV s/s Jammalamadugu - proposed 220kV s/s Bethamcherla in Kurnool District | D/C | 220 | 152 | 260 | 259 | 259 | 140.94 | JUN-24 | AUG-24 | RFD |  | Work permit received from Forest CF/Kurnool on 16.04.2024. Work under Progress
5 | 220kV multi circuit line for making Double LILO of 220kV Gudivada-Akiveedu-Bhimavaram DC line at Proposed 400/220kV S/S Gudivada | M/C | 220 | 38 | 63 | 40 | 0 | 0 | DEC-24 | DEC-24 | RFD |  | work under progress
6 | 220kV SMDC line converted to TMDC from 400kV Hindupur - 220kV Pampanurthanda | D/C | 220 | 148 | 268 | 235 | 220 | 52.42 | JUN-24 | DEC-24 | RFD |  | work under progress
7 | 400kV QMDC line from 400kv Polavaram SS - 400/220/11kV Guddigudem | D/C | 400 | 49 | 72 | 68 | 67 | 33.68 | MAY-24 | DEC-24 | RFD |  | Works are under progress. 3 Locations (Loc.Nos. 7,8,11) are in forest area.Loc.No.7 and 8: CA land allotted. Permission from Forest authorities awaited.Loc.No. 11: CA land yet to be allotted by Revenue authorities.
8 | LILO of 220 kv ongole-Racherlpadu line at 220 kv ss Kandukur | D/C | 220 | 6 | 13 | 13 | 12 | 1 | MAY-24 | MAY-24 | RFD |  | work under progress
9 | LILO of 220kV VTS-Tallapally-1 at 220/132 kV SS Rentachintala | D/C | 220 | 3 | 5 | 5 | 4 | 3 | APR-24 | JUN-24 | RFD |  | Commissioned 05/24.
10 | LILO of 400kV Vemagiri-Sattenapalli TMDC lineat 400kV s/s Gudiwada | D/C | 400 | 51 | 90 | 66 | 14 | 0 | MAR-25 | MAR-25 | RFD |  | work under progress
11 | LILO of 400kV VTS-IV Sattenapalli TMDC line at Thallayapalem and Temporary diversion of PGCIL VTS/Nunna-Nellore 3 and 4 Ckts. to avoid aerial passage over 400/220kV GIS Thallayapalem | D/C | 400 | 3 | 7 | 4 | 3 | 2.42 | JUN-24 | JUN-24 | RFD |  | work under progress
12 | LILO of existing 220kV Gooty -Shapuram line at proposed 220kV Dharmavaram S/S | D/C | 220 | 3 | 8 | 8 | 8 | 3.28 | JUN-24 | JUN-24 | RFD |  | works completed
13 | LILO of existing 220 KV Nunna - KTPS Single Ckt. line at 220kV SS Tiruvuru | D/C | 220 | 2 | 16 | 10 | 4 | 0 | JUL-24 | JUL-24 | RFD |  | work is under progress
14 | LILO of existing one circuit of 220kV VTS-Kamavarapukota line at 400/220kV S/S Kamavarapukota | D/C | 220 | 3 | 9 | 9 | 8 | 0 | MAY-24 | JUN-24 | RFD |  | work under progress
15 | LILO of Palamaneru-Madanapalli line at 220kV S/S Punganuru | D/C | 220 | 6 | 13 | 13 | 11 |  | JUN-24 | JUN-24 | RFD |  | work under progress
16 | LILO of VSS - Kakinada line and Anrak-Samakota line at Chandanada line | D/C | 220 | 11 | 60 | 53 | 26 | 1.03 | DEC-24 | DEC-24 | RFD
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | 220KV Pulakurthy - Kakatiya Mega Textile Park | D/C | 220 | 60 | 110 | 99 | 89 | 18 | DEC-24 | DEC-24 | RFD |  | Works under progress. Foundations are pending due to Severe ROW
2 | Damaracherla -Huzurnagar line | D/C | 220 | 77 | 137 | 137 | 137 | 76.06 | MAY-24 | JUL-24 | RFD |  | Line works completed, except stringing of 3km of OPGW Cable ( from Loc. No. 79 to 91) , which is under progress. After completion of OPGW stringing, Statutory inspection works will be carried out.
3 | Dichpally - Yacharam Thanda line | D/C | 220 | 54 | 97 | 97 | 97 | 54 | JUL-24 | JUL-24 | RFD |  | Works under progress.
4 | Janagon -Husnabad | D/C | 220 | 79 | 139 | 139 | 139 | 73 | AUG-24 | JUL-24 | RFD |  | Works under progress.
5 | Narsapur to Bowrampet line (lattice structure) | M/C | 220 | 134 | 136 | 136 | 136 | 134.26 | SEP-24 | JUN-24 | RFD |  | work under progress
6 | Narsapur to Bowrampet (Monopole towers) | D/C | 220 | 7 | 23 | 15 | 14 |  | SEP-24 | JUN-24 | RFD |  | Works under progress.
7 | Narsapur to Bowrampet (XLPE UG Cable ) | D/C | 220 | 7 | 1 | 0 | 0 | 7 | SEP-24 | JUN-24 | RFD |  | Works under progress.
8 | Veltoor SS - Yedula SS | D/C | 400 | 94 | 139 | 139 | 139 | 94 | JUN-24 | OCT-23 | RFD |  | All works completed. Ready for charging. Statutory inspection is under progress
9 | Yadadri TPP Switchyard - Choutuppal S/S | D/C | 400 | 185 | 259 | 259 | 258 | 66.3 | JUN-24 | MAR-24 | RFD |  | Standing crops issue
10 | Yadadri TPP switchyard - Jangaon S/S | D/C | 400 | 278 | 402 | 367 | 283 | 44 | DEC-19 | FEB-24 | RFD |  | Works under progress.
11 | YTPP Switchyard - 400kV Dindi SS | D/C | 400 | 208 | 290 | 290 | 290 | 208 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | 400kV Shamli - Aligarh Line | D/C | 400 | 482 | 737 | 737 | 736 | 482 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
2 | Aurai - Mizapur | S/C | 220 | 43 | 148 | 116 | 73 | 0 | DEC-24 |  | RFD |  | Work alloted to M/s Rama Power for completing the left over work on debitable basis. REC scheme is exdhausted. Proposal is under considration for ETF approval.
3 | Aurai - Phoolpur | S/C | 220 | 71 | 223 | 191 | 185 | 41 | DEC-24 |  | RFD |  | Work alloted to M/s Gayatri Ganga for completing the left over work on debitable basis. REC scheme is exhausted. Proposal has been submitted for funding from IR Head is under approval.
4 | Badhaikalan (Muzaffarnagar) - Shamli line | D/C | 220 | 66 | 113 | 113 | 108 | 34 | AUG-24 |  | RFD |  | Work in progress.
5 | Darshan Nagar GIS to Sohawal (Tower NO. 152 of Gonda line) | S/C | 220 | 1 | 2 | 2 | 2 | 1 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
6 | Indrapuram (400 kV)- Sector-62 DC line (Under Ground Cable) | D/C | 220 | 5 | 0 | 0 | 0 |  | DEC-24 |  | RFD |  | Work in progress.
7 | LILO of 220 kV Nara- Jansath line at Meerut(765) | D/C | 220 | 95 | 150 | 142 | 131 | 58.94 | JUN-24 | SEP-24 | RFD |  | Work in progress.
8 | LILO of Aligarh - Shamli Line at Kurja (Power Plant) | D/C | 400 | 21 | 0 | 0 | 0 |  | JUL-24 |  | RFD |  | To be constructed in TBCB mode.
9 | LILO of Badaun(400 kV)- C.B. Ganj line at Badaun Road | D/C | 220 | 1 | 3 | 3 | 3 | 1.2 | JUN-24 |  | RFD |  | Line completed.
10 | LILO of Ckt.II of 400 KV DC Quad Varanasi (PG) (Thathra) -Biharsharif at 400 kV Sahupuri SS (charged on 18-05-2024 however late reported by UPPTCL) | D/C | 400 | 53 | 0 | 0 | 0 | 53 |  | JUL-24 | RFD |  | Commissioned 06/24 (Late Reported).
11 | LILO of Ckt-I of 400kV Varanasi (PG (Thathra) - Biharshariff DC Line at 400kV Sahupuri | D/C | 400 | 52 | 92 | 92 | 92 | 52 | APR-24 | MAY-24 | RFD |  | Commissioned 04/24.
12 | LILO of Unnao(400 kV)- Bithoor line at Trans Ganga city (220 kV) | D/C | 220 | 9 | 19 | 19 | 18 |  | AUG-24 |  | RFD |  | Work in progress.
13 | Modipuram-II-Shamli Line | D/C | 220 | 148 | 262 | 262 | 262 | 147.36 | APR-24 | AUG-24 | RFD |  | Line completed and ready to energized.
14 | Raebareli (400) -Bachhrawan line | D/C | 220 | 162 | 273 | 273 | 28 | 127.72 | JUN-24 | AUG-24 | RFD |  | Work in progress.
15 | Shamli (400) - Deoband line | D/C | 220 | 93 | 150 | 150 | 147 | 32.42 | MAY-24 | AUG-24 | RFD |  | Erection & Stringing work is in progress.
UTTARAKHAND POWER CORPORATION LIMITED ( UKPCL )
1 | Balance work of Baramwari -Srinagar line (Single Zebra conductor from Interconnection point of Singoli Bhatwari HEP to Baramwari) | D/C | 220 | 31 |  |  |  |  | JUN-24 |  | RFD
2 | Pipalkoti-Srinagar Line | D/C | 400 | 173 |  |  |  |  | SEP-24 |  | RFD
3 | Vishnugad-Pipalkoti Line | D/C | 400 | 36 |  |  |  |  | DEC-24 |  | RFD
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
1 | Connectivity between New Bishnupur - Raghunathpur New Bishnupur-Hura Hura-Raghunathpur and connectivity between STPS and Hura 220kV s/s | S/C | 220 | 1 | 2 | 2 | 0 | 0 | OCT-24 | OCT-24 | RFD
2 | LILO of 229kV Domjur-Arambagh line at proposed Khanakul 220kV GIS | D/C | 220 | 11 | 45 | 43 | 40 | 11.04 | MAR-25 | MAR-25 | RFD
3 | LILO of Birpara -Alipurduar line (PGCIL) at proposed line at Falakata s/s | D/C | 220 | 17 | 39 | 39 | 37 | 14.06 | SEP-24 | DEC-24 | RFD |  | All tower foundations are completed only 2 Nos. online tower erection at AP 15/0 & 21A/0 are pending for want of S/D of existing PGCIL 220 KV Line. Falakata Substation is not ready.
4 | LILO of Durgapur -DPL at Durgapur AB Zone (for Upgradation of Durgapur AB Zone S/S | D/C | 220 | 8 | 14 | 14 | 14 | 4.52 | JUL-24 | SEP-24 | RFD |  | All tower foundation and erection work completed. Line will be commissioned matching with Durgapur AB Zone Substation.
5 | LILO of Existing STPS - JK Nagar 220kV line at Asansol 220kV S/S | D/C | 220 | 62 | 126 | 120 | 111 | 45.29 | JUL-24 | DEC-24 | RFD |  | Land owners of Loc 49/2, 46/0, 50/0 are creating severe hinderences in construction work , though several meetings were conducted with various administrative authorities, however till date this issue remain unresolved.
6 | LILO of Gokarna-New Chanditala Transmission Line at proposed Satgachia 400 KV GIS S/S | D/C | 400 | 11 | 22 | 19 | 17 | 0 | JAN-25 | JAN-25 | RFD
7 | STPS - Raghunathpur | D/C | 220 | 45 | 94 | 94 | 94 | 43.85 | MAR-25 | MAR-25 | RFD |  | Hotline power line crossing for AP-9/0 to AP-10/0 was scheduled on 18.07.2024, but it was deferred by SLDC.
PRIVATE SECTOR
ADANI POWER LIMITED ( APL )
1 | Narendra New (GIS) - Pune (GIS) (line with 1x330MVA r switchable line reactor (SLR) on each ckt. at both ends) | D/C | 765 | 636 |  |  |  |  | DEC-24 |  | RFD
Apraava Energy Pvt. Ltd. ( APRAAVA )
1 | Fatehgarh-3- Bhadla-3 400kV D.C line (Quad) line | D/C | 400 | 446 |  |  |  |  | FEB-25 |  | RFD
2 | Fatehgarh-4 - Fatehgarh-3 PS 400kV D/c | D/C | 400 | 42 |  |  |  |  | FEB-25 |  | RFD
Megha Engineering & Infrastructures Limited ( MEGHA )
1 | Khandkha (Srinagar) - Rampura (Kashipur ) line (Twin HTLS) | D/C | 400 | 384 |  |  |  |  | SEP-24 |  | RFD
2 | KPS1-Khavda PS GIS (KPS2) 765kV D/C line | D/C | 765 | 42 |  |  |  |  | FEB-25 |  | RFD
ReNew Transmission Ventures Private Limited ( RTVPL )
1 | Gadag PS- Koppal (PS) line | D/C | 400 | 100 |  |  |  |  | AUG-23 |  | RFD
2 | Gadag (PS) - Narendra (New) Trans. Ltd. | D/C | 400 | 185 | 232 | 160 | 83 | 13 | MAY-24 | SEP-23 | RFD |  | Bagalkot Forest Division : DFO, Bagalkote has recommended the proposal on 03.03.2023 and forwarded to CCF, Belgaum. Gadag Forest Division : Reply against DFO, Gadag queries dated 20.02.2023 was submitted on 02.03.2023. Proposal is pending with DFO, Gadag & PCCF, Karnataka for acceptance and further processing of proposal & ROW compensation fixation order have been issued for Bagalkote, Gadag & Vijayapura Districts (except Koppal district) by the respective DCs on 27.10.2022, 04.03.2023 & 06.03.2023 respectively.
STERLITE GRID LTD. ( SGL )
1 | Bongaigaon (POWERGRID) - Nangalbibra (Twin ACSR Moose) line | D/C | 400 | 246 |  |  |  |  | JUN-24 |  | RFD
2 | Fatehgarh-III PS - Beawar 765 kV D/C line (Rajasthan (20GW) under Phase-III Part F) | D/C | 765 | 635 |  |  |  |  | MAR-25 |  | RFD
3 | Fatehgar III - Beawar 765kV line (Rajasthan (20GW) under Phase-III Part -G) | D/C | 765 | 630 |  |  |  |  | MAR-25 |  | RFD
4 | LILO of 400kV Kota- Merta line at Beawar (Rajasthan (20GW) under Phase-III Part F) | D/C | 400 | 64 |  |  |  |  | MAR-25 |  | RFD
5 | LILO of Apta-Kalwa/Taloja at Navi Mumbai (PG) | D/C | 220 | 5 |  |  |  |  | MAY-24 |  | RFD
6 | LILO of both Ckts. of Ajmer - Chittorgarh 765kV D/C at Beawar (Rajasthan (20GW) under Phase-III Part F) | D/C | 765 | 136 |  |  |  |  | MAR-25 |  | RFD
7 | LILO of Padghe (PG) -Ghatkopar at Navi Mumbai GIS (PG) | S/C | 400 | 38 |  |  |  |  | JUN-24 |  | RFD
8 | Padghe (PG) -Kharghar 400 kV D/C (quad) line | D/C | 400 | 140 |  |  |  |  | JUN-24 |  | RFD
9 | Vapi II -Sayali 220 kV D/C line | D/C | 220 | 45 |  |  |  |  | MAY-24 |  | RFD
10 | Xeldem (Existing) - Xeldem (New) Transmission line | D/C | 220 | 44 |  |  |  |  | JUN-24 |  | RFD
11 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | 400 | 105 | 148 | 14 | 2 |  | JUN-24 | JAN-23 | RFD |  | 1. Delay due to occurrence of Force Majeure (FM) event i.e. outbreak of COVID-19 and this FM event has been intimated to all LTTCs 2.The progress is suffered due to petition filed by Goa Foundation in Central Empowered Committee (CEC) constituted by Supreme court and High Court of Mumbai and Goa 3. The introduction of Guidelines being issued by District Collector, North Goa vide letter dated 06-11-2020 for payment of Additional Compensation towards damages in regards of Right of Way for transmission Line has consequently led to an escalation in the cost of the project and the same is covered under Article 12 of the TSA as Change in law event
Tata Power Ltd ( TATAPOWER )
1 | 400kV D/C Koteshwar - Rishikesh line | D/C | 400 | 77 |  |  |  |  | DEC-24 |  | RFD