## line_completed
Transmission Lines Completed During FY- 2024-25
As on 28-Feb-2025
Voltage Level (kV) | Name of Transmission Lines | Circuit Type | Executing Agency | Line Length (cKM) | Month of Completion
1. | 2. | 3. | 4. | 5. | 6.
765 kV
CENTRAL SECTOR
1 | Fatehgarh II- Bhadla II 765kV D/C Line ( 2nd) Under Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part B | D/C | PGCIL | 405 | AUG-24
2 | Sikar II - Aligarh 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part D) | D/C | PGCIL | 513 | OCT-24
3 | Bhadla II - Sikar II 765 kV D/C line (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | PGCIL | 618 | DEC-24
Total of CENTRAL SECTOR |  |  |  | 1536
Total of 765 kV |  |  |  | 1536
400 kV
CENTRAL SECTOR
4 | Sikar II - Neemrana 400kV D/C line (Twin HTLS) (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | PGCIL | 270 | OCT-24
5 | RIL (Oil Refinery Jamnagar) GIS Jam Khabaliya (GIS) PS line (Antitheft charged in April-2024) | D/C | PGCIL | 90 | JAN-25
Total of CENTRAL SECTOR |  |  |  | 360
STATE SECTOR
6 | LILO of Ckt-I of 400kV Varanasi (PG (Thathra) - Biharshariff DC Line at 400kV Sahupuri | D/C | UPPTCL | 52 | APR-24
7 | LILO of Ckt.II of 400 KV DC Quad Varanasi (PG) (Thathra) -Biharsharif at 400 kV Sahupuri SS (charged on 18-05-2024 however late reported by UPPTCL) | D/C | UPPTCL | 53 | JUN-24
8 | YTPP Switchyard - 400kV Dindi SS | D/C | TSTRANSCO | 208 | JUN-24
9 | LILO of one Ckt. of 400kV Ludhiana PGCIL-Koldam at proposed 400kV s/s Ropar | D/C | PSTCL | 14 | JUL-24
10 | 400kV Shamli - Aligarh Line | D/C | UPPTCL | 482 | JUL-24
11 | LILO of Kayathar - Thennampatti 400 kV line Virudhunagar 765/400 KV SS | D/C | TANTRANSCO | 140 | AUG-24
12 | LILO of 400kV VTS-IV Sattenapalli TMDC line at Thallayapalem and Temporary diversion of PGCIL VTS/Nunna-Nellore 3 and 4 Ckts. to avoid aerial passage over 400/220kV GIS Thallayapalem | D/C | APTRANSCO | 2 | OCT-24
13 | Vemagiri - Kamavarapukota | D/C | APTRANSCO | 116 | OCT-24
14 | LILO of Talegaon -Kalwa at Vikroli (Intra State TBCB) | D/C | MSETCL | 24 | OCT-24
15 | Chandwa - Latehar (JUSNL) line | D/C | JUSNL | 83 | DEC-24
16 | LILO of 400 kV Rajwest-Kankani line at 400 kV Pachpadra GSS | D/C | RVPNL | 72 | DEC-24
17 | LILO of CKT-I of Patna (PG) - Barh (NTPC) at Bakhtiyarpur SS | D/C | BSPTCL | 21 | JAN-25
18 | LILO of CKT-II of Patna (PG) - Barh (NTPC) at Bakhtiyarpur SS | D/C | BSPTCL | 21 | FEB-25
Total of STATE SECTOR |  |  |  | 1288
PRIVATE SECTOR
19 | 400 kV D/C Gadag PS-Narendra (New) line (Trans. Scheme for Solar Energy Zone in Gadag (1000MW) Karnataka-Part-A Phase-I) | D/C | RENEW | 187 | SEP-24
20 | LILO of Padghe (PG)-Ghatkopar/Vikroli 400 kV S/C line at Navi Mumbai GIS(PG) (WRSS-XIX and NERS-IX) | S/C | STERLITE | 38 | SEP-24
21 | Padghe (PG) - Kharghar 400 kV D/C (Quad) line (WRSS-XIX and NERSS-IX) | D/C | STERLITE | 140 | SEP-24
22 | Bongaigaon (POWERGRID) - Nangalbibra (Twin ACSR Moose) line | D/C | STERLITE | 246 | OCT-24
23 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | STERLITE | 106 | OCT-24
Total of PRIVATE SECTOR |  |  |  | 717
Total of 400 kV |  |  |  | 2365
230 kV
STATE SECTOR
24 | Extension of Shoolagiri Karimangalam line (from location no. 6 of Shoolagiri Karimangalam line) to Udanapally 230 KV SS | S/C | TANTRANSCO | 2 | APR-24
25 | UG Cable from Basin Bridge to TNEB Head Quarters | S/C | TANTRANSCO | 6 | APR-24
26 | LILO of 230 kV Basin Bridge -TNEB Head Quarters feeder at Pulianthope 400 KV GIS SS (230KV UG Cable) | D/C | TANTRANSCO | 1 | JUL-24
27 | LILO of Pudhansandhai - Pugalur 230 kV Feeder at Nallur SS | D/C | TANTRANSCO | 12 | JAN-25
Total of STATE SECTOR |  |  |  | 21
Total of 230 kV |  |  |  | 21
220 kV
CENTRAL SECTOR
28 | LILO of CTPS (A) - Kalyaneswari line at RTPS | D/C | DVC | 52 | JUN-24
Total of CENTRAL SECTOR |  |  |  | 52
STATE SECTOR
29 | BTPP - Karmnasa GSS line (twin moose conductor) | D/C | BSPTCL | 59 | APR-24
30 | LILO of both circuits of 220kV D/C Mota - Ambheta (Chikhli) line at proposed 220kV Mahuva | M/C | GETCO | 44 | APR-24
31 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | PSTCL | 16 | APR-24
32 | LILO of 220 KV Balimela Jayanagar Circuit III at 220/33 | D/C | OPTCL | 2 | MAY-24
KV GSS Govindpali
33 | BTPP - Dumraon (New) GSS | D/C | BSPTCL | 129 | MAY-24
34 | Kudligi (Badeladaku) line from existing 220 kV Itagi SS to the proposed Station at Kudligi | D/C | KPTCL | 65 | MAY-24
35 | LILO of 220 kV line New Duburi - Paradeep Circuit I at 220/33 KV GSS Balichandrapur Palei | D/C | OPTCL | 2 | MAY-24
36 | LILO of 220kV VTS-Tallapally-1 at 220/132 kV SS Rentachintala | D/C | APTRANSCO | 3 | MAY-24
37 | 400/220 kV GIS of POWERGRID at Airendwala to 220/132/33 kV AIS of HPPTCL at Andheri Kala Amb Distt. Sirmaur | D/C | HPPTCL | 11 | MAY-24
38 | Pusouli (New) - Dehri | D/C | BSPTCL | 125 | JUN-24
39 | LILO of both circuits of Satna-Chhatarpur 220kV line at Ajaygarh (TBCB) | D/C | MPPTCL | 14 | JUN-24
40 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | D/C | CSPTCL | 45 | JUN-24
41 | LILO of 220 kV S/Stn Mansa - Sunam at 400 kV S/Stn Patran | D/C | PSTCL | 85 | JUN-24
42 | 220 kV Brandix - Atchuthapuram | D/C | APTRANSCO | 7 | JUL-24
43 | 220kV DC line from 400kV Kamavarapukota to 220kV SS Bhimadole SS | D/C | APTRANSCO | 37 | JUL-24
44 | 220 kV D/C Choraniya - Salejada line | D/C | GETCO | 136 | JUL-24
45 | Conversion of 220 kV Bidnal-Soundatti-Mahalingapura S/C line - 220 kV Bidnal - Mahalingapur D/C line | D/C | KPTCL | 125 | JUL-24
46 | LILO of 2nd circuit of 220kV Bidnal -Mahalinapur DC Line at Soundatti SS | D/C | KPTCL | 21 | JUL-24
47 | Sagar - Begamganj 220 kV line (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | D/C | MPPTCL | 125 | JUL-24
48 | 220 kV Koradi-II to Butibori-III DCMC line | D/C | MSETCL | 109 | JUL-24
49 | Connecting 220 kV PGCIL Ludhiana-Doraha SC line with 220 kV Lalton Kalan-Dhandari Kalan forming PGCIL Ludhiana- Dhandari Kalan SC line (charged in June-2024 however late reported by PSTCL) | S/C | PSTCL | 10 | JUL-24
50 | Darshan Nagar GIS to Sohawal (Tower NO. 152 of Gonda line) | S/C | UPPTCL | 1 | JUL-24
51 | LILO of KTPP- Jangalpur 220 kV D/C line at Food Park 220 kV Substation | D/C | WBSETCL | 2 | JUL-24
52 | Damaracherla -Huzurnagar line | D/C | TSTRANSCO | 77 | AUG-24
53 | LILO of 220 kv ongole-Racherlpadu line at 220 kv ss Kandukur | D/C | APTRANSCO | 7 | AUG-24
54 | Devanahalli Hardware Park (WORK-A) from 400 kV DWHP to CTT for Double LILO of 220 kV Nelamanagal -Hoody DC line (Vidyanagar 66kV line corridor) | M/C | KPTCL | 21 | AUG-24
55 | LILO on 220kV Bhigwan Kurkumb line at 400kV Karjat s/s | D/C | MSETCL | 34 | AUG-24
56 | 220 kV Modipuram-II - Shamli Line | D/C | UPPTCL | 150 | AUG-24
57 | LILO of KTPP-Howrah 220 kV D/C Line at Proposed Food Park 220/132 KV GIS S/S | M/C | WBSETCL | 2 | AUG-24
58 | LILO of Mylsandra-Yeradanahalli at Keonics (Electronic City) | D/C | KPTCL | 7 | SEP-24
59 | LILO of 220 kV Shendra- Chitepimpalgaon line at 220 kV Shendra DMIC GIS s/s (UG cable) | D/C | MSETCL | 12 | SEP-24
60 | 220kV D/C line from 220kv Meerpur Kurali to TSS Rundhi as a deposit work of Indian Railway | D/C | HVPNL | 25 | OCT-24
61 | Jerur- Karjat line | D/C | MSETCL | 101 | OCT-24
62 | LILO of Badaun(400 kV)- C.B. Ganj line at Badaun Road | D/C | UPPTCL | 1 | OCT-24
63 | 220 kV Krishnagiri- Nansuralla Line | S/C | APTRANSCO | 24 | NOV-24
64 | Jammalamadugu (400 kV SS) to proposed Bethamcherla (220 kV SS) in Kurnool District | D/C | APTRANSCO | 151 | NOV-24
65 | Banka(PG)-Goradih Transmission line | D/C | BSPTCL | 65 | NOV-24
66 | 220 kV U/G cable from Kashmiri Gate SS to 220 kV Timarpur (GIS) SS | D/C | DTL | 10 | NOV-24
67 | Sonepat to GIS Rai line (late reported commissioned in May-2024) | D/C | HVPNL | 51 | NOV-24
68 | LILO of 220 kV Allipura-Ragalapadu line at Somasamudra SS | D/C | KPTCL | 12 | NOV-24
69 | LILO of Somanahalli-hoody line at Keonics (Electronic City) | D/C | KPTCL | 14 | NOV-24
70 | 220 kV D/C Surpura-Banar line (late reported commissioned in October-2024) | D/C | RVPNL | 20 | NOV-24
71 | LILO of 220 kV Durgapur -DPL unit-8 line at AB Zone 220 kV Substation. | D/C | WBSETCL | 8 | NOV-24
72 | LILO of Sec -72 Gurugram (PGCIL 400 kV SS) to Sec -72 Gurugram (HVPNL 220 kV SS) ckt - IV at 220 kV Sec 15-II Gurugram220kV Sec 15-II Gurugram | D/C | HVPNL | 16 | DEC-24
73 | LILO of existing 220 kV Madanapalli-Palamaner line to 220 kV Punganur S/S | D/C | APTRANSCO | 5 | DEC-24
74 | LILO of both circuits of 220 kV D/C Jambuva - Karamsad line at Dhuvaran CCPP | D/C | GETCO | 18 | DEC-24
75 | LILO of 220 kV D/C Bajoli Holi to Lahal Transmission Line at 220/66 kV Heiling S/S | D/C | HPPTCL | 1 | DEC-24
76 | Powerloom metta to Parambayi | M/C | KSEB | 1 | DEC-24
77 | LILO of both circuits of Sidhi - Hindalco 220 kV line at Bargawan (220 kV) S/s (TBCB)(late reported commissioned in Nov-2024) | D/C | MPPTCL | 8 | DEC-24
78 | LILO of 220 kV Jalna - Chikhali line at 220 kV Nagewadi S/s | D/C | MSETCL | 3 | DEC-24
79 | LILO of 220 kV Balotra-Boranada line at 400 kV Pachpadra GSS | D/C | RVPNL | 18 | DEC-24
80 | Tajpur - Samastipur line (late reported antitheft charged in Dec-24) | D/C | BSPTCL | 41 | JAN-25
81 | Thakurganj-Kishanganj line (Antitheft Charged) | D/C | BSPTCL | 95 | JAN-25
82 | 220 kV D/C Motigop Babarzar line (Babarzar gantry to AP 7) - (charged by connecting to stopgap SS) | D/C | GETCO | 5 | JAN-25
83 | LILO of both circuits of Sidhi - Hindalco line at Bargawan 220 kV S/s (Intrastate TBCB) (8 ckm reported earlier however revised to 17 ckm hence additional length considered in Jan-2025) | D/C | MPPTCL | 9 | JAN-25
84 | LILO of 220kV Eklahare - Navsari line (ckt-I) at 220 kV Reliance Life science GIS SS | S/C | MSETCL | 1 | JAN-25
85 | Pachpadra (400kV GSS)- HRRL (Hindustan Rajasthan Refinery Limited) line Ckt-I and Ckt-II | D/C | RVPNL | 30 | JAN-25
86 | LILO of STPS - J K NAGAR line at 220 kV Asansol SS | D/C | WBSETCL | 63 | JAN-25
87 | LILO of Kamavarapukota (220 kV) - Nuziveedu line at Kamavarapukota SS (400 kV) | S/C | APTRANSCO | 3 | FEB-25
88 | Kurud-Rajim line (Ckt-I) | D/C | CSPTCL | 33 | FEB-25
89 | Ghangapura (Nimbarga) SS to Sindagi (Aheri) SS in Vijayapura Dist | D/C | KPTCL | 112 | FEB-25
90 | Halabarga SS to Santhpur SS | D/C | KPTCL | 57 | FEB-25
91 | Narsapur - Bowrampet line | MC+D/C | TSTRANSCO | 149 | FEB-25
92 | Bachhrawan-Sirsira (400) line | D/C | UPPTCL | 161 | FEB-25
93 | Shatabdinagar- NCRTC RSS line | D/C | UPPTCL | 5 | FEB-25
94 | Unnao(400)- Ajgain TSS Line | S/C | UPPTCL | 12 | FEB-25
Total of STATE SECTOR |  |  |  | 2811
PRIVATE SECTOR
95 | Vapi-II-Sayali 220 kV D/C line (WRSS-XIX and NERSS-IX) | D/C | STERLITE | 45 | SEP-24
96 | Xeldem (Existing) - Xeldem (New) Transmission line | D/C | STERLITE | 45 | OCT-24
97 | LILO of Apta-Kalwa/Taloja at Navi Mumbai (PG) | D/C | STERLITE | 5 | OCT-24
Total of PRIVATE SECTOR |  |  |  | 95
Total of 220 kV |  |  |  | 2958
Grand Total |  |  |  | 6880