## line_construction_status_test_r
REPORT INDICATING STATUS OF CONSTRUCTION OF TRANSMISSION LINES (220 kV & ABOVE) IN RFD PROGRAMME DURING- 2024-25
As on 31-MAR-2025
Sl No | Name of Transmission Lines | Ckts (S/C) & (D/C) | Voltage Level (kV) | Total Length (cKm) | Progress Status of Transmission |  |  |  | Target Date |  | Tag Names |  | Remarks
[5 empty] | Total Locations (Nos) | Foundation completed (Nos) | Tower Erected (Nos) | Stringing completed (CKm) | Schedule | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12. |  | 13.
CENTRAL SECTOR
DAMODAR VALLEY CORPORATION ( DVC )
1 | LILO of CTPS (A) - Kalyaneswari line at RTPS | D/C | 220 | 52 | 72 | 72 | 72 | 52 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
2 | LILO of MTPS (A) - Borjora line at MTPS (B) | D/C | 220 | 84 | 76 | 76 | 76 | 84 | MAY-24 | APR-25 | RFD |  | Delay due to severe ROW problem and non-obtaining of Forest clearance. Stage I Forest Clerance received. FRA received. Application for Stage 2 Forest Clearnce submitted and is in process, clearance awaited. Tree cutting in presence of Forest Department completed. Foundation, erection and stringing completed. CEA inspection done and clearance received. Revised date of completion changed to April'2025.
POWER GRID CORPORATION OF INDIA LIMITED ( PGCIL )
1 | 2nd Circuit of Kishenpur - Dulhasti 400kV D/c (Q) line (Kishtwar - Kishenpur Section) | S/C | 400 | 130 | 29 | 21 | 17 | 73.15 | MAR-25 |  | RFD
2 | 400kV D/C Jeypore (POWERGRID) - Jagdalpur (CSPTCL) line | D/C | 400 | 137 | 172 | 112 | 1 |  | MAR-25 |  | RFD |  | 1) Forest Chhatisgarh (4.48 Ha): Forest proposal for Chhattisgarh submitted on 09.06.23, Revised Proposal Submitted on 09/11/2023​.Stage-I Awaited.2) Forest Odisha (18.1 Ha): Forest proposal for Jeypore (Odisha) side initially submitted in Oct 2023 which got rejected. Stage-I Awaited.
3 | 765kV Dc/KPS2-KPS3 line | D/C | 765 | 30 | 40 | 17 | 0 |  | MAR-25 |  | RFD |  | Stone piling work in progress.
4 | 765 kV D/C Kurnool III (PS) - Kurnool (New) line Part-A and Part-B | D/C | 765 | 226 | 299 | 299 | 299 | 226 | MAR-25 | APR-25 | RFD |  | Commissioned 03/25.
5 | Banskantha-Ahemadabad line | D/C | 765 | 269 | 362 | 143 | 45 |  | MAR-25 |  | RFD |  | Patan Dist.: Section 16 (1) Orders awaited: 30 locs. Mehsana: Orders awaited: 04 locs. Ahmedabad: Orders awaited: 29 locs.
6 | Bhadla II - Sikar II 765 kV D/C line (2nd) Rajasthan (8.1 GW) under Phase-II Part-E | D/C | 765 | 600 | 816 | 469 | 175 |  | DEC-24 |  | RFD |  | RoW issues at 7 loc. in Sikar, 37 loc. in Didwana Kuchman . Forest (0.77 Ha): Proposal submitted on 23.10.23. Stage-I clearance accorded on 10.04.24. Working permission Awaited.
7 | Bhadla II - Sikar II 765 kV D/C line (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 765 | 618 | 808 | 808 | 808 | 618 | DEC-24 | JAN-25 | RFD |  | Commissioned 12/24.
8 | Fatehgarh II- Bhadla II 765kV D/C Line ( 2nd) Under Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part B | D/C | 765 | 405 | 529 | 529 | 529 | 405 | MAY-24 | SEP-24 | RFD |  | Commissioned 08/24.
9 | Khetri-Narela 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part G) | D/C | 765 | 340 | 463 | 366 | 320 | 60 | JUL-24 | SEP-24 | RFD |  | 1. RoW at 88 loc. in Jhajjar district in Haryana. 2. RoW at 8 loc. in North Delhi district
10 | Kurnool - III - Maheshwaram (PG) (PGCIL-RTM) | D/C | 765 | 504 | 673 | 345 | 48 |  | MAR-25 | DEC-19 | RFD |  | Forest: 26.993 Ha: Stage-I Approval Pending
11 | Laying of cable between Minamarg and Zojilla top section of Alusteng- Drass 220kV Section | S/C | 220 | 12 | 0 | 0 | 0 |  | DEC-24 |  | RFD |  | Present Status: Cable Trench-Excavation Work under progress (5.0 Km completed).PCC --3.685 km Completed HDPE Pipe-2.65/12 Km laying along with jointing completed. Note:- Work is at halt due to extreme weather conditions
12 | LILO of 765kV S/C Meerut -Bhiwani line at Narela | S/C | 765 | 68 | 97 | 58 | 24 |  | JUL-24 | SEP-24 | RFD |  | 1. RoW at 27 loc. in Sonipat district in Haryana. 2. RoW at 12 loc. in North Delhi district
13 | Magarwada (GIS) - Kala (GIS) 400 kV D/C line | D/C | 400 | 89 | 149 | 71 | 13 |  | DEC-24 |  | RFD |  | Gujarat: Valsad Dist. Orders awaited: 01 loc. Maharashtra: RoW are being faced at 30 locs. in palghar Dist. Farmers/landowners are demanding rate revision of land compensation.
14 | Navsari (New (South Gujarat) (GIS) - Padghe (GIS) 765 kV D/C line | D/C | 765 | 453 | 616 | 331 | 136 | 5.57 | DEC-24 |  | RFD |  | Navsari Dist.: Section 16 (1) Orders awaited: 24 locs. Valsad: Orders awaited: 01 loc. ROW issues are being faced in 13 locations in Palghar & 29 locatrions in Thane district in construction of 765 kV D/C Navsari (New) - Padghe (GIS) TL of Maharashtrafor portion. Farmers/landowners are demanding high compensation.
15 | Navsari (New) (South Gujurat) (GIS) - Magarwada (GIS)400kV D/C line | M/C | 400 | 385 | 266 | 235 | 115 |  | DEC-24 |  | RFD |  | Daman: Section 16(1) Orders awaited: 04 locs. Navsari Dist.: Section 16 (1) Orders awaited: 3 locs. Valsad Dist. Section 16(1) Orders awaited: 06 locs.
16 | Raipur Pool - Dhamtari 400 kV D/C line under Project WRES-XXVII (SPV Name POWERGRID Raipur Pool Dhamtari Transmission Limited) | D/C | 400 | 176 | 232 | 232 | 232 | 176 | DEC-24 | APR-25 | RFD |  | Commissioned 03/25.
17 | Removal of LILO of Bawana- Mandola 400kv D/C line at Maharanibagh s/s and Extension of above LILO section from Maharanibagh upto Narela s/s so as to from 2x400 kV D/C Maharanibagh- Narela line on Mult | D/C | 400 | 57 | 123 | 63 | 38 | 4 | JUL-24 | SEP-24 | RFD |  | Work affected due to RoW Issue at 30 locations in Delhi
18 | Sikar II - Aligarh 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part D) | D/C | 765 | 513 | 679 | 679 | 679 | 513 | DEC-24 | NOV-24 | RFD |  | Commissioned 10/24.
19 | Sikar II - Neemrana 400kV D/C line (Twin HTLS) (Rajasthan (8.1 GW) under phase-II- Part C) | D/C | 400 | 270 | 368 | 368 | 368 | 270 | DEC-24 | NOV-24 | RFD |  | Commissioned 10/24.
STATE SECTOR
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED ( BSPTCL )
1 | Bakhtiyarpur (New) - Fatuha (BSPTCL) | D/C | 220 | 92 | 157 | 142 | 107 | 0 | OCT-24 | DEC-22 | RFD |  | Work under progress.
2 | Banka(PG)-Goradih Transmission line | D/C | 220 | 65 | 0 | 0 | 0 | 65 | SEP-24 | DEC-24 | RFD |  | Commissioned 11/24.
3 | BTPP - Dumraon (New) GSS | D/C | 220 | 129 | 215 | 215 | 215 | 129 | MAY-24 | JUN-24 | RFD |  | Commissioned 05/24. (ANTITHEFT CHARGED on 13-05-2024)
4 | LILO of CKT-II of Patna (PG) - Barh (NTPC) at Bakhtiyarpur SS | D/C | 400 | 21 | 0 | 0 | 0 | 20 |  | MAR-25 | RFD |  | Commissioned 02/25.
5 | LILO of CKT-I of Patna (PG) - Barh (NTPC) at Bakhtiyarpur SS | D/C | 400 | 21 | 61 | 61 | 61 | 21 | OCT-24 | FEB-25 | RFD |  | Commissioned 01/25.
6 | LILO of Sipara (BSPTCL) - Bihta (BSPTCL) at Jakkanpur (New) | D/C | 220 | 47 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | M/s BGCL
7 | Pusouli (New) - Dehri | D/C | 220 | 125 | 159 | 159 | 159 | 125 | MAY-24 | JUL-24 | RFD |  | Commissioned 06/24.
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD. ( CSPTCL )
1 | Kurud-Gurur line | D/C | 220 | 74 |  |  |  |  | DEC-24 |  | RFD
2 | Kurud-Rajim line (Ckt-I) | D/C | 220 | 33 | 0 | 0 | 0 | 33 | FEB-25 | MAR-25 | RFD |  | Commissioned 01/25.
3 | LILO of 400kV Raita-Jagdalpur line at 400kV Kurud (Dhamtari) s/s | D/C | 400 | 3 |  |  |  |  | SEP-24 |  | RFD
4 | LILO of Khedamara-Thelkadih at Semariya | D/C | 220 | 3 |  |  |  |  | DEC-24 |  | RFD
5 | Patan (Upgradation of existing 132/33 KV S/s by 220/132 KV S/s ) | D/C | 220 | 45 | 0 | 0 | 0 | 44 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
DELHI TRANSCO LIMITED ( DTL )
1 | 220kV D/C underground cable from IP -New Rajghat GIS | D/C | 220 | 4 |  |  |  |  | MAR-25 |  | RFD
2 | 220 kV U/G cable from Kashmiri Gate SS to 220 kV Timarpur (GIS) SS | D/C | 220 | 10 | 0 | 0 | 0 | 10 | JUN-24 | DEC-24 | RFD |  | Commissioned 11/24.
GUJARAT ENERGY TRANSMISSION CORP. LIMITED ( GETCO )
1 | 220 kV D/C Choraniya - Salejada line | D/C | 220 | 136 | 221 | 221 | 221 | 136 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
2 | 220kV D/C Motigop Babarzar line (AP-7-Motigop gantry) | D/C | 220 | 32 |  |  |  |  | SEP-24 |  | RFD
3 | 220 kV D/C Motigop Babarzar line (Babarzar gantry to AP 7) - (charged by connecting to stopgap SS) | D/C | 220 | 5 | 0 | 0 | 0 | 5 | SEP-24 | FEB-25 | RFD |  | Commissioned 01/25.
4 | 220kV D/C Shapar- Ghiyavad line with AL-59 Conductor | D/C | 220 | 85 | 168 | 116 | 108 | 36.47 | SEP-24 | SEP-24 | RFD
5 | 220kV S/C Dhama-Bechraji line on 220kV D/C towers (Tap location of existing220kV Bechraji-Surel line to 220kV Dhama S/S | D/C | 220 | 23 |  |  |  |  | JAN-25 |  | RFD
6 | 400kV D/C Shapar-Pachcham (Fedra) Line with Twin AL-59 cond. and 1 OPGW and 1 Earth Wire | D/C | 400 | 197 | 301 | 289 | 279 | 114.16 | JUN-24 | DEC-24 | RFD |  | WIP
7 | 400kV D/C Varsana-Halvad (PACKAGE-1) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 144 |  |  |  |  | DEC-24 |  | RFD
8 | 400kV D/C Varsana-Halvad (PACKAGE-2) (Varsana -AP-44) with Quad Moose Condu and 1 OPGW and 1 Earth Wire | D/C | 400 | 94 |  |  |  |  | DEC-24 |  | RFD
9 | Balance work of 400kV D/C Vadavi -Halvad Line (PACKAGE-2) (AP-41 to Halvad) with Twin AL-59 Condu. and 1 and OPGW and 1 Earth Wire | D/C | 400 | 149 |  |  |  |  | JUN-24 |  | RFD
10 | Gavasad - Salejada line with AL-59 conductor and Earth Wire | D/C | 220 | 194 | 327 | 305 | 289 | 146.93 | JUN-24 | SEP-24 | RFD |  | W I P / Severe RoW problems
11 | LILO of both Ckts. of 220kV D/C Kalawad-Kangasiyali line at Siddheshwar s/s | D/C | 220 | 10 |  |  |  |  | JUL-24 |  | RFD
HARYANA VIDYUT PRASARAN NIGAM LIMITED ( HVPNL )
1 | 220kV D/C line from 220kv Meerpur Kurali to TSS Rundhi as a deposit work of Indian Railway | D/C | 220 | 25 | 47 | 47 | 47 | 25 | MAY-24 | NOV-24 | RFD |  | Commissioned 10/24.
2 | 220 kV D/C Line from 220KV S/S Sonipat - 220KV Sector-6 Sonipat | D/C | 220 | 6 | 14 | 12 | 0 | 0 | MAR-25 | MAY-25 | RFD |  | Amount deposited to HSVP in lieu of tree cutting, tree cutting in progress. Work in progress
3 | 220kV D/C line from 400kV PGCIL Panchkula to 220kV Sadhaura | D/C | 220 | 76 | 163 | 135 | 71 | 5.63 | AUG-24 | MAY-25 | RFD |  | ROW issue TL no. 14 to 38 due to farmer agitation demanding higher compensation and not satisfied with the latest compensation policy notified on 10.07.2024..
4 | 220kV D/C line from 765kV S/stn. PGCIL Bhiwani to 220kV S/stn. Isherwal | D/C | 220 | 100 | 212 | 209 | 193 | 37.83 | JUL-24 | JUN-25 | RFD |  | Severe RoW due to the Kissan union interference.
5 | 220kV D/C line on M/C towers from 400kV S/S Prithla - 220kV S/Stn. Sector 78 FBD | D/C | 220 | 59 | 169 | 168 | 136 | 0.97 | SEP-24 | JUL-25 | RFD |  | RoW issue. Slow progress by the firm. Work in progress
6 | 220KV KV D/C Line from 400KV S/Stn PGCIL Bahadurgarh to IMT Pocket-B Kharkhoda | D/C | 220 | 56 | 106 | 44 | 25 | 0 | MAR-25 | JUN-25 | RFD |  | ROW issue at few location. forest clearance, 2 no. NHAI crossing, 1 available crossing pending
7 | 220KV KV D/C Line from 400KV S/Stn PGCIL Sonipat to IMT Pocket-A Kharkhoda | D/C | 220 | 44 | 89 | 88 | 67 | 5.08 | MAR-25 | MAY-25 | RFD |  | Forest clearance is pending. and one no. NHAI crossing pending.
8 | LILO of 220KV D/C PTPS Jind line at 400KV PGCIL Khatkar (Jind) | M/C | 220 | 18 | 46 | 46 | 46 | 5.5 | MAR-25 | MAR-25 | RFD |  | Line has been test charged.
9 | LILO of 220KV Mohana- Samalkha D/C line at 400KV S/S Jhajji (PGCIL) on M/C towers | M/C | 220 | 13 | 24 | 24 | 24 | 2.69 | JUN-24 | MAR-25 | RFD |  | Stage 2 forest approval is pending.. It is expected stage-2 clearance will be received very soon. The remaining strining work in the forest area will be done subsequently.
10 | LILO of both circuit of 220 kV PTPS-Jind D/C line at 220 kV Nain SS | M/C | 220 | 32 | 39 | 39 | 39 | 32 | FEB-25 | APR-25 | RFD |  | Commissioned 03/25.
11 | LILO of Both Circuits of 220kV PGCIL Hisar- Fatehabad D/C line at 220kV Chikanwas (Hisar) with 0.4 sq. inch ACSR | M/C | 220 | 19 | 25 | 25 | 23 | 4.64 | MAR-25 | MAR-25 | RFD |  | Work of OPGW on existing line is in progress.
12 | LILO of both Ckts of 220kV Pali-Sector-65 D/C Line at 400kV S/S Kadarpur | M/C | 220 | 26 | 45 | 45 | 45 | 24 | MAY-24 | MAR-25 | RFD |  | Erection of telecommunication equipment is in progress.
13 | LILO of one ckt of 220kV D/C Samaypur-Palwal at 220kV Harfali | D/C | 220 | 19 | 4 | 4 | 4 | 19 | MAR-25 | APR-25 | RFD |  | Commissioned 03/25.
14 | LILO of Sec -72 Gurugram (PGCIL 400 kV SS) to Sec -72 Gurugram (HVPNL 220 kV SS) ckt - IV at 220 kV Sec 15-II Gurugram220kV Sec 15-II Gurugram | D/C | 220 | 16 | 28 | 28 | 28 | 16 | MAY-24 | DEC-24 | RFD |  | Commissioned in Dec-2024
15 | LILO of Tepla (220kV) - Madanpur (220kV) line at 220kV Sadhaura S/S and LILO of Tepla (220kV) to Rajwali (220kV) at 220kV Sadhaura S/S | M/C | 220 | 103 | 128 | 128 | 123 | 72.77 | AUG-24 | MAY-25 | RFD |  | Delay in forest clearance.
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD. ( HPPTCL )
1 | 220/132kV MCT Transmission Line from Kala Amb to T-19 of Jamta Kala Amb Line | M/C | 220 | 36 |  |  |  | 36 | JUL-24 | OCT-24 | RFD |  | Commissioned 09/24.
2 | 400/220 kV GIS of POWERGRID at Airendwala to 220/132/33 kV AIS of HPPTCL at Andheri Kala Amb Distt. Sirmaur | D/C | 220 | 11 | 0 | 0 | 0 | 11 | APR-24 | JUN-24 | RFD |  | Commissioned 05/24.
3 | LILO of 220 kV D/C Bajoli Holi to Lahal Transmission Line at 220/66 kV Heiling S/S | D/C | 220 | 1 | 0 | 0 | 0 | 1 | JUL-24 | JAN-25 | RFD |  | Commissioned 12/24.
4 | LILO of 400kV Lahal Rajera Transmission line at Kuther (240 MW) HEP | D/C | 400 | 1 |  |  |  |  | JUN-24 |  | RFD
5 | Stringing of 2nd Circuit from Dehar HEP of BBMB to Kangoo S/S | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-24 | MAR-23 | RFD
JHARKHAND URJA SANCHAR NIGAM LTD. ( JUSNL )
1 | Chandwa - Latehar (JUSNL) line | D/C | 400 | 83 | 122 | 122 | 122 | 83 | OCT-24 | JAN-25 | RFD |  | Commissioned 12/24.
2 | LILO of 220kV D/C Govindpur -TTPS at Jainmore | D/C | 220 | 47 | 92 | 82 | 67 | 24.3 | OCT-24 | MAR-23 | RFD |  | Work in Progress.
3 | PUVNL- Patratu | D/C | 400 | 14 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Request letter regarding additional fund as difference of sanctioned cost and offered price of L-1 bidder has been sent to energy dept. Govt of Jharkhand. After sanctioning of requisite fund, work order will be issued.
KARNATAKA POWER TRANSMISSION CORP. LIMITED ( KPTCL )
1 | 220kV CB Pura I/A -Work-A Construction of 220kV DC LILO line from proposed 220 kV Chintamani-Mittemari D/ C line (both Ckts.) at proposed 220kV CTT | D/C | 220 | 111 | 101 | 75 | 70 | 32 | NOV-24 |  | RFD |  | Work under progress
2 | 400/220 kV BTPS(Kudithini) to Somasamudra S/s for a distance of 20.387 Kms | D/C | 220 | 41 | 64 | 64 | 64 | 41 | AUG-24 | APR-25 | RFD |  | Commissioned 03/25.
3 | Conversion of 220 kV Bidnal-Soundatti-Mahalingapura S/C line - 220 kV Bidnal - Mahalingapur D/C line | D/C | 220 | 125 | 457 | 457 | 457 | 125 | JUL-24 | AUG-24 | RFD |  | Commissioned 07/24.
4 | Ghanagapura - Aaheri line | D/C | 220 | 112 | 215 | 214 | 212 | 88.72 | SEP-24 | DEC-24 | RFD |  | Work under progress
5 | Ghanagapura - link Shahpur - Khanapura line | D/C | 220 | 21 | 32 | 17 | 14 |  | SEP-24 | MAR-25 | RFD |  | Tower no. 6 to 22(7.161km) is under SEW by Shree cements ltd. Hence the work will be completed 3months from the date of LOI of SEW.
6 | Ghangapura (Nimbarga) SS to Sindagi (Aheri) SS in Vijayapura Dist | D/C | 220 | 112 | 0 | 0 | 0 | 112 |  | MAR-25 | RFD |  | Commissioned 02/25.
7 | Halabarga SS to Santhpur SS | D/C | 220 | 57 | 103 | 103 | 103 | 57 | AUG-24 | MAR-25 | RFD |  | Commissioned 02/25.
8 | Hangal Construction of 220kV DC line on DC towers from 220 kV Hiremallanahole (Jagalur) to Hangal D/C Line | D/C | 220 | 73 | 140 | 87 | 59 | 0.85 | FEB-25 | FEB-25 | RFD |  | WUP
9 | LILO of 220 kV Allipura-Ragalapadu line at Somasamudra SS | D/C | 220 | 12 | 28 | 28 | 28 | 12 | AUG-24 | DEC-24 | RFD |  | Commissioned 11/24.
10 | LILO of 220kV Kudigi-Vajramatti DC line at proposed 220/110kV Bilagi S/S | D/C | 220 | 74 | 73 | 62 | 35 | 25.99 | OCT-24 |  | RFD |  | Some of the towers are coming under Krishna Back water area.
11 | LILO of Mylsandra-Yeradanahalli at Keonics (Electronic City) | D/C | 220 | 7 | 7 | 7 | 7 | 7 | MAY-24 | OCT-24 | RFD |  | Commissioned 09/24.
12 | LILO of Somanahalli-hoody line at Keonics (Electronic City) | D/C | 220 | 14 | 0 | 0 | 0 | 14 | MAY-24 | DEC-24 | RFD |  | Commissioned 11/24.
13 | Srinivasapura from existing s/s -to the proposed Srinivasapura s/s | D/C | 220 | 48 | 99 | 99 | 99 | 48 | OCT-23 | NOV-23 | RFD |  | Commissioned 10/23.
14 | Yelburga from the existing 220/110/11kV Kushtagi S/S- the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 68 | 68 | 59 | 1 | 0 | AUG-24 |  | RFD |  | Work under progress
15 | Yelburga from the existing 220/110/11kV Kushtagi S/S -to the proposed 220/110/11kV Yelburga S/S | D/C | 220 | 57 | 113 | 97 | 84 | 24 | AUG-24 |  | RFD |  | Work under progress
KERALA STATE ELECTRICITY BOARD ( KSEB )
1 | Kanhirode-Mylatty 220 kV DC line | D/C | 220 | 168 | 273 | 271 | 271 | 159.62 | JUN-24 | JUN-25 | RFD |  | Unexpected rain and water logged tower locations.The work is executed in a phased manner by upgrading existing 110kV to 220kV line. Final lap of phase IV , is delayed due to public objection and litigation.
2 | Pathanamthitta - Kakkad s/s | D/C | 220 | 114 | 197 | 177 | 169 | 86.55 | MAY-24 | JAN-25 | RFD |  | Delay due to continuous rain at Pathanamthitta and Kakkad area, Litigation in Adoor -Edappon line. In Kakkad area the line passess through the forest area where "grow more food scheme" implementd by the forest department. Disbursement of compensation issues led to mass protest from public.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD. ( MSETCL )
1 | 220kV DC Kalmeshwar-Warud (PhaseI and II ) (from Kalmeshwar s/s to loc no 90) | D/C | 220 | 53 | 75 | 75 | 75 | 43.34 | DEC-23 | MAR-25 | RFD |  | Commissioned 03/24 (Partially Charged (Package -III Shifted to FY -2024-25). Balance phase III to be included in Target. Only stringing between 3 spans( 1Km) in forest balance, forest approval awaited. NBWL: Proposal approved by MoEF & CC subject to use of insulated conductors. Meeting held on 21.12.2024 with MoEFCC, Delhi, minutes awaited.
2 | 220KV DC Kalmeshwar-Warud Phase-III | D/C | 220 | 45 | 75 | 75 | 75 | 45 | JUN-24 | APR-25 | RFD |  | Commissioned 03/25.
3 | 220kV D/C line from Vishwind- Bhenda | D/C | 220 | 86 | 141 | 140 | 139 | 64.19 | JUN-24 | MAR-25 | RFD |  | 1. Severe ROW in Saundala, Vaiju Babhulgaon & Lohsar village. 2. Police protection in Saundala availed but could not be utilized due to Local political interference, FIR lodged. 3. 3 towers collapsed on 30.07.2024 out of which 2 foundations re-casted. Rework is also creating ROW.
4 | 220 kV Koradi-II to Butibori-III DCMC line | D/C | 220 | 109 | 189 | 189 | 189 | 109 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
5 | 220 kV Kumbhargaon - Kurunda line (Pkg-B) | D/C | 220 | 57 | 107 | 107 | 107 | 57 | JUN-24 | APR-25 | RFD |  | Commissioned 03/25.
6 | 220KV Nagewadi- Bhokardhan line | D/C | 220 | 90 | 151 | 142 | 138 | 66.45 | JUN-24 | MAR-25 | RFD |  | 1) Severe ROW issues. Order under section 16 awaited from Collector Jalna for 3 locs. Hearing is conducted on 03.02.205. 2) Valuation given by concerned SDOs, however, farmers denied and asked to revisit and revaluation. 3) Supply of narrow base towers -6 nos awaited.
7 | Babhaleshwar-Kudus DC line | D/C | 220 | 457 | 719 | 690 | 678 | 311.76 | DEC-24 | MAR-25 | RFD |  | i) Severe RoW issues at Ale village for 22 locations. Ii) And fresh ROW are being faced due to delay in providing police protection and help from revenue Authorities.Police Protection received on 09.09.24 but work could not started due to strong oppose from cultivators and intervention from leaders. Negotiation with cultivators is under progress. Meeting conducted at Honble Collector Pune on 07.01.2025.
8 | Jerur- Karjat line | D/C | 220 | 101 | 163 | 163 | 163 | 101 | MAY-24 | NOV-24 | RFD |  | Commissioned 10/24.
9 | LILO of 220kV Kalwa- Bapgaon line at Mankoli s/s | D/C | 220 | 1 | 4 | 4 | 4 | 1 |  | FEB-25 | RFD |  | 1) Substation work delayed due to modification in technical specifications of 220kV GIS modules and cable size. 2)Line test charged on 01.02.2025 by bunching at SS end. Substation work is in progress.
10 | LILO of 220 kV M/C Tarapur-Borivali and Boisar-Ghodbandar line at Kudus (400 kV SS) | M/C | 220 | 126 | 120 | 120 | 120 | 126 | NOV-24 | APR-25 | RFD |  | Commissioned 03/25.
11 | LILO of 220 kV Shendra- Chitepimpalgaon line at 220 kV Shendra DMIC GIS s/s (UG cable) | D/C | 220 | 12 |  |  |  | 12 | JUN-24 | OCT-24 | RFD |  | Commissioned 09/24.
12 | LILO on 220kV Bhigwan Kurkumb line at 400kV Karjat s/s | D/C | 220 | 34 | 52 | 52 | 52 | 34 | MAY-24 | SEP-24 | RFD |  | Commissioned 08/24.
13 | LILO on Kolshet-Wada and Padghe-Wada line at 400kV Kudus S/s | M/C | 220 | 36 | 50 | 29 | 27 | 14.8 | DEC-24 | MAR-25 | RFD |  | 1) All works except forest area completed. 2) PCCF, Wild life permission received on 08.10.2024. 3) APCCF Nagpur forwarded proposal to IRO Nagpur on 11.11.2024. 4) IRO Nagpur raised query on 23.12.2024. Queries received at CCF Thane on 06.01.2025. 5) Meeting conducted at DCF Thane on 31.01.2025, reply will be submitted soon. 6) As all works except forest area completed, work can be scheduled on receipt of forest approval.
14 | Umred S/stn to Nagbhid s/s (Part-II) | D/C | 220 | 49 | 94 | 90 | 90 | 32.47 | NOV-24 | MAR-25 | RFD |  | i) Last 4 locations in forest balance, Forest approval awaited. ii) NBWL: Proposal approved by MoEF & CC on 21.10.2024 subject to use of insulated conductors. Meeting conducted on 21.12.2024 with MoEFCC, Delhi, MSETCL's representation for review of use of insulated conductor is considered. Accordingly, amended MOM received with modification in place of use of insulated conductor.
15 | Uppalwadi-Pardi UG Cable | D/C | 220 | 26 | 0 | 0 | 0 | 24.21 | JUN-24 | MAR-25 | RFD |  | 1) Involvement of 4 bridges & HDD (Horizontal Directional Drilling) work for which permission from Nagpur Municipal Corporation and Railways received late. 2) NMC structural Bridge ramp Fabrication work on Nag river is completed. Cable laying setup preparation work under progress.
M.P. POWER TRANSMISSION CORPORATION LIMITED ( MPPTCL )
1 | LILO of both circuit of Itarsi (PGCIL) - Bhopal 400kV line (on Twin Moose) at Mandideep 400kV S/s | D/C | 400 | 20 | 7 | 7 | 0 | 0 |  | DEC-25 | RFD |  | TBCB work . Work needed is only 7.16 CktKm based on revised location of S/s.
2 | LILO of both circuits of Hoshangabad - Mandideep - Adampur 220kV line at Mandideep 400kV S/s | D/C | 220 | 40 | 6 | 0 | 0 | 0 | JAN-25 | DEC-25 | RFD |  | TBCB work. Work needed is only 6.08 cktkm based on revised location of S/s.
3 | LILO of both circuits of Satna-Chhatarpur 220kV line at Ajaygarh (TBCB) | D/C | 220 | 14 | 0 | 0 | 0 | 14 | DEC-24 | JUL-24 | RFD |  | Commissioned 06/24.
4 | LILO of both circuits of Satpura-Itarsi-Handiya 220kV line at Bisonikala 220 kV S/s | D/C | 220 | 20 | 15 | 0 | 0 |  | JAN-25 | NOV-25 | RFD |  | TBCB work. Work needed is only 17 cktkm based on revised location of S/s.
5 | LILO of both circuits of Sidhi - Hindalco 220 kV line at Bargawan (220 kV) S/s (TBCB)(late reported commissioned in Nov-2024) | D/C | 220 | 8 | 21 | 21 | 21 | 8 | DEC-24 | JAN-25 | RFD |  | Commissioned 12/24.
6 | LILO of both circuits of Sidhi - Hindalco line at Bargawan 220 kV S/s (Intrastate TBCB) (8 ckm reported earlier however revised to 17 ckm hence additional length considered in Jan-2025) | D/C | 220 | 9 | 0 | 0 | 0 | 9 |  | FEB-25 | RFD |  | Commissioned 01/25.
7 | LILO of one circuit of 400KV Damoh(PGCIL) - Bhopal line at Sagar 400KV S/S | D/C | 400 | 38 | 58 | 58 | 58 | 37.73 | MAR-25 | MAR-25 | RFD |  | work completed on 31.03.2025.
8 | LILO of one circuit of Satpura TPS-Itarsi 220 kV line at Shahpur 220 kV S/s | D/C | 220 | 10 | 23 | 16 | 0 | 0 | JAN-25 | NOV-25 | RFD |  | TBCB work. Work needed is only 12.60 cktkm based on revised location of S/s.
9 | Sagar - Begamganj 220 kV line (TBCB) (charged on 24-04-2024 however late reported by MPPTCL) | D/C | 220 | 125 | 0 | 0 | 0 | 125 | DEC-24 | AUG-24 | RFD |  | Commissioned 04/24 (Late Reported).
ORISSA POWER TRANSMISSION CORPORATION LTD. ( OPTCL )
1 | Kesinga - Baliguda GSS | D/C | 220 | 202 |  |  |  |  | MAR-25 | JUN-26 | RFD
2 | LILO of 220 kV Nuapada Pratapsasan Line at Balianta GSS | D/C | 220 | 20 | 48 | 48 | 48 | 20 | JUN-24 | MAY-25 | RFD |  | OPGW Stringing under progress
3 | LILO of 220 KV TTPS -Joda DC Line at 220/33 KV GIS Keonjhar (Ranki) | D/C | 220 | 27 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Repeat may be deleted
4 | LILO of Bhanjanagar-Meramundali line at Daspalla | D/C | 220 | 59 | 113 | 108 | 99 | 45 | JUN-24 | DEC-25 | RFD |  | Forest issue
5 | PGCIL Keonjhar - Turumunga GS | D/C | 220 | 34 | 0 | 0 | 0 |  | JUN-24 |  | RFD |  | Repeat may be deleted
PUNJAB STATE TRANSMISSION CORPORATION LIMITED ( PSTCL )
1 | 220 KV D/C line from 400 KV S/S Dhanansu to Tata Steel plant Kadiana Khurd (Contributory work) | D/C | 220 | 5 | 30 | 21 | 15 | 0 | MAR-25 | MAR-25 | RFD |  | Work in progress. likely to be completed by Mar'25.
2 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | 220 | 16 | 31 | 31 | 31 | 16 | MAY-24 | MAY-24 | RFD |  | Commissioned 04/24.
3 | LILO of 220 kV S/Stn Mansa - Sunam at 400 kV S/Stn Patran | D/C | 220 | 85 | 144 | 144 | 144 | 85 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
4 | LILO of one ckt of 220 KV Ganguwal-Jamalpur at 400 KV S/S Dhanansu | D/C | 220 | 9 | 33 | 5 | 5 | 0 | MAR-25 | MAR-25 | RFD |  | Work is in progress. likely to be completed by Mar'25.
5 | Lilo of one ckt of 220 KV Jamalpur-Dhandari Kalan-1 line at 220 Kv Sherpur S/S | D/C | 220 | 4 | 5 | 5 | 5 | 1.14 | JUN-24 | FEB-25 | RFD |  | work delayed due to non availability of regular shutdowns, likely to be completed by Feb'25.
6 | LILO of one Ckt. of 400kV Ludhiana PGCIL-Koldam at proposed 400kV s/s Ropar | D/C | 400 | 14 | 0 | 0 | 0 | 14 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
7 | Mansa - Budhlada line | D/C | 220 | 52 | 100 | 100 | 100 | 52 | JUL-24 | MAR-25 | RFD |  | Work Completed Line yet to be energised.
8 | Rajpura s/s to 220 kv Rajpura s/s D/C on D/C towers | D/C | 220 | 3 | 14 | 6 | 0 | 0 | SEP-24 | SEP-25 | RFD |  | ROW issue by Kisan Union.
9 | Shifting of 220 KV S/C Patti-Verpal line from 220 KV Verpal to 400 KV S/S Amritsar | D/C | 220 | 2 | 8 | 8 | 8 | 2 | APR-24 | OCT-24 | RFD |  | Work Completed Line yet to be energised.
10 | Work for connecting 400kV Rajpura -220kV Mohali-1 (one ckt direct one via 220 kV Banur) | D/C | 220 | 4 | 19 | 1 | 0 |  | JUL-24 | MAR-25 | RFD |  | ROW issue by kisan union.
TAMILNADU TRANSMISSION CORPORATION LTD. ( TANTRANSCO )
1 | 400 KV UG Cable laying work from UG common point near Pallikarunai to O.H U.G common point near Perambakkam | S/C | 400 | 10 |  |  |  |  | MAR-25 |  | RFD
2 | CMRL Central Jail to proposed Mambalam 230kV GIS SS (UG Cable) | S/C | 230 | 9 | 0 | 0 | 0 |  | JUN-24 | JAN-24 | RFD |  | Total sections: 19. Laying 19/19 completed. Joints 54/54 completed. Sheath fault rectification work under progress.
3 | Extension of Shoolagiri Karimangalam line (from location no. 6 of Shoolagiri Karimangalam line) to Udanapally 230 KV SS | S/C | 230 | 2 | 0 | 0 | 0 | 2 | APR-24 | MAY-24 | RFD |  | Commissioned 04/24.
4 | Kilpauk - TNEB HQ | S/C | 230 | 6 | 0 | 0 | 0 |  | JUN-24 | MAR-24 | RFD |  | Total: 13 sections. Total:36 joints.Cable Laying 13/13 Completed. Joints 36/36 completed. Cable fault rectification work under progress.
5 | Laying of 400KV UG Cable from OH and UG common point at Manjambakkam to the proposed Korattur 400KV SS | S/C | 400 | 12 |  |  |  |  | JUN-24 |  | RFD
6 | Laying of UG cable by making LILO in the existing 230 KV Korattur- Kilpauk water works at Ganesh Nagar 230 KV SS | D/C | 230 | 3 |  |  |  |  | JUN-24 |  | RFD
7 | Laying of UG cable by making LILO in the proposed 230 KV Alamathy-Srperumbudur feeder at the proposed Avadi 230/110 KV SS | D/C | 230 | 9 |  |  |  |  | JUN-24 |  | RFD
8 | LILO of 230 kV Abishekapatti - Udayathur line at Nanguneri | D/C | 230 | 40 | 84 | 84 | 84 | 40.35 | SEP-24 |  | RFD |  | Line work completed. Will be energised on energisation of Nanguneri 230KV Substation.
9 | LILO of 230 kV Mylapore - Tarammani feeder at the proposed Thiruvanmiyur (400 kv GIS) | D/C | 230 | 2 | 0 | 0 | 0 |  | DEC-24 | DEC-23 | RFD |  | Cable laying work completed.Cable will be energised during commissioning of SS.
10 | LILO of Arasur- Ingur 230kV line at Kalivelampatty 230kV s/s | D/C | 230 | 31 |  |  |  |  | NOV-24 |  | RFD
11 | LILO of existing 230 kV Arni - Sriperumbudur feeder (0.81KM) at the proposed Vembakkam 230 kV S/S | D/C | 230 | 2 |  |  |  |  | JUN-24 |  | RFD
12 | LILO of Ottiyambakkam Guiny 400 KV SC feeder at Tharamani 400 KV GIS UG Cable -3.925 KM | D/C | 400 | 8 |  |  |  |  | MAR-25 |  | RFD
13 | LILO of Ottiyambakkam - Omega 2 at proposed 230/110kV Mambakkam SS (by overhead 230kV D/C line on M/C tower with zebra conductor (Loc 24 to Loc.150) for a route length of 19.918 km (OH portion) | D/C | 230 | 40 | 0 | 0 | 0 | 40 | SEP-24 | APR-25 | RFD |  | Commissioned 03/25.
14 | LILO of Pudhansandhai - Pugalur 230 kV Feeder at Nallur SS | D/C | 230 | 12 |  |  |  | 12 | MAR-25 | FEB-25 | RFD |  | Commissioned 01/25.
15 | LILO of S. P. Koil - Oragadam at Maraimalai Nagar 230 KV S/S | D/C | 230 | 9 |  |  |  |  | SEP-24 |  | RFD
16 | LILO of Thappagundu - Anaikadavu at Udumalpet (PGCIL SS) | D/C | 400 | 40 |  |  |  |  | JUN-24 |  | RFD
17 | LILO of the exisiting 230 kV Myvady - Kurukathi - Pugalur feeder at sanctioned Rasipalayam 400 kV SS | D/C | 230 | 46 | 93 | 92 | 92 | 41 | SEP-24 | MAR-24 | RFD |  | Row issues land owners are demanding yield compensation prior to commencement of further works tender floated for supply and erection of 5 nos towers.
18 | LILO of Thiruvalam - Singarapet 230 KV Feeder at Sathumadurai 230KV SS (OH- 1.75 Kms and UG -0.800 Kms.) | D/C | 230 | 5 |  |  |  |  | MAR-25 |  | RFD
19 | Ottiyambakkam (Sholinganallur) - KITS | D/C | 230 | 21 | 35 | 33 | 33 | 12.8 | SEP-24 | MAR-24 | RFD |  | OH line work completed for 33/35 locations (6.40/7.30 KM ) for balance 2 Nos loc Alternate route tender under process. UG cable laying for 3.04 KM proposed in lieu of OH line in marsh land.Tender awarded. Route survey under progress.
20 | Thervaikandikai - Manali | D/C | 400 | 73 | 113 | 111 | 106 | 58.6 | JUN-24 | MAR-23 | RFD |  | Work under progress. Row issues Enter upon permission awaited.
21 | UG Cable from Basin Bridge to TNEB Head Quarters | S/C | 230 | 6 | 0 | 0 | 0 | 6 | JUN-24 | MAY-24 | RFD |  | Commissioned 04/24.
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED ( APTRANSCO )
1 | 220 kV Brandix - Atchuthapuram | D/C | 220 | 7 | 11 | 11 | 11 | 7 | JUN-24 | AUG-24 | RFD |  | Commissioned 07/24.
2 | 220KV DC line from 220KV Gunadala S/S - 220KV Nunna S/s | D/C | 220 | 13 | 34 | 34 | 34 | 12.32 | MAY-24 | DEC-24 | RFD
3 | 220kV DC line from 400kV Kamavarapukota to 220kV SS Bhimadole SS | D/C | 220 | 37 | 69 | 69 | 69 | 37 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
4 | 220kV SMDC line converted to TMDC from 400kV Hindupur - 220kV Pampanurthanda | D/C | 220 | 148 | 268 | 235 | 220 | 52.42 | JUN-24 | DEC-24 | RFD |  | work under progress
5 | 400kV QMDC line from 400kv Polavaram SS - 400/220/11kV Guddigudem | D/C | 400 | 49 | 72 | 68 | 67 | 33.68 | MAY-24 | DEC-24 | RFD |  | Works are under progress. 3 Locations (Loc.Nos. 7,8,11) are in forest area.Loc.No.7 and 8: CA land allotted. Permission from Forest authorities awaited.Loc.No. 11: CA land yet to be allotted by Revenue authorities.
6 | Jammalamadugu (400 kV SS) to proposed Bethamcherla (220 kV SS) in Kurnool District | D/C | 220 | 151 | 260 | 260 | 260 | 151 | JUN-24 | DEC-24 | RFD |  | Commissioned 11/24.
7 | LILO of 220 kv ongole-Racherlpadu line at 220 kv ss Kandukur | D/C | 220 | 7 | 13 | 13 | 13 | 7 | MAY-24 | SEP-24 | RFD |  | Commissioned 08/24.
8 | LILO of 220kV VTS-Tallapally-1 at 220/132 kV SS Rentachintala | D/C | 220 | 3 | 5 | 5 | 4 | 3 | APR-24 | JUN-24 | RFD |  | Commissioned 05/24.
9 | LILO of 400kV VTS-IV Sattenapalli TMDC line at Thallayapalem and Temporary diversion of PGCIL VTS/Nunna-Nellore 3 and 4 Ckts. to avoid aerial passage over 400/220kV GIS Thallayapalem | D/C | 400 | 2 | 7 | 7 | 7 | 3 | JUN-24 | NOV-24 | RFD |  | Commissioned 10/24.
10 | LILO of existing 220kV Gooty -Shapuram line at proposed 220kV Dharmavaram S/S | D/C | 220 | 3 | 8 | 8 | 8 | 3.28 | JUN-24 | JUN-24 | RFD |  | works completed
11 | LILO of existing 220 kV Madanapalli-Palamaner line to 220 kV Punganur S/S | D/C | 220 | 5 | 13 | 13 | 13 | 5 | JUN-24 | DEC-24 | RFD |  | Commissioned 12/24.
12 | LILO of existing 220 KV Nunna - KTPS Single Ckt. line at 220kV SS Tiruvuru | D/C | 220 | 2 | 16 | 10 | 4 | 0 | JUL-24 | JUL-24 | RFD |  | work is under progress
13 | LILO of Kamavarapukota (220 kV) - Nuziveedu line at Kamavarapukota SS (400 kV) | S/C | 220 | 3 | 9 | 9 | 9 | 3 | MAY-24 | MAR-25 | RFD |  | Commissioned 02/25.
Transmission Corporation of Telangana Limited ( TSTRANSCO )
1 | 220KV Pulakurthy - Kakatiya Mega Textile Park | D/C | 220 | 60 | 110 | 99 | 89 | 18 | DEC-24 | DEC-24 | RFD |  | Works under progress. Foundations are pending due to Severe ROW
2 | Damaracherla -Huzurnagar line | D/C | 220 | 77 | 137 | 137 | 137 | 76.06 | MAY-24 | JUL-24 | RFD |  | Line commissioned on 26-08-2024
3 | Dichpally - Yacharam Thanda line | D/C | 220 | 54 | 97 | 97 | 97 | 54 | JUL-24 | JUL-24 | RFD |  | Works under progress.
4 | Janagon -Husnabad | D/C | 220 | 79 | 139 | 139 | 139 | 73 | AUG-24 | JUL-24 | RFD |  | Works under progress.
5 | Narsapur - Bowrampet line | MC+D/C | 220 | 149 | 136 | 136 | 136 | 149 | SEP-24 | MAR-25 | RFD |  | Commissioned 02/25.
6 | Narsapur to Bowrampet (Monopole towers) | D/C | 220 | 7 | 23 | 15 | 14 |  | SEP-24 | JUN-24 | RFD |  | Works under progress.
7 | Narsapur to Bowrampet (XLPE UG Cable ) | D/C | 220 | 7 | 1 | 0 | 0 | 7 | SEP-24 | JUN-24 | RFD |  | Works under progress.
8 | Veltoor SS - Yedula SS | D/C | 400 | 94 | 139 | 139 | 139 | 94 | JUN-24 | OCT-23 | RFD |  | All works completed. Ready for charging. Statutory inspection is under progress
9 | Yadadri TPP Switchyard - Choutuppal S/S | D/C | 400 | 185 | 259 | 259 | 258 | 66.3 | JUN-24 | MAR-24 | RFD |  | Standing crops issue
10 | Yadadri TPP switchyard - Jangaon S/S | D/C | 400 | 278 | 402 | 367 | 283 | 44 | DEC-19 | FEB-24 | RFD |  | Works under progress.
11 | YTPP Switchyard - 400kV Dindi SS | D/C | 400 | 208 | 290 | 290 | 290 | 208 | APR-24 | JUL-24 | RFD |  | Commissioned 06/24.
U.P. POWER TRANSMISSION CORPORATION LTD. ( UPPTCL )
1 | 220 kV Modipuram-II - Shamli Line | D/C | 220 | 150 | 262 | 262 | 262 | 150 | APR-24 | SEP-24 | RFD |  | Commissioned 08/24.
2 | 400kV Shamli - Aligarh Line | D/C | 400 | 482 | 737 | 737 | 736 | 482 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
3 | Badhaikalan (Muzaffarnagar) - Shamli line | D/C | 220 | 66 | 113 | 113 | 112 | 60.16 | AUG-24 | SEP-25 | RFD |  | ROW resolved with the help of District Administration.
4 | Darshan Nagar GIS to Sohawal (Tower NO. 152 of Gonda line) | S/C | 220 | 1 | 2 | 2 | 2 | 1 | MAY-24 | AUG-24 | RFD |  | Commissioned 07/24.
5 | Indrapuram (400 kV)- Sector-62 DC line (Under Ground Cable) | D/C | 220 | 5 | 0 | 0 | 0 | 3.7 | DEC-24 | JUL-25 | RFD |  | Cable laying for NHAI crossing is under progress.
6 | LILO of 220 kV Nara- Jansath line at Meerut(765) | D/C | 220 | 95 | 150 | 150 | 146 | 82 | JUN-24 | SEP-25 | RFD |  | RoW at location no. 8/3, 8/4, 8/8, 40/3. Matter is being resolved with the help of District Administration.
7 | LILO of 400kV Shamli-Aligarh Line at THDC Khurja Power Plant | D/C | 400 | 23 | 38 | 38 | 38 | 23 | JUL-24 | APR-25 | RFD |  | Commissioned 03/25.
8 | LILO of Badaun(400 kV)- C.B. Ganj line at Badaun Road | D/C | 220 | 1 | 3 | 3 | 3 | 1 | JUN-24 | NOV-24 | RFD |  | Commissioned 10/24.
9 | LILO of Ckt.II of 400 KV DC Quad Varanasi (PG) (Thathra) -Biharsharif at 400 kV Sahupuri SS (charged on 18-05-2024 however late reported by UPPTCL) | D/C | 400 | 53 | 0 | 0 | 0 | 53 |  | JUL-24 | RFD |  | Commissioned 06/24 (Late Reported).
10 | LILO of Ckt-I of 400kV Varanasi (PG (Thathra) - Biharshariff DC Line at 400kV Sahupuri | D/C | 400 | 52 | 92 | 92 | 92 | 52 | APR-24 | MAY-24 | RFD |  | Commissioned 04/24.
11 | LILO of Unnao(400 kV)- Bithoor line at Trans Ganga city (220 kV) | D/C | 220 | 9 | 20 | 19 | 16 | 4 | AUG-24 | JUN-25 | RFD |  | RoW issue resolved with NHAI and survey for diverted route completed and approval for additional supply and work received.
12 | Raebareli (400) -Bachhrawan line | D/C | 220 | 162 | 273 | 273 | 273 | 160.78 | JUN-24 |  | RFD |  | Line antitheft charged on dt. 28.02.2025. (2x80.390)
13 | Shamli (400) - Deoband line | D/C | 220 | 93 | 150 | 150 | 150 | 84 | MAY-24 | SEP-25 | RFD |  | ROW issue at AP-15 TO AP-16 for stringing work is being resolved with the help of District Administration.
14 | Sirsira (Raebareli 400 kV SS )- Bachhrawan (220 kV SS) line | D/C | 220 | 161 | 0 | 0 | 0 | 161 |  | MAR-25 | RFD |  | Commissioned 02/25.
UTTARAKHAND POWER CORPORATION LIMITED ( UKPCL )
1 | Balance work of Baramwari -Srinagar line (Single Zebra conductor from Interconnection point of Singoli Bhatwari HEP to Baramwari) | D/C | 220 | 31 |  |  |  |  | JUN-24 |  | RFD
2 | Pipalkoti-Srinagar Line | D/C | 400 | 173 |  |  |  |  | SEP-24 |  | RFD
3 | Vishnugad-Pipalkoti Line | D/C | 400 | 36 |  |  |  |  | DEC-24 |  | RFD
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED ( WBSETCL )
1 | Connectivity between New Bishnupur - Raghunathpur New Bishnupur-Hura Hura-Raghunathpur and connectivity between STPS and Hura 220kV s/s | S/C | 220 | 1 | 2 | 2 | 0 | 0 | OCT-24 | MAR-25 | RFD |  | Online tower erection and stringing activity may be taken up after receiving shutdown of the following existing lines: 220 KV D/C STPS to New Bishnupur T/L and 220 KV Raghunathpur to Hura T/L
2 | LILO of 220 kV Durgapur -DPL unit-8 line at AB Zone 220 kV Substation. | D/C | 220 | 8 | 14 | 14 | 14 | 8 | JUL-24 | DEC-24 | RFD |  | Commissioned 11/24.
3 | LILO of 229kV Domjur-Arambagh line at proposed Khanakul 220kV GIS | D/C | 220 | 11 | 47 | 45 | 45 | 14.82 | MAR-25 | MAR-25 | RFD |  | Loc. Nos.- 9/0; 9D/0- Severe hindrance from Landowners.
4 | LILO of Birpara -Alipurduar line (PGCIL) at proposed line at Falakata s/s | D/C | 220 | 17 | 39 | 39 | 37 | 14.06 | SEP-24 | MAR-25 | RFD |  | All tower foundations are completed only 2 Nos. online tower erection at AP 15/0 & 21A/0 are pending for want of S/D of existing PGCIL 220 KV Line. Falakata Substation is not ready.
5 | LILO of Gokarna-New Chanditala Transmission Line at proposed Satgachia 400 KV GIS S/S | D/C | 400 | 11 | 22 | 19 | 17 | 0 | JAN-25 | JAN-25 | RFD
6 | LILO of STPS - J K NAGAR line at 220 kV Asansol SS | D/C | 220 | 63 | 124 | 124 | 124 | 63 | JUL-24 | FEB-25 | RFD |  | Commissioned 01/25.
7 | STPS - Raghunathpur | D/C | 220 | 45 | 94 | 94 | 94 | 46.3 | MAR-25 | MAR-25 | RFD |  | Awaiting approval for hotline power line crossing for AP-9/0 to AP-10/0.
PRIVATE SECTOR
ADANI Energy solution Limited ( ADANI )
1 | Narendra New (GIS) - Pune (GIS) (line with 1x330MVA r switchable line reactor (SLR) on each ckt. at both ends) | D/C | 765 | 636 |  |  |  |  | DEC-24 |  | RFD
Apraava Energy Pvt. Ltd. ( APRAAVA )
1 | Fatehgarh-3- Bhadla-3 400kV D.C line (Quad) line | D/C | 400 | 446 |  |  |  |  | FEB-25 |  | RFD
Megha Engineering & Infrastructures Limited ( MEGHA )
1 | 765kV D/C KPS1 to KPS2 GIS (41ckm) | D/C | 765 | 41 | 0 | 0 | 0 | 41 | FEB-25 | APR-25 | RFD |  | Commissioned 03/25.
ReNew Transmission Ventures Private Limited ( RENEW )
1 | 400 kV D/C Gadag PS-Narendra (New) line (Trans. Scheme for Solar Energy Zone in Gadag (1000MW) Karnataka-Part-A Phase-I) | D/C | 400 | 187 | 232 | 232 | 232 | 187 | MAY-24 | OCT-24 | RFD |  | Commissioned 09/24.
2 | Gadag PS- Koppal (PS) line | D/C | 400 | 100 |  |  |  |  | AUG-23 |  | RFD
STERLITE GRID LTD. ( STERLITE )
1 | Bongaigaon (POWERGRID) - Nangalbibra (Twin ACSR Moose) line | D/C | 400 | 246 | 311 | 311 | 311 | 246 | JUN-24 |  | RFD |  | Ready for commissioning on Oct-2024.
2 | Fatehgarh-III PS - Beawar 765 kV D/C line (Rajasthan (20GW) under Phase-III Part F) | D/C | 765 | 635 |  |  |  |  | MAR-25 |  | RFD
3 | Fatehgar III - Beawar 765kV line (Rajasthan (20GW) under Phase-III Part -G) | D/C | 765 | 630 |  |  |  |  | MAR-25 |  | RFD
4 | LILO of Apta-Kalwa/Taloja at Navi Mumbai (PG) | D/C | 220 | 5 | 0 | 0 | 0 | 5 | MAY-24 | NOV-24 | RFD |  | Commissioned 10/24.
5 | LILO of Padghe (PG)-Ghatkopar/Vikroli 400 kV S/C line at Navi Mumbai GIS(PG) (WRSS-XIX and NERS-IX) | S/C | 400 | 38 | 0 | 0 | 0 | 38 | JUN-24 | OCT-24 | RFD |  | Commissioned 09/24.
6 | Padghe (PG) - Kharghar 400 kV D/C (Quad) line (WRSS-XIX and NERSS-IX) | D/C | 400 | 140 | 0 | 0 | 0 | 140 | JUN-24 | OCT-24 | RFD |  | Commissioned 09/24.
7 | Vapi-II-Sayali 220 kV D/C line (WRSS-XIX and NERSS-IX) | D/C | 220 | 45 | 0 | 0 | 0 | 45 | MAY-24 |  | RFD |  | Commissioned 09/24.
8 | Xeldem (Existing) - Xeldem (New) Transmission line | D/C | 220 | 45 | 66 | 66 | 66 | 45 | JUN-24 |  | RFD |  | Ready for commissioning on Oct-2024.
9 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | 400 | 106 | 142 | 142 | 142 | 106 | JUN-24 | JAN-23 | RFD |  | Ready for commissioning on Oct-2024.