## state_trans_utility_ATS
31-July-2024
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Adhunik Power TPP (Mahadev Prasad TPP) (2x270 MW), PS,Jhk, APCL.U1-11/12(C),U2-3/13 (C)
| 1 |  |  | Adhunik - Jamshedupur (PG) (Padampur) |  |  | ADHUNIK | D/C |  |  | 400 | 1 | [6 empty] | 1 |  |  |  | JUL-12 |  | Commissioned. 7/12
Remark:
Agartala (AGTP) (4x21 MW), PS NEEPCO, Tripura,ST-I, 08/16 (C),ST-2,3/15(C)
| 1 |  |  | AGTP - Kumarghat line |  |  | TSECL | S/C |  |  | 132
| 2 |  |  | AGTP - Agartala line |  |  | TSECL | D/C |  |  | 132
|  | Remark: |  |  | Agrartala Gas Turbine Combinedd Cycle Extension Plant Stg-1 (25.5MW) commissioned on 23.08.2015.
Akaltara(Naiyara) TPP (6x600 MW), Chg, KSK, U1-8/13(c),U2-8/14(c),U3-12/17,U4-3/18,U5-9/18,U6-12/18
| 1 |  |  | LILO of both ckt, of Raigarh - Raipur at Akaltara TPP |  |  |  | 2xD/C |  |  | 400 | 71 | 118 | 118 |  |  | 118 |  | 71 |  |  |  | APR-15 |  | Commissioned 04/15. (Interim)
| 2 |  |  | KSK Mahanadi (Warda Power) - Champa Pooling Station |  |  |  | 2xD/C |  |  | 400 | 105 | 164 | 164 |  |  | 164 |  | 105 |  |  |  | JUN-15 |  | Ready for Commissioning 06/15.
Remark:
Alaknanda HEP (6x50 MW), PS, UK, Badrinath, Project dropped
| 1 |  |  | Alaknanda HEP - Joshimath |  |  | GMR | D/C |  |  | 220
|  | Remark: |  |  | Generation project has been dropped.
Amravati, TPS,(5x270+5x270), Phase-II-uncertain
| 1 |  |  | Amravati - Akola (Bableshwar) - I |  |  | IBPL | D/C |  |  | 400 | 207 | 279 | 279 |  |  | 279 |  | 207 |  |  |  | MAR-15 |  | Commissioned 03/15.
| 2 |  |  | LILO of Koradi -Akola at Amravati |  |  | IBPL | D/C |  |  | 400 | 14 | 22 | 22 |  |  | 22 |  | 14 |  |  |  | OCT-12 |  | Commissioned 10/12.
Remark:
Anpara C (2X600 MW),PS,UP,LANCO,U1&2-11/11(C)
| 1 |  |  | Shifting of Anpara B-Unnao termination point from Anpara B to Anpara C sw. yard. |  |  | UPPTCL | S/C |  |  | 765 | 1 | 6 | 6 |  |  | 6 |  | 1 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 2 |  |  | Shiffting of 765 kV Anpara- Unnao at Unnao |  |  | UPPTCL | S/C |  |  | 765 | 1 | 3 | 3 |  |  | 3 |  | 1 |  |  |  | OCT-11 |  | Line charged at 400 kV Oct'11
| 3 |  |  | Extn. of Bus from Anpara B to Anpara C. |  |  | LEPP | D/C |  |  | 400 | [11 empty] | JUN-10 |  | Work completed. 6/10.
| 4 |  |  | Unnao |  |  | UPPTCL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-12 |  | Commissioned 3/12.
Remark:
Anpara-D TPP (2x500 MW),SS,UP,UPRVUNL, U6-6/15 (C),U7-3/16 (C)
| 1 |  |  | Anpara D - Unnao |  |  | UPPTCL | S/C |  |  | 765 | 426 | 1225 | 1225 |  |  | 1225 |  | 426 | AUG-19 |  |  | NOV-21 |  | Commissioned 11/21.
| 2 |  |  | Anpara B-Anpara D (Ckt-I) |  |  | UPPTCL | D/C |  |  | 400 | 5 | 23 | 23 |  |  | 23 |  | 5 |  |  |  | MAR-16 |  | Commissioned 03/16.
| 3 |  |  | Anpara C - Anpara D |  |  | UPPTCL | S/C |  |  | 765 | 3 | 11 | 11 |  |  | 11 |  | 3 | JAN-12 |  |  | JUN-14 |  | Commissioned 06/14.
| 4 |  |  | Anpara D. S/S |  |  | UPPTCL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-14 |  | Commissioned 06/14.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 1 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Anuppur TPP Ph-I, (2x600 MW),PS,MP,Moser Baer Power MP, U1-4/15 (C),U2-2/15 (C)
| 1 |  |  | LILO of Amarkantak - Korba at Anooppur |  |  | MPPTCL | D/C |  |  | 220 | 16 | 18 | 18 |  |  | 18 |  | 16 |  |  |  | NOV-12 |  | Commissioned 11/12.
| 2 |  |  | Jabalpur Pooling Station - Jabalpur (High Capacity) line |  |  | PGCIL | D/C |  |  | 400 | 31 | 45 | 45 |  |  | 45 |  | 31 |  |  |  | DEC-13 |  | Commissioned in Dec'13.
| 3 |  |  | Anuppur (Moser Baer) - Jabalpur Pooling Station |  |  | PGCIL | D/C |  |  | 400 | 492 | 600 | 600 |  |  | 600 |  | 492 |  |  |  | AUG-14 |  | Commissioned 08/14.
Remark:
Avantha Bhandar TPS, (2x600 MW), PS,Chhattisgarh,Korba West Power Comany Limited U1-3/14(C),
| 1 |  |  | Avantha Bhandar TPS (Korba West) - Raigarh (Kotra) |  |  | KWPCL | D/C |  |  | 400 | 37 | 64 | 64 |  |  | 64 |  | 37 |  |  |  | DEC-16 |  | Commissioned 05/2016 (Late Reported)
| 2 |  |  | LILO of on Ckt of Raigarh - Raipur at Avantha Bhandar (Korba west ) TPS |  |  | KWPCL | D/C |  |  | 400 | 10 | 22 | 22 |  |  | 22 |  | 10 | [5 empty] | Interim arrangement.
Remark:
Avantha (Jhabua Power) (2x600 MW), PS,Seoni,MP, BHEL, U1-03/14 (C)
| 1 |  |  | Jhabua Power TPS - Jabalpur Pooling Station. |  |  | JHAPL | D/C |  |  | 400 | 131 | 207 | 207 |  |  | 207 |  | 131 |  |  |  | MAY-15 |  | Commissioned 05/15.
Remark:
Babandh - (Dhenkanal) TPS , (2x660 MW), PS Orissa, Lanco Infratech U1-7/18,U2-1/19
| 1 |  |  | Babandh TPP - Angul Pooling Station |  |  | LEPP | D/C |  |  | 400 | 48 | 72 | 0 |  |  | 0 |  | 0 | [5 empty] | Work yet to start.
Remark:
Baghliar-II HEP (3x150MW) SS,J&K, JKPDC, U1-9/15 (C),U2-9/15(C),U3- 10/15 (C)
| 1 |  |  | LILO of one ckt. of Kishanpur - New wanpoh at Baglihar HEP |  |  | JKPDD | D/C |  |  | 400 | 8 | 16 | 16 |  |  | 16 |  | 8 |  |  |  | MAY-18 |  | Ready for Commissioning 05/18.
Remark:
Bajoli Holi HEP(3x60=180 MW), HP, GMR-BHHPPL, U1-U3 (03/20)
| 1 |  |  | Lahal GISS - Chamera (PS) (Both Ckts.) |  |  | HPPTCL | D/C |  |  | 400 | 71 | 114 | 114 |  |  | 114 |  | 71 | JUL-22 |  |  | JAN-23 |  | Commissioned 01/23.
| 2 |  |  | Bajoli Holi - Lahal |  |  | HPPTCL | D/C |  |  | 220 | 36 | 59 | 59 |  |  | 59 |  | 36 | JUN-21 |  |  | DEC-21 |  | Commissioned 12/21 (Late Reported).
| 3 |  |  | Lahal S/S |  |  | HPPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | JAN-18 |  |  | NOV-20 |  | Commissioned 11/20.
Remark:
Balco TPS PS,Chg,Sterlite,U1-6/15 (C),U2-3/16 (C),U3-2/14,(4x300 MW, 4x67.5 (CPP) ) 4x67.5 (C)
| 1 |  |  | LILO of one ckt of Korba - Birsinghpur at Balco |  |  | BALCO | D/C |  |  | 400 | 35 | [6 empty] | 35 |  |  |  | MAR-12 |  | commissioned 3/12 (Interim)
| 2 |  |  | Balco - Dharamjaygar Pooling Station |  |  | BALCO | D/C |  |  | 400 | 46 | 72 | 72 |  |  | 70 |  | 46 |  |  |  | DEC-16 |  | Commissioned 06/2016 (Late Reported).
Remark:
Bandakhar TPP, (300 MW), PS,Chg, MCC&PL, U1-6/15 (C)
| 1 |  |  | LILO of ACBIL-Baraari (Bilaspur) PS at Bandakhar (Maruti Clean Coal) |  |  | MCCPL | D/C |  |  | 400 | 6 | 14 | 14 |  |  | 14 |  | 6 |  |  |  | JUN-14 |  | Commissioned 06/14.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 2 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Banswara and Pratpgarh Wind Project
| 1 |  |  | Nimbahera - Pratapgarh (Part of Pratapgarh -Chittorgarh line) |  |  | RVPNL | D/C |  |  | 220 | 181 | 421 | 421 |  |  | 421 |  | 181 |  |  |  | JUN-17 |  | Commissioned 06/2017.
| 2 |  |  | Pratapgarh (Upgradation)(160-100) |  |  | RVPNL |  |  |  | 220/132 | 60 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-17 |  | Commissioned 06/2017.
Remark:
Banswara Super Critical TPS (2x660 MW), SS,Raj, U1 & U2 -2016/2017
| 1 |  |  | Jodhpur s/s (New) |  |  | RVPNL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | OCT-18 |  | Commissioned 10/18.
| 2 |  |  | Chitorgarh S/S |  |  | RVPNL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-14 |  | Commissioned 11/14.
Remark:
Baradarha TPP (2x600 MW), PS,D.B.P.C.L, Dist.. Jangir Champa ,Chhattisgarh,U1-8/13, U2-2/14
| 1 |  |  | DB Power (Baradarha) - Raigarh (Kotra) Pooling Station |  |  | DBPCL | D/C |  |  | 400 | 36 | 54 | 54 |  |  | 54 |  | 36 |  |  |  | AUG-14 |  | Commissioned 08/14.
| 2 |  |  | LILO of Raigarh - Raipur (3rd Ckt) at Baradhara TPP ( Interim arrangement) |  |  | DBPCL | D/C |  |  | 400 | 30 | 44 | 44 |  |  | 44 |  | 30 | [5 empty] | Line completed. (Interim)
Remark:
Bara TPP (3x660MW),PS,UP,PPGCL,U1-12/15(C),U2-9/16(C),U3-9/15 (C)
| 1 |  |  | LILO of Panki - Obra at Rewa Road |  |  | UPPTCL | D/C |  |  | 400 | 1 | 2 | 2 |  |  | 2 |  | 1 |  |  |  | MAR-15 |  | Commissioned 03/15.
| 2 |  |  | Bara - Karchana |  |  | SEUPPTCL | D/C |  |  | 400 | 80 | 124 | 0 |  |  | 0 |  | 0 | [5 empty] | Karchana gantry not finalised. The project is at stand still pending of a time extension requested to UPPTCL in June 2015
| 3 |  |  | LILO of Orai - Mainpuri line at Mainpuri |  |  | SEUPPTCL | 2xD/C |  |  | 400 | 93 | 135 | 135 |  |  | 135 |  | 93 |  |  |  | DEC-16 |  | Ready for commissioning 12/2016
| 4 |  |  | Mainpuri - Bara Ckt-II |  |  | SEUPPTCL | S/C |  |  | 765 | 377 | 899 | 899 |  |  | 899 |  | 377 |  |  |  | DEC-16 |  | Ready for commissioning 12/2016
| 5 |  |  | Mainpuri - Bara Ckt-I |  |  | SEUPPTCL | S/C |  |  | 765 | 375 | 889 | 613 |  |  | 346 |  | 0 | [5 empty] | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
| 6 |  |  | Mainpuri - Aligarh |  |  | SEUPPTCL | D/C |  |  | 400 | 186 | 219 | 219 |  |  | 219 |  | 186 |  |  |  | DEC-16 |  | Ckt-I commissioned 12/2016 and Ckt-II Ready for commissioning 12/2016
|  | Remark: |  |  | Unit - II (660MW) commissioned on 06.09.2016.
Barauni TPS Extn (2x250, Bihar, BSPGCL,U8-12/17,U9-3/18(C)
| 1 |  |  | Barauni TPS Exte. - Hazipur |  |  | BSPTCL | D/C |  |  | 220 | 214 | 403 | 403 |  |  | 403 |  | 214 | JUN-16 |  |  | JUN-18 |  | Commissioned 06/18.
| 2 |  |  | LILO of Both ckt. of Biharsharif - Begusarai at BTPS Extn. |  |  | BSPTCL | D/C |  |  | 220 | 4 | 9 | 9 |  |  | 9 |  | 4 |  |  |  | DEC-17 |  | Commissioned 10/2017 (Late Reported).
| 3 |  |  | Barauni (TPS ) (ICT) |  |  | BSPTCL |  |  |  | 220/132 | 300 | 100 | 90 |  |  | 90 |  | 90 | [5 empty] | yet to be commissioned
Remark:
Barh STPP -Stage-I (3x660 MW), Stage-2 (2x660 MW), CS, Bihar, U4,5-11/13(C),U1-3/18,U2-09/18,U3-3/19
| 1 |  |  | Barh-II - Gorakhpur |  |  | PGCIL | D/C |  |  | 400 | 698 | 944 | 944 |  |  | 944 |  | 698 | AUG-14 |  |  | MAY-15 |  | Commissioned 05/15.
| 2 |  |  | Barh-Balia (Quad) |  |  | PGCIL | D/C |  |  | 400 | 488 | 645 | 645 |  |  | 645 |  | 488 | SEP-09 |  |  | JUN-10 |  | Commissioned 06/10.
| 3 |  |  | Balia & Bhiwadi convertor Stn. (Pole-II) |  |  | PGCIL |  |  |  | 500 | 1250 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-12 |  | Commissioned 6/12
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 3 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Barkhera TPP (2x45 MW), PS,UP, Bajaj,
| 1 |  |  | Barkhera (Bajaj) - Dohna |  |  | UPPTCL | D/C |  |  | 132 |  | 203 | 203 |  |  | 203 |  | 128.96 | [5 empty] | Line energised on 13.09.2017. To be deleted
Remark:
Bela TPP (1x270 MW),PS,Maha,IEPL,U1-3/13(C)
| 1 |  |  | LILO of Koradi II- Wardh(PG) at Bela TPP |  |  | MSETCL | D/C |  |  | 400 | 49 | 75 | 75 |  |  | 75 |  | 49 |  |  |  | DEC-15 |  | Commissioned 12/15. (Only LILO Portion 2x24.3 Ckm has been taken).
| 2 |  |  | LILO of Mouda - Wardha at Bela |  |  | IEPL | D/C |  |  | 400 | 0 | 2 | 2 |  |  | 2 |  | 0.3 | [5 empty] | Completed (Interim)
Remark:
Bellary TPP (3X500 MW),SS,KAR,KPCL,U1-12/07(C),U2-6/14,U3-3/16 (C)
| 1 |  |  | LILO of RTPS - Guttur at BTPS. |  |  | KPTCL | D/C |  |  | 400 | 2 | 3 | 3 |  |  | 3 |  | 2 |  |  |  | JUN-08 |  | Commissioned 6/08
| 2 |  |  | BTPS- Hiriyur |  |  | KPTCL | D/C |  |  | 400 | 313 | 440 | 440 |  |  | 440 |  | 313 | DEC-08 |  |  | MAR-12 |  | Commissioned 3/12
Remark:
Bhadla Sikar Transmission Limited
| 1 |  |  | Bhadla II - Sikar II 765 kV D/C line (2nd) Rajasthan (8.1 GW) under Phase-II Part-E |  |  | PGCIL | D/C |  |  | 765 | 600 | 816 | 469 |  |  | 175 |  |  | DEC-24 |  |  |  |  | RoW issues at 7 loc. in Sikar, 37 loc. in Didwana Kuchman . Forest (0.77 Ha): Proposal submitted on 23.10.23. Stage-I clearance accorded on 10.04.24. Working permission Awaited.
Remark:
Bhadradri TPP (Manuguru) (4x270 MW),TSGENCO, U1-12/17,U2-2/18,U3-5/18,U4-8/18
| 1 |  |  | Julurupadu - Manuguru TPP |  |  | TSTRANS | D/C |  |  | 400 | 225 | 313 | 313 |  |  | 313 |  | 225 | MAR-17 |  |  | NOV-19 |  | Commissioned 02/19 (Late Reported).
| 2 |  |  | Julurupadu (QM) - Suryapet S/s |  |  | TSTRANS | D/C |  |  | 400 | 219 | 306 | 306 |  |  | 306 |  | 219 | MAR-17 |  |  | JAN-18 |  | Commissioned 12/2017(Late Reported)
| 3 |  |  | Julurupadu S/S |  |  | TSTRANS |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUL-18 |  | Commissioned 07/18.
| 4 |  |  | 400kV Suryapet Bay Extensions |  |  | TSTRANS |  |  |  | 400 | 50
Remark:
Bhasmey HEP (2x25.5 MW),PS,Sikkim,Gati Infra,U1,2&3 (2021-22)
| 1 |  |  | LILO of one circuit of Chujachen - Rangpo line at Bhasmay |  |  | GIPL | 2xS/C |  |  | 220 | 10 | [12 empty] | Work yet to be awarded.
|  | Remark: |  |  | Generation Projects stopped since Dec-16
Bhavanagar Padva (2x250MW),SS,Guj,BHEL,U1-6/16,U2-9/16
| 1 |  |  | LILO of Savarkundla - Vartej at BECL (Padva) |  |  | GETCO | D/C |  |  | 220 | 56 | 97 | 97 |  |  | 97 |  | 56 |  |  |  | JUN-13 |  | Commissioned 06/13.
| 2 |  |  | BECL (Padva) - Botad line |  |  | GETCO | D/C |  |  | 220 | 188 | 310 | 254 |  |  | 217 |  | 33.79 | [5 empty] | Tender on website and last date is 10.12.2018. (Risk & cost for Balance work).
| 3 |  |  | BECL (Padva)- Sagapara line |  |  | GETCO | D/C |  |  | 220 | 83 | 139 | 139 |  |  | 139 |  | 83 |  |  |  | MAR-14 |  | Commissioned 03/14.
Remark:
Bhavanapaddu TPP, (2x660MW),PS, AP,East cost Energy, U1-12/17,U2-05/18
| 1 |  |  | Bhavanapaddu TPP - Srikakulam(PS) |  |  | XYZ | D/C |  |  | 400 | 44
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 4 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Bhawani Barrage HEP -II & III (4x15 MW), SS,TN, TANGEDCO, BB-II (U1-8/13 (C ),U2-9/13(C), BB-III (U1-12/12 (C),U2-9/13(C)
| 1 |  |  | BKB-III Common point - Nallur line |  |  | TANTRAN | S/C |  |  | 110 | 10 | 36 | 36 |  |  | 36 |  | 10.3 |  |  |  | AUG-12 |  | Energised on 13.08.12.
| 2 |  |  | BKB-III - Common point line. |  |  | TANTRAN | D/C |  |  | 110 | 6 | 13 | 13 |  |  | 13 |  | 6 |  |  |  | AUG-12 |  | Energised on 13.08.12.
| 3 |  |  | BKB-II Common point - Pallipalayam line |  |  | TANTRAN | S/C |  |  | 110 | 2 | 7 | 7 |  |  | 7 |  | 2.15 |  |  |  | AUG-12 |  | Energised on 23.08.12.
| 4 |  |  | LILO of BKB-I - SP Budur at BKB-II line |  |  | TANTRAN | D/C |  |  | 110 | 5 | 10 | 10 |  |  | 10 |  | 5 |  |  |  | JUN-11 |  | Energised on 06/11
| 5 |  |  | BKB-III Common point - BKB-II line |  |  | TANTRAN | S/C |  |  | 110 | 22 | 69 | 69 |  |  | 69 |  | 22 |  |  |  | JUN-12 |  | Energised 6/12
| 6 |  |  | BKB-II - Common Point line |  |  | TANTRAN | D/C |  |  | 110 | 15 | 30 | 30 |  |  | 30 |  | 15.01 |  |  |  | AUG-12 |  | Energised on 23.08.12.
| 7 |  |  | BKB-II Common point - Thirucengode line |  |  | TANTRAN | S/C |  |  | 110 | 9 | 40 | 40 |  |  | 40 |  | 9.127 |  |  |  | AUG-12 |  | Energised on 23.08.12.
| 8 |  |  | LILO of Mettupalayam - Irumborai line at BKB-II |  |  | TANTRAN | D/C |  |  | 110 | 4 | 12 | 12 |  |  | 12 |  | 4 |  |  |  | SEP-12 |  | Commissioned 09/13.
Remark:
Bhusaval TPS (2x500 MW),SS,MAHA,MSPGCL,U4-3/12 (C),U5-3/12 (C)
| 1 |  |  | Bhusaval - II - Aurangabad |  |  | MSTRANS | D/C |  |  | 400 | 185 | 283 | 283 |  |  | 283 |  | 185 |  |  |  | DEC-11 |  | Commissioned 12/11.
| 2 |  |  | Bhusaval - II - Amalner |  |  | MSETCL | D/C |  |  | 220 | 197 | 331 | 331 |  |  | 331 |  | 197 |  |  |  | NOV-11 |  | Commissioed 11/11
| 3 |  |  | Bhusaval - II - existing Khadka |  |  | MSETCL | D/C |  |  | 400 | 15 | 26 | 26 |  |  | 26 |  | 15 | DEC-09 |  |  | APR-10 |  | Commissioned 4/10.
| 4 |  |  | Bhusaval (ICT -II) S/S |  |  | MSETCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | SEP-11 |  | Commissioned 9/11.
| 5 |  |  | Bhusaval (ICT-I) S/S |  |  | MSETCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-11 |  | Commissioned 8/11.
Remark:
Bijora Ghanmukh TPP (2x300MW), Maharashtra ,JPGPL, Uncertain
| 1 |  |  | JPGPL TPS Switchyard - Warora PS (JPGPL-TBCB) |  |  | MSETCL | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Not in STU Plan.
Remark:
Bina TPS (2x250 MW),PS,MP,Bina power,U1-8/12(C),U2-3/13(c )
| 1 |  |  | Bina TPS - Suitable location (along Bina (PG) - Bina (MPPTCL) |  |  | JV(PG&JP) | D/C |  |  | 400 | 40 | [6 empty] | 40 |  |  |  | JAN-15 |  | Commissioned 01/15.
| 2 |  |  | Termination of Ckt of above at Bina (PG) & otuer ckt at Bina (MPTCL) |  |  | JV(PG&JP) | D/C |  |  | 400 | [11 empty] | JAN-15 |  | Commissioned.
Remark:
Binjkote TPP (4x300 MW),PS,Chg,SKS Power, U1-4/17(c),U2-3/18(c), U3,4-unknown
| 1 |  |  | Binjkote - Raigarh (Kotra) Pooling Station |  |  | SKS | D/C |  |  | 400 | 55 | 93 | 93 |  |  | 93 |  | 55 |  |  |  | MAY-15 |  | Commissioned 05/15.
Remark:
Bokaro TPS
| 1 |  |  | Bokaro TPS Extn.- Koderma TPS |  |  | PGCIL | D/C |  |  | 400 | 200 | 276 | 276 |  |  | 276 |  | 200 | AUG-12 |  |  | DEC-14 |  | Commissioned 12/14.
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 5 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Bongaigaon TPS (3x250 MW),CS, Assam, NTPC, U1-6/15 (C),U2-3/17(C),U3-12/17
| 1 |  |  | Bongaigaon TPS - Bongaigaon |  |  | PGCIL | D/C |  |  | 400 | 6 | 11 | 11 |  |  | 11 |  | 6 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 2 |  |  | Bongaigaon TPS - Rangia (Salakati) |  |  | AEGCL | D/C |  |  | 220 | 324 | 516 | 516 |  |  | 516 |  | 324 | JUN-19 |  |  | NOV-19 |  | Commissioned 08/19 (Late Reported).
| 3 |  |  | BTPS - Kokrajhar line |  |  | AEGCL | S/C on D/C |  |  | 132 | 10 | 39 | 39 |  |  | 39 |  | 10 | DEC-13 |  |  |  |  | Line charged on 30.06.2016.
| 4 |  |  | Kokrajhar - Bilashipara - Gauripur |  |  | AEGCL | S/C on D/C |  |  | 132 | 63 | 203 | 203 |  |  | 203 |  | 63 | SEP-13 |  |  |  |  | Kokrajhar to Bilashipara charged on 24.06.16 and Bilashipara to Gauripur charged on 14.06.2016
| 5 |  |  | BTPS-Agia-Sarusajai (2nd Circuit, Balance portion) |  |  | AEGCL | S/C |  |  | 220 | 65 | 195 | 195 |  |  | 195 |  | 65 |  |  |  | SEP-14 |  | commissioned 9/14
Remark:
Budhil HEP (2x35 MW), PS, H.P., LANCO Green, U1-5/12(C),U2-5/12.(C)
| 1 |  |  | Budhil -Chamera III |  |  | LEPP | S/C on D/C |  |  | 220 | 40 | 62 | 62 |  |  | 62 |  | 40 |  |  |  | MAR-12 |  | Commissioned 3/12
Remark:
Butibori (2x300 MW) TPS Phase -II,PS,Maha,RPL,U1-8/12(C),U2-11/12
| 1 |  |  | Buttibori TPS -Buttibori-III |  |  | MSETCL | D/C |  |  | 220 | 1 | [6 empty] | 1 |  |  |  | DEC-11 |  | Commissioned 12/11.
| 2 |  |  | butibori III |  |  | MSETCL |  |  |  | 220/132 | 100 | 100 | 90 |  |  | 100 |  | 90 |  |  |  | MAR-13 |  | Commissioned on 26.03.2013
Remark:
Chamera-II HEP,CS,HP,
| 1 |  |  | Chamera-II HEP (Part-I)- Chamera Pooling Station |  |  | PGCIL | S/C |  |  | 400 | 1 | 3 | 3 |  |  | 3 |  | 1 | APR-10 |  |  | MAR-11 |  | Commissioned 3/11.
Remark:
Chamera-III HEP (3x77 MW), CS,H.P.,NHPC, U1-6/12,( C) U2-6/12(C), U3-6/12 (C )
| 1 |  |  | Chamera-II HEP - Jullandur line |  |  | PGCIL | D/C |  |  | 400 | 324 | 444 | 444 |  |  | 444 |  | 324 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 2 |  |  | Chamera-III - Pooling Station Near Chamera-II HEP |  |  | PGCIL | D/C |  |  | 220 | 30 | 46 | 46 |  |  | 46 |  | 30 |  |  |  | AUG-11 |  | Commissioned 8/11
| 3 |  |  | GIS Pooling Station near Chamera-II HEP |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-11 |  | Commisiioned 8/11.
Remark:
Chandrapur TPS, (2x500 MW), SS, Maha, MSPGCL, U1 to 7 (C) U8-3/15 (C), U9-3/16 (C)
| 1 |  |  | Chandrapur-II - Warora |  |  | MSETCL | D/C |  |  | 400 | 91 | 138 | 138 |  |  | 137 |  | 91 |  |  |  | JUN-13 |  | Commissioned 06/13.
| 2 |  |  | LILO of Chandrapur - Parli at Chandrapur II |  |  | MSETCL | D/C |  |  | 400 | 3 | 11 | 11 |  |  | 11 |  | 3 |  |  |  | APR-13 |  | Commissioned 4/13.
| 3 |  |  | Warora-Wardha(2nd Ckt) |  |  | MSETCL | S/C |  |  | 400 | 76 | 223 | 223 |  |  | 223 |  | 76 |  |  |  | JAN-13 |  | Commissioned 01/13.
| 4 |  |  | Chandrapur switching Stn. - Chandrapur II S/S |  |  | MSETCL | S/C |  |  | 400 | 4 | 11 | 11 |  |  | 11 |  | 4 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 5 |  |  | Chandrapur-II (Addl.) |  |  | MSETCL |  |  |  | 400/220 | 500 | 100 | 97 |  |  | 96 |  | 85 |  |  |  | MAR-18 |  | Priority Bay 410, 426, 408 (Tie Bay) and 409 ,411, 412, 428, 429, 404, 405 commissioned from 30.12.2013 to 13.3.2014. In 400KV Switchyard- erection of ICT-2 is balance. ICT-I (500 MVA) commissioned on 31-03-2018.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 6 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Chango Yangthang (140 MW), PS, Spiti,HP, MPCL, Project dropped
| 1 |  |  | Chango Yangthang - Ka Dogri Pooling Station |  |  | MPCL | D/C |  |  | 220
| 2 |  |  | Ka Dogri - Jangi Pooling Station |  |  | MPCL | D/C |  |  | 400
|  | Remark: |  |  | Project has been dropped from generation program.
Chanju-I HEP (3x12 MW) on Ravi river, SS HPPTCL, IA Energy, U1,2-2/17(C), U3-9/17
| 1 |  |  | 220 kV Double Circuit Transmission Line from 220/132 kV GIS Sub-Station Mazra to 220/33 GIS Sub-Station Karian |  |  | HPPTCL | D/C |  |  | 220 | 36 | 52 | 52 |  |  | 52 |  | 36 | JUL-23 |  |  | JAN-24 |  | Commissioned 01/24.
| 2 |  |  | Chanju - Nakrot line |  |  | HPPTCL | D/C |  |  | 132 | 12 | 30 | 29 |  |  | 27 |  | 10 | [5 empty] | commissioned.
| 3 |  |  | LILO of one ckt Kurthala - Bathri at Nakrot Pooling Station |  |  | HPPTCL | D/C |  |  | 132 | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  |  | MAR-17 |  | Completed.
| 4 |  |  | 220/132 kV GIS Sub-Station at Mazra Distt Chamba |  |  | HPPTCL |  |  |  | 220/132 | 200 | 100 | 100 |  |  | 100 |  | 100 | JUN-23 |  |  | JAN-24 |  | Commissioned 01/24.
Remark:
Chhabra TPP Extn. (2x250 MW) SS,Raj, RRVUNL, U3-9/13(C),U4-6/14 (C)
| 1 |  |  | Chhabra TPS -Hindaun |  |  | RVPNL | S/C |  |  | 400 | 342 | 803 | 803 |  |  | 803 |  | 342 |  |  |  | APR-10 |  | Commissioned 4/10
| 2 |  |  | Chhabra TPS - Jhalawar |  |  | RVPNL | S/C |  |  | 220 | 101 | 329 | 329 |  |  | 329 |  | 101 |  |  |  | AUG-11 |  | Commissioned 8/11.
Remark:
Chhabra TPS-II(2x660),SS,RRVUNL,Rajasthan, U5-4/17(c),U6-12/18
| 1 |  |  | Chhabra TPS - Anta (Baran) |  |  | RVPNL | D/C |  |  | 400 | 179 | 244 | 244 |  |  | 244 |  | 179 |  |  |  | JAN-15 |  | Commissioned 01/15.
Remark:
Chitrangi TPP Ph-I (6x660 MW), Ph-II (3x660 MW),SS,MP,Ph-I,U1-9/13,U2-12/13,U3-3/14,U4-6/14,U5-9/14,U6-12/14, Ph-II,U1-3/15,U2-6/15,U3-9/19
| 1 |  |  | Chitrangi TPS - Vindhyachal Pooling Station |  |  | XYZ | D/C |  |  | 765
Remark:
Chujachen HEP (2x49.5 MW)PS,Sikkim,GIL,U1-4/13(C),U2-4/13 (C).
| 1 |  |  | LILO of Melli - Gantok at Chuzachen (LILO point at namthang) |  |  | GISL | D/C |  |  | 132 | 47 | 91 | 91 |  |  | 91 |  | 47 |  |  |  | MAR-17 |  | Commissioned 04/13. (Interim arrangement)
| 2 |  |  | Chujachen HEP - Rangpo PS |  |  | GISL | D/C |  |  | 132 | [11 empty] | MAR-17 |  | Line commissioned.
Remark:
Chutak-HEP (4x11 MW), CS, J&K, NHPC, U1-11/12( C), U2- 11/12( C), U3- 11/12(C), U4-1/13(C)
| 1 |  |  | Gramthong -II - Sankoo |  |  | JKPDD | S/C |  |  | 66 | 27 | 154 | 154 |  |  | 154 |  | 27 |  |  |  | MAR-17 |  | Commissioned.
| 2 |  |  | Khangral - Mulbek -II |  |  | JKPDD | S/C |  |  | 66 | 23 | 117 | 117 |  |  | 117 |  | 23 |  |  |  | MAR-17 |  | Commissioned
| 3 |  |  | Chutak HEP-Gramthong -II |  |  | JKPDD | S/C |  |  | 66 | 5 | 29 | 29 |  |  | 29 |  | 5 |  |  |  | MAR-17 |  | Commissioned.
| 4 |  |  | Chutak HEP-Kargil-I |  |  | JKPDD | S/C |  |  | 66 | 10 | 55 | 55 |  |  | 55 |  | 10 |  |  |  | MAR-17 |  | Commissioned.
| 5 |  |  | Mulbek-II - Kargil -I |  |  | JKPDD | S/C |  |  | 66 | 28 | 124 | 124 |  |  | 124 |  | 28 |  |  |  | MAR-17 |  | Commissioned.
| 6 |  |  | Mulbeck |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 7 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 7 |  |  | Khangral (Bodhkharbu) |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
| 8 |  |  | Gramthong S/S |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
| 9 |  |  | Kargil S/S |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
| 10 |  |  | Sankoo S/S |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
Remark:
Common System Associated with Costal Energen Private Ltd and Ind-Barath Power Ltd. (LTOA) Gen. Proj. in Tuticorin area Part - B..
| 1 |  |  | Salem PS - Madhugiri PS line |  |  | PGCIL | S/C |  |  | 765 | 243 | 644 | 644 |  |  | 644 |  | 243 | SEP-14 |  |  | OCT-18 |  | Commissioned 10/18.
| 2 |  |  | Salem Pooling Station - Salem |  |  | PGCIL | D/C |  |  | 400 | 120 | 165 | 165 |  |  | 165 |  | 120 | SEP-14 |  |  | AUG-15 |  | Ready for commissioning 08/15.
| 3 |  |  | Tuticorin Pooling Station - Salem Pooling Station |  |  | PGCIL | D/C |  |  | 765 | 731 | 1000 | 1000 |  |  | 1000 |  | 731 | SEP-14 |  |  | NOV-16 |  | Commissioned 11/2016.
Remark:
Cosmos Sponge TPS, (1x350 MW), PS,Chh,CSPL,U1-6/13
| 1 |  |  | CSPL TPS - Raigarh Pooling Station (Near Kotra) |  |  | XYZ | D/C |  |  | 400
Remark:
Cuddalore TPP (2x600 MW), PVT, IL&FS, SS, Tamil Nadu, U1-9/15 (C) U2-05/16
| 1 |  |  | Cuddalore - Naggapattinam |  |  | ITPCL | D/C |  |  | 400 | 95 | 138 | 138 |  |  | 138 |  | 95 |  |  |  | AUG-16 |  | Commissioned 01/15. (Late reported.)
Remark:
Dada Dhuni wale TPP, Khandwa (2x800 MW) SS,MP, U1-7/15,1U2-12/16
| 1 |  |  | Dada Dhuniwale TPP - Moondi Pooling Point |  |  | MPPTCL | D/C |  |  | 400 | 80
| 2 |  |  | Badnawar (New) s/s |  |  | MPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | MAR-19 |  |  | MAR-19 |  | Commissioned 03/19.
| 3 |  |  | Handia S/S |  |  | MPPTCL |  |  |  | 400/220 | 630 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Dropped
Remark:
Damaracherla Power Evacuation Scheme
| 1 |  |  | Damaracherla -Huzurnagar line |  |  | TSTRANS | D/C |  |  | 220 | 77 | 137 | 137 |  |  | 137 |  | 76.06 | MAY-24 |  |  |  |  | Line works completed, except stringing of 3km of OPGW Cable ( from Loc. No. 79 to 91) , which is under progress. After completion of OPGW stringing, Statutory inspection works will be carried out.
Remark:
Damaracherla TPP (2*600+4*800), TSGenco, Telangana
| 1 |  |  | Damaracherla TPP - Maheswaram (TS) |  |  | TSTRANS | D/C |  |  | 400 | 310 | [7 empty] | SEP-18
| 2 |  |  | Damacherla TPP - Dindi |  |  | TSTRANS | D/C |  |  | 400 | 280 | [7 empty] | SEP-18
| 3 |  |  | Damacherla TPP - Choutuppal |  |  | TSTRANS | D/C |  |  | 400 | 300 | [7 empty] | SEP-18
| 4 |  |  | Damaracherla TPP - Jangaon |  |  | TSTRANS | D/C |  |  | 400 | 310 | [7 empty] | SEP-18
Remark:
Damodaram Sanjeevaiah(Krishnapatnam) TPP, (2x800MW) SS,AP, APPDCL, U1-9/14 (C), U2-3/15 (C)
| 1 |  |  | Krishnapatnam TPS - Nellore. |  |  | APTRANS | D/C |  |  | 400 | 72 | 112 | 112 |  |  | 112 |  | 72 |  |  |  | NOV-12 |  | Commissioned 11/12.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 8 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Bonapally - Chittoor (Quad) |  |  | APTRANS | D/C |  |  | 400 | 196 | 281 | 281 |  |  | 281 |  | 196 |  |  |  | FEB-15 |  | Commissioned 02/15.
| 3 |  |  | Krishnapatnam TPS- Chittoor(Balance) |  |  | APTRANS | D/C |  |  | 400 | 180 | [6 empty] | 180 |  |  |  | JUL-15 |  | Commissioned 07/15.
Remark:
Darlipalli TPS(2x800), Odissa, NTPC, U1-02/18, U2-08/18
| 1 |  |  | Darlipalli TPS - Jharsuguda (Sundergarh) PS line |  |  | PGCIL | D/C |  |  | 765 | 41 | 61 | 61 |  |  | 61 |  | 41 |  |  |  | APR-17 |  | Ready for Commissioning 04/2017
Remark:
Derang TPP (2x600MW) PS, Orissa, JIPL, U1-5/14 (C), U2-1/15 (C)
| 1 |  |  | Derang - Angul Pooling Station |  |  | JPL | MC+D/C |  |  | 400 | 154 | 231 | 231 |  |  | 231 |  | 154 |  |  |  | AUG-14 |  | Commissioned 08/14.
Remark:
DGEN TPS (3x400MW), Torrent Power Ltd, Gujarat
| 1 |  |  | Navseri - Bhasten (DGEN TL - TBCB) |  |  | TOR. | D/C |  |  | 220 | [13 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
| 2 |  |  | DGEN - Vadodara (DGEN TL - TBCB) |  |  | TOR. | D/C |  |  | 400 | [13 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
| 3 |  |  | DGEN TPS - Bharuch/Dahej Pooling Station |  |  | TOR. | D/C |  |  | 400
| 4 |  |  | Bharuch/Dahej |  |  | TOR. |  |  |  | 765/400 | 1500 | 0 | 0 |  |  | 0 |  | 0
Remark:
Dhariwal TPS (2x300 MW), PS, Maharashtra, DIPL, U1-11/13(C),U2-5/14 (C)
| 1 |  |  | LILO of one ckt of Bhadravati (PG) - Parli at Dhariwal |  |  | DIL | D/C |  |  | 400 | 31 | 51 | 51 |  |  | 51 |  | 31 |  |  |  | AUG-14 |  | Commissioned 08/14.
| 2 |  |  | Dhariwal TPS -Channdrapur II (1st Ckt) |  |  | DIL | S/C |  |  | 400 | 10 | 29 | 29 |  |  | 29 |  | 10 |  |  |  | SEP-13 |  | Commissioned 09/13.
Remark:
Dharmpura TPP (4x300 MW), Jain Energy, P.S,
| 1 |  |  | Jain Energy TPS - Dharamjaygarh Korba Pooling station |  |  | JAIN ETL | D/C |  |  | 400
Remark:
Dikchu HEP (2x48MW)PS,Sikkim,SKPPL,U1,U2-4/17(C)
| 1 |  |  | (Sikkim) Dikchu Pool - Parbing line |  |  | PGCONSU | D/C |  |  | 132 | 42 | 96 | [6 empty] | DEC-18
| 2 |  |  | (Sikkim) Dikchu Pool - Singhik |  |  | PGCONSU | D/C |  |  | 220 | 46 | [7 empty] | DEC-18
| 3 |  |  | Dikchu HEP - Dikchu Pool |  |  | SIKKIM | D/C |  |  | 132 |  | 0 | 0 |  |  | 0 | [7 empty] | Yet to award
| 4 |  |  | (Sikkim) Dikchu Pool - Rangpo (Samardong) (twin) |  |  | PGCONSU | D/C |  |  | 220 | 50 | [7 empty] | DEC-18
| 5 |  |  | LILO of Teesta III - Rangpo 400 kv line at Dikchu (Interim connectivity) |  |  | SIKKIM | D/C |  |  | 400 | 1 | 2 | 2 |  |  | 12 |  | 1 | [5 empty] | Completed.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 9 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 6 |  |  | (Sikkim) Dikchu pool (new) S/S |  |  | PGCONSU |  |  |  | 132/33/11 | 100 |  | 0 |  |  | 0 |  | 0 | DEC-18
Remark:
Durgapur (DPL) Extn. (250 MW), SS,WB, U8-3/14 (C)
| 1 |  |  | DPL - Bidhan nagar |  |  | DPL | D/C |  |  | 400 | [11 empty] | MAR-12 |  | Existing line.
Remark:
Durgapur TPS (2x500 MW),CS,WB,DVC,U1-7/11(C),U2-3/1 (C)
| 1 |  |  | LILO of Durgapur-Jamshedpur (PG) at Durgapur STPS |  |  | DVC | D/C |  |  | 400 | 7 | 14 | 14 |  |  | 14 |  | 7 | MAY-09 |  |  | JAN-11 |  | Commissioned 3/11.
| 2 |  |  | Durgapur-Jamshedpur (Part Line) |  |  | PGCIL | D/C |  |  | 400 | 276 | 519 | 469 |  |  | 451 |  | 276 |  |  |  | APR-12 |  | Commissioned 4/12.
| 3 |  |  | Durgapur STPS - Raghunathpur |  |  | DVC | D/C |  |  | 400 | 138 | 208 | 208 |  |  | 208 |  | 138 | MAY-10 |  |  | JUL-13 |  | Commissioned 07/13.
Remark:
Dwarkesh Energy Ltd TPP (2x660 MW) PS, Khandwa, MP,
| 1 |  |  | Dwarkesh Energy TPP - Indore |  |  | XYZ | D/C |  |  | 765
Remark:
Eastern region expansion scheme-XXIX (ERSS-XXIX)
| 1 |  |  | Reconductoring of Jharsuguda/Sundargarh(PG) Rourkela(PG) 400 kV twin moose line with twin HTLS |  |  | PGCIL | D/C |  |  | 400 | 1404 | 0 | 0 |  |  | 0 |  | 284 | NOV-25 |  |  |  |  | Awarded in Mar'23. .Ckt-1 completed in March 2024 (142 CKM). 105.354 CKm of Ckt-3 completed . 8 Ckm of Ckt-4 completed.
Remark:
Eastern region expansion scheme-XXXIII (ERSS-XXXIII)
| 1 |  |  | Reconductoring of Rangpo-Gangtok 132kV D/c line with single HTLS conductor of 800A (at nominal voltage level) |  |  | PGCIL | D/C |  |  | 132 | 54 | 0 | 0 |  |  | 0 |  | 5 | NOV-24 |  |  |  |  | Shutdown constraint from Sikkim. S/D denied by Sikkim Power Department.
Remark:
EMCO Warora TPP (2x300 MW), PS,Maha,GMR, U1-2/13 (C),U2-8/13(C)
| 1 |  |  | EMCO - Bhadrawathi (PG) |  |  | GMR | D/C |  |  | 400 | 80 | 96 | 96 |  |  | 96 |  | 80 |  |  |  | JAN-13 |  | Commissioned 01/13.
Remark:
Ennore TPP, Ennore Exp, N Chennai-III(2X660, 660, 800),TG,TANGENDCO,U1-3/20,U2-4/19;U1-9/21;U1-9/18
| 1 |  |  | ETPS exp.- Ennore SEZ |  |  | TANTRAN | D/C |  |  | 400 | 24 | 22 | 21 |  |  | 19 |  | 9.72 | APR-19 |  |  |  |  | Work under progress.line stringing pending for want LC
| 2 |  |  | Ennore SEZ - North Chennai Pooling Station |  |  | TANTRAN | D/C |  |  | 400 | 33 | 51 | 40 |  |  | 36 |  | 15.18 | SEP-23 |  |  |  |  | Work under progress.ROW issues involved . PWD approval awaited
| 3 |  |  | ETPS exp. - North Chennai Pooling Station |  |  | TANTRAN | D/C |  |  | 400 | 24 | 9 | 8 |  |  | 8 |  | 3.78 | SEP-18 |  |  |  |  | Work under progress.
Remark:
Establishment of Khavda Pooling Station-2 (KPS2) in Khavda RE Park (KPS2 TRANSMISSION LIMITED)
| 1 |  |  | 765/400kV 4x1500MVA KPS2 New SS (GIS) |  |  | PGCIL |  |  |  | 765/400 | 6000 | 100 | 30 |  |  | 20 |  | 0 | DEC-24
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 10 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Establishment of Khavda Pooling Station-3 (KPS3) in Khavda RE Park (SPV Name: KPS3 TRANSMISSION LIMITED)
| 1 |  |  | 765kV Dc/KPS2-KPS3 line |  |  | PGCIL | D/C |  |  | 765 | 30 | 40 | 17 |  |  | 0 |  |  | MAR-25 |  |  |  |  | Stone piling work in progress.
| 2 |  |  | 765/400kV 3x1500MVA KPS-3 SS |  |  | PGCIL |  |  |  | 765/400 | 45000 | [7 empty] | DEC-24
Remark:
Evacuation of power from rajgarh SEZ (2500MW)
| 1 |  |  | Pachora SEZ PP - Bhopal (Sterlite) line (Quad/HTLS) |  |  | GRINFRA | D/C |  |  | 400 | 288 | 0 | 0 |  |  | 0 |  | 288 | NOV-23 |  |  | FEB-24 |  | Commissioned 02/24.
| 2 |  |  | Establishment of 400/220 kV 3X500 MVA at Pachora SEZ PP with 420 kV (125 MVAR) bus reactor |  |  | GRINFRA |  |  |  | 400/220 | 1500 | 100 | 100 |  |  | 100 |  | 100 | NOV-23 |  |  | FEB-24 |  | Commissioned 02/24.
Remark:
Evacuation of power from RE Projects in Osmanabad area (1 GW) in Maharashtra
| 1 |  |  | LILO of both Ckts. of Parli (PG) -Pune (GIS) line at Kallam (PS) |  |  | INDIGRID | M/C |  |  | 400 | 68 | 47 | 47 |  |  | 47 |  | 68 | OCT-23 |  |  | MAR-24 |  | Commissioned 03/24.
| 2 |  |  | Establishment of 2x500MVA (400/220kV) near Kallam PS |  |  | INDIGRID |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | DEC-23 |  |  | MAR-24 |  | Commissioned 03/24.
Remark:
Evacuation of power from RE sources in Koppal Wind Energy Zone (Karnataka ) (2500MW)
| 1 |  |  | Koppal PS - Narendra (New) Trans. Ltd. |  |  | RTVPL | D/C |  |  | 400 | 276 | 352 | 352 |  |  | 352 |  | 276 | JUN-23 |  |  | OCT-23 |  | Commissioned 10/23.
| 2 |  |  | Augmentation of 400/220 KV Koppal Substation with 2x500 MVA ICTs |  |  | RTVPL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | JAN-24 |  |  | JAN-24 |  | Commissioned 01.24.
| 3 |  |  | Koppal (PS) |  |  | RTVPL |  |  |  | 400/220 | 1500 | 100 | 100 |  |  | 100 |  | 100 | NOV-23 |  |  | OCT-23 |  | Commissioned 10/23.
Remark:
Evacuation of Power from SEZ in Gadag(2500 MW)
| 1 |  |  | Gadag (PS) - Narendra (New) Trans. Ltd. |  |  | RTVPL | D/C |  |  | 400 | 185 | 232 | 160 |  |  | 83 |  | 13 | MAY-24 |  |  |  |  | Bagalkot Forest Division : DFO, Bagalkote has recommended the proposal on 03.03.2023 and forwarded to CCF, Belgaum. Gadag Forest Division : Reply against DFO, Gadag queries dated 20.02.2023 was submitted on 02.03.2023. Proposal is pending with DFO, Gadag & PCCF, Karnataka for acceptance and further processing of proposal & ROW compensation fixation order have been issued for Bagalkote, Gadag & Vijayapura Districts (except Koppal district) by the respective DCs on 27.10.2022, 04.03.2023 & 06.03.2023 respectively.
Remark:
Gadarwara STPS-I (2x800 MW), NTPC, U1-1/18,U2-07/18
| 1 |  |  | LILO of Wardha - Parli at Warora PS (PWTL-TBCB) |  |  | PGCIL | D/C |  |  | 400 | 196 | 269 | 269 |  |  | 269 |  | 196 | NOV-17 |  |  | MAY-18 |  | Commissioned 05/18.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 11 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Gadarwara - Jabalpor Pool line (Balance Portion from LILO of Seoni - Bina to Jabalpur) (PWTL-TBCB) |  |  | PGCIL | D/C |  |  | 765 | 187 | 271 | 271 |  |  | 271 |  | 187 | NOV-17 |  |  | MAY-17 |  | Commissioned 05/17.
| 3 |  |  | Gadarwara - Warora PS (PWTL-TBCB) |  |  | PGCIL | D/C |  |  | 765 | 627 | 837 | 837 |  |  | 837 |  | 616 | NOV-17 |  |  | JUN-18 |  | Ready for Commissioning 06/18.
| 4 |  |  | LILO of existing Seoni-Bina at Gadarwara STPP |  |  | PGCIL | D/C |  |  | 765 | 16 | 43 | 43 |  |  | 43 |  | 16 |  |  |  | JAN-17 |  | commissioned 11/2016 (Late Reported)
| 5 |  |  | Warora PS (PWTL-TBCB) |  |  | PGCIL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 | NOV-17 |  |  | JUN-18 |  | Commissioned 06/18.
|  | Remark: |  |  | SPV/BPC - Powergrid Warora Transmission Ltd / REC
Gadarwara STPS-II (2x800 MW), NTPC (Part-B) (TBCB)
| 1 |  |  | Warora PS - Parli (PPTL-TBCB) |  |  | PGCIL | D/C |  |  | 765 | 694 | 920 | 920 |  |  | 920 |  | 694 | JAN-18 |  |  | JUN-18 |  | Commissioned 06/18.
| 2 |  |  | Parli - Solapur (PPTL - TBCB) |  |  | PGCIL | D/C |  |  | 765 | 236 | 311 | 311 |  |  | 311 |  | 236 | JAN-18 |  |  | APR-18 |  | Commissioned 04/18.
| 3 |  |  | Parli (MSETCL) - Parli (PG) |  |  | PGCIL | D/C |  |  | 400 | 10 | 15 | 15 |  |  | 15 |  | 10 | JUL-10 |  |  | FEB-11 |  | Ready for Commissioning 2/11.
| 4 |  |  | Parli (New) S/s (PPTL -TBCB) |  |  | PGCIL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 | JAN-18 |  |  | APR-18 |  | Commissioned 04/18.
|  | Remark: |  |  | SPV/BPC - Powergrid Parli Transmission Ltd / REC
GAMA CCPP (225 MW), M/s GAMA Infraprojects Ltd., UK, Module-1:4/16(C)
| 1 |  |  | LILO of Mahuakheraganj-Kashipur line at GAMA CCPP |  |  | XYZ | D/C |  |  | 220 | 3
Remark:
GEPL Ph -1 (2x60 MW ), U1-60 MW,9/12 (C) & Ph-2 (2x270 MW) TPS,PS,Maha,GEPL,U2-4/12(C)
| 1 |  |  | LILO of one ckt of Bhadrawati -Parli at GEPL TPS |  |  | GEPL | D/C |  |  | 400
| 2 |  |  | GEPL -MIDC S/S |  |  | GEPL | D/C |  |  | 220 | 20 | [6 empty] | 20 |  |  |  | SEP-14 |  | Commissioned 9/14
Remark:
Ghatampur TPP (3x660 MW), UP, NLC JV, U1-02/22, U2-08/23, U3-02/23
| 1 |  |  | Agra (UP) - Greater Noida (UP) |  |  | UPPTCL | S/C |  |  | 765 | 0 | 0 | 0 |  |  | 0 | [7 empty] | To be deleted
| 2 |  |  | Ghatampur TPS - Kanpur (PG) line |  |  | UPPTCL | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Commissioned in Jan'2020
| 3 |  |  | Ghatampur TPS - Hapur |  |  | UPPTCL | S/C |  |  | 765 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Line Antitheft energized on 18.06.2022.
| 4 |  |  | Ghatampur TPS - Agra (UP) |  |  | UPPTCL | S/C |  |  | 765 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Commissioned in Mar'2021
| 5 |  |  | ICT at Ghatampur (3x200 MVA) s/s |  |  | UPPTCL |  |  |  | 400/132 | 600 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | JV b/w Neyveli Lignite UPRVUNL. ICT-I and ICT-II likely to be Energised on Oct' 2024
| 6 |  |  | ICT at Ghatampur (2x1500 MVA) s/s |  |  | UPPTCL |  |  |  | 765/400 | 3000 | 100 | 0 |  |  | 0 |  | 0 | [5 empty] | JV b/w Neyveli Lignite & UPRVUNL. ICT-I and ICT-II likely to be Energised on Nov.' 2024
Remark:
Ghazipur (2x660 MW), PS, UP, BEL Spun,
| 1 |  |  | Ghazipur - Rasra |  |  | UPPTCL | S/C |  |  | 220 | 59 | 186 | 186 |  |  | 186 |  | 59 | FEB-11 |  |  | SEP-14 |  | Commissioned 09/14.
Remark:
Goindwal Sahib (2x270MW), PS,Punjab,GVK, U1-2/16(C),U2-3/16 (C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 12 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Goindwal Sahib - Bottianwala |  |  | PSTCL | D/C |  |  | 220 | 129 | 203 | 203 |  |  | 203 |  | 129 |  |  |  | SEP-18 |  | Ready for Commissioning 09/18 (Commissioning held up due to tree cutting).
| 2 |  |  | Goindwal Sahib - Chola Sahib |  |  | PSTCL | D/C |  |  | 220 | 55 | 92 | 92 |  |  | 92 |  | 55 |  |  |  | DEC-15 |  | Ready for Commissioning 12/15.
| 3 |  |  | Goindwal Sahib - Sultanpur Lodhi |  |  | PSTCL | D/C |  |  | 220 | 38 | 60 | 60 |  |  | 60 |  | 38 |  |  |  | AUG-12 |  | Commissioned 8/12
Remark:
Gongri HEP (2x72 MW), PS, Arp, Dirang Energy, U1&U2 (2022-23)
| 1 |  |  | Gongri - Dinchang Pooling Station |  |  | DEPL | D/C |  |  | 220
Remark:
Gorgi TPP (2x660MW), MP, DB Power Ltd. , Uncertain
| 1 |  |  | DBTPS - Vindhyachal PS (Quad) line |  |  | MPPTCL | D/C |  |  | 400 | 0
Remark:
Green Energy Corridor - I Intrastate
| 1 |  |  | Hindupur (400) - Pampanur Tanda (220)(GEC-I). |  |  | APTRANS | D/C |  |  | 220 | 140 | 239 | 239 |  |  | 239 |  | 140 | APR-23 |  |  | MAY-23 |  | Commissioned 05/23.
| 2 |  |  | 400kV D/C Bhogat -Kalawad line with Twin AL-59 Cond. and 1 OPGW and 1 Earth Wire |  |  | GETCO | D/C |  |  | 400 | 250 | 410 | 410 |  |  | 410 |  | 250 | NOV-23 |  |  | MAR-24 |  | Commissioned 03/24.
| 3 |  |  | Wankaner S/S (Dist. Rajkot) (GEC-I) |  |  | GETCO |  |  |  | 220/132 | 300 | 100 | 100 |  |  | 100 |  | 100 | JUL-19 |  |  | OCT-21 |  | Commissioned 10/21.
| 4 |  |  | Pampanur Tanda (GEC-I) (160 MVA T/F-II) |  |  | APTRANS |  |  |  | 220/132 | 160 | 100 | 100 |  |  | 100 |  | 90 | JUN-24 |  |  |  |  | Substation charged on 18.05.2023. PTR-1 Charged on 08.12.2023
| 5 |  |  | Hindupur (ICT 3rd ) |  |  | APTRANS |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | JUN-23 |  |  | MAY-23 |  | Commissioned 05/23.
Remark:
Haldia TPP (2x300 MW) SS, WB, IPC(H)L. U1 - 07/16, U2 - 11/16
| 1 |  |  | Haldia TPP (IPCL) - New Haldia (WBSETCL) |  |  | IPCHL | D/C |  |  | 220 | 5 | 15 | 15 |  |  | 15 |  | 5 |  |  |  | MAY-17 |  | Commissioned 03/17 (Late Reported).
| 2 |  |  | Haldia TPP - Egra |  |  | ISPAT | D/C |  |  | 220 | 180 | [12 empty] | Under planning stage by WBSETCL.
Remark:
Harduaganj TPS (2x250 MW),SS,UP,UPRVUNL,U8-9/11(C),U9-5/12(C)
| 1 |  |  | Harduaganj - Jahangirabad |  |  | UPPTCL | D/C |  |  | 220 | 99 | 151 | 151 |  |  | 151 |  | 99 | AUG-09 |  |  | NOV-14 |  | Commissioned 11/14.
Remark:
Harduaganj TPS Exp-II (1x660MW), UP, UPRVUNL , U-6/19
| 1 |  |  | LILO of 400 kV Aligarh-Sikandrabad at Harduaganj TPS Line |  |  | UPPTCL | D/C |  |  | 400 | 61 | 84 | 84 |  |  | 84 |  | 61 |  |  |  | MAY-21 |  | Commissioned 05/21.
| 2 |  |  | ICT at Harduaganj Extn |  |  | UPPTCL |  |  |  | 400/220 | 630 | 100 | 0 |  |  | 0 |  | 0 | [5 empty] | ICT-I Energised in 02.09.2019 and ICT-II Energised in 28.09.2020. To be deleted.
Remark:
Hazaira CCPP (351 MW),SS,GUJ,GSECL,,GT+ST-2/12(c )
| 1 |  |  | Hazaira (GSEC)-Kosamba |  |  | GETCO | D/C |  |  | 220 | 125 | 211 | 211 |  |  | 211 |  | 125 | APR-11 |  |  | SEP-11 |  | Commissioned 9/11.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 13 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Hazaira (GSEC) - Mota |  |  | GETCO | D/C |  |  | 220 | 111 | 182 | 111 |  |  | 96 |  | 41.82 | [5 empty] | Inter connection of Utran-Kosamba charged under stop gap arrangement (Kosamba-Mota & Utran-Mota) on 16.06.2018 as per system requirement.
Remark:
Hindustan Electricity GCL TPP (1x350+3x379 MW), PS, Maha, U1-3/14, U2, & U3
| 1 |  |  | HEGCL TPP - Pune (AIS) (PG) |  |  | XYZ | D/C |  |  | 400 | 110
| 2 |  |  | LILO of Lonikhand - Kalwa at HEGCL TPP |  |  | XYZ | D/C |  |  | 400
Remark:
Ind Barath TPP (Utkal)(2x350MW),PS,Orissa,Barath, U1-2/16(C), U2-11/17
| 1 |  |  | Ind - Barath (Power Plant (Shahjbahal) - Jharsuguda (Sundargarh)line |  |  | IBPIL | D/C |  |  | 400 | 124 | 125 | 125 |  |  | 125 |  | 124 |  |  |  | OCT-17 |  | Commissioned 06/2017 (Late Reported).
| 2 |  |  | LILO of Rouekila - Raigarh at Ind Barath |  |  | IBPIL | D/C |  |  | 400 | 47 | 72 | 72 |  |  | 72 |  | 47
Remark:
Inter-regional ER-WR Interconnection (SPV Name: ERWR TRANSMISSION LIMITED)
| 1 |  |  | 400kV D/C Jeypore (POWERGRID) - Jagdalpur (CSPTCL) line |  |  | PGCIL | D/C |  |  | 400 | 137 | 172 | 112 |  |  | 1 |  |  | MAR-25 |  |  |  |  | 1) Forest Chhatisgarh (4.48 Ha): Forest proposal for Chhattisgarh submitted on 09.06.23, Revised Proposal Submitted on 09/11/2023​.Stage-I Awaited.2) Forest Odisha (18.1 Ha): Forest proposal for Jeypore (Odisha) side initially submitted in Oct 2023 which got rejected. Stage-I Awaited.
Remark:
Jal Churk (4x60 MW), PS,UP, M/S Jal ,
| 1 |  |  | Churk - Robertsganj |  |  | UPPTCL | D/C |  |  | 220 | 13 | [6 empty] | 13 |  |  |  | JAN-14 |  | Commissioned 01/14.
Remark:
Jallipa-Kapurdi TPP(8x135MW),PS,RAJ, RW Power, U1 to U8: Comm from 10/09(c) to 2/13(c)
| 1 |  |  | Rajwest- Barmer |  |  | RVPNL | D/C |  |  | 400 | 30 | 44 | 44 |  |  | 44 |  | 30 | APR-10 |  |  | MAY-10 |  | 1 ckt Commissioned 5/10
| 2 |  |  | Raj West-Dhorimana |  |  | RVPNL | S/C |  |  | 220 | 83 | 283 | 283 |  |  | 283 |  | 83 |  |  |  | MAR-12 |  | Commisisoned 3/12
| 3 |  |  | Rajwest- Jodhpur |  |  | RVPNL | D/C |  |  | 400 | 417 | 560 | 560 |  |  | 560 |  | 417 | APR-09 |  |  | MAY-10 |  | Commissioned 5/10
| 4 |  |  | LILO of Giral - Barmer Ckt 1 at Raj West LTPS. |  |  | RVPNL | D/C |  |  | 220 | 5 | 10 | 10 |  |  | 10 |  | 5 |  |  |  | AUG-08 |  | Commissioned 8/10
Remark:
Jawaharpur TPP, (3x660 MW), Uttar Pradesh, JVUNL, 2020-21
| 1 |  |  | LILO of Mainpuri - G Noida at Jawaharpur TPS |  |  | UPPTCL | S/C |  |  | 765 | 30 | 66 | 66 |  |  | 66 |  | 25.84 | [5 empty] | Line charged on 10.04.2023. Being constructed in TBCB mode by PGCIL.
| 2 |  |  | LILO Agra(South)-Fahtehabad(Agra) at Firozabad |  |  | UPPTCL | D/C |  |  | 400 | 26 | 47 | 47 |  |  | 47 |  | 26 |  |  |  | MAR-21 |  | Commissioned 02/21 (Late Reported).
| 3 |  |  | Jawahapur TPS-Firozabad Line |  |  | UPPTCL | D/C |  |  | 400 | 80 | 204 | 204 |  |  | 204 |  | 140.98 | [5 empty] | Energized on 07,08.07.2021 . Being constructed in TBCB mode by PGCIL.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 14 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 4 |  |  | Jawaharpur TPP - yet to be decided |  |  | JAWAHAR | D/C |  |  | 400
| 5 |  |  | LILO of Mainpuri- Sikandrarao at Jawarharpur TPS |  |  | UPPTCL | S/C |  |  | 220 | 22 | 49 | 49 |  |  | 49 |  | 22 |  |  |  | JUL-19 |  | Commissioned 07/19.
Remark:
Jegurupadu extesion project (Phase II) GVK Group) 220 MW U (C)
| 1 |  |  | Jegurupadu - Vemagiri line |  |  | GVKP&IL | D/C |  |  | 400 | 14 | [6 empty] | 14 |  |  |  | MAR-09 |  | Commissioned in FY 2008-09.
Remark:
Jhajjar Mahatama Gandhi (CLP) (2x660 MW), PS, U1-1/12(C),U2-4/12(C)
| 1 |  |  | LILO of Jhajjar (APCPL) - Daultabad line at MG Jhajjar (CLP) |  |  | HVPNL | D/C |  |  | 400 | 10 | 23 | 23 |  |  | 23 |  | 10 |  |  |  | OCT-11 |  | Commissioned 10/11.
| 2 |  |  | Kabalpur - Badhan |  |  | HVPNL | D/C |  |  | 220 | 46 | 97 | 97 |  |  | 97 |  | 46 |  |  |  | SEP-13 |  | Commissioned 09/13
| 3 |  |  | Jhajjar - Kabulpur |  |  | HVPNL | D/C |  |  | 400 | 70 | 95 | 95 |  |  | 95 |  | 95 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 4 |  |  | Jhajjar -Dhanonda |  |  | HVPNL | D/C |  |  | 400 | 40 | 64 | 64 |  |  | 64 |  | 64 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 5 |  |  | Deepalpur-Barhi |  |  | HVPNL | D/C |  |  | 220 | 25 | 95 | 95 |  |  | 95 |  | 25 |  |  |  | MAY-13 |  | Commissioned 05/13.
| 6 |  |  | Kabulpur-Deepalpur |  |  | HVPNL | D/C |  |  | 400 | 133 | [10 empty] | FEB-12 |  | Commissoned 2/12.
| 7 |  |  | LLIO of Bahadurgarh- Rohtak at Kabulpur |  |  | HVPNL | D/C |  |  | 220 | 47 | 94 | 94 |  |  | 94 |  | 47 |  |  |  | NOV-13 |  | Commissioned 11/13.
| 8 |  |  | LILO of abdullapur-Bawana at deepalpur |  |  | HVPNL | D/C |  |  | 400 | 2 | 3 | 3 |  |  | 3 |  | 2 |  |  |  | FEB-12 |  | commissioned 2/12.
| 9 |  |  | Deepalpur-Sonepat HSIIDC Rai ( terminated at Rajiv Gandhi s/s) |  |  | HVPNL | M/C |  |  | 220 | 41 | 101 | 101 |  |  | 101 |  | 41 | MAY-13 |  |  | DEC-16 |  | Ready for commissioning 02/2016 (Late Reported)
| 10 |  |  | Kabulpur S/S |  |  | HVPNL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 11 |  |  | Deepalpur S/S |  |  | HVPNL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 0 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 12 |  |  | Kabulpur S/S |  |  | HVPNL |  |  |  | 220/132 | 200 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 13 |  |  | Deepalpur S/S |  |  | HVPNL |  |  |  | 220/132 | 200 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-12 |  | Commissioned 2/12.
Remark:
Jhajjar TPS (Indira Gandhi ) TPS (3x500 MW),CS,HR,ACPCL,U1- (C),U2-(C),U3-12/12
| 1 |  |  | Jhajjar - Daultabad |  |  | HVPNL | D/C |  |  | 400 | 136 | 175 | 175 |  |  | 175 |  | 136 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 2 |  |  | Jhajjar - Mundka |  |  | APCPL | D/C |  |  | 400 | 132 | 186 | 186 |  |  | 186 |  | 132 | MAR-10 |  |  | NOV-10 |  | 1st cket commissioned 9/10 & 2nd ckt in 11/10.
| 3 |  |  | Mundka (1st ICT) |  |  | DTL |  |  |  | 220/66 | 160 | 100 | 100 |  |  | 100 | [5 empty] | MAR-11 |  | Commissioned 3/11.
| 4 |  |  | Mundka (2x315) S/S |  |  | DTL |  |  |  | 400/220 | 630 | 0 | 0 |  |  | 0 | [5 empty] | MAR-11 |  | 1st Trans. Commissioned 9/10. 2nd trf 3/11.
| 5 |  |  | Daultabad S/S |  |  | HVPNL |  |  |  | 400/220 | 945 | 0 | 0 |  |  | 0 | [5 empty] | DEC-10 |  | Commissioned 12/10
| 6 |  |  | Mundka (2nd ICT) |  |  | DTL |  |  |  | 220/66 | 160 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | SEP-12 |  | Commissioned 9/12.
Remark:
Jharsuguda (Sterlite TPP),PS, Ori,Sterlite, U1-12/10(C), U2-10/10(C),U3-8/11(C),U4-6/12 (c)
| 1 |  |  | LILO of Rourkela - Raigarh at Sterlite TPP (Existing line) |  |  | VEDANTA | D/C |  |  | 400 | 49 | 85 | 85 |  |  | 85 |  | 49 |  |  |  | FEB-10 |  | Commissioned 2/11. (Interim arrangement).
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 15 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Sterlite TPP - Jharsuguda (LILO-II to Jharsuguda) |  |  | VEDANTA | D/C |  |  | 400 | 40 | 0 | 0 |  |  | 0 |  |  | NOV-16 |  |  |  |  | Transmission work not started yet. SEL will approach CEA for approval of continuing the LILO-II.
| 3 |  |  | Sterlite TPP (Vedanta)- Jharsuguda (Sundergarh) (Balance portion from LILO-I point to Jharsuguda) |  |  | VEDANTA | D/C |  |  | 400 | 41 | 64 | 64 |  |  | 64 |  | 47 | NOV-16 |  |  | OCT-17 |  | Commissioned 10/2017
| 4 |  |  | LILO of Rourkela - Raigarh at Sterlite TPP ( 2nd LILO) |  |  | VEDANTA | D/C |  |  | 400 | 60 | 92 | 92 |  |  | 92 |  | 60 |  |  |  | MAR-14 |  | Commissioned 03/14. (Interim arrangement).
| 5 |  |  | Sterlite TPP - Sterlite captive plant D/C |  |  | VEDANTA | 2xD/C |  |  | 220 | 9 | [6 empty] | 9 |  |  |  | AUG-10 |  | Ist ckt commissioned, 2nd ckt commissioned 8/10.
Remark:
Jorethang Loop HEP (2x48MW)PS,Sikkim,DANS,U1-9/15 (C), U2-9/15 (C).
| 1 |  |  | Jorethang HEP - New Melli |  |  | DEPL | D/C |  |  | 220 | 20 | 35 | 35 |  |  | 35 |  | 20 |  |  |  | NOV-16 |  | Commissioned 11/2016.(Interim connection removed- LILO on one ckt of New Melli - Rangpo D/C tr. Line at Jorethang ).
Remark:
JSW Ratnagiri TPP (4x300 MW) ,PS,MAHA,JSW Energy ,U1-8/10(C),U2-12/10(C),U3-5/11(C),U4-10/11(C)
| 1 |  |  | Jaigad - New Koyna |  |  | JSWEL | D/C |  |  | 400 | 110 | 160 | 160 |  |  | 160 |  | 110 | MAY-10 |  |  | AUG-10 |  | Ckt 1 commissioned 7/10 & ckt 2 commissioned 8/10.
| 2 |  |  | Jaigad - karad. |  |  | JSWEL | D/C |  |  | 400 | 219 | 300 | 300 |  |  | 300 |  | 218 |  |  |  | SEP-11 |  | Commissioned 10/11.
Remark:
Kaiga APP (220 MW),CS,KAR,NPCIL,U4-11/10(C)
| 1 |  |  | Mysore - Kozhikode |  |  | PGCIL | D/C |  |  | 400 | 420 | 614 | 614 |  |  | 614 |  | 420 | DEC-07 |  |  | SEP-15 |  | Ready for Commissioning 09/15.
| 2 |  |  | Narendra - Davangere |  |  | PGCIL | D/C |  |  | 400 | 310 | 422 | 422 |  |  | 422 |  | 310 |  |  |  | MAR-08 |  | Commissioned 03/08
| 3 |  |  | Hirriyur (Extn.) S/S |  |  | PGCIL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-08 |  | Commissioned 03/08
| 4 |  |  | Kozhikode S/Stn. (2x315) |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | DEC-07 |  |  | OCT-15 |  | Commissioned 10/15.
Remark:
Kakatiya TPP Extn (2x600 MW) SS,TCTL, APGENCO, U1-5/10 (C),U2-12/15 (C)
| 1 |  |  | Bhoopalapally (Kakatiya) - Gajwel |  |  | APTRANS | D/C |  |  | 400 | 262 | 363 | 363 |  |  | 363 |  | 262 |  |  |  | SEP-13 |  | Commissioned 09/13.
| 2 |  |  | Bhupalapally (KTPP) SS (2x160) |  |  | TSTRANS |  |  |  | 220/132 | 320 | 100 | 85 |  |  | 95 |  | 95 | JUL-23
| 3 |  |  | Bhupalapally (KTPP) SS (2x500 ) |  |  | TSTRANS |  |  |  | 400/220 | 1000 | 100 | 75 |  |  | 80 |  | 80 | JUL-23
Remark:
Kalisindh TPS (2x600 MW), SS,Raj,RRVUNL, U1-5/14 (C),U2-6/15 (C)
| 1 |  |  | Kalisndh TPS - Anta (Baran) Pooling Station (Quad) |  |  | RVPNL | D/C |  |  | 400 | 159 | 220 | 220 |  |  | 220 |  | 159 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 2 |  |  | Anta - Phagi (Jaipur South Ckt-2)(Charged at 400 kV) |  |  | RVPNL | S/C |  |  | 765 | 214 | 570 | 570 |  |  | 570 |  | 214 |  |  |  | JAN-14 |  | Charged at 400 kV 01/14.
| 3 |  |  | Kalisindh-Jhalawar line |  |  | RVPNL | D/C |  |  | 220 | 19 | 35 | 35 |  |  | 35 |  | 19 |  |  |  | APR-12 |  | Commissioned 4/12.
| 4 |  |  | Anta - Phagi (Jaipur South Ckt-1) |  |  | RVPNL | S/C |  |  | 765 | 212 | 586 | 586 |  |  | 586 |  | 212 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 5 |  |  | Phagi GSS (Jaipur) - Heerpura line |  |  | RVPNL | D/C |  |  | 400 | 104 | 126 | 126 |  |  | 126 |  | 104 | SEP-12 |  |  | DEC-16 |  | Commissioned 11/2016 (Reported Late)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 16 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 6 |  |  | Phagi (Jaipur south-765 kV)-Ajmer (Ckt. - I) |  |  | RVPNL | D/C |  |  | 400 | 106 | 284 | 284 |  |  | 284 |  | 106 | SEP-12 |  |  | MAR-18 |  | Commissioned 03/18.
| 7 |  |  | Ajmer S/S |  |  | RVPNL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JAN-16 |  | Commissioned 01/16.
| 8 |  |  | Phagi (jaipur South ) (2x1500 ) S/S |  |  | RVPNL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-15 |  | Commissioned 02/15.
| 9 |  |  | Anta (Distt. Banra) Pooling Station |  |  | RVPNL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-15 |  | Commissioned 02/15.
Remark:
Kalpakkam PFBR (Bhavini) (500 MW)
| 1 |  |  | Kalpakkam - Arni |  |  | PGCIL | D/C |  |  | 230 | 213 | [6 empty] | 213 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 2 |  |  | Kalpakkam PFBR-Kanchepurram |  |  | PGCIL | D/C |  |  | 230 | 160 | 306 | 306 |  |  | 306 |  | 160 |  |  |  | AUG-12 |  | Commissioned 8/12.
| 3 |  |  | Kalpakkam PFBR-Sirucheri |  |  | PGCIL | D/C |  |  | 230 | 72 | 140 | 140 |  |  | 140 |  | 72 |  |  |  | NOV-11 |  | Line commissioned in Nov'11
Remark:
Kamalanga TPP (3x350MW),PS,GMR, Orissa, U1-3/13(C),U2-9/13(C),U3-9/13
| 1 |  |  | Kamalanga (GMR) - Angul pooling station |  |  | GMR | D/C |  |  | 400 | 60 | 103 | 103 |  |  | 103 |  | 60 |  |  |  | DEC-14 |  | Commissioned 12/14.
| 2 |  |  | LILO of Talchar -Meramundli at Kamalanga TPP |  |  | GMR | D/C |  |  | 400 | 1 | 3 | 3 |  |  | 3 |  | 1 | [5 empty] | For start up power,work completed 5/12.
Remark:
Kameng HEP,(4x150 MW) SS,ArP, NEEPCO,U1-4 (02/22)
| 1 |  |  | Kameng - Balipara line |  |  | PGCIL | D/C |  |  | 400 | 114 | 151 | 151 |  |  | 151 |  | 114 | AUG-13 |  |  | MAR-18 |  | Commissioned 03/18.
Remark:
Karcham Wangtoo HEP ( 4x250 MW)PS, HP, JKHCL, U1-5/11(C), U2-6/11( C), U3-9/11 (C), U4,9/11 (C).
| 1 |  |  | Abdullapur - Sonepat |  |  | PGCIL | D/C |  |  | 400 | 291 | 403 | 395 |  |  | 385 |  | 230 | SEP-11 |  |  | MAR-11 |  | Commissioned 3/11.
| 2 |  |  | Karcham Wangtoo-Abdullapur |  |  | JV(PG&JP) | D/C |  |  | 400 | 432 | 518 | 518 |  |  | 518 |  | 432 |  |  |  | JUL-12 |  | Commissioned. 7/12
Remark:
Kasaipalli TPP (2x135 MW),PS,Cha,ACB,U1- 12/11(C),U2-6/12(C)
| 1 |  |  | LILO of Korba - Bhatapara at Kasaipalli |  |  | ACB | D/C |  |  | 400 | 6 | [6 empty] | 6 |  |  |  | NOV-11 |  | Commissioned 11/11.
| 2 |  |  | Kasaipalli TPP -Bharai (Sipat) Pooling station |  |  | ACB | D/C |  |  | 400 | 112 | 181 | 181 |  |  | 181 |  | 112 |  |  |  | JUL-12 |  | Commissioned. 7/12
Remark:
Kashang-I,II & III HEP (1x65+2x65MW) on Satluj river,SS,HP,U1 -10/16 (C),U2-8/16 (C),U1-01/17 (C)
| 1 |  |  | Kashang - Bhaba (2nd Ckt) |  |  | HPPTCL | D/C |  |  | 220 | 39 | 100 | 100 |  |  | 100 |  | 39 | OCT-15 |  |  | APR-16 |  | Commissioned 04/16.
| 2 |  |  | Kashang - Jangi Pooling Station |  |  | HPPTCL | D/C |  |  | 220 |  | 0 | 0 |  |  | 0 | [7 empty] | power of kashang and other generating projects in vicinity was planned to be pooled at Jangi pooling station, since other generating projects have withdrawn LTA therefore the construction of Jangi pooling station has been dropped for the time being.
Remark:
Kashipur CCPP (225+225 MW) (Gas),SEPL, UK, Mod-1:11/16(C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 17 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Kashipur - Mahuakheraganj |  |  | PTCUL | D/C |  |  | 220 | 34 | [10 empty] | JUL-14
Remark:
Kawai Super Critical TPS (2x660 MW),Raj, PS,Adani , Unit 1-5/13 (C),U2-12/13 (C)
| 1 |  |  | Kawai - Anta (Baran) |  |  | RVPNL | D/C |  |  | 400 | 101 | 136 | 136 |  |  | 136 |  | 101 |  |  |  | JAN-14 |  | Commissioned 01/14.
| 2 |  |  | Chhabra TPS-Kawai SCTPS |  |  | RVPNL | S/C |  |  | 400 | 16 | 46 | 46 |  |  | 46 |  | 16 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 3 |  |  | Anta GSS (ICT-3) |  |  | RVPNL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | APR-17 |  | Commissioned 09/2016 (Late Reported)
Remark:
Khaperkheda (500 MW),SS,MAHA,MSPGCL,U1-8/11(C)
| 1 |  |  | LILO of Koradi - Chandrapur at Khaperkheda TPS. |  |  | MSETCL | D/C |  |  | 400 | 3 | 8 | 8 |  |  | 8 |  | 3 |  |  |  | NOV-09 |  | Commissioned 11/9
| 2 |  |  | Khaperkheda TPS - Khaperkheda (Existing) |  |  | MSETCL | 2xD/C |  |  | 220 | 12 | 19 | 19 |  |  | 19 |  | 12 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 3 |  |  | Khaperkheda S/S (2x500) |  |  | MSETCL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | DEC-11 |  | Commissioned 12/11.
Remark:
Khargone Super Critical TPP(2x660 MW),CS,MP,NTPC,U1-3/19,U2-9/19 (TBCB)
| 1 |  |  | LILO of one ckt. of Khandwa - Rajgarh at Khargone TPP (KTL - TBCB) |  |  | SGL | D/C |  |  | 400 | 14 | 21 | 21 |  |  | 21 |  | 14 | FEB-18 |  |  | FEB-18 |  | Commissioned 02/2018.
| 2 |  |  | Khandwa Pool - Dhule Line (KTL - TBCB) |  |  | SGL | D/C |  |  | 765 | 383 | 492 | 492 |  |  | 492 |  | 383 | JUN-21 |  |  | DEC-21 |  | Commissioned 12/21.
| 3 |  |  | Khandwa Pool - Indore (KTL - TBCB) |  |  | SGL | D/C |  |  | 765 | 180 | 243 | 243 |  |  | 243 |  | 180 | JUL-19 |  |  | MAR-20 |  | Commissioned 03/20
| 4 |  |  | Khargone TPP - Khandwa Pool (Q) (KTL - TBCB) |  |  | SGL | D/C |  |  | 400 | 50 | 66 | 66 |  |  | 66 |  | 50 | JUL-19 |  |  | MAR-20 |  | Commissioned 03/20
| 5 |  |  | Khandwa PS (KTL - TBCB) |  |  | SGL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 | JUL-19 |  |  | MAR-20 |  | Commissioned 03/20
|  | Remark: |  |  | Khargone Transmission Limited (SGL)
Khurja STPP (2x660MW), THDC, UP, U1-02/24, U-08/24
| 1 |  |  | LILO of one Ckt. 400kV (Twin Moose) Shamli -Aligarh line at THDC Khujra Power Plant |  |  | UPPTCL | D/C |  |  | 400 | 26 | 0 | 0 |  |  | 0 | [7 empty] | To be constructed in TBCB mode.
Remark:
Kishanganga HEP (3x110MW) CS, J&K, NHPC, U1-3/18(C),2 & 3-03/18(C)
| 1 |  |  | Kishanganga - Amargarh line |  |  | PGCIL | D/C |  |  | 220 | 85 | 150 | 150 |  |  | 150 |  | 85 | JUL-17 |  |  | FEB-18 |  | Commissioned 02/2018.
| 2 |  |  | Kishanganga - Wagoora line |  |  | PGCIL | D/C |  |  | 220 | 232 | 252 | 252 |  |  | 252 |  | 232 | MAR-18 |  |  | JUL-19 |  | Commissioned 07/19.
Remark:
Koderma TPS 2x500 MW,CS,JHA,DVC,U1-7/11 (C),U2-2/13 (C)
| 1 |  |  | LILO of Barhi-Koderma at Koderma S/S |  |  | DVC | D/C |  |  | 132 | 32 | 66 | 66 |  |  | 66 |  | 32 |  |  |  | AUG-10 |  | Commissioned 8/10
| 2 |  |  | Koderma-Biharshariff (Quad) |  |  | PGCIL | D/C |  |  | 400 | 222 | 294 | 294 |  |  | 294 |  | 222 | APR-10 |  |  | MAY-11 |  | Commissioned 5/11.
Remark:
Koldam HEP (4x200 MW),CS,HP,NTPC, U3-4/15 (C), U4-6/15 (C)
| 1 |  |  | Koldam - Ludhinana (JV Portion) |  |  | PKTCL | D/C |  |  | 400 | 301 | 423 | 423 |  |  | 423 |  | 301 | SEP-08 |  |  | SEP-14 |  | Commissioned 09/14.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 18 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Koldam - Nalagarh |  |  | PGCIL | D/C |  |  | 400 | 93 | 127 | 127 |  |  | 127 |  | 93 |  |  |  | MAR-10 |  | Commissioned 03/10.
Remark:
Koradi TPP Expn. (3x660 MW), SS,Maha, MSPGCL, U8-3/15 (C) ,U9-3/16 (C),U10-6/16
| 1 |  |  | Koradi TPS-New Khaparhkeda |  |  | MSETCL | D/C |  |  | 220 | 28 | 72 | 72 |  |  | 72 |  | 28 | DEC-13 |  |  | MAR-16 |  | Commissioned 03/16.
| 2 |  |  | Koradi TPS - Wardha |  |  | MSETCL | D/C |  |  | 400 | 144 | 336 | 336 |  |  | 336 |  | 144 | APR-11 |  |  | JAN-16 |  | Commissioned 01/16.. (97 Ckm had already been taken as commissioned in May 2015.)
| 3 |  |  | Koradi-II - Koradi-III (Ckt-I) |  |  | MSETCL | D/C |  |  | 400 | 38 | 111 | 111 |  |  | 111 |  | 38 |  |  |  | DEC-16 |  | Commissioned 12/2016
Remark:
Korba (E) (2x250 MW), SS, Chg, U2-7/12 (C)
| 1 |  |  | Korba -Vishrampur |  |  | CSPTCL | S/C |  |  | 220 | 153 | 505 | 505 |  |  | 505 |  | 153 | MAR-12 |  |  | AUG-14 |  | Commissioned 08/14.
Remark:
Korba (W) (1x500 MW),SS,Cha,CSEB,U5-3/13(C)
| 1 |  |  | Korba (W)-Bhilai (khedamara) |  |  | CSPTCL | D/C |  |  | 400 | 447 | 640 | 640 |  |  | 640 |  | 447 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 2 |  |  | LILO Korba (West)-Bhilai at Raipur (CSPTCL) |  |  | CSPTCL | D/C |  |  | 400 | 47 | 70 | 70 |  |  | 70 |  | 47 | MAR-10 |  |  | SEP-12 |  | Commissioned 9/12.
| 3 |  |  | Raipur S/S (ICT I & II.) |  |  | CSPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-16 |  | Commissioned 03/13 & 03/14. (Reported Late)
Remark:
Koteshwar HEP (4x100 MW),CS,UK, THDC,U3-1/12,U4-3/12.
| 1 |  |  | Koteshwar -Tehri Pooling Point |  |  | PGCIL | D/C |  |  | 400 | 5 | 9 | 9 |  |  | 9 |  | 5 | JUN-08 |  |  | APR-11 |  | Commissioned 3/11.
| 2 |  |  | LILO of Tehri - Meerut at Tehri Pooling Point (to be charged at 400 KV) |  |  | PGCIL | 2xD/C |  |  | 765 | 13 | 59 | 59 |  |  | 59 |  | 13 | JUN-08 |  |  | JUN-11 |  | Commissioned 6/11.
Remark:
Kothagudem TPS St-VII (1x800), TPGenco, U12-07/18
| 1 |  |  | Julurupadu - Jangaon |  |  | TSTRANS | D/C |  |  | 400 | 349 | 489 | 489 |  |  | 489 |  | 349 | SEP-18 |  |  | JUN-19 |  | Commissioned 06/19.
| 2 |  |  | Julurupadu - KTPS (Stage-VII) |  |  | TSTRANS | D/C |  |  | 400 | 78 | 119 | 119 |  |  | 119 |  | 78 | MAR-17 |  |  | FEB-18 |  | Ready for Commissioning 02/18.
| 3 |  |  | Julurupadu 2nos 400kV bay |  |  | TSTRANS |  |  |  | 400 | 50 | [7 empty] | SEP-17
| 4 |  |  | Jangaon s/s (3x500) (ICT-I) |  |  | TSTRANS |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | AUG-18 |  |  | MAY-19 |  | Commissioned 05/19.
Remark:
Koyna Left Bank PSS (2x40MW), Maharashtra, WRD Maharashtra
| 1 |  |  | Koyna PSS - Karad(Loc. 8 - 144) line |  |  | MSETCL | S/C on D/C |  |  | 220 | 44 | 170 | 170 |  |  | 170 |  | 44 |  |  |  | FEB-17 |  | Commissioned 02/2017
|  | Remark: |  |  | Current expenditure on the project has already reached to original administrative approved cost level hence expenditure on the project is stopped and is presently stalled since year 2015.
KTPP Power Evacuation Scheme
| 1 |  |  | LILO of Salivagu- Bheemghanpur line to KTPP SS |  |  | TSTRANS | D/C |  |  | 220 | 42 | 83 | 83 |  |  | 83 |  | 42 | JUN-23 |  |  | SEP-23 |  | Commissioned 09/23.
| 2 |  |  | LILO of Pulukurthy- Bheemghanpur line to KTPP SS |  |  | TSTRANS | D/C |  |  | 220 | 46 | 88 | 88 |  |  | 88 |  | 46 | SEP-23 |  |  | JUN-23 |  | Commissioned 06/23.
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 19 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Kudgi TPS-I (3x800), NTPC Ltd., U1-12/16(C),U2-3/17(C),U3-11/17
| 1 |  |  | Madhugiri - Bidadi (KTL - TBCB) |  |  | KTCL | D/C |  |  | 400 | 185 | 256 | 256 |  |  | 256 |  | 185 | DEC-15 |  |  | AUG-16 |  | Commissioned 08/16.
| 2 |  |  | LILO of B.Bagewadi - Bijapur line at Kudgi 400kV STPP |  |  | KPTCL | M/C |  |  | 220 | 80 | 99 | 99 |  |  | 99 |  | 80 | JUN-17 |  |  | DEC-17 |  | Commissioned 12/2017.
| 3 |  |  | Kudgi STPS - Narendra (KTL - TBCB) |  |  | KTCL | 2xD/C |  |  | 400 | 36 | 46 | 46 |  |  | 46 |  | 36 | FEB-15 |  |  | AUG-15 |  | Ready for Commissioning 08/15.
| 4 |  |  | Narendra (New) - Madhugiri (KTL - TBCB) |  |  | KTCL | D/C |  |  | 765 | 758 | 867 | 867 |  |  | 867 |  | 758 | DEC-15 |  |  | SEP-16 |  | Ready for Commissioning 09/16.
| 5 |  |  | Kudagi - Tapping point of NTPC (part of Kudagi-Vajramatti line) |  |  | KPTCL | D/C |  |  | 220 | 153 | 267 | 267 |  |  | 267 |  | 153 | OCT-19 |  |  | MAR-21 |  | Commissioned 03/21.
|  | Remark: |  |  | Transmission System required for evacuation of power from Kudgi TPS (3x800 MW in Phase-I) of NTPC Ltd. (TBCB) SPV/BPC - Kudgi Transmission Company Ltd. / REC
Kundah Pumped storage HEP (4x125MW), TN, TANTRANSCO, U1,U2,U3 & U4 (03/23)
| 1 |  |  | LILO of KPSHEP - Kundah PH-III at Parali (400/230 kV S/S) |  |  | TANTRAN | D/C |  |  | 230 | 0 | 0 | 0 |  |  | 0 | [7 empty] | The existing LILO of KPSHEP - Kundah PH-III, 230 kv D/C line to Parali 400/230 kV S/S . And utilizing the existing 230kV corridor upto Parli.
| 2 |  |  | Parali - Karamadai line |  |  | TANTRAN | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Parali - Karamadai 400 kV D/C line is to run on D/C tower up to location no. 57 (Hilly terrain area) and subsequently on 400 kV M/C tower (with four circuits) upto Karamadai 400/230 kV S/S (S/S (in Plains area ), which will also accommodate existing Parali-Karamadai 400 kV D/C line utilizing the corridor of existing Kundah PH-II-ARasur 230 kV S/C line. the lines will have HTLS conductor.
| 3 |  |  | KPSHEP - Parali lines on M/C towers |  |  | TANTRAN | S/C |  |  | 230 | 0 | 114 | 40 |  |  | 22 |  | 0 | [5 empty] | Work under progress
| 4 |  |  | Establishment of 400/230 kV S/S ICTs at Parali (near existing Kundah PH-III |  |  | TANTRAN |  |  |  | 400/230 | 1000 | 100 | 5 |  |  | 0 |  | 0 | [5 empty] | Work to resume after finalization of compensatory afforestation proposal as ordered by supreme court.
Remark:
Kundankulam - APP Transmission System - PGCIL
| 1 |  |  | LILO of Madurai - Trivandrum at Tirunelveli 2 X D/C |  |  | PGCIL | D/C |  |  | 400 | 213 | 300 | 300 |  |  | 300 |  | 213 |  |  |  | APR-08 |  | Commissioned 4/08.
| 2 |  |  | Tirunelveli - Udumaplet |  |  | PGCIL | D/C |  |  | 400 | 533 | 730 | 730 |  |  | 730 |  | 533 |  |  |  | MAR-09 |  | Commissioned 03/09.
| 3 |  |  | Kudankulam-Tirunelveli (Quad) 2nd. |  |  | PGCIL | D/C |  |  | 400 | 160 | 213 | 213 |  |  | 213 |  | 160 |  |  |  | MAR-09 |  | Commissioned 03/09.
| 4 |  |  | Tirunelveli - Edamon |  |  | PGCIL | M/C |  |  | 400 | 327 | 235 | 235 |  |  | 235 |  | 327 |  |  |  | MAR-10 |  | Commissioned 03/10.
| 5 |  |  | Edamon (KSEB) - Muvattupuzha (PG) Quad) line (1st Ckt.) |  |  | PGCIL | D/C |  |  | 400 | 149 | 447 | 447 |  |  | 447 |  | 149 | SEP-19 |  |  | SEP-19 |  | Commissioned 09/19.
| 6 |  |  | Muvattupuzha (PG) - North Trichur (PG) |  |  | PGCIL | D/C |  |  | 400 | 157 | 224 | 224 |  |  | 224 |  | 157 |  |  |  | NOV-11 |  | Line commissioned in Nov'11.
| 7 |  |  | Kudankulam-Tirunelveli (Quad) 1st. |  |  | PGCIL | D/C |  |  | 400 | 145 | 199 | 199 |  |  | 199 |  | 145 |  |  |  | MAR-09 |  | Commissioned 03/09.
| 8 |  |  | Muvattapuzha s/s (2 nd ICT) |  |  | PGCIL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-11 |  | ICT-II commissioned in Nov'11.
| 9 |  |  | Tirunelveli S/S |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-08 |  | ICT-I Commissioned 4/08, ICT-II Commissioned 11/08.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 20 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 10 |  |  | Trivandrum |  |  | PGCIL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-09 |  | Commissioned 6/09.
| 11 |  |  | Udumalpet (PG) Ext. |  |  | PGCIL |  |  |  | 400/200 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-09 |  | Commissioned 3/09
Remark:
Lakhwar (300 MW) Yamuna river,UK,UJVNL - 2018-19
| 1 |  |  | Lakhwar- Dehradun |  |  | PTCUL | D/C |  |  | 220 | 60 | 110 | 57 |  |  | 52 |  | 0 | [5 empty] | Foundation Completed : 57Nos. Tower erection : 52 Nos. Stringing :0.000 Kms
| 2 |  |  | LILO of Lakhwar HEP- Muzaffarnagar at Vyasi HEP |  |  | NHPC | D/C |  |  | 220 | [8 empty] | JAN-17
Remark:
Lalitpur Ph-I (3x660MW), Ph-II (3x660 MW )PS,UP,BHL, U1-03/16 (C),U2-1/16(C),U3-04/16(C)
| 1 |  |  | LILO of one ckt of 400 kV Agra (UP) - Agra (PG) 400 kV D/C line at Agra (UP) 765/400 kV S/S |  |  | UPPTCL | D/C |  |  | 400 | 73 | 100 | 100 |  |  | 100 |  | 73 | AUG-16 |  |  | SEP-16 |  | Ready for Commissioning 09/16.
| 2 |  |  | Lalitpur TPS - Fatehabad (Agra (UP)) Ckt-II |  |  | UPPTCL | S/C |  |  | 765 | 335 | 902 | 902 |  |  | 902 |  | 335 | AUG-16 |  |  | APR-17 |  | Commissioned 04/2017
| 3 |  |  | Maath (Mathura) -Chhata line |  |  | UPPTCL | D/C |  |  | 220 | 68 | 119 | 119 |  |  | 119 |  | 68 |  |  |  | APR-17 |  | Commissioned 04/2017
| 4 |  |  | LILO of Agra - Muradnagar at Mathura |  |  | UPPTCL | D/C |  |  | 400 | 64 | 88 | 88 |  |  | 88 |  | 64 | AUG-16 |  |  | JUN-17 |  | Commissioned 06/2017.
| 5 |  |  | LILO of 400 kV Agra (UP) - Muradnagar 400 kV S/C line at Agra (UP) 765/400 kV S/S |  |  | UPPTCL | D/C |  |  | 400 | 156 | 219 | 219 |  |  | 219 |  | 156 | AUG-16 |  |  | SEP-16 |  | Commissioned 09/16.
| 6 |  |  | Fatehabad (Agra (UP)) - Maath ( Mathura) line |  |  | UPPTCL | S/C |  |  | 400 | 142 | 382 | 382 |  |  | 382 |  | 142 | AUG-16 |  |  | APR-17 |  | Commissioned 04/2017
| 7 |  |  | Lalitpur TPS - Agra (UP) Ckt-I |  |  | UPPTCL | S/C |  |  | 765 | 337 | 955 | 955 |  |  | 955 |  | 336.81 | AUG-16 |  |  | SEP-16 |  | Ready for commissioning 09/16.
| 8 |  |  | Agra(UP) - Agra (South) |  |  | UPPTCL | D/C |  |  | 400 | 139 | 203 | 203 |  |  | 203 |  | 139 | AUG-16 |  |  | JUN-17 |  | Ready for commissioning 06/2017.
| 9 |  |  | Agra (UP) S/S (ICT-I) (Fatehabad) |  |  | UPPTCL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 | AUG-16 |  |  | SEP-16 |  | Commissioned 09/16.
| 10 |  |  | Maath Mathura (New) (ICT-II) |  |  | UPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAY-17 |  | Commissioned 05/2017.
| 11 |  |  | Agra (South) S/S |  |  | UPPTCL |  |  |  | 400/132 | 600 | 100 | 100 |  |  | 100 |  | 100 | AUG-16 |  |  | JUN-17 |  | 3x200 MVA, 400/132 KV ICTs energised on 10/07/2017
| 12 |  |  | Agra (UP) S/S (ICT-II) (Fatehabad) |  |  | UPPTCL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-17 |  | Commissioned 02/2017
| 13 |  |  | Maath (Mathura) s/s (ICT-1) |  |  | UPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | AUG-16 |  |  | APR-17 |  | Commissioned 04/2017
Remark:
Lanco Amarkantak TPS -II, (2x660 MW), PS,Chg,LPT, U3 -11/18,U4-2/18
| 1 |  |  | Lanco Amarkantak - Champa Pooling Station |  |  | LEPP | D/C |  |  | 400 | 95 | 158 | 96 |  |  | 12 |  | 0
Remark:
Lanco Vidarbha (Dhenkanal )TPS (2x660 MW), PS,LIL, U1-12/18,U2-3/19
| 1 |  |  | LILO of Seoni - Wardha at Lanco Vidarbha TPS |  |  | LEPP | D/C |  |  | 765 | 15 | 16
Remark:
Lara STPP-I (2x800 MW), CS, Chh, NTPC, U1-3/18(c), U2-6/18
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 21 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Lara STPS - Champa Pooling Station line (Q) |  |  | PGCIL | D/C |  |  | 400 | 224 | 306 | 306 |  |  | 306 |  | 224 | APR-17 |  |  | JUN-17 |  | Ready for commissioning 06/17
| 2 |  |  | Lara STPS - Raigarh (Kotra) line |  |  | PGCIL | D/C |  |  | 400 | 36 | 50 | 50 |  |  | 50 |  | 36 | APR-17 |  |  | APR-16 |  | Commissioned 04/16.
Remark:
Lata Tapovan (3x57 MW),CS,UK,NTPC- 2021-22
| 1 |  |  | Lata Tapovan- Joshimath |  |  | PTCUL | D/C |  |  | 220 | 24 | 36 | 0 |  |  | 0 |  | 0 | [5 empty] | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
| 2 |  |  | Joshimath - Kunwari Pass (Pipalkoti) |  |  | PTCUL | D/C |  |  | 220 | 40 | 0 | 0 |  |  | 0 | [7 empty] | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
|  | Remark: |  |  | Contract has been terminated on 23.01.2017 as per the stay order of hon'ble Supreme Court for construction of HEP of Lata Tapovan after June 2013 natural disaster in Uttarakhand. Currently work is stalled
Loharinagpala (NTPC),CS,UK,NTPC,Unit-14/15.
| 1 |  |  | LILO of Loharinagpala - Koteshwar at Pala - Maneri |  |  | PTCUL | D/C |  |  | 400 | 10 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | The work at Pala Maneri HEP stopped as per GOI order.
| 2 |  |  | Loharinagpala-Koteshwar line |  |  | PTCUL | D/C |  |  | 400 | 180 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | The work at Loharinagpala HEP stopped as per GOI order.
Remark:
Lower Jurala HEP (6x40MW) SS,TCTL,TSGENCO,U1-10/15(C),U2-9/15(C),U3-1/16 (C),U4-11/15,U5-8/16 (C),U6-9/16(C).
| 1 |  |  | LILO of Veltoor -Jurala at Lower Jurala HEP |  |  | APTRANS | D/C |  |  | 220 | 9 | 17 | 17 |  |  | 17 |  | 9 |  |  |  | DEC-13 |  | Commissioned 12/13.
| 2 |  |  | Lower Jurala HEP - Upper Jurala |  |  | TSTRANS | D/C |  |  | 220 | 21 | 36 | 36 |  |  | 36 |  | 21 |  |  |  | AUG-16 |  | Commissioned 05/16. (Late Reported).
Remark:
Lower Kalnai (2x24MW),J&K, JKSPDC
| 1 |  |  | Lower Kalnai - Thathri S/s (existing) line |  |  | JKPDD | D/C |  |  | 132 | 6
|  | Remark: |  |  | Project is in initial stage of construction and recently works are stalled. Its commissioning can be assessed after restart of works.
Mahan TPP Ph-1(2x600 MW),PS, MP,ESSAR Power TCL, U1-2/13 (C), U2-9/17
| 1 |  |  | Mahan -Sipat |  |  | EPTCL | D/C |  |  | 400 | 673 | 942 | 942 |  |  | 942 |  | 673 |  |  |  | SEP-18 |  | Commissioned 09/18.
| 2 |  |  | Gandhar-Hazira |  |  | EPTCL | D/C |  |  | 400 | 208 | 287 | 287 |  |  | 287 |  | 208 |  |  |  | MAR-13 |  | Commissioned 3/13.
| 3 |  |  | LILO of Viindhyachal -Korba line at Mahan S/S |  |  | EPTCL | D/C |  |  | 400 | 44 | 67 | 67 |  |  | 67 |  | 44 |  |  |  | MAR-13 |  | Commissioned 3/12. (Interim)
| 4 |  |  | Hazira S/S |  |  | EPTCL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUL-15 |  | commissioned in March 2013. Reported in July 2015.
Remark:
Maheshwar HEP (10x40 MW),PS,MP,SMHPCL,U1 to U10 (2020-21)
| 1 |  |  | Maheshwar - Pithampur |  |  | MPPTCL | D/C |  |  | 220 | 115 | 195 | 195 |  |  | 195 |  | 115 |  |  |  | FEB-12 |  | Commissioned 2/12.
| 2 |  |  | Maheshwar - Nimrani |  |  | MPPTCL | D/C |  |  | 220 | 54 | 90 | 90 |  |  | 90 |  | 54 | APR-09 |  |  | MAY-10 |  | Commissioned 5/10.
Remark:
Maithon RBTPP (2x525 MW),PS,JHA,DVC-JV TATA ,U1-6/11(C),U2-3/12 (C)
| 1 |  |  | Maithon RB - Maithon (PG) |  |  | PGCIL | D/C |  |  | 400 | 62 | 94 | 94 |  |  | 94 |  | 62 | APR-10 |  |  | SEP-10 |  | Commissioned 09/10
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 22 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Maithon (RB) - Ranchi |  |  | PGCIL | D/C |  |  | 400 | 376 | 534 | 534 |  |  | 534 |  | 376 |  |  |  | DEC-11 |  | Commissioned 12/11.
Remark:
Malana - II HEP (2x50 MW)PS,HP,EPPL,U1-8/11(C),U2-8/11(C),
| 1 |  |  | LILO of Allain Duhangan- Nalagarh at Chhaur |  |  | EPCL | D/C |  |  | 220 | 2 | 4 | 4 |  |  | 4 |  | 2 | SEP-09 |  |  | SEP-11 |  | Commissioned 9/11.
| 2 |  |  | Malana - II HEP - Chhaur. |  |  | EPCL | D/C |  |  | 132 | 36 | 51 | 51 |  |  | 51 |  | 36 |  |  |  | SEP-11 |  | Commissioned 9/11.
| 3 |  |  | Chhaur |  |  | EPCL |  |  |  | 230/132 | 170 |  | 0 |  |  | 0 |  | 0 |  |  |  | SEP-11 |  | Commissioned 9/11
Remark:
Malibrahmini (2x525MW),PS,Orissa, MPL,U1-3/18,U2-3/18
| 1 |  |  | Malibrahmani - Angul |  |  | MPCL | D/C |  |  | 400 | 62 | 108 | 100 |  |  | 80 |  | 20
Remark:
Malwa TPP(Shree Singaji), (2x600+2x660), SS,MP,MPPGCL, U1-11/13,U2-10/14,U3-07/18,U411/18
| 1 |  |  | Malwa TPP - Pithampur |  |  | MPPTCL | D/C |  |  | 400 | 272 | 397 | 397 |  |  | 397 |  | 267.58 |  |  |  | NOV-13 |  | Commissioned 11/13.
| 2 |  |  | Shri Singaji TPS - Pithampur DCDS (QM) line |  |  | MPPTCL | D/C |  |  | 400 | 281 | 0 | 0 |  |  | 0 |  | 281 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 3 |  |  | Pithampur - Badnawar DCDS (Quad Moose ) line |  |  | MPPTCL | D/C |  |  | 400 | 71 | 203 | 203 |  |  | 203 |  | 71 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 4 |  |  | Malwa TPP - Chhegaon |  |  | MPPTCL | D/C |  |  | 400 | 105 | 158 | 158 |  |  | 158 |  | 105.2 |  |  |  | FEB-13 |  | Commissioned 02/13
| 5 |  |  | Malwa TPP - Chhegaon |  |  | MPPTCL | D/C |  |  | 220 | 95 | 160 | 160 |  |  | 160 |  | 95 |  |  |  | MAR-12 |  | Commisioned 3/12
| 6 |  |  | Chhegaon - Julwania |  |  | MPPTCL | D/C |  |  | 400 | 225 | 340 | 340 |  |  | 340 |  | 225 |  |  |  | NOV-14 |  | Commissioned 11/14.
| 7 |  |  | Pithampur-Indore |  |  | MPPTCL | D/C |  |  | 400 | 128 | 193 | 193 |  |  | 193 |  | 128 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 8 |  |  | LILO of both ckts of Nimrani-Julwania at Julwania |  |  | MPPTCL | D/C |  |  | 220 | 6 | 9 | 9 |  |  | 9 |  | 5.06 |  |  |  | SEP-13 |  | Commissioned 09/13.
| 9 |  |  | Chhegaon S/S |  |  | MPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 10 |  |  | Pithampur S/S |  |  | MPPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | APR-13 |  | Commissioned 4/13.
| 11 |  |  | Julwania S/S |  |  | MPPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-14 |  | Commissioned 11/14.
Remark:
Mangaon CCPP(338 MW), PS, MH, PGPL, U1-2/13(C)
| 1 |  |  | Mangaon CCPP(Vile)- Bhagad |  |  | MSETCL | D/C |  |  | 220 | 4 | 0 | 0 |  |  | 0 | [7 empty] | commissioned 03/16
Remark:
Marwa TPP (2x500 MW) SS,Chg,CSPGCL U1-3/14 (C), U2 -6/16
| 1 |  |  | Marwa - Raipur (Raitha) |  |  | CSPTCL | D/C |  |  | 400 | 281 | 379 | 379 |  |  | 379 |  | 281 |  |  |  | JUN-13 |  | Commissioned 06/13.
| 2 |  |  | LILO of One ckt of Korba (W) - Khedamara at Marwa |  |  | CSPTCL | D/C |  |  | 400 | 116 | 161 | 161 |  |  | 161 |  | 116 | MAR-13 |  |  | MAY-15 |  | Commissioned 05/15.
| 3 |  |  | Marwa - Banari (Start up power) |  |  | CSPTCL | D/C |  |  | 220 | 28 | 55 | 55 |  |  | 55 |  | 28 |  |  |  | JAN-13 |  | Commissioned 1/13. (Loc 39 to 51 charged on 7.11.12)
Remark:
Matrishri Usha TPP (Corporate Power) (4x270MW), U1-3/18,U2-3/19,U3,4-uncertain
| 1 |  |  | Corporate TPP - Jharkhand Pooling Station |  |  | CPL | D/C |  |  | 400 | 6 | 11
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 23 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Latehar - Namkum |  |  | CPL | D/C |  |  | 400 | 216 | 320 | 293 |  |  | 274 |  | 132
Remark:
Mauda TPS (500 MW),Phase-II (2x660 MW) CS, Maha, NTPC, U1-4/12 (C), U2-3/13(C),U3-7/16,U4-03/17 (C)
| 1 |  |  | Mauda - Wardha line (Quad)(Ckt-1) |  |  | PGCIL | S/C |  |  | 400 | 124 | 345 | 345 |  |  | 345 |  | 124 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 2 |  |  | Mauda - Wardha (2nd Ckt) |  |  | PGCIL | S/C |  |  | 400 | 124 | [10 empty] | MAY-12 |  | Commisisoned 05/12
Remark:
Meja TPP Ph-I (2x660 MW)(UPPCL & NTPC), U1-3/18(C),U2-1/19
| 1 |  |  | Rewa Road - Meza line |  |  | UPPTCL | D/C |  |  | 400 | 68 | 91 | 91 |  |  | 91 |  | 68 |  |  |  | MAR-15 |  | Commissioned 03/15.
| 2 |  |  | Meja - Allahabad line |  |  | PGCIL | D/C |  |  | 400 | 56 | 81 | 81 |  |  | 81 |  | 56 | JUL-15 |  |  | AUG-16 |  | Ready for Commissioning 08/16.
| 3 |  |  | Bara - Meza line |  |  | UPPTCL | D/C |  |  | 400 | 65 | 83 | 83 |  |  | 83 |  | 65 |  |  |  | MAR-15 |  | Commissioned 03/15.
Remark:
Mettur TPS Stage III (600 MW), SS,TN,U1-10/12(C)
| 1 |  |  | LILO of MTPS -Malco at MTPS Stage III |  |  | TANTRAN | D/C |  |  | 230 | 3 | 9 | 9 |  |  | 9 |  | 3 |  |  |  | FEB-11 |  | MTPS III- Malco energised 2/11 for start up power.
| 2 |  |  | MTPS Stage-III - Gobi |  |  | TANTRAN | S/C |  |  | 230 | 3 | 8 | 8 |  |  | 8 |  | 3 |  |  |  | MAR-12 |  | Commissioned 3/12
| 3 |  |  | MTPS St.III - Arasur |  |  | TANTRAN | D/C |  |  | 400 | 220 | 325 | 325 |  |  | 325 |  | 220 |  |  |  | JAN-13 |  | Commissioned 01/13.
Remark:
Monarchak CCPP (101 MW), CS,Tripura, NEEPCO, GT - 3/15 (C), ST - 1/16(C).
| 1 |  |  | Surajmani Nagar - Rabindra nagar |  |  | TSECL | D/C |  |  | 132 | 3 | 13 | 13 |  |  | 13 |  | 3 |  |  |  | MAR-17 |  | Completed 9/13
| 2 |  |  | Monarchak - Surajmani Nagar |  |  | TSECL | D/C |  |  | 132 | 43 | 154 | 145 |  |  | 128 |  | 15 | [5 empty] | RoW issues. TSECL has connected a portion of the said D/C line splitting the existing Rokhia - Udaipur 132 KV S/C line near Melaghar (12.178 Km distance from Monarchak) thereby connecting Monarchak with Rokhia and Udaipur sub-stations. The said arrangement has already been commissioned and is in operation w.e.f January 2015 for evacuation of Monarchak Power.
Remark:
Moti Khavdi (500 MW), PS,Guj,RPL,U1
| 1 |  |  | Moti Khavdi TPP - Jam Nagar |  |  | RPTL | D/C |  |  | 400
Remark:
M/s. Sembcorp Energy India Ltd, Projects-2, 625MW (Thermal)
| 1 |  |  | LILO of Krishnapatnam - Manubolu (Ckt - I) Quad Moose line to M/s SEIL- P2 400KV GIS Substation |  |  | APTRANS | D/C |  |  | 400 | 7 | 16 | 16 |  |  | 16 |  | 7 | SEP-23 |  |  | JAN-24 |  | Commissioned 01/24.
Remark:
M/s Sembcorp Gayatri Power Ltd. (SGPL) (Formerly NCC Power Project Ltd.) Super-critical TPP (2x660 MW),PS,AP,Nellore, U1-11/16 (C), U2-11/16
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 24 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | NCC gen Sw Yd. - Nellore PS line (Q) |  |  | PGCIL | D/C |  |  | 400 | 66 | 101 | 101 |  |  | 101 |  | 66 | FEB-17 |  |  | MAR-16 |  | Commissioned 03/16.
Remark:
M/s Vinirrmaa Energy Generation Pvt Ltd (40MW) & M/s.Ecoren Energy India Pvt Ltd (128.50MW)
| 1 |  |  | Jammalamadugu - Porumamilla YSR Kadapa District |  |  | APTRANS | D/C |  |  | 220 | 200 | 133 | 133 |  |  | 133 |  | 200 | AUG-23 |  |  | SEP-23 |  | Commissioned 09/23.
Remark:
Mundra TPP & Mundra UMPP (3x660&5x800),PS,Guj, Adani & TATA, both project commissioned by 03/13(c)
| 1 |  |  | +/- 500 kV Mundra - Bipole Mohindergarh |  |  | APL | BIPOLE |  |  | 500 | 1980 | 2693 | 2693 |  |  | 2693 |  | 1980 |  |  |  | MAR-12 |  | Commissioned 3/12
| 2 |  |  | Mohindergarh HVDC- Mohindergarh HVPNl (Dhanonda) |  |  | APL | D/C |  |  | 400 | 10 | 15 | 15 |  |  | 15 |  | 10 | APR-11 |  |  | JUL-12 |  | Commissioned. 7/12
| 3 |  |  | Mohindergarh HVDC - Bhiwani |  |  | APL | D/C |  |  | 400 | 100 | 139 | 139 |  |  | 139 |  | 100 | APR-11 |  |  | JUL-12 |  | Commissioned. 7/12
| 4 |  |  | Daultabad -Dhanonda |  |  | HVPNL | D/C |  |  | 400 | 146 | 219 | 219 |  |  | 219 |  | 146 |  |  |  | JAN-13 |  | Commissioned 1/13.
| 5 |  |  | Dhanoda (Mohindergarh) |  |  | HVPNL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | APR-12 |  | Commissioned 4/12
Remark:
Mundra TPP Ph.II (2x660 MW) ,PS,GUJ,Adani ,U1-12/10(C),U2-7/11(C)
| 1 |  |  | Mundra (Adani) - Zerda line 1 |  |  | GETCO | D/C |  |  | 400 | 640 | 997 | 491 |  |  | 293 |  | 120.94 | [5 empty] | W I P / Severe RoW problems
| 2 |  |  | Mundra (Adani) - Zerda line 2 |  |  | GETCO | D/C |  |  | 400 | 671 | 956 | 956 |  |  | 956 |  | 671 |  |  |  | FEB-16 |  | Commissioned 02/16. (One Circuit is via varsana.)
Remark:
Mundra UMPP WR system Strengething
| 1 |  |  | LILO of both ckts of Kawas-Navsari at Navsari. |  |  | PGCIL | D/C |  |  | 220 | 82 | 145 | 145 |  |  | 145 |  | 82 |  |  |  | JUL-12 |  | Commisisoned 7/12.
| 2 |  |  | Navsari - Boisor line (Balance portion ) |  |  | PGCIL | D/C |  |  | 400 | 161 | 567 | 567 |  |  | 567 |  | 161 | OCT-12 |  |  | DEC-16 |  | Commissioned 12/2016. (Remaining portion was taken as commissioned as Vapi-Navsari line in Mar'13)
| 3 |  |  | Shifting of Ankola -Aurangabad (MSETCL) to Aurangabad (PG) |  |  | PGCIL | D/C |  |  | 400 | 102 | [6 empty] | 102 |  |  |  | JAN-14 |  | Commissioned 01/14.
| 4 |  |  | Wardha - Aurangabad line (up-gradable on 1200 kV) |  |  | PGCIL | D/C |  |  | 400 | 696 | 961 | 961 |  |  | 961 |  | 696 | NOV-20 |  |  | MAR-21 |  | Commissioned 03/21.
| 5 |  |  | LILO of Halvad-Morbi II at Bhachau |  |  | GETCO | D/C |  |  | 220 | 216 | 333 | 333 |  |  | 333 |  | 216 |  |  |  | MAY-12 |  | Commissioned 5/12.
| 6 |  |  | Gandhar - Navsari |  |  | PGCIL | D/C |  |  | 400 | 204 | 288 | 288 |  |  | 288 |  | 204 |  |  |  | JUL-12 |  | Commisisoned 7/12
| 7 |  |  | LILO of Halvad-Morbi I at Bhachau |  |  | GETCO | D/C |  |  | 220 | 217 | 315 | 315 |  |  | 315 |  | 217 |  |  |  | MAY-12 |  | Commissioned 5/12.
| 8 |  |  | Aurangabad (PG)-Aurangabad (MSETCL) |  |  | PGCIL | D/C |  |  | 400 | 118 | [6 empty] | 118 | OCT-12 |  |  | APR-14 |  | Commissioned 04/14.
Remark:
Mutiara (Melamaruthur) (Coastal Energen) TPP (2x600 MW),PS,CEPL,U1-12/14 (C),U2-1/16(C)
| 1 |  |  | Mutiara TPP(Coastal Energen Gen. Switchyard) - Tuticorin Pooling Station (Balance portion) |  |  | CEPL | D/C |  |  | 400 | 24 | 32 | 32 |  |  | 32 |  | 24 |  |  |  | OCT-16 |  | Commissioned 10/2016
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 25 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | LILO of Madurai - Tuticorin at Costal Energen |  |  | CEPL | D/C |  |  | 400 | 52 | [6 empty] | 52 |  |  |  | MAR-12 |  | commissioned 3/12. (Interim arrangement).
Remark:
Muzaffarpur TPP Exp, Kanti-II (2x195MW) CS, Bihar, JV-NTPC U3-03/15 (C), U4-3/17 (C)
| 1 |  |  | Kanti - Darbhanga (2nd Ckt) |  |  | BSPTCL | S/C |  |  | 220 | 68 | [6 empty] | 68 |  |  |  | SEP-14 |  | Commissioned 09/14.
| 2 |  |  | Kanti - Gopalganj (2nd Ckt.) |  |  | BSPTCL | S/C |  |  | 220 | 101 | [6 empty] | 101 |  |  |  | MAR-16 |  | Commissioned 03/16.
Remark:
Mylavaram Solar park, 1,000MW
| 1 |  |  | Aug. at Jammalamadugu |  |  | APTRANS |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | SEP-23 |  |  | APR-23 |  | Commissioned 04/23.
Remark:
Myntdu (Leshka) HEP (3x42 MW),SS,Meg,MeECL, U1&U2-3/13,U3-3/13 (C)
| 1 |  |  | Leshka Myntdu - Khliehriat |  |  | MeECL | D/C |  |  | 132 | 53 | 85 | 85 |  |  | 85 |  | 53 |  |  |  | MAY-10 |  | The Line was initially charged at 33 kV from 22.05.2010 and subsequently at 132 kV on 25.11.2011.
Remark:
NABINAGAR -II STPS (3x660), CS, Bihar, NTPC, U1-1/18,U2-6/18,U3-12/18
| 1 |  |  | Nabinagar-II - Gaya (Q) |  |  | PGCIL | D/C |  |  | 400 | 184 | 245 | 245 |  |  | 245 |  | 184 |  |  |  | FEB-18 |  | Ready for Commissioning 02/18.
| 2 |  |  | Nabinagar-II - Patna line (Q) |  |  | PGCIL | D/C |  |  | 400 | 282 | 392 | 392 |  |  | 392 |  | 282 | JUN-19 |  |  | JUL-19 |  | Commissioned 07/19.
| 3 |  |  | Bay Extn. at 765/400KV at Patna S/stn. for 400KV D/C Nabinagar-II -Patna line (Q) |  |  | PGCIL |  |  |  | 400 | 50 | 100 | 0 |  |  | 0 |  | 0 | JUN-19 |  |  |  |  | Award placed in Mar'17. Engg. in progress.
|  | Remark: |  |  | Associated Transmission System for NABINAGAR -II STPS (3 x 660) - PGCIL
Nabi Nagar TPP (4x250 MW), CS,Bihar, NTPC, U1-3/16(C),U2-3/17,U3-12/17,U4-05/18
| 1 |  |  | Nabinagar - Sasaram line (Twin lapwing) |  |  | PGCIL | D/C |  |  | 400 | 164 | 216 | 216 |  |  | 216 |  | 164 |  |  |  | MAY-12 |  | Commissioned 05/12.
Remark:
Nagarjana Sagar TR HEP ( 2x25 MW),SS,AP,APGENCO,Unit-1&2-01/17(c)
| 1 |  |  | Rentachintala - Nagarjuna Sagar Plant |  |  | APTRANS | S/C |  |  | 132 | 16 | 34 | 34 |  |  | 34 |  | 16 |  |  |  | MAR-17 |  | Commissioned 08/14.
| 2 |  |  | LILO of VTS - Tallapally line at Rentachintala |  |  | APTRANS | D/C |  |  | 220 | 2 | 0 | 0 |  |  | 0 |  | 2 |  |  |  | NOV-08 |  | Commissioned 11/08
| 3 |  |  | Rentachintala - Macherla S/S |  |  | APTRANS | S/C |  |  | 132 | 17 | 58 | 58 |  |  | 58 |  | 17 |  |  |  | MAR-17 |  | Commissioned 27.03.2013
| 4 |  |  | Rentachintala S/S |  |  | APTRANS |  |  |  | 220/132 | 200 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-08 |  | Commissioned 11/08
Remark:
Naitwar Mori HEP (2x30 MW),CS,UK,SJVNL,U1&2 -12/21
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 26 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Mori -Dehradun |  |  | PTCUL | D/C |  |  | 220 | 200 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
| 2 |  |  | Naitwar Mori HEP - Mori SS |  |  | PTCUL | D/C |  |  | 220 | 0 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
Remark:
Namrup CCGT (100 MW),SS, Assam,GT/ST,U1-10/17,U2-11/17
| 1 |  |  | Namrup - Mariani |  |  | AEGCL | S/C |  |  | 220 | 145 | 448 | 448 |  |  | 448 |  | 145 | DEC-13 |  |  | JAN-16 |  | Commissioned 01/16.
Remark:
Nasik (5x270 + 5x270) TPS, PS, Maha, India Bulls, ph-II- uncertain
| 1 |  |  | Nasik-Bableshwar (1st Ckt) |  |  | IBPL | D/C |  |  | 400 | 57 | 152 | 152 |  |  | 152 |  | 57 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 2 |  |  | Nasik - Bobleshwar (2nd Ckt) |  |  | IBPL | D/C |  |  | 400 | 57 | 152 | 152 |  |  | 152 |  | 57 |  |  |  | AUG-15 |  | Ready for commissioning 08/15.
Remark:
Navapura TPP (TRN ) (2x300 MW), Chhattisgarh Pvt. Sector , TRN Energy Pvt. Ltd. U1-08/16 (C)
| 1 |  |  | TRN (TPP) - Raigarh PS (Tamnar) |  |  | TRNE | D/C |  |  | 400 | 30 | [6 empty] | 30 |  |  |  | JAN-16 |  | Commissioned 01/16.
|  | Remark: |  |  | Unit-1 Commissioned on 14.08.2016.
Navbharat TPP Ph-1 (2x525 MW), PS,Chh, U1&2
| 1 |  |  | Navbharat TPP - Angul P.S. (PG) |  |  | EPTCL | D/C |  |  | 400
Remark:
New Umtru HEP (2x20 MW),SS,Meg,MeECL,U1-4/17(C), U2-6/17(C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 27 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | New Umtru - Umtru HEP |  |  | MeECL | S/C |  |  | 132 | 0 | 1 | 1 |  |  | 1 |  | 0.5 | [5 empty] | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion work 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm and 132 kV S/C line - 0.36 ckm 7. The total expenditure incurred is Rs. 448.76 Lakhs and is inclusive of the cost of 132 kV New Umtru HEP - Norbong -EPIP-II line.
| 2 |  |  | New Umtru HEP - Norbong (EPIP-II) |  |  | MeECL | D/C |  |  | 132 | 1 | 7 | 7 |  |  | 7 |  | 1.21 | [5 empty] | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion was 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm, 132 kV S/C line - 1.07 ckm 7. The total expenditure incurred is Rs.471.87 Lakhs and is inclusive of 132 kV New Umtru - Umtru HEP line.
Remark:
Neyveli TPS-II Exp. (2x250MW) CS,TN, NLC, U1-1/12(C),U2-1/15 (C)
| 1 |  |  | Neyveli TS-II - Pugalur |  |  | NLC | D/C |  |  | 400 | 398 | 576 | 576 |  |  | 576 |  | 398 |  |  |  | AUG-09 |  | Commissioned 08/09.
| 2 |  |  | Neyveli (Exp-II) - Neyveli TS-II |  |  | NLC | 2xS/C |  |  | 400 | 3 | 17 | 17 |  |  | 17 |  | 3 |  |  |  | AUG-09 |  | Commissioned 08/09
Remark:
Nigri TPP (2x660 MW), PS,MP, JPVL, U1-8/14 (C),U2-2/15 (C)
| 1 |  |  | LILO of one ckt of Vindhychal - Satna at Nigrie |  |  | MPPTCL | D/C |  |  | 400
| 2 |  |  | JP Nigri TPP - Satna (PG) |  |  | JAL | D/C |  |  | 400 | 322 | [6 empty] | 322 |  |  |  | FEB-17 |  | Commissioned 08/2014 (Late Reported)
Remark:
Nilanchal TPP,(3x350MW), PS,Orissa, KVK, uncertain
| 1 |  |  | LILO of Mendasal - Baripada at Nilanchal TPP |  |  | KVK | D/C |  |  | 400 | 16 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Work yet to Start.
Remark:
Nimoo Bazgo (NHPC) (3x15 MW),CS,J & K,NHPC,U1-11/13(C),U2-10/13(C),U3-10/13(C).
| 1 |  |  | Nimoo S/S- Leh S/S |  |  | JKPDD | S/C |  |  | 66 | 31 | 152 | 152 |  |  | 152 |  | 31 |  |  |  | MAR-12 |  | Commissioned 03/12.
| 2 |  |  | Alachi - Khalsi S/S |  |  | JKPDD | S/C |  |  | 66 | 31 | 140 | 140 |  |  | 140 |  | 31 |  |  |  | MAR-17 |  | Commissioned.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 28 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 3 |  |  | Leh III (Army base) - Leh |  |  | JKPDD | S/C |  |  | 66 | 10 | 53 | 29 |  |  | 8 |  | 2 | [5 empty] | Rerouting of line and ganglas s/s droped. Leh Army S/S shall be connected with Leh S/S.
| 4 |  |  | Leh (C.P.) - Kharu S/S |  |  | JKPDD | S/C |  |  | 66 | 25 | 107 | 107 |  |  | 107 |  | 25 |  |  |  | MAR-17 |  | Commissioned.
| 5 |  |  | Kharu S/S - Himya S/S |  |  | JKPDD | S/C |  |  | 66 | 51 | 242 | 239 |  |  | 204 |  | 36 | [5 empty] | Slow progress.
| 6 |  |  | Leh (C.P.) - Leh S/S |  |  | JKPDD | S/C |  |  | 66 | 7 | 39 | 39 |  |  | 39 |  | 7 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 7 |  |  | Nimoo Bazgo HEP - Alachi |  |  | JKPDD | S/C |  |  | 66 | 4 | 13 | 13 |  |  | 13 |  | 4 |  |  |  | NOV-11 |  | Commissioned 11/12.
| 8 |  |  | Nimoo S/S - Alachi S/S |  |  | JKPDD | S/C |  |  | 66 | 17 | 77 | 77 |  |  | 77 |  | 17 |  |  |  | SEP-12 |  | Commissioned 09/12.
| 9 |  |  | Leh |  |  | JKPDD |  |  |  | 66/11 | 13 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned 12/12.
| 10 |  |  | Himya |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 30 |  |  | 0 |  | 0
| 11 |  |  | Khalsi |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned
| 12 |  |  | Alchi. S/S |  |  | JKPDD |  |  |  | 66/11 | 6 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned 11/12.
| 13 |  |  | Nimoo S/S |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned.
| 14 |  |  | Kharu |  |  | JKPDD |  |  |  | 66/11 | 60 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned
Remark:
North Chennai Thermal Power Project Stage-III (1x800)MW , Ennore SEZ Thermal Power Project( 2x660MW) , ETPS Expansion Thermal Power Project- 1x660MW
| 1 |  |  | Ariyalur S/S |  |  | TANTRAN |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 | SEP-23 |  |  | DEC-23 |  | Commissioned 12/23.
| 2 |  |  | North Chennai Pooling Station (GIS) (3X1500) |  |  | TANTRAN |  |  |  | 765/400 | 4500 | 100 | 100 |  |  | 100 |  | 100 | AUG-23 |  |  | FEB-24 |  | Commissioned 02/24.
Remark:
North Chennai TPP Stage-III (1x800MW), TN, TANGEDCO, U1-09/20
| 1 |  |  | NCTPS Stage-III - North Chennai (PS) line |  |  | TANTRAN | D/C |  |  | 765 | 13 | 20 | 20 |  |  | 20 |  | 13 | JUN-23 |  |  | MAR-24 |  | Commissioned 03/24.
Remark:
North Chennai TPS St.II (2x600 MW),SS,TN,U1-9/13(C),U2-3/13 (C).
| 1 |  |  | LILO of NCTPS- Mosur at NCTPS Stage II (for startup power) |  |  | TANTRAN | D/C |  |  | 230 | 2 | 2 | 2 |  |  | 2 |  | 2 | DEC-10 |  |  | NOV-10 |  | Commissioned 11/10.
| 2 |  |  | Alamathy -Sunguvarchatram (1st Ckt) |  |  | TANTRAN | D/C |  |  | 400 | 98 | 161 | 161 |  |  | 161 |  | 98 | JUN-10 |  |  | JAN-14 |  | Commissioned 01/14.
| 3 |  |  | Alamathy -Sunguvarchatram (2nd Ckt) |  |  | TANTRAN | D/C |  |  | 400 | 100 | [6 empty] | 100 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 4 |  |  | NCTPS St.II- Alamathy 400 kV S/S |  |  | TANTRAN | M/C |  |  | 400 | 136 | 114 | 114 |  |  | 114 |  | 136 |  |  |  | JAN-13 |  | Commissioned 01/13.
Remark:
North Eastern Region Expansion Scheme-XX (NERES-XX)
| 1 |  |  | Reconductoring of existing Single ACSR Panther Kopili (NEEPCO) |  |  | PGCIL | S/C |  |  | 132 | 10 | 0 | 0 |  |  | 0 |  | 11.03 | NOV-24 |  |  |  |  | Line commissioned on 09.05.2024
| 2 |  |  | Reconductoring of existing Single ACSR Panther Khandong (NEEPCO) |  |  | PGCIL | S/C |  |  | 132 | 42 | 0 | 0 |  |  | 0 |  | 42.48 | NOV-24 |  |  |  |  | Work completed & charged on 30.03.2024.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 29 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 3 |  |  | Reconductoring of existing Single AAAC Panther Khliehriat (POWERGRID) |  |  | PGCIL | S/C |  |  | 132 | 73 | 0 | 0 |  |  | 0 |  | 7.34 | NOV-24
| 4 |  |  | Reconductoing of existing Single AAAC Panther Khandong (NEEPCO) |  |  | PGCIL | S/C |  |  | 132 | 40 | [7 empty] | NOV-24
Remark:
North Karanpura (3x660MW), NTPC, Adani, U1-2/20,U2-8/20,U3-2/21
| 1 |  |  | North Karanpura - Gaya line (NKTL - TBCB) |  |  | APL | D/C |  |  | 400 | 196 | 286 | 140 |  |  | 132 |  | 37 | [5 empty] | Work in progress.
| 2 |  |  | LILO of Gaya-Chandwa(existing) at North Karanpura STPP (Interim) |  |  | PGCIL | M/C |  |  | 400 | 38 | [7 empty] | DEC-18
| 3 |  |  | North Karanpura - Chandwa (Jharkhand) PS line (NKTL -TBCB) |  |  | APL | D/C |  |  | 400 | 50 | 73 | 73 |  |  | 73 |  | 50 | JAN-23 |  |  | OCT-22 |  | Commissioned 10/22.
| 4 |  |  | LILO of both ckt. of Ranchi - Maithon-RB line at Dhanbad (NKTL-TBCB) |  |  | APL | D/C |  |  | 400 | 5 | 10 | 10 |  |  | 10 |  | 5 | MAY-21 |  |  | JUL-21 |  | Commissioned 07/21.
| 5 |  |  | Dhanbad New s/s (NKTL-TBCB) |  |  | APL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | MAY-21 |  |  | JUL-21 |  | Commissioned 07/21.
|  | Remark: |  |  | SPV/BPC - North Karanpura Transco Ltd / REC
NSL TPP (2x660 MW), PS, Orrisa, NPPL,
| 1 |  |  | NSL TPP - Angul |  |  | NSLNPPL | D/C |  |  | 400 | 46 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Project Authority intimated that PGCIL yet to award construction of work.
Remark:
Obra-C STPP (1x660MW), UP, UPRVUNL , 2021
| 1 |  |  | Obra-C-Jaunpur Line |  |  | UPPTCL | D/C |  |  | 400 | 400 | 459 | 459 |  |  | 459 |  | 334 | [5 empty] | Charged on 03.09.2023
| 2 |  |  | LILO of Anpara D-Unnao line at Obra |  |  | UPPTCL | S/C |  |  | 765 | 40 | 28 | 28 |  |  | 28 |  | 18 | [5 empty] | Line energised on 20.04.2023
| 3 |  |  | ICT at Obra C s/s |  |  | UPPTCL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Implemented by UPRVUNL. 1st bank of 1000 MVA T/F will be energised in Aug- 2024
Remark:
OPGC TPS-II(2X660)& other projects in Odisha, Ib Valley, U3-8/18,U4-10/18
| 1 |  |  | Jharsuguda (Sundargarh) - Raipur (OGP-IITL - TBCB) |  |  | SGL | D/C |  |  | 765 | 610 | 782 | 782 |  |  | 782 |  | 610 | AUG-19 |  |  | DEC-18 |  | Commissioned 12/18.
| 2 |  |  | OPGC - Jharsuguda (OGP-IITL - TBCB) |  |  | SGL | D/C |  |  | 400 | 103 | 152 | 152 |  |  | 152 |  | 103 | JUL-17 |  |  | AUG-17 |  | Ready for commissioned 08/2017.
|  | Remark: |  |  | SPV/BPPC - Orissa Generation Phase-II Transmission ltd. / PFC
Orissa UMPP (Bedabahal, Orissa), (5x800MW),(Orissa Integrated Power Ltd. (OPIL)
| 1 |  |  | Orrisa UMPP - Jharsuguda Pooling Station |  |  | XYZ | D/C |  |  | 765
Remark:
Painampuram TPP (2x660MW),PS,AP,Thermal power tech Development Corp (India) ltd.,U1-2/15 (C),U2-9/15 (C)
| 1 |  |  | Thermal Powertech - Nellore Pooling Station |  |  | PGCIL | D/C |  |  | 400 | 65 | 92 | 92 |  |  | 92 |  | 65 |  |  |  | AUG-13 |  | Commissioned 08/13.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 30 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Pakaldue (1000MW), Kiru (624MW) and Kwar (240MW) of Cehnab Valley Power Projects
| 1 |  |  | LILO of one Ckt. of Kishenpur -Dulhasti (Quad) line at Kishtwar |  |  | SGL | D/C |  |  | 400 | 5 | [7 empty] | APR-25
| 2 |  |  | Establishment of (PS) at Kishtwar (GIS) |  |  | SGL |  |  |  | 400/132 | 400 | [7 empty] | APR-25
Remark:
Pakal Dul HEP (4x250MW), J&K, JKSPDC, U,U2,U3,U4 (2023-24)
| 1 |  |  | Kiru HEP - Kishtwar Pooling Station (Triple HLTS Conductor) |  |  | JKPDD | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | work under planning stage.
| 2 |  |  | LILO of one Ckt. of Kiru HEP - Kishtwar PS at Kwar HEP and Pakal Dul HEP |  |  | JKPDD | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | Work under planning stage.
| 3 |  |  | Establishment of 400 kV switching station at Kishtwar (GIS) |  |  | JKPDD |  |  |  | 400 | 40
Remark:
Palatana CCGT (2x363.3),P S,Tri,OTPC, Module-1:1/13(c), Module 2 - 11/14 (C)
| 1 |  |  | Byrnihat - Azara (2nd Ckt) (Part of Silchar - Azara) |  |  | NETC | S/C |  |  | 400 | 42 | [6 empty] | 42 |  |  |  | JUL-14 |  | Commissioned 07/14.
| 2 |  |  | Azara - Bongaigaon |  |  | NETC | D/C |  |  | 400 | 201 | 442 | 442 |  |  | 442 |  | 201 | DEC-14 |  |  | MAR-15 |  | Commissioned 03/15.
| 3 |  |  | Silchar - Byrnihat |  |  | NETC | D/C |  |  | 400 | 428 | 590 | 590 |  |  | 590 |  | 428 |  |  |  | FEB-13 |  | Commissioned.
| 4 |  |  | LILO of Palatana - Bongaigaon at Killing (Byrnihat) |  |  | MeECL | D/C |  |  | 400 | 9 | 10 | 10 |  |  | 10 |  | 9 |  |  |  | MAR-13 |  | commissioned 3/13
| 5 |  |  | Azara - Bongaigaon (2nd Ckt) |  |  | NETC | D/C |  |  | 400 | 159 | [6 empty] | 159 |  |  |  | JAN-15 |  | Commissioned 01/15.
| 6 |  |  | LILO of Palatana - Bongaigaon at Azara S/S |  |  | AEGCL | D/C |  |  | 400 | 7 | 14 | 14 |  |  | 14 |  | 7 |  |  |  | JAN-15 |  | Commissioned 01/15.
| 7 |  |  | Palatana -Silchar |  |  | NETC | D/C |  |  | 400 | 495 | 680 | 680 |  |  | 680 |  | 495 |  |  |  | AUG-12 |  | Commissioned 8/12
| 8 |  |  | Kukumara S/S (2x50) |  |  | AEGCL |  |  |  | 220/132 | 100 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-19 |  | Commissioned 01/15 (Late Reported).
| 9 |  |  | Killing (Byrnihat) (Ist Trf.)S/S |  |  | MeECL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-13 |  | Ist transformer commissioned.
| 10 |  |  | Kukurmara (Azara) S/S |  |  | AEGCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | SEP-11 |  |  | MAY-15 |  | Commissioned 05/15.
Remark:
Panan HEP (4x75MW), PS, Sikkim, HHEPL, U1-U4-03/24
| 1 |  |  | Panan HEP - Mangan |  |  | HHEPL | 2xD/C |  |  | 220
|  | Remark: |  |  | Civil works were awarded on 22.02.2014 but project could not be started because of non availability of NWLB clearance.It was concluded that since the matter is subjudice , commissioning can be assessed after clearance from NWLB and approach road to dam site is available.
Panki TPS Extn. (1x660 MW), UP, URVUNL, U1-09/23
| 1 |  |  | 400 kV Panki - PTPS Line (Ckt-II) |  |  | UPPTCL | D/C |  |  | 400 | 1 | 0 | 0 |  |  | 0 |  | 1 | JUN-22 |  |  | MAR-24 |  | Commissioned 03/24.
Remark:
Parbati-II HEP (4x200), (PGCIL & JP) CS, HP, NHPC, U1 - 4 (12/21)
| 1 |  |  | Parbati -II- Koldam line -II |  |  | PKTCL | S/C |  |  | 400 | 76 | 157 | 157 |  |  | 157 |  | 76 |  |  |  | SEP-14 |  | Commissioned 9/14.
| 2 |  |  | Parbati- II - Koldam line-I |  |  | PKTCL | S/C |  |  | 400 | 81 | 173 | 173 |  |  | 173 |  | 81 |  |  |  | OCT-14 |  | Commissioned 10/14.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 31 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Remark:
Parbati-III HEP (4x130 MW),CS,HP,NHPC,U1-6/14 (C),U2-2/14 (C),U3-3/14 (C),U4-5/14 (C)
| 1 |  |  | LILO of Parbati -II - Parbati Pooling Point at Parbati -III |  |  | PGCIL | D/C |  |  | 400 | 4 | 7 | 7 |  |  | 7 |  | 4 |  |  |  | JUL-13 |  | Commissioned 07/2013.
| 2 |  |  | Parbati Pooling Point - Amritsar |  |  | PGCIL | D/C |  |  | 400 | 501 | 668 | 668 |  |  | 668 |  | 501 |  |  |  | JUL-13 |  | Commissioned 07/2013.
| 3 |  |  | LILO of Parbati -II - Koldam at Parbati Pooling Point. |  |  | PGCIL | D/C |  |  | 400 | 1 | 5 | 5 |  |  | 5 |  | 1 | JAN-10 |  |  | JUL-13 |  | Commissioned 07/2013.
Remark:
Pare HEP (2x55MW)CS,ARP,NEEPCO,U1,2-5/18(c)
| 1 |  |  | LILO of Ranganadi - Nirjuli at Pare HEP |  |  | PGCIL | D/C |  |  | 132 | 3 | 10 | 10 |  |  | 10 |  | 3 | [5 empty] | Line work completed. Test charged on 03.03.2018.
| 2 |  |  | LILO of Ranganadi - Itanagar at Pare HEP |  |  |  | D/C |  |  | 132 | 5 | 12 | 12 |  |  | 12 |  | 5 | [5 empty] | Line work completed. a) RHEP Section: Charged on 06.07.2018. b) Itanagar Section: Charged on 07.07.2018.
Remark:
Parichha Extn. TPS (2x250 MW),SS,UP,UPRVUNL,U5-5/12(C),U6-3/13 (C)
| 1 |  |  | Parichha - Bhauti |  |  | UPPTCL | S/C |  |  | 220 | [11 empty] | MAR-10 |  | Commissioned 3/11
| 2 |  |  | Parichha - Banda |  |  | UPPTCL | S/C |  |  | 220 | 210 | 606 | 606 |  |  | 606 |  | 210 |  |  |  | MAR-12 |  | Commissioned 3/12
| 3 |  |  | Paricha - Mainpuri 2nd Ckt.) |  |  | UPPTCL | D/C |  |  | 400 | 259 | 402 | 402 |  |  | 402 |  | 259 |  |  |  | JAN-14 |  | Commissioned 01/14.
| 4 |  |  | Parichha - Mainpuri (1st Ckt.) |  |  | UPPTCL | D/C |  |  | 400 | 259 | 301 | 301 |  |  | 301 |  | 259 | DEC-10 |  |  | DEC-13 |  | Commissioned 12/13.
| 5 |  |  | Moth-II Jhansi T/F-I |  |  | UPPTCL |  |  |  | 220/132 | 160 | 100 | 100 |  |  | 100 |  | 100 | JUL-23 |  |  | APR-23 |  | Commissioned 04/23.
| 6 |  |  | Orai (New) (ICT-II) |  |  | UPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-17 |  | Commissioned 11/2017.
| 7 |  |  | Orai S/S (new) (ICT-I) |  |  | UPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-16 |  | Commissioned 11/2016
Remark:
Parli TPP Expn. (250 MW), SS,Maha,MSPGCL, U8-3/16(C)
| 1 |  |  | Parli TPS-Nanded (waghala) |  |  | MSETCL | M/C |  |  | 220 | 181 | 300 | 300 |  |  | 300 |  | 181 | APR-11 |  |  | OCT-12 |  | Commissioned 10/12.
Remark:
Parnai HEP (3x12.5),JKPDC,03/22
| 1 |  |  | Parnai HEP - Parnai (JKPDD) |  |  | JKPDD | D/C |  |  | 132 | 30
Remark:
Part ATS for RAPP U-7&8 in Rajasthan (TBCB)
| 1 |  |  | RAPP - Shujalpur line (RAPPTCL - TBCB) |  |  | SGL | D/C |  |  | 400 | 402 | 521 | 521 |  |  | 521 |  | 402 | FEB-16 |  |  | JUN-16 |  | Ready for Commissioning 06/16. (RTCL).
|  | Remark: |  |  | SPV/BPC - RAPP Transmission Company Ltd. / PFC
Patratu STPP (3x800 MW), Th, JV of NTPC & JBVNL, U1-05/22, U2-09/22, U3-12/22
| 1 |  |  | TTPS-PTPS (Modification and upgradation) to provide startup power to PVUNL) |  |  | JUSNL | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0 | [7 empty] | LOA placed on 15.07.22. Schedule completion 14.10.22.
| 2 |  |  | PVUNL-Koderma |  |  | JUSNL | D/C |  |  | 400 | 300 | 0 | 0 |  |  | 0 | [7 empty] | Technical evaluation under progress.
| 3 |  |  | PVUNL-Chandil |  |  | JUSNL | D/C |  |  | 400 | 270 | 0 | 0 |  |  | 0 | [7 empty] | Technical evaluation under progress.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 32 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 4 |  |  | PUVNL- Patratu |  |  | JUSNL | D/C |  |  | 400 | 14 | 0 | 0 |  |  | 0 |  |  | JUN-24 |  |  |  |  | Request letter regarding additional fund as difference of sanctioned cost and offered price of L-1 bidder has been sent to energy dept. Govt of Jharkhand. After sanctioning of requisite fund, work order will be issued.
| 5 |  |  | GSS Koderma s/s |  |  | JUSNL |  |  |  | 400/220 | 1560 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Technical evaluation under progress
| 6 |  |  | Patratu GSS |  |  | JUSNL |  |  |  | 220/132/33 | 500 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Technical evaluation under progress.
| 7 |  |  | Latehar GSS |  |  | JUSNL |  |  |  | 400/220 | 630 | [7 empty] | AUG-24
| 8 |  |  | GSS Chandil s/s |  |  | JUSNL |  |  |  | 400/220/132 | 1000 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Technical evaluation under progress
| 9 |  |  | Lohardaga GSS (PGCIL) |  |  | JUSNL |  |  |  | 220/132 | 300 | 100 | 95 |  |  | 90 |  | 90 | MAY-24 |  |  |  |  | Work in Progress.
Remark:
Petronet LNG (3x395 MW), PS,Guj,PLNGL, U1,U2,U3
| 1 |  |  | PLNGL TPP - Vadodra |  |  | XYZ | D/C |  |  | 400
Remark:
Phata Byung HEP (2x38 MW),PS, UK, Lanco, U1 & U2
| 1 |  |  | Phata HEP-Baramwari (Rudrpur) |  |  | LEPP | D/C |  |  | 220 | 8 | 20 | 0 |  |  | 0 |  | 0
| 2 |  |  | Rudrapur (Brahmwari) - Ghansali (Srinagar) line |  |  | PTCUL | D/C |  |  | 220 | 150 | 260 | 260 |  |  | 260 |  | 150 | JUN-19 |  |  | JUN-20 |  | Commissioned 07/20.
| 3 |  |  | Phata HEP-Baramwari (Rudrpur) |  |  | PTCUL | D/C |  |  | 220 | 8 | 8 | 0 |  |  | 0 | [7 empty] | Pertains with L&T HEP.
| 4 |  |  | Ghansali (GIS) |  |  | PTCUL |  |  |  | 220/33 | 60 | 100 | 0 |  |  | 0 |  | 0 | [5 empty] | Will be planned matching with commissioing schedule of Bhilanga-II HEP of UJVN Ltd.
| 5 |  |  | Srinagar S/S |  |  | PTCUL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | DEC-12 |  |  | JUL-16 |  | Commissioned 07/16.
| 6 |  |  | Baramwari (GIS) |  |  | PTCUL |  |  |  | 220/132 | 60 | 100 | 0 |  |  | 0 |  | 0 | [5 empty] | Tendering is in progress.
|  | Remark: |  |  | All construction activities on project site is on hold since Jul'17 as EPC contractor has been reffered to National company law tribunal under IBC 2016. The project is likely to be commissioned within 2 years after the restart of works.
Pipalkoti HEP (Vishnugad Pipalkoti) (THDC) ( Kuwari Pass ) (4x111 MW),SS,UK,PTCUL,U1-4 (12/22)
| 1 |  |  | Pipalkoti HEP (THDC) - Pipalkoti (Kuwari Pass) Switching Substation T/line |  |  | PTCUL | D/C |  |  | 400 | 2 | 0 | 0 |  |  | 0 |  |  | SEP-19 |  |  |  |  | Construction of line shall be planned as per schedule of Pipalkoti HEP (THDC) after signing of Implementation Agreement with PTCUL.
| 2 |  |  | Pipalkot (THDC) Switching Substation |  |  | PTCUL |  |  |  | 400 | 10 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Substation land is inside the premises of Pipalkoti HEP. Construction of Substation shall be planned as per schedule of Pipalkoti HEP (THDC) after signing of Implementation Agreement with PTCUL.
Remark:
Pipavav CCPP(2x351MW),SS,Guj,GSECL,Block-1-2/14 (C), Block-2-3/13 (C).
| 1 |  |  | GPPC (Pipavav)- Dhokadva |  |  | GETCO | D/C |  |  | 220 | 94 | 152 | 152 |  |  | 152 |  | 94 | MAR-12 |  |  | JUL-16 |  | Ready for Commissioning 07/16.
| 2 |  |  | LILO of Savarkundla - Mahva (otha) at Pipavav (GPPC) (line-2) |  |  | GETCO | D/C |  |  | 220 | 81 | 133 | 133 |  |  | 133 |  | 81 | APR-11 |  |  | AUG-12 |  | Commissioned 8/12
| 3 |  |  | LILO of Savarkundla - Mahva(otha) at Pipavav (GPPC) (line-1) |  |  | GETCO | D/C |  |  | 220 | 91 | 149 | 149 |  |  | 149 |  | 91 | AUG-10 |  |  | MAR-12 |  | Commissioned 3/12
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 33 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 4 |  |  | Otha (Mahuva) - Sagapara (Palitana) |  |  | GETCO | D/C |  |  | 220 | 96 | 161 | 161 |  |  | 161 |  | 96 |  |  |  | JUN-13 |  | Commissioned 06/13.
Remark:
Polavaram HEP (12x80MW),SS,AP,PPA,U1-12
| 1 |  |  | Polavaram-Kamavarapukota (QM) |  |  | APTRANS | D/C |  |  | 400 | 140 | 0 | 0 |  |  | 0 |  |  | AUG-19 |  |  |  |  | The scope of the work revised due to site constraints. 400kV QMDC Line from 400kV Polavaram SS to 400/22/11 kV Guddigudem SS is proposed in place of earlier approved 400kV Polavaram-K.Kota QMDC Line.Tenders floated with revised scope of work on 28.01.2019.Tenders finalized and LOI placed on 29,04.2019 .Line survey works completed. Works will be taken up after finalization of award of contract of Polavaram Hydro Electric Project by APGENCO.
|  | Remark: |  |  | Work is in standstill condition as review of present contract is under progress
Polavaram Hydro Electric Project, 960MW (12x80)
| 1 |  |  | 220kV Guddigudem -Purushothapatnam D/C line |  |  | APTRANS | D/C |  |  | 220 | 47 | 65 | 65 |  |  | 65 |  | 47 | OCT-23 |  |  | MAR-24 |  | Commissioned 03/24.
| 2 |  |  | LILO Pallantla -Pattiseema line at Guddigudem line |  |  | APTRANS | D/C |  |  | 220 | 23 | 49 | 49 |  |  | 49 |  | 23 | JUL-23 |  |  | JUL-23 |  | Commissioned 07/23.
Remark:
Pragati CCGT Ph-III(4X250+2X250MW),SS,DEL,PPCL,GT1-10/10(C),GT2-2/11(C),GT3-6/12,(C)ST1-2/12(C),GT4-5/13(C),ST2-2/14 (C)
| 1 |  |  | Extension of bus and connection with DTL Substation |  |  | PPCL |  |  |  | 400 | 630 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | commissioned
Remark:
Pulichintala HEP (4x30MW),SS,TelanganA,TSGENCO,U1- 9/16 (C), U2-9/16,U 3-9/17,U4-10/17
| 1 |  |  | Pulichintala HEP - Huzurnagar line |  |  | TSTRANS | D/C |  |  | 220 | 74 | 132 | 132 |  |  | 132 |  | 74 |  |  |  | NOV-16 |  | Commissioned 10/2016 (Late Reported)
| 2 |  |  | LILO of Chillakallu S/S - Narketpally line at Huzurnagar S/S |  |  | TSTRANS | D/C |  |  | 220 | 24 | 42 | 42 |  |  | 42 |  | 24 |  |  |  | JUN-17 |  | Ready for commissioning 06/2017.
| 3 |  |  | Huzumagar S/S |  |  | TSTRANS |  |  |  | 220/132/33 | 200 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned on 10.12.2018
Remark:
RaghunathpurTPS (2x600 MW),CS,WB,DVC,U1-8/14 (C),U2-1/16(C).
| 1 |  |  | LILO of Maithon-Ranchi (PG) at Raghunathpur |  |  | DVC | D/C |  |  | 400 | 21 | 33 | 33 |  |  | 33 |  | 21 |  |  |  | MAR-11 |  | Commissioned 3/11. (Interim arrangement)
| 2 |  |  | Raghunathpur TPS -Ranchi (PG) |  |  | DVC | D/C |  |  | 400 | 311 | 439 | 439 |  |  | 439 |  | 311 | AUG-10 |  |  | SEP-17 |  | Commissioned 08/2017(Late Reported).
Remark:
Raikheda TPP (2x685 MW), PS,Chh, GMR, U1-2/15 (C), U2-3/16 (C),
| 1 |  |  | Raikheda (GMR) - Raipur Pooling Station |  |  | GMR | D/C |  |  | 400 | 131 | 181 | 181 |  |  | 181 |  | 131 |  |  |  | JUL-15 |  | Commissioned in February 2014. Reported in July 2015.
Remark:
Rajasthan New Solar and Wind Power Plant
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 34 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Sirohi-Pindwara line |  |  | RVPNL | S/C |  |  | 220 | 23 | 80 | 80 |  |  | 80 |  | 23 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 2 |  |  | Bikaner -Sikar (PG) |  |  | RVPNL | D/C |  |  | 400 | 420 | 445 | 445 |  |  | 445 |  | 420 |  |  |  | MAR-18 |  | Commissioned 12/17 (Late Reported).
| 3 |  |  | Chatrail-Ramgarh |  |  | RVPNL | D/C |  |  | 220 | 90 | 146 | 146 |  |  | 146 |  | 90 |  |  |  | AUG-16 |  | Ready for Commissioning 08/16.
| 4 |  |  | LILO of Jodhpur -Merta at Pooling station Badla |  |  | RVPNL | D/C |  |  | 400 | 405 | 557 | 557 |  |  | 557 |  | 405 |  |  |  | NOV-18 |  | Ready for Commissioning 11/18.
| 5 |  |  | Jaisalmer -2 -Barmer line |  |  | RVPNL | D/C |  |  | 400 | 234 | 332 | 332 |  |  | 332 |  | 234 |  |  |  | JAN-19 |  | Commissioned 01/19.
| 6 |  |  | LILO of both ckts Ramgarh GTPS -Dechu at Ramgarh |  |  | RVPNL | D/C |  |  | 220 | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  |  | DEC-16 |  | Ready for commissioning 12/2016.
| 7 |  |  | Aau - Badisid |  |  | RVPNL | D/C |  |  | 220 | 118 | 196 | 196 |  |  | 196 |  | 118 |  |  |  | APR-16 |  | Commissioned 04/16.
| 8 |  |  | Ramgarh (Jaisalmer)-Akal (Jaisalmer ) |  |  | RVPNL | D/C |  |  | 400 | 198 | 278 | 278 |  |  | 278 |  | 198 |  |  |  | DEC-17 |  | Ready for Commissioning 12/2017.
| 9 |  |  | Ramgarh - Bhadla line (Ckt-I) |  |  | RVPNL | D/C |  |  | 400 | 160 | 446 | 446 |  |  | 446 |  | 160 | DEC-20 |  |  | DEC-20 |  | Commissioned 12/20.
| 10 |  |  | LILO of one ckt Raj west -Jodhpur at Jodhpur (New) |  |  | RVPNL | D/C |  |  | 400 | 102 | 138 | 138 |  |  | 138 |  | 102 |  |  |  | APR-16 |  | Commissioned 04/16.
| 11 |  |  | Akal -Jodhpur (New) |  |  | RVPNL | D/C |  |  | 400 | 447 | 620 | 620 |  |  | 620 |  | 447 |  |  |  | AUG-18 |  | Ready for Commissioning 08/18.
| 12 |  |  | Barmer-Bhinmal line |  |  | RVPNL | D/C |  |  | 400 | 288 | 399 | 399 |  |  | 399 |  | 288 |  |  |  | MAY-19 |  | Commissioned 05/19.
| 13 |  |  | Bhadla-Bikaner |  |  | RVPNL | D/C |  |  | 400 | 379 | 512 | 512 |  |  | 512 |  | 378 |  |  |  | APR-17 |  | Commissioned 04/2017
| 14 |  |  | Aau-Baithwasia |  |  | RVPNL | D/C |  |  | 220 | 93 | 155 | 155 |  |  | 155 |  | 93 |  |  |  | NOV-14 |  | Commissioned 11/14.
| 15 |  |  | Bhadla-Kanasar |  |  | RVPNL | D/C |  |  | 220 | 63 | 105 | 105 |  |  | 105 |  | 63 |  |  |  | JUN-16 |  | Commissioned 06/16.
| 16 |  |  | Jaisalmer -2 S/S |  |  | RVPNL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 17 |  |  | Kuchera S/S |  |  | RVPNL |  |  |  | 220/132 | 100 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | DEC-15 |  | Commissioned 12/15.
| 18 |  |  | Aau S/S |  |  | RVPNL |  |  |  | 220/132 | 160 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAY-15 |  | Commissioned 05/15.
| 19 |  |  | Kanasar S/S |  |  | RVPNL |  |  |  | 220/132 | 160 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-16 |  | Commissioned 06/16.
Remark:
Rajpura (NABA) TPP, (2x700MW) U1-1/13 (C) ,& U2-7/14 (C)
| 1 |  |  | Rajpura - Dhuri |  |  | PSTCL | D/C |  |  | 400 | 171 | 242 | 242 |  |  | 242 |  | 171 |  |  |  | MAY-13 |  | Commissioned 05/13.
| 2 |  |  | Rajpura Thermal - Rajpura |  |  | PSTCL | D/C |  |  | 400 | 18 | 29 | 29 |  |  | 29 |  | 18 |  |  |  | MAY-13 |  | Commissioned 05/13.
| 3 |  |  | Rajpura Thermal - Nakodar |  |  | PSTCL | D/C |  |  | 400 | 279 | 381 | 381 |  |  | 381 |  | 279 |  |  |  | MAY-14 |  | Commissioned 05/14.
| 4 |  |  | Rajpura (New) (2x500) (ICT-II) |  |  | PSTCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | DEC-16 |  |  | MAR-17 |  | Commissioned 03/2017
| 5 |  |  | Rajpura (New) (2x500) (ICT-I) |  |  | PSTCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-16 |  | Commissioned 06/16.
Remark:
Ramgarh CCPP Extn.-III, (110+50 MW), SS,Raj, RRVUNL, (GT-3/13(C),ST-5/14 (C)
| 1 |  |  | Ramgarh (GTPP) - Chandan |  |  | RVPNL | D/C |  |  | 220 | 194 | 309 | 309 |  |  | 309 |  | 194 |  |  |  | NOV-14 |  | Commissioned 11/14.
| 2 |  |  | Dechu - Phalodi |  |  | RVPNL | D/C |  |  | 220 | 71 | 119 | 119 |  |  | 119 |  | 71 |  |  |  | SEP-12 |  | Commissioned 9/12.
| 3 |  |  | Chandan - Dechu |  |  | RVPNL | D/C |  |  | 220 | 202 | 322 | 322 |  |  | 322 |  | 202 |  |  |  | DEC-14 |  | Commissioned 12/14.
Remark:
RAMMAM-III HEP (3x40 MW), NTPC, WBSTCL (02/22)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 35 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Rammam III - Chalsa |  |  | WBSETCL | D/C |  |  | 132 | 130 | 0 | 0 |  |  | 0 |  |  | APR-19 |  |  |  |  | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
| 2 |  |  | LILO of 132 kV One Ckt of Rammam-II - NBU at Rammam -III HEP |  |  | WBSETCL | D/C |  |  | 132 | 20 | 0 | 0 |  |  | 0 |  |  | APR-19 |  |  |  |  | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
|  | Remark: |  |  | Discussion going on with WB
Rampur HEP (6x68.67 MW),CS,HP,SJVNL,U1-2/14 (C),U2-2/14 (C),U3-3/14 (C), U4-6/14(C), U5-3/14 (C), U6 - 12/14(C)
| 1 |  |  | Patiala - Ludhiana |  |  | PGCIL | D/C |  |  | 400 | 156 | 217 | 217 |  |  | 217 |  | 156 | NOV-11 |  |  | SEP-11 |  | Commissioned 9/11.
| 2 |  |  | LILO of Nathpa Jhakri - Nalagarh at Rampur (2nd Ckt balance) |  |  | PGCIL | D/C |  |  | 400 | 2 | [6 empty] | 2 |  |  |  | OCT-14 |  | Commissioned 10/14.
| 3 |  |  | LILO of Nathpa Jhakri - Nalagarh at Rampur (Loop in portion) |  |  | PGCIL | D/C |  |  | 400 | 5 | 12 | 12 |  |  | 12 |  | 5 | NOV-11 |  |  | FEB-14 |  | Commissioned 02/14.
| 4 |  |  | LILO of Patiala - Hissar at Kaithal |  |  | PGCIL | D/C |  |  | 400 | 66 | 90 | 90 |  |  | 90 |  | 66 | NOV-11 |  |  | AUG-11 |  | Commissioned 8/11.
Remark:
Rangit-II HEP (2x33MW)PS,Sikkim, SHPL,U1&2 (2020-21)
| 1 |  |  | LILO of one ckt of Legship - New Melli at Rangit-II |  |  | SHPL | D/C |  |  | 220
Remark:
Rangit-IV HEP (3x40MW),PS,Sikkim,JPCL,U1,2&3
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 36 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Rangit IV - New Melli line |  |  | JPCL | D/C |  |  | 220 | 7 | 15 | [11 empty] | Work of 220kV line has been awarded to M/s. Ashish Infratech and completion period is 8 months from start of work. Generation project will take about 2? years for completion as against 8 months for completion of associated transmission line, there will be no mismatch for evacuation of power. It may also be mentioned that route survey of transmission line has been completed and design work of transmission system including towers (15 nos.) has also been completed. 220kV GIS bays at PGCIL substation at New Melli have also been awarded to M/s. PGCIL as deposit work. Line length is 3.3 KM. Associated transmission system comprises of 220kV GIS in PH building, 3.3 km long 220kV D/C line from PH to PGCIL pooling station at New Melli. Work for 220kV GIS substation at PH has been awarded to M/s. Siemens and GIS equipment has already been delivered at site.
| 2 |  |  | Routing of one circuit of Jorthong - New Melli via Rangit - IV |  |  | LEPP | D/C |  |  | 220 | [13 empty] | Work in generation project is stopped for since 2013.
|  | Remark: |  |  | Work remain suspended since Oct'13 due to fund constraints. Project is likely to be commissioned within 30 months after restart of works
Ratija ( 1x50 MW) TPS,P.S.,Spectrum Coal & Power ltd.,Chh, U1-2/13(C)
| 1 |  |  | Ratija - Kasiapalli |  |  | SCPL | D/C |  |  | 132 | 24 | [6 empty] | 24 |  |  |  | MAR-17 |  | Commissioned.
Remark:
Ratle HEP, (4x205+1x30 MW), PS, J&K, GVK, U-I - U-5 (2023-24)
| 1 |  |  | LILO of one circuit of Dulhasti - Kishenpur at Ratle HEP. |  |  | PGCIL | D/C |  |  | 400
| 2 |  |  | Kishenpur - Ratle, (Dulhasti- Kishenpur Second Ckt stringing extending up to Ratle HP) |  |  | PGCIL | S/C |  |  | 400 |  | 0 | 0 |  |  | 0
|  | Remark: |  |  | Work yet to be award.
Rayalseema ( Stage-IV) (600 MW), SS,AP,BHEL,U6-08/17
| 1 |  |  | Rayalaseema TPP - Chittoor line |  |  | APTRANS | D/C |  |  | 400 | 429 | 321 | 321 |  |  | 321 |  | 429 | MAY-15 |  |  | JUN-17 |  | Ready for commissioning 06/2017.
Remark:
Reliable TPP (RTPL), (2x660 MW), PS, MP, RTPL,U1-6/16 (Tentative), U2-12/16 (Tentative)
| 1 |  |  | Reliable TPP - Vindhyachal Pooling Station |  |  | XYZ | D/C |  |  | 765
Remark:
Rewa TPP, Khandwa (2x800 MW), SS,MP
| 1 |  |  | LILO of Handia - Barwaha at Handia |  |  | MPPTCL | D/C |  |  | 220 | 40
| 2 |  |  | Handia - Ashta(2nd stage) |  |  | MPPTCL | D/C |  |  | 400 | 180
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 37 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 3 |  |  | Nagda - Ujjain line (GEC-I) |  |  | MPPTCL | DCDS |  |  | 400 | 53 | 152 | 152 |  |  | 152 |  | 53 | SEP-20 |  |  | FEB-21 |  | Commissioned 02/21.
Remark:
Rongnichu HEP (2x48 MW) PS,Sikkim, MBPCL,U1 & U2 (10/20)
| 1 |  |  | Rongnichu - Rangpo Pooling Station |  |  | MBPC | D/C |  |  | 220
Remark:
Rosa TPP Extn Ph-II (2x300), PS, UP, Reliance, Northern Region, U3-12/11 (C), U4-3/12 (C)
| 1 |  |  | LILO of Lucknow - Bareilly at Shahjahanpur |  |  | RPTL | D/C |  |  | 400 | 15 | [6 empty] | 15 |  |  |  | MAR-12 |  | Commissioned 3/12
| 2 |  |  | Rosa - Shahjehanpur (PG) |  |  | RPTL | D/C |  |  | 400 | 16 | [6 empty] | 16 |  |  |  | JUL-15 |  | Commissioned in March 2012. reported in july 2015.(Line Charged by passing Shahjehanpur S/S).
| 3 |  |  | Roza - Dohna |  |  | UPPTCL | D/C |  |  | 220 | 216 | 340 | 340 |  |  | 340 |  | 216 |  |  |  | AUG-16 |  | Commissioned 04/16. (Late Reported.)
Remark:
Sagardighi TPP (2x300 MW) Phase-II(2x660 MW),SS,WBPDCL U1-12/07(C),U2-7/08(C), U3-12/15(C), U4-12/16
| 1 |  |  | Sagardighi TPS - Gokarna line |  |  | WBSETCL | D/C |  |  | 400 | 89 | 154 | 154 |  |  | 154 |  | 89 | DEC-19 |  |  | OCT-20 |  | Commissioned 10/20.
| 2 |  |  | Sagardighi - Parulia (PGCIL) |  |  | WBSETCL | S/C on D/C |  |  | 400 | 255 | 340 | 340 |  |  | 340 |  | 255 | DEC-08 |  |  | APR-11 |  | Commissioned 4/11.
Remark:
Sainj HEP (2x50 MW) on Sainj river,SS,HP,HPPCL,U-08/17
| 1 |  |  | LILO of Parbati - II HEP - Parbati-III Pooling station at Sainj |  |  | HPPTCL | D/C |  |  | 400 | 1 | 1 | 1 |  |  | 1 |  | 1 |  |  |  | MAR-18 |  | Commissioned 04/17 (Late Reported).
Remark:
Salaya (Essar Power ) (2x600 MW),PS, Guj, Essar Power U1-2/12(C),U2-6/12 (C)
| 1 |  |  | Vadinar - Amreli (Part line) |  |  | GETCO | D/C |  |  | 400 | 117 | 294 | 294 |  |  | 294 |  | 117 |  |  |  | JAN-14 |  | Commissioned 01/14.
| 2 |  |  | Essar Gujarat TPS - Bachau (Tripal) |  |  | PGCIL | D/C |  |  | 400 | 446 | 606 | 606 |  |  | 606 |  | 446 | FEB-14 |  |  | SEP-16 |  | Ready for Commissioning 09/16. (Due to delay in Essar Generation Project & non finalization of gentry 6 ckm work is pending balance 446 ckm has been test charged.
| 3 |  |  | Vadinar (Essar)-Hadala |  |  | GETCO | D/C |  |  | 400 | 226 | 353 | 353 |  |  | 353 |  | 226 | NOV-09 |  |  | MAY-11 |  | Commissioned 5/11.
Remark:
Salora TPS (M/s Vandana Vidyut ) (2x135 MW), U2- uncertain
| 1 |  |  | LILO of one ckt Korba- Birsinghpur at Vandana |  |  | VVL | D/C |  |  | 400 | 6 | [6 empty] | 6 |  |  |  | JUL-12 |  | Commissioned. 7/12. (Interim )
| 2 |  |  | Salora TPS - Dharamjaigarh (Korba) (PGCIL) Pooling Station |  |  | VVL | D/C |  |  | 400 | 60 | 84 | [11 empty] | Target Commissioning date will be provided after approval/receipet of loan from lenders.
Remark:
Sandila TPP (2x660 MW), PS,UP,TPL,
| 1 |  |  | Sandila TPP - ATS not defind |  |  | TOR. | D/C |  |  | 400
|  | Remark: |  |  | Status Not Reported (UP share 1188 MW)
Santaldih TPP (250 MW),SS,WB,WBPDCL,U6-6/11(C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 38 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | LILO of Santaldih - Durgapur (I Ckt) at Asansol |  |  | WBSETCL | D/C |  |  | 220 | 80 | 152 | 152 |  |  | 152 |  | 80 |  |  |  | DEC-07 |  | Commissioned 12/07
| 2 |  |  | LILO of STPS - Arambagh at Bishnupur |  |  | WBSETCL | D/C |  |  | 220 | 4 | 11 | 11 |  |  | 11 |  | 4 |  |  |  | APR-08 |  | Commissioned 4/08
Remark:
Sasan UMPP (6x660 MW),PS,MP,Reliance,U1-5/14 (C),U2-12/13 (C),U3-5/13 (C),U4-3/14 (C),U5-8/14 (C),U6-3/15 (C)
| 1 |  |  | LILO of both ckt Vindhyachal -Jabalpur at Sasan |  |  | PGCIL | 2xD/C |  |  | 400 | 13 | 26 | 26 |  |  | 26 |  | 13 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 2 |  |  | Indore - Indore Ckt-II |  |  | PGCIL | D/C |  |  | 400 | 50 | 139 | 139 |  |  | 139 |  | 50 |  |  |  | JUN-13 |  | 2nd Ckt Commissioned 06/13.
| 3 |  |  | Satna - Bina line -I |  |  | PGCIL | S/C |  |  | 765 | 274 | 738 | 738 |  |  | 738 |  | 274 |  |  |  | JAN-12 |  | Line commissioned in Jan'12(charged at 400 KV)
| 4 |  |  | Satna - Bina line -II |  |  | PGCIL | S/C |  |  | 765 | 276 | 737 | 737 |  |  | 737 |  | 276 |  |  |  | JUN-12 |  | Commissioned 6/12
| 5 |  |  | Indore - Indore (MPPTL)(Partly) |  |  | PGCIL | D/C |  |  | 400 | 50 | 139 | 139 |  |  | 139 |  | 98 |  |  |  | MAR-12 |  | Commisisoned 03/12
| 6 |  |  | Sasaram - Fatehpur line-II |  |  | PGCIL | S/C |  |  | 765 | 355 | 954 | 954 |  |  | 954 |  | 355 |  |  |  | MAY-13 |  | Commissioned 05/13.
| 7 |  |  | Sasan - Satna line -II |  |  | PGCIL | S/C |  |  | 765 | 242 | 670 | 670 |  |  | 670 |  | 242 |  |  |  | APR-13 |  | Commissioned 4/13.
| 8 |  |  | Sasan - Satna line -I |  |  | PGCIL | S/C |  |  | 765 | 241 | 689 | 689 |  |  | 689 |  | 241 | DEC-12 |  |  | DEC-12 |  | Commissioned 12/12.
| 9 |  |  | Bina - Bina (MPPTCL) |  |  | PGCIL | D/C |  |  | 400 | 1 | 6 | 6 |  |  | 6 |  | 1 | DEC-12 |  |  | JAN-13 |  | Commissioned 01/13.
| 10 |  |  | Fatehpur- Agra line-II |  |  | PGCIL | S/C |  |  | 765 | 334 | 896 | 896 |  |  | 896 |  | 334 | DEC-12 |  |  | SEP-13 |  | Commissioned 09/13.
| 11 |  |  | Satna (2nd ICT) |  |  | PGCIL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-12 |  | Commissioned 8/12.
| 12 |  |  | Bina (ICT-II) S/S |  |  | PGCIL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 13 |  |  | Satna (1st ICT) |  |  | PGCIL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-12 |  | ICT-I Commissioned 6/12.
| 14 |  |  | Indore (1st Trf.) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUN-13 |  | Commissioned 06/13.
| 15 |  |  | Bina. S/S |  |  | PGCIL |  |  |  | 765/400 | 1000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-12 |  | Commissioned 8/12.
| 16 |  |  | Indore (2nd Trf.) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | SEP-13 |  | Commissioned 09/13.
| 17 |  |  | Gwalior |  |  | PGCIL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-13 |  | Commissioned 03/13.
Remark:
Satpura Ext TPS (250 MW),SS, MP,MPPGCL, U10-3/13 (C), U11-12/13(C)
| 1 |  |  | Ashta - Indore - II (Jetpura) |  |  | MPPTCL | S/C on D/C |  |  | 220 | 199 | 317 | 317 |  |  | 317 |  | 199 |  |  |  | FEB-15 |  | Commissioned 02/15.
| 2 |  |  | Satpura - Ashta |  |  | KPTL | D/C |  |  | 400 | 482 | 651 | 651 |  |  | 651 |  | 482 |  |  |  | MAR-15 |  | Commissioned 03/15.
| 3 |  |  | Ashta New (2nd Trf.) |  |  | MPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JAN-15 |  | Commissioned 01/15.
| 4 |  |  | Ashta (Add.) Trf. S/S |  |  | MPPTCL |  |  |  | 220/132 | 160 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | OCT-11 |  | Commissioned 10/11
| 5 |  |  | Ashta New S/S |  |  | MPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | SEP-13 |  | Commissioned 09/13.
Remark:
Sawra Kuddu HPPCL (3x37MW), U1,U2,U3 (2019-20)
| 1 |  |  | Hatkoti - Gumma |  |  | HPPTCL | D/C |  |  | 220 | 52 | 80 | 80 |  |  | 80 |  | 52 |  |  |  | AUG-18 |  | Ready for Commissioning 08/18.
| 2 |  |  | LILO of both ckt. Jhakri Abdullapur at (Gumma) Pragati Nagar |  |  | HPPTCL | D/C |  |  | 400 | 3 | 15 | 15 |  |  | 15 |  | 3 | JUN-19 |  |  | OCT-20 |  | Commissioned 10/20.
| 3 |  |  | Snail -Hatkoti |  |  | HPPTCL | D/C |  |  | 220 | 13 | 37 | 37 |  |  | 37 |  | 13 | SEP-19 |  |  | NOV-20 |  | Commissioned 11/20.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 39 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 4 |  |  | Hatkoti Switching Station |  |  | HPPTCL |  |  |  | 220 | 50 | 0 | 0 |  |  | 0 |  | 0
| 5 |  |  | Gumma S/S |  |  | HPPTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | NOV-20 |  | Commissioned 11/20.
Remark:
Scheme to relieve high loading of WR-NR Inter Regional Corridor (400 kV Bhinmal Zerda line)
| 1 |  |  | Reconductoring of 400 kV Jodhpur (Surpura) (RVPN)- Kankroli s/c (twin moose) line with twin HTLS conductor inl c. OPGW installation |  |  | PGCIL | S/C |  |  | 400 | 188 | 0 | 0 |  |  | 0 |  | 188 | MAY-24 |  |  | FEB-24 |  | Commissioned 02/24.
Remark:
Shahpurkandi Dam(3x33+3x33+1x8), Punjab, Ravi river, PSPCL (08/24)
| 1 |  |  | Shahpur Kandi PH-I - Shahpur Kandi PH-II |  |  | PSTCL | S/C on D/C |  |  | 220 | 4 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | PSTCL to fund the upfront payment for this work .
| 2 |  |  | RSD - Shahpur Kandi PH-I |  |  | PSTCL | S/C on D/C |  |  | 220 | 20 | 0 | 0 |  |  | 0
| 3 |  |  | Shahpur Kandi PG-II - Sarna with HTLS conductor of 1200 A Capacity |  |  | PSTCL | S/C on D/C |  |  | 220 | 18 | 0 | 0 |  |  | 0
| 4 |  |  | LILO of Ckt. one RSP - Sarna at Shahpur Kandi PH-I and PH-II |  |  | PSTCL | S/C on D/C |  |  | 220 | 0 | 0 | 0 |  |  | 0 |  | 0
Remark:
Shapoorji Pallonji,Kodinar,(2x660),PS,Guj, SPEPL. U1-5/15,U2-8/15
| 1 |  |  | Shapporji Pallonji TPS - Amreli |  |  | SPPCL | D/C |  |  | 400 | 107 | 339 | 330 |  |  | 292 |  | 59
| 2 |  |  | Shapoorji Pallonji generating station |  |  | GETCO | D/C |  |  | 400 | 220 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Generation not coming
| 3 |  |  | SPEL - Pirana (PG) |  |  | SPPCL | D/C |  |  | 400
Remark:
Shirpur TPP (2x150MW), Maharashtra, Shripur power, U1&2-11/17
| 1 |  |  | Shirpur Power Plant - Amalner line |  |  | MSETCL | D/C |  |  | 220 | 70 | 0 | 0 |  |  | 0 |  | 70 |  |  |  | OCT-17 |  | Commissioned 01/2017 (Late Reported).
Remark:
Shongtong Karcham HEP (3x150 MW) on Satluj river, U1,U2&U3, (04/24)
| 1 |  |  | Shongtong Karcham HEP - Wangtoo (Quad) |  |  | HPPTCL | D/C |  |  | 400 | 18 |  | 0 |  |  | 0 | [7 empty] | Preliminert Survey has been carried out and is under tendering process for the detailed Survey of the route.
| 2 |  |  | Wangtoo (GIS) S/S |  |  | HPPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | JUN-19 |  |  | OCT-19 |  | Commissioned 09/19 (Late Reported).
Remark:
Sikka TPP Extn, (2x250 MW) SS, Gujarat, GSECL, U3 -3/15 (C),U4-9/15 (C)
| 1 |  |  | Sikka - Moti Paneli line |  |  | GETCO | D/C |  |  | 220 | 157 | 259 | 259 |  |  | 259 |  | 157 |  |  |  | AUG-15 |  | Commissioned 08/15.
| 2 |  |  | LILO of Jamnagar - Jetpur line-II at Sikka |  |  | GETCO | D/C |  |  | 220 | 117 | 189 | 189 |  |  | 189 |  | 117 |  |  |  | MAR-18 |  | Commissioned 03/18.
Remark:
Simhapuri PH-I,(150 MW),PS,U2-7/12(C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 40 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Simhapuri-Nellore |  |  |  | S/C |  |  | 400 | 26 | [6 empty] | 26 |  |  |  | MAR-12 |  | Commissioned 3/12
Remark:
Singareni Colleries Generation Project (2x 600 MW), Telangana,U1-3/16 (C),U2-11/16(C)
| 1 |  |  | Singareni TPS (Jaipur TPP) - Gajwel |  |  | TSTRANS | D/C |  |  | 400 | 325 | 459 | 459 |  |  | 459 |  | 325 |  |  |  | NOV-15 |  | Commissioned 11/15.
Remark:
Singhitarai TPP (2x600 MW),PS,Chg,, Athena Chhg Power Ltd.,U1,U2-uncertain
| 1 |  |  | Athena Singhitarai - Raigarh Pooling Station (near Kotra) |  |  | ACPLT | D/C |  |  | 400 | 50 | 75 | 75 |  |  | 75 |  | 50 |  |  |  | MAY-16 |  | Commissioned 4/16 (Late Reported)
Remark:
Singoli Bhatwari HEP (3x33MW)PS,UK,L&T,U1,2,3 & 4 (03/20)
| 1 |  |  | LILO of Baramwari - Srinagar at Singoli Bhatwari |  |  | PTCUL | D/C |  |  | 220 | 5 | 0 | 0 |  |  | 0 |  | 0 | DEC-19 |  |  |  |  | Work held up due to COVID-19.
Remark:
SJK Powergen TPP (2x660 MW),PS, MP GMR, U1-12/14,U2-6/14
| 1 |  |  | SJK TPS - Jabalpur Pooling Station |  |  | XYZ | D/C |  |  | 400 | 107 | 339 | 330 |  |  | 292 |  | 59
Remark:
Solapur TPP (2x660 MW),CS, Maha, TPL, U1-4/17(c) & U2-10/18
| 1 |  |  | Sholapur STPP - Sholapur line-I |  |  | PGCIL | D/C |  |  | 400 | 22 | 35 | 35 |  |  | 35 |  | 22 | OCT-15 |  |  | APR-15 |  | Ready for commissioning 04/15.
| 2 |  |  | Bay Extn. at 400/220KV Sholapur S/stn. |  |  | PGCIL |  |  |  | 400 | 50 | 100 | 60 |  |  | 50 |  | 20 | MAR-17 |  |  | SEP-17 |  | Award placed in Jun'15. Work under progress.
Remark:
Sorang HEP (2x50 MW),PS,HP,HSPCL,U1 & U2 (03/20)
| 1 |  |  | LILO of one ckt Karcham wangto - Abdullapur at Sorang HEP |  |  | HSPPL | D/C |  |  | 400 | 7 | 11 | 11 |  |  | 11 |  | 7 |  |  |  | OCT-15 |  | Commissioned 10/15.
Remark:
Srinagar HEP, (4x82.5 MW),PS,UK,AHPC Ltd.,U1-4/15 (C) ,U2-6/15 (C), U3-4/15 (C)U4-6/15 (C)
| 1 |  |  | Srinagar HEP - Sringar 400 kV S/S. |  |  | PTCUL | D/C |  |  | 400 | 28 | 39 | 39 |  |  | 39 |  | 28 |  |  |  | JUL-16 |  | Commissioned 07/16.
| 2 |  |  | LILO of Muzaffarnagar -Vishnuprayag at Srinagar |  |  | UPPTCL | D/C |  |  | 400 | 7 | 20 | 20 |  |  | 20 |  | 7 |  |  |  | NOV-14 |  | Commissioned 11/14.
Remark:
Subansiri Lower (HEP) (8x250 MW) ,CS, ArP, NHPC, U1&2-12/19, U3&4 -06/20
| 1 |  |  | Lower Subhansiri - Biswanath Chariyali line -I |  |  | PGCIL | D/C |  |  | 400 | 354 | 480 | 480 |  |  | 480 |  | 354 | AUG-22 |  |  | FEB-23 |  | Commissioned 02/23.
| 2 |  |  | Lower Subhansiri - Biswanath Chariyali line -II |  |  | PGCIL | D/C |  |  | 400 | 371 | 515 | 515 |  |  | 515 |  | 371 | SEP-23 |  |  | DEC-23 |  | Commissioned 12/23.
|  | Remark: |  |  | The works of the project is stalled since Dec 2011 due to agitation by various pressure groups of Assam and the balance works are likely to be completed within four years after resumption of works
Suratgarh Super Critical TPS (2x660 MW),SS, Raj,RRVUNL U7-11/17,U8-3/18
| 1 |  |  | Bikaner- Merta |  |  | RVPNL | S/C |  |  | 400 | 172 | 465 | 465 |  |  | 465 |  | 172 | MAR-14 |  |  | NOV-15 |  | Commissioned 11/15.
| 2 |  |  | Suratgarh TPS- Bikaner |  |  | APL | D/C |  |  | 400 | 279 | 351 | 351 |  |  | 351 |  | 279 | JUL-18 |  |  | JUL-18 |  | Commissioned 07/18.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 41 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 3 |  |  | Suratgarh - Babai |  |  | RVPNL | D/C |  |  | 400 | 491 | 676 | 676 |  |  | 676 |  | 469 | DEC-23 |  |  |  |  | 1. Earlier Work order awarded to M/s Aster Chennai has been withdrawn at risk and cost of the firm. 2. Stay against termination of contract issued by court. 3. Matter is under the jurisdiction of court. IA Cancelled in hearing on 11.09.23. 4. For balance work revised detailed W.O. issued to M/s Kay Cee Infra & Energy on 8.4.22 W.O. short closed. 5. For balance work, W.O. issued on 15.06.24 to JV of M/s Navdurga
| 4 |  |  | GSS Babai S/S |  |  | RVPNL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-18 |  | Commissioned 03/18.
Remark:
Suzlon wind farm (100 MW), PS,Kutch, GETCO, U1-5/13
| 1 |  |  | Suzlon wind farm - Bhachau (PG) |  |  | XYZ | D/C |  |  | 220
Remark:
S V Power TPP (63 MW),PS,Cha,KVK,U1-12/11(C),
| 1 |  |  | LILO of Korba-Mopaka line at S.V. Power |  |  | SVPPL | D/C |  |  | 132 | 12 | [6 empty] | 12 |  |  |  | NOV-11 |  | Commissioned 11/11.
Remark:
Swastik TPP, (25 MW), PS,Chg, ACB, U1-12/13
| 1 |  |  | LILO of Korba-Mopka at Swastic TPP |  |  | APL | D/C |  |  | 132 | [7 empty] | 132 |  |  |  | MAR-17 |  | Commissioned
Remark:
System Strengthening
| 1 |  |  | Kukurmara - Azara line |  |  | AEGCL | S/C on D/C |  |  | 132 | 5 | 29 | 29 |  |  | 29 |  | 6 | DEC-11 |  |  |  |  | Court case pending at Loc-19. Stringing of Railway and Highway crossing left to be done.
| 2 |  |  | Surajmani Nagar - Badarghat |  |  | TSECL | D/C |  |  | 132 | 6 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Fund proposed in World Bank.
| 3 |  |  | Silchar - Melriat (New) |  |  | PGCIL | D/C |  |  | 400 | 287 | 451 | 451 |  |  | 451 |  | 287 | DEC-12 |  |  | NOV-18 |  | Commissioned 11/18.
| 4 |  |  | Silchar - Srikona line |  |  | PGCIL | D/C |  |  | 132 | 2 | 7 | 7 |  |  | 7 |  | 2 |  |  |  | MAR-12 |  | Line commissioned in Mar'12.
| 5 |  |  | Balance work of 400kV D/C Vadinar -Amreli line (PKG-III) with ACSR Twin Moose Condu. and Earth Wire M/s Jyoti |  |  | GETCO | D/C |  |  | 400 | 121 | 533 | 533 |  |  | 533 |  | 121 | JAN-24 |  |  | MAR-24 |  | Commissioned 03/24.
| 6 |  |  | Palatana - Surajmaninagar line (Charged at 132 KV) |  |  | PGCIL | D/C |  |  | 400 | 74 | 118 | 118 |  |  | 118 |  | 74 |  |  |  | JUN-12 |  | Commissioned 6/12
| 7 |  |  | Roing - Tezu line |  |  | PGCIL | S/C on D/C |  |  | 132 | 73 | 244 | 244 |  |  | 244 |  | 72 | APR-12 |  |  |  |  | Line commissioned in Jun'17.
| 8 |  |  | Udaipur - Palatana |  |  | TSECL | D/C |  |  | 132 | 12 | 41 | 41 |  |  | 413 |  | 12 |  |  |  | AUG-11 |  | Line test charged on 21.08.2011.
| 9 |  |  | 400KV D/C Gadag PS - Koppal PS Tran. line |  |  | RTVPL | D/C |  |  | 400 | 127
| 10 |  |  | Melriat (New) - Sihmui line |  |  | PGCIL | D/C |  |  | 132 | 12 | 20 | 20 |  |  | 20 |  | 12 | DEC-12 |  |  |  |  | Line commissioned in Nov'18.
| 11 |  |  | Balance work of 220 kV D/C Kalawad- Kangasiyali line with AL-59 Conductor and OPGW |  |  | GETCO | D/C |  |  | 220 | 114 | 0 | 0 |  |  | 0 |  | 114 | OCT-23 |  |  | NOV-23 |  | Commissioned11/23.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 42 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 12 |  |  | 220KV DC/SC (2-Phase) line from the existing 220/11KV LIS SS Settypalli to proposed 220/25KV RTSS Veldurthy |  |  | APTRANS | D/C+S/C |  |  | 220 | 6 | [10 empty] | MAY-23
| 13 |  |  | Surajmani nagar-P.K.Bari |  |  | TSECL | D/C |  |  | 400 | 260 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Fund not yet tied up. Proposed under World Bank Financing /SPA/NEC.
| 14 |  |  | ETPS to Tondiarpet point ATS |  |  | TANTRAN | D/C |  |  | 400 | 18 | 5 | 5 |  |  | 5 |  | 1.73 | SEP-17 |  |  |  |  | Work is under progress. Line stringing pending for want of LC.
| 15 |  |  | Extn. of new EGT supply Laying of 230kV XLPE AI UG cable for a route length of 1Km from CTT tower - Metering point inside consumer premises |  |  | TANTRAN | S/C |  |  | 230 | 1 | 0 | 0 |  |  | 0 |  | 1 |  |  |  | FEB-23 |  | Commissioned 02/23.
| 16 |  |  | KPS1-Khavda PS GIS (KPS2) 765kV D/C line |  |  | MEGHA | D/C |  |  | 765 | 42 | [7 empty] | FEB-25
| 17 |  |  | Reconductoring of exiting Single ACSR Panther Khliehriat (POWERGRID) |  |  | PGCIL | S/C |  |  | 132 | 7 | 0 | 0 |  |  | 0 |  | 7.8 | NOV-24
| 18 |  |  | Silchar - Purba Kanchan Bari line (charged at 132KV) |  |  | PGCIL | D/C |  |  | 400 | 254 | 373 | 373 |  |  | 373 |  | 254 | DEC-12 |  |  | JUL-15 |  | Commissioned 07/15.
| 19 |  |  | LILO of Korattur - Koyambedu at Alamathy (Balance Portion) |  |  | TANTRAN | D/C |  |  | 220 | 23 | [6 empty] | 23 |  |  |  | SEP-15 |  | Commissioned 09/15.
| 20 |  |  | Mariani (New) - Mokikchung (PG) |  |  | PGCIL | D/C |  |  | 220 | 97 | 163 | 163 |  |  | 163 |  | 97 | DEC-12 |  |  | JUN-15 |  | Ready for Commissioning 06/15.
| 21 |  |  | Killing (Byrnihat)-EPIP-I |  |  | MeECL | M/C |  |  | 132 | 17 | 19 | 19 |  |  | 19 |  | 21.75 | [5 empty] | 1. Date of award of contract is 18.03.2011. 2. Schedule date of completion was 18.03.2012. 3. The line was completed on 11.02.2016 and commissioned on 12.05.2017. 4. Delay was due to RoW issue, all of which have been resolved and also due to delay in commissioning of SAS at 400/220/132 kV Killing sub-station.
| 22 |  |  | LILO of Agia - Sarusajai line at Kukurmara S/S |  |  | AEGCL | D/C |  |  | 220 | 4 | 8 | 8 |  |  | 8 |  | 4 |  |  |  | SEP-12 |  | Commissioned 9/12.
| 23 |  |  | Reconductiong of Parli (PG) - Parli (M) 400kV D/C line section of above line (at SI.1) with twin HTLS conductor with a minimum capacity of 196 MVA Ckt. at a nominal voltage |  |  | PGCIL | S/C |  |  | 400 | 5 | 0 | 0 |  |  | 0 |  | 5 | AUG-23 |  |  | DEC-23 |  | Commissioned 12/23.
| 24 |  |  | Erection of 230KV SC on DC tower with ZEBRA conductor from Pudukottai 230 LV SS to Vellalaviduthy 400/230 KV SS. |  |  | TANTRAN | S/C |  |  | 230 | 51 | [10 empty] | MAY-23
| 25 |  |  | Mokokchung (PG) - Mokokchung (Nagaland) line |  |  | PGCIL | D/C |  |  | 132 | 2 | 11 | 11 |  |  | 11 |  | 2 | DEC-12 |  |  | MAR-17 |  | Line commissioned in Jul'15.
| 26 |  |  | LILO of MTPS-A - Durgapur line at Barjora s/s |  |  | DVC | S/C |  |  | 220 | 9 | 17 | 17 |  |  | 17 |  | 79 | JAN-24 |  |  | JAN-24 |  | Commissioned 01/24.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 43 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 27 |  |  | Reconductoring of Aizawal (POWERGRID) - Luangmual (Mizoram 132kV ACSR Panther S/C line with Single HTLS Conductor of 800A (at nominal Voltage Level ) |  |  | PGCIL | S/C |  |  | 132 | 1 | 0 | 0 |  |  | 0 |  |  | APR-25 |  |  |  |  | Reconductoring works completed by Dept. of Power, Mizoram, Informed/requested to CTUIL for scope deletion
| 28 |  |  | Silchar - Badarpur (PG) line. |  |  | PGCIL | D/C |  |  | 132 | 38 | 69 | 69 |  |  | 69 |  | 38 |  |  |  | APR-12 |  | Commissioned 4/12.
| 29 |  |  | LILO of Kaithalguri - Misa line at Mariani (New) (Charged at 220KV) |  |  | PGCIL | D/C |  |  | 400 | 1 | 4 | 4 |  |  | 4 |  | 1 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 30 |  |  | Laying of 400 KV 1X2500 Sq.mm XLPE UG cable from perumbakkam junction to Pallikarunai OH/UG Junction in the Sholinghanallur to Guindy 400 KV Feeder for aroute length of 8.546 Km under turnkey basis |  |  | TANTRAN | S/C |  |  | 400 | 8 | [10 empty] | MAY-23
| 31 |  |  | Silchar - Imphal (New) line (to be charged at 132KV) |  |  | PGCIL | D/C |  |  | 400 | 334 | 479 | 479 |  |  | 479 |  | 334 | DEC-12 |  |  | MAR-15 |  | Commissioned 03/15.
| 32 |  |  | LILO of Zemabawk - W.Phaileng at Sihhmui |  |  | PEDMIZO | S/C |  |  | 132 | 5 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Approval from State Govt. obtained
| 33 |  |  | LILO of 220kV Phulpur- Jhunsi 400kV Machhalishahar |  |  | UPPTCL | S/C |  |  | 220 | 99 | [10 empty] | MAY-23
| 34 |  |  | Baramwari (GIS)-Srinagar S/S |  |  | UKPCL | D/C |  |  | 220 | 180 | 228 | 210 |  |  | 182 |  | 72 | DEC-19 |  |  |  |  | Baramwari  Srinagar 220 kV D/C line and LILO of this line at Singoli Bhatwari HEP are required for transfer of power from Singoli Bhatwari HEP up to Srinagar pooling station.But after the works of Phata Byung (2x38 MW) being severely affected due to flash floods in June, 2013 and all works being stalled since July, 2017 due to Funds constraints with the developer , this Baramwari switching station is not being constructed, therefore currently above line is being constructed from 400kV S/s Srinagar to interconnection point of 99MW Singoli Bhatwari HEP.This line is of 150 Ckm out of which 72 Ckm stringing have been completed. Also out of 220 tower locations, 210 fdns have been completed and 182 towers have been erected
| 35 |  |  | Surajmani Nagar - Rokhia |  |  | TSECL | D/C |  |  | 132 | 20 | 80 | 68 |  |  | 56 |  | 7 | [5 empty] | RoW issue
| 36 |  |  | Pasighat - Roing line. |  |  | PGCIL | S/C on D/C |  |  | 132 | 102 | 347 | 347 |  |  | 347 |  | 104 | DEC-12 |  |  |  |  | Line commissioned in Jun'17.
| 37 |  |  | LILO of MTPS (A) - Borjora line at MTPS (B) |  |  | DVC | D/C |  |  | 220 | 84 | 76 | 75 |  |  | 75 |  | 78.55 | MAY-24 |  |  |  |  | Line length = 21.52KM, Route lenth = 21.52*4 = 86CKM . Stringing completed: 19.637*4=78.548CKM. Due to severe ROW problem and non-obtaining of Forest clearance. FRA received but stage I awaited. Revised date of completion changed to September'2024.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 44 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 38 |  |  | Surajmani Nagar - Budhujngnagar |  |  | TSECL | D/C |  |  | 132 | 36 | 63 | 63 |  |  | 63 |  | 36 |  |  |  | AUG-12 |  | Commissioned 08/12.
| 39 |  |  | LILO of CTPS (A) - Kalyaneswari line at RTPS |  |  | DVC | D/C |  |  | 220 | 52 | 72 | 72 |  |  | 72 |  | 52 | APR-24 |  |  | JUN-24 |  | Commissioned 06/24.
| 40 |  |  | Surajmani Nagar - Udaipur |  |  | TSECL | D/C |  |  | 132 | 50 | 50 | 0 |  |  | 0 |  | 0 | [5 empty] | Proposed under NEC.
| 41 |  |  | Stringing of 2nd Circuit from Dehar HEP of BBMB to Kangoo S/S |  |  | HPPTCL | D/C |  |  | 220 | 4 | 0 | 0 |  |  | 0 |  |  | SEP-24
| 42 |  |  | Renew Solar Power Pvt. Ltd. -Koppal PS 220kV S/C line |  |  | RENEWS | S/C |  |  | 220 | 54 | 0 | 0 |  |  | 0 |  | 54 |  |  |  | MAR-24 |  | Commissioned 03/24. (Commissioned 10/2023).
| 43 |  |  | Silchar - Hailakandi (Contingency arrangement) |  |  | PGCIL | D/C |  |  | 132 | 60 | 110 | 110 |  |  | 110 |  | 60 | [5 empty] | Part line commissioned (35Ckm) through contingency in Jun'12. Balance line commissioned in Nov'17.
| 44 |  |  | LILO of Loktak - Imphal at Imphal (New) line |  |  | PGCIL | D/C |  |  | 132 | 1 | 5 | 5 |  |  | 5 |  | 1 | DEC-12 |  |  | MAR-17 |  | Commissioned 03/13.
| 45 |  |  | Ramgarh-II SEZ PP- Fateharh-II (Twin HTLS) |  |  | PGCIL | D/C |  |  | 400 | 88 | [7 empty] | NOV-23
| 46 |  |  | Kamudhi - Kavanoor Ckt-II |  |  | TANTRAN | D/C |  |  | 230 | 56 | 229 | 229 |  |  | 229 |  | 56 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 47 |  |  | 220KV Pallantla-Guddigudem DC Line at Loc.No.54 to 400/220/11KV Guddigudem SS |  |  | APTRANS | D/C |  |  | 220 | 25 | [10 empty] | MAY-23
| 48 |  |  | Surajmani Nagar - Agartala 79 Tilla Grid S/S |  |  | TSECL | D/C |  |  | 132 | 18 | 71 | 71 |  |  | 71 |  | 18 |  |  |  | MAR-17 |  | Completed 9/13
| 49 |  |  | Gadag PS- Koppal (PS) line |  |  | RTVPL | D/C |  |  | 400 | 100 | [7 empty] | AUG-23
| 50 |  |  | Tezu - Namsai line. |  |  | PGCIL | S/C on D/C |  |  | 132 | 96 | 332 | 332 |  |  | 332 |  | 95 | DEC-12 |  |  |  |  | Line commissioned in Jul'18.
| 51 |  |  | LILO of Aizwol (PG) - Zemabawk at Melriat (PG) |  |  | PGCIL | D/C |  |  | 132 | 30 | 17 | 17 |  |  | 17 |  | 10 | DEC-12 |  |  |  |  | Line commissioned in Nov'18.
| 52 |  |  | 2-Phase Single Circuit Transmission line on D/C towers from 220 kV S/s Jafferpur to TSS Rudraupur for M/s IRCON |  |  | PTCUL | S/C |  |  | 220 | 10 | [10 empty] | MAY-23
| 53 |  |  | 1X1500MVA 765/400 KV ICT-3rd at Raigarh Kotra Section-B) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 45 |  |  | 30 |  | 0 | FEB-25
| 54 |  |  | 1X500MVA 765/400 ICT-2 at KPS-2 New S/S |  |  | PGCIL |  |  |  | 765/400 | 1500 | [7 empty] | JAN-25
| 55 |  |  | 1x500 MVA 400/220kV ICT-5 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | FEB-25
| 56 |  |  | Wathar (Addl.) |  |  | MSETCL |  |  |  | 220/33 | 50 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-17 |  | Commissioned 03/2017
| 57 |  |  | 1x500 MVA 400/220kV ICT-6 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | FEB-25
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 45 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 58 |  |  | Xeldem (Goa) S/S (G-TTPL - TBCB) |  |  | SGL |  |  |  | 400/220 | 1000 | 100 | 0 |  |  | 0 |  | 0 | JUN-24 |  |  |  |  | 1.Delay due to occurrence of Force Majeure (FM) event i.e. outbreak of COVID-19 and this FM event has been intimated to all LTTCs 2. The construction work will be started after getting Conversion Sanad order from Revenue authorities. The construction License from Gram Panchayat, Molem has been received on 13 Nov 2020. 3.The progress is suffered due to petition filed by Goa Foundation in Central Empowered Committee (CEC) constituted by Supreme court and High Court of Mumbai and Goa
| 59 |  |  | Narendra New (upgradation to its rated voltage of 765 Kv along with 4x1500 MVA T/F) |  |  | APL |  |  |  | 765/400 | 6000 | [7 empty] | DEC-24
| 60 |  |  | Namsai S/S |  |  | PGCIL |  |  |  | 132/33 | 30 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned in Jul'18.
| 61 |  |  | Khavda PS1 Augmentation |  |  | MEGHA |  |  |  | 765/400 | 6000 | [7 empty] | JAN-25
| 62 |  |  | 1X1500MVA 765/400KV ICT-1 at Kurnool (III) (AP) -Part-A and Part-B |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 25 |  |  | 25 |  | 0 | JAN-25
| 63 |  |  | 1X500MVA 765/400 ICT-1 at KPS-2 New S/S |  |  | PGCIL |  |  |  | 765/400 | 1500 | [7 empty] | DEC-24
| 64 |  |  | 1X500 MVA 400/220KV ICT-5 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 65 |  |  | 50 |  | 20 | DEC-24
| 65 |  |  | 1X500 MVA 400/220KV ICT-4 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 65 |  |  | 50 |  | 20 | DEC-24
| 66 |  |  | Roing S/S |  |  | PGCIL |  |  |  | 132/33 | 30 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Commissioned in Jun'17.
| 67 |  |  | Augmentation of 400/220 KV Gadag S/S with 3x500 MVA ICT |  |  | RTVPL |  |  |  | 400/220 | 1500 | [7 empty] | MAY-24
| 68 |  |  | 1x500 MVA 400/220kV ICT-7 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | MAR-25
| 69 |  |  | 1x 500MVA 765/400kV ICT-1 at Fatehgarh-3 (New Section) |  |  | POWERIC |  |  |  | 765/400 | 1500 | [7 empty] | FEB-25
| 70 |  |  | 1X500 MVA, 400/220 kV ICT-2 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E) |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | JUL-24 |  |  | JUL-24 |  | Commissioned 07/24.
| 71 |  |  | 1x1500 MVA 765/400kV ICT-1 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 60 |  |  | 35 |  | 15 | DEC-24
| 72 |  |  | 1x500 MVA 400/220kV ICT-1 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | JAN-25
| 73 |  |  | 1X500 MVA 400/220 kV ICT-1 at Bikaner-II PS (Phase-IV (Part 1) Bikaner Complex- PART E |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | JUN-24 |  |  | MAY-24 |  | Commissioned 05/24.
| 74 |  |  | 1x500 MVA 400/220kV ICT-3 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | JAN-25
| 75 |  |  | 1x500 MVA 400/220kV ICT-8 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | MAR-25
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 46 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 76 |  |  | 1X1500 MVA 765/400KV ICT-2 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 85 |  |  | 85 |  | 55 | JUL-24
| 77 |  |  | Tezu S/S |  |  | PGCIL |  |  |  | 132/33 | 30 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Charged in Jun'17.
| 78 |  |  | DSTPS ICT-II S/s |  |  | DVC |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | JAN-21 |  |  | FEB-21 |  | Commissioned 02/21.
| 79 |  |  | 1x500 MVA 400/220kV ICT-4 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | FEB-25
| 80 |  |  | Yurembam (Aug.) S/S |  |  | ED, |  |  |  | 132/33 | 90 | 100 | 0 |  |  | 0 |  | 0
| 81 |  |  | 1x1500 MVA 765/400kV ICT-2 at Sikar-II s/s (Rajasthan (8.1 GW) under phase-II- Part C) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 60 |  |  | 35 |  | 15 | DEC-24
| 82 |  |  | Panchgram (Aug.) S/S |  |  | AEGCL |  |  |  | 132/33 | 50 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | DEC-11 |  | Commissioned 12/11
| 83 |  |  | 1X500MVA 765/400 ICT-2 at KPS-3 New S/S |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 25 |  |  | 20 |  | 0 | MAR-25
| 84 |  |  | 1x1500MVA 765/400 4th ICT Bikaner (PG) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 45 |  |  | 55 |  | 0 | DEC-24
| 85 |  |  | 1x500 MVA 400/220kV ICT-2 at Kurnool PS (Part-A and Part-B |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 25 |  |  | 25 |  | 0 | JAN-25
| 86 |  |  | Surajmaninagar S/S (Upgrdable to 400 kV) |  |  | TSECL |  |  |  | 132/33 | 100 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | DEC-12 |  | Commissioned 12/12
| 87 |  |  | 1X1500 MVA 765/400KV ICT-3 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 85 |  |  | 85 |  | 55 | JUL-24
| 88 |  |  | 1X1500MVA 765/400KV ICT (4th) at 765/400KV Bhadla-II PS (Phase -II Part -BI) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 90 |  |  | 85 |  | 85 | JUN-24 |  |  |  |  | Transformer diverted to other site where RE generation was coming up.
| 89 |  |  | 1X1500MVA 765/400KV ICT-2 at Kurnool (III) (AP) -Part-A and Part-B |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 25 |  |  | 25 |  | 0 | FEB-25
| 90 |  |  | 1X500MVA 765/400 ICT-1 at KPS-3 New S/S |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 25 |  |  | 20 |  | 0 | FEB-25
| 91 |  |  | Vapi (Ambheti) (Vapi-II) (VNLTL-TBCB) |  |  | SGL |  |  |  | 400/220 | 1000 | 0 | 0 |  |  | 0 |  | 0 | MAY-24
Remark:
System Strengthening Scheme for Eastern and North Eastern Regions (ER NER Transmission Limited)
| 1 |  |  | 1X500MVA ICT-1 at Banka S/S along with Extn. of 400KV AIS Switch. and creation of 220KV GIS at Banka |  |  | PGCIL |  |  |  | 400/220 | 500 | 100 | 95 |  |  | 50 |  | 50 | OCT-24
| 2 |  |  | Extn. of 132kV AIS switchyard and Upgradation of existing 132kV Namsai (POWERGRID) S/s |  |  | PGCIL |  |  |  | 220/132 | 320 | [7 empty] | OCT-25
Remark:
Talwandi Sabo TPP (3x660MW),PS,Punjab, Sterlite, U1-6/14 (C),U2-10/15 (C),U3-03/16 (C)
| 1 |  |  | Talwandi Sabo - Moga |  |  | PSTCL | D/C |  |  | 400 | 204 | 287 | 287 |  |  | 287 |  | 204 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 2 |  |  | Moga- Nakodar |  |  | PSTCL | D/C |  |  | 400 | 128 | 178 | 178 |  |  | 178 |  | 128 |  |  |  | APR-14 |  | Commissioned 04/14.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 47 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 3 |  |  | Talwandi Sabo - Dhuri |  |  | PSTCL | D/C |  |  | 400 | 175 | 250 | 250 |  |  | 250 |  | 175 |  |  |  | JAN-13 |  | Commissioned 01/13. (Line energised on 21.8.12 but intimated in Jan 2013)
| 4 |  |  | Talwandi Sabo-Mukatsar |  |  | PSTCL | D/C |  |  | 400 | 201 | 277 | 277 |  |  | 277 |  | 201 |  |  |  | SEP-14 |  | Commissioned 09/14.
| 5 |  |  | Nakodar (1st Trf.) |  |  | PSTCL |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | APR-14 |  | Commissioned 04/14.
| 6 |  |  | Mukatsar (2x315) |  |  | PSTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | JAN-13 |  |  | SEP-14 |  | Commissioned 09/14.
Remark:
Tamnar TPP (4x600 MW),PS,Chatt,JPL, U1-3/14 (C),U2-3/14 (C),U3-1/15 (C),U4-3/15 (C)
| 1 |  |  | Tamnar TPP - Raigarh (Tamnar) Pooling Station |  |  | JPL | 2xD/C |  |  | 400 | 44 | 67 | 67 |  |  | 67 |  | 44 |  |  |  | JAN-15 |  | Commissioned 01/15.
Remark:
Tanda Extn. (2x660 MW), CS,UP, NTPC,U1-3/19,U2-7/19
| 1 |  |  | Tanda TPS Extn- Basti (Q) |  |  | UPPTCL | S/C |  |  | 400 | 43 | 137 | 137 |  |  | 137 |  | 87.72 | OCT-19 |  |  |  |  | Line energised on 14/03/2021. To be deleted.
| 2 |  |  | Tanda TPS Extn - Gonda |  |  | SEUPPTCL | S/C |  |  | 400 | 100 | 241 | 97 |  |  | 54 |  | 0 | [5 empty] | "Work is standstill for more than a year due to poor financial health of SEUPPTCL, the transmission service provider, owned by M/s Isolux. The line is a part of TBCB project awarded to M/s Isolux. UPPTCL representative informed that GoUP is considering to take over transmission project and evaluation of completed work is under progress. Bids for valuers have been invited by M/s PFC. Valuation is under progress. Final decision will be taken after valuation."
| 3 |  |  | Gonda - Shahjehanpur (PG) |  |  | UPPTCL | D/C |  |  | 400 | 460 | 543 | 296 |  |  | 140 |  | 0 | [5 empty] | To being constructed in TBCB mode
| 4 |  |  | Tanda (NTPC) - Tanda (New) line |  |  | UPPTCL | D/C |  |  | 220 | 42 | 94 | 94 |  |  | 94 |  | 42.08 |  |  |  | FEB-19 |  | Commissioned 02/19.
| 5 |  |  | LILO of Azamgarh - Sultanpur at Tanda TPS Extn. |  |  | UPPTCL | D/C |  |  | 400 | 133 | 206 | 206 |  |  | 206 |  | 133 |  |  |  | MAR-19 |  | Ready for Commissioning 03/19.
| 6 |  |  | Gonda |  |  | UPPTCL |  |  |  | 400/220 | 630 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Developed by M/s Isolux under TBCB S/s is complete and energised at 220 kV since 2016
| 7 |  |  | Tanda TPS |  |  | UPPTCL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | To be deleted. Both ICTs are energised in Mar-19.
| 8 |  |  | Basti (GIS) (T/F-I) |  |  | UPPTCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | JUN-21 |  |  | JAN-22 |  | Commissioned 10/21 (Late Reported).
Remark:
Tangnu Romai-I HEP (2x22MW)PS,HP,U1 & U2 (2021-22)
| 1 |  |  | Sunda-Hatkoti |  |  | HPPTCL | D/C |  |  | 220 | 50 | 69 | 69 |  |  | 69 |  | 50 | MAY-22 |  |  | JUN-22 |  | Commissioned 06/22.
| 2 |  |  | Tangnu Romai-I HEP - 220/132 kV Sunda S/S |  |  | HPPTCL | D/C |  |  | 132 | 24 | 37 | 25 |  |  | 17 |  | 5 | [5 empty] | work is progress and all efforts have been made to complete the work by Dec-21.
| 3 |  |  | Sunda S/S |  |  | HPPTCL |  |  |  | 220/132 | 200 | 100 | 100 |  |  | 100 |  | 100 | MAY-22 |  |  | AUG-22 |  | Commissioned 08/22.
|  | Remark: |  |  | Project work stopped due to fund issue.
Tapovan Vishnugad HEP (4x130MW), CS,UK,NTPC,U1-4 (12/20)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 48 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Tapovan (Vishnugad) - Pipalkoti |  |  | PTCUL | D/C |  |  | 400 | 36 | 48 | 13 |  |  | 4 |  |  | MAR-23 |  |  |  |  | Final approval on forest proposal was accorded on dt 21.07.2020. Natural calamity happened on dt.07.02.2021in Joshimath,Dist Chamoli at Rishi Ganga, which also affected the NTPC HEP. Revised commissioning schedule of Tapovan-Vishnugad HEP is awaited from NTPC.
| 2 |  |  | Kuwari Pass (Pipalkoti)-Karanprayag -Srinagar(Khandukhal) |  |  | PTCUL | D/C |  |  | 400 | 184 | 220 | 45 |  |  | 0 |  | 0 | [5 empty] | Contract awarded in 03 no. packages in Sep 2017. Forest proposal had been submitted on dated 24.11.2018 for Package-I, on dated 23/10/2018 for Package-II and on dated 23/02/2019 for Package-III. Stage-I clearance of forest case for Package I, II and III is expected by Oct'19, Oct'19 and Nov'19 resp. Construction work of line will be started after approval of stage-I clearance of forest.
| 3 |  |  | Srinagar(Khandukhal)-Kashipur(Rampura) |  |  | PTCUL | D/C |  |  | 400 | 362 | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | Implementation of line to be taken up under central sector as an ISTS scheme with the matching timeframe of commissioning of Vishnugad -Pipalkoti(HEP) of THDC i.e June 2023 or Tapovan-Vishnugad HEP of NTPC whichever is earlier as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21.
| 4 |  |  | LILO of Vishnu Prayag - Muzaffarnagar at Tapovan Vishnugarh HEP |  |  | PTCUL | D/C |  |  | 400 | 2 | 0 | 0 |  |  | 0 | [7 empty] | Approval is pending in Standing Committee, CEA. Construction of Transmission line will be planned after due approval from competent authority.
Remark:
Tashiding HEP (2x48.5MW)PS,Sikkim,Shiga Energy,U1-11/17,U2-11/17
| 1 |  |  | Tashiding - Legship |  |  | SEPL | D/C |  |  | 220 | 17 | 23 | 23 |  |  | 23 |  | 17 |  |  |  | MAR-18 |  | Commissioned 11/17 (Late Reported).
| 2 |  |  | Legship - New Malli |  |  | SIKKIM | D/C |  |  | 220 | 20 | 35 | 35 |  |  | 35 |  | 20 |  |  |  | JUN-18 |  | Commissioned 10/17 (Late Reported).
| 3 |  |  | Legship S/S |  |  | PGCIL |  |  |  | 220/132 | 100 | 0 | 0 |  |  | 0 |  | 0
Remark:
Teesta-III(6x200 MW),PS,Sikkim,TUL,U1to6- 2/17 (C)
| 1 |  |  | LILO OUT of Teesta-III - Kishanganj at Rangpo |  |  | PGCIL | D/C |  |  | 400 | 15 | 35 | 35 |  |  | 35 |  | 23 | JUN-20 |  |  |  |  | Work affected due to RoW in stringing at one section due to Tashi Choling trust. Progress also affected due to COVID-19 restrictions. Lockdown extended upto 14.07.2021.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 49 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Teesta III - Kishanganj |  |  | TUL | D/C |  |  | 400 | 427 | 590 | 586 |  |  | 581 |  | 391.8 | [5 empty] | Teesta III  Rangpo (CKT-II) and Teesta III  Dikchu (Ckt 1(a)) Lines are in commercial operation from 16.01.2017 & 14.04.2017 respectively. Dikchu- Rangpo (Ckt 1 (b)) is energized on 30.06.2018 (i.e. trial operation for 24 hours) and could successfully complete the trial operation on 1st July 2018. 46.1 Kms line from Kishanganj Substation has been successfully energized for antitheft purpose. Re-Stringing works, in last span of 290-291 is under progress and back charging would be extended stretch by stretch on completion of re-stringing. RoW and Forest issues faced in Darjeeling distt.
| 3 |  |  | LILO IN of Both Ckt Teesta-III - Kishanganj at Rangpo |  |  | PGCIL | MC+D/C |  |  | 400 | 21 | 36 | 36 |  |  | 36 |  | 21 | NOV-13 |  |  | JUL-16 |  | Commissioned 03/16..(Late Reported).
Remark:
Teesta LD IV HEP (4x40 MW),CS,WB,NHPC,U1:03/16, U2:03/16(C), U3-7/16 (C),U4-8/16 (C)
| 1 |  |  | Teesta LDP -III - Teesta LDP-IV |  |  | WBSETCL | S/C |  |  | 220 | 21 | 94 | 94 |  |  | 94 |  | 21 | SEP-08 |  |  | SEP-18 |  | Ready for Commissioning 09/18.
| 2 |  |  | Teesta LDP - IV - New Jalpaiguri (NJP) |  |  | WBSETCL | D/C |  |  | 220 | 145 | 250 | 250 |  |  | 250 |  | 145 | SEP-08 |  |  | FEB-16 |  | Commissioned 02/16.
|  | Remark: |  |  | Unit-4 (40MW) commissioned on 11.08.2016.
Teesta Low Dam III (4x33 MW),CS,WB,NHPC, U1-1/13(C) ,(C) U2-1/13(C), U3-2/13(C), U4/13(C)
| 1 |  |  | Teesta LD III-New Jalpaiguri |  |  | WBSETCL | S/C |  |  | 220 | 81 | 282 | 282 |  |  | 282 |  | 81 | DEC-09 |  |  | JAN-13 |  | Commissioned 01/13.
Remark:
Teesta-VI HEP (4x125 MW), PS, M/S LANCO Urja, SIKKIM,U1-4 (2021-22)
| 1 |  |  | Teesta VI HEP - Rangpo Pooling Station |  |  | LEPP | D/C |  |  | 220 | 25 | [12 empty] | Detail survey completed section 164 approval received. Work yet to started.
Remark:
Tehri PSS (THDC) (4x250 MW) U1-4 (06/22)
| 1 |  |  | Tehri Gen. - Tehri Pooling Station |  |  | PGCIL | S/C |  |  | 400 | 13 | 38 | 38 |  |  | 38 |  | 13 | NOV-17 |  |  | JAN-21 |  | Commissioned 01/21.
| 2 |  |  | Tehri Pooling Station - Meerut (Remaining part) |  |  | PGCIL | S/C |  |  | 765 | 1 | 8 | 8 |  |  | 8 |  | 1 | NOV-17 |  |  | APR-20 |  | Commissioned 04/20.
| 3 |  |  | Extn at Meerut substation |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 | MAY-20 |  |  | JUN-20 |  | Commissioned 07/20.
| 4 |  |  | Tehri PS (GIS) (3 ICTs) |  |  | PGCIL |  |  |  | 765/400 | 2400 | 100 | 100 |  |  | 100 |  | 100 | MAR-18 |  |  | APR-20 |  | Commissioned 04/20.
Remark:
Telangana STPP (2x800 MW), Telangana, NTPC, U1-01/20, U2-01/20
| 1 |  |  | Telangana STPP - Ramadugu |  |  | TSTRANS | D/C |  |  | 400 | 104 | 161 | 161 |  |  | 161 |  | 104 | DEC-19 |  |  | AUG-21 |  | Commissioned 08/21.
| 2 |  |  | Telangana STPP - Narsapur |  |  | TSTRANS | D/C |  |  | 400 | 354 | 492 | 492 |  |  | 492 |  | 354 | DEC-19 |  |  | AUG-21 |  | Commissioned 08/21.
Remark:
Thamminapatnam (Meenakshi) (2x150, MW ),PS, Ph-II (U3-12/17,U4-3/18)
| 1 |  |  | Thamminapatnam (Meenakshi) -Nellore |  |  |  | S/C |  |  | 400 | 26 | [6 empty] | 26 |  |  |  | MAR-12 |  | Commissioned 3/12
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 50 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Meenakshi - Simhapuri |  |  |  | D/C |  |  | 400 | 2 | [6 empty] | 2 |  |  |  | MAR-12 |  | Commissioned 3/12
Remark:
Tidong-I HEP (2x50MW)PS,HP,NSL,U1 & U2 (10/21)
| 1 |  |  | LILO of Kasang - Bhbaba at Tidong-I |  |  | NSLNPPL | D/C |  |  | 220 | 32 | 57 | 44 |  |  | 40 | [7 empty] | Being Executed by M/s Statkraft. St-II clearance obtained for 17 locations in Nov-22.
Remark:
Tilaiya UMPP
| 1 |  |  | LILO of Tilaiya - Balia line at Gaya |  |  | PGCIL | D/C |  |  | 765
Remark:
Tiroda TPP (Gondia ) PH-I (2x660 MW),PS,MAHA,ADANI,U1-9/12, (C),U2-11/12 ,PH II (3x660 MW) U1-6/13(C), U2- 3/14(C),U3-9/14 (C)
| 1 |  |  | Tiroda - Koradi - Akola - Aurangabad line ckt-II |  |  | APL | S/C |  |  | 765 | 575 | 1582 | 1582 |  |  | 1582 |  | 575 | AUG-12 |  |  | MAR-15 |  | Commissioned 03/15.
| 2 |  |  | Akola- I - Akola-II |  |  | APL | D/C |  |  | 400 | 61 | 90 | 90 |  |  | 90 |  | 61 |  |  |  | FEB-14 |  | Commissioned 02/14.
| 3 |  |  | Tiroda - Akola-II |  |  | APL | S/C |  |  | 765 | 361 | 1011 | 1011 |  |  | 1011 |  | 361 |  |  |  | FEB-14 |  | Commissioned 02/14.
| 4 |  |  | Aurangabad - III - Aurangabad (PG) |  |  | PGCIL | 2xS/C |  |  | 765
| 5 |  |  | Tiroda TPP - Warora (2nd ckt) |  |  | APL | D/C |  |  | 400 | 218 | 587 | 587 |  |  | 587 |  | 218 |  |  |  | AUG-12 |  | 218 Ckm Commissioned 8/12
| 6 |  |  | Tiroda TPP -Warora (1st ckt) |  |  | APL | S/C |  |  | 400 | 218 | 587 | 587 |  |  | 587 |  | 218 |  |  |  | MAR-13 |  | Commissioned 3/13.
| 7 |  |  | Koradi - III S/S |  |  | APL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-15 |  | Commissioned 03/15.
| 8 |  |  | Warora S/S |  |  | MSETCL |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | SEP-12 |  |  | MAR-13 |  | Commissioned 03/13.
| 9 |  |  | Tiroda S/S |  |  | APL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-14 |  | Commissioned 02/14.
| 10 |  |  | Aurangabad - III (Ektuni) S/S (ICT-II) |  |  | MSETCL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-16 |  | Commissioned 03/16.
| 11 |  |  | Akola -II S/S |  |  | APL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-14 |  | Commissioned 02/14.
Remark:
Tori TPP (2x600 MW),PS,Jhh, Essar, Uncertain
| 1 |  |  | Tori - Jhharkhand Pooling Station |  |  | EPTCL | D/C |  |  | 400
|  | Remark: |  |  | Delay in grant of mega power project status, cancellation of coal block & non-availability tapering/long term coal linkage etc.
Transmission Network Expansion in Gujarat associated with integration of RE projects from Khavda potential RE zone (KHAVDA RE TRANSMISSION LIMITED)
| 1 |  |  | Banskantha-Ahemadabad line |  |  | PGCIL | D/C |  |  | 765 | 269 | 362 | 143 |  |  | 45 |  |  | MAR-25 |  |  |  |  | Patan Dist.: Section 16 (1) Orders awaited: 30 locs. Mehsana: Orders awaited: 04 locs. Ahmedabad: Orders awaited: 29 locs.
Remark:
Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part B
| 1 |  |  | Magarwada (GIS) - Kala (GIS) 400 kV D/C line |  |  | PGCIL | D/C |  |  | 400 | 89 | 149 | 71 |  |  | 13 |  |  | DEC-24 |  |  |  |  | Gujarat: Valsad Dist. Orders awaited: 01 loc. Maharashtra: RoW are being faced at 30 locs. in palghar Dist. Farmers/landowners are demanding rate revision of land compensation.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 51 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Navsari (New) (South Gujurat) (GIS) - Magarwada (GIS)400kV D/C line |  |  | PGCIL | M/C |  |  | 400 | 385 | 266 | 235 |  |  | 115 |  |  | DEC-24 |  |  |  |  | Daman: Section 16(1) Orders awaited: 04 locs. Navsari Dist.: Section 16 (1) Orders awaited: 3 locs. Valsad Dist. Section 16(1) Orders awaited: 06 locs.
| 3 |  |  | Navsari (New (South Gujarat) (GIS) - Padghe (GIS) 765 kV D/C line |  |  | PGCIL | D/C |  |  | 765 | 453 | 616 | 331 |  |  | 136 |  | 5.57 | DEC-24 |  |  |  |  | Navsari Dist.: Section 16 (1) Orders awaited: 24 locs. Valsad: Orders awaited: 01 loc. ROW issues are being faced in 13 locations in Palghar & 29 locatrions in Thane district in construction of 765 kV D/C Navsari (New) - Padghe (GIS) TL of Maharashtrafor portion. Farmers/landowners are demanding high compensation.
| 4 |  |  | Ext at 765/400kV Padghe (GIS) PG SS (2 no. 400kV line bays) (1x1500MVA 765/400kV ICT) |  |  | PGCIL |  |  |  | 765/400 | 1500 | [7 empty] | FEB-24
| 5 |  |  | Establishment of 765/400/220 kV Navsari (new) (South Gujarat) S/s (GIS) (2x1500MVA 765/400kV ICT-I |  |  | PGCIL |  |  |  | 765/400 | 3000 | [7 empty] | JUN-23
| 6 |  |  | Establishment of 400/220 kV Navsari (new) (South Gujarat) S/s (GIS) (2x1500MVA 765/400kV ICT-I |  |  | PGCIL |  |  |  | 400/220 | 1500 | [7 empty] | JUN-23
Remark:
Transmission Network Expansion in Gujarat to increase its ATC from ISTS Part C
| 1 |  |  | 400kV D/C Banaskantha- Sankhari line (2nd ckt. ) |  |  | PGCIL | D/C |  |  | 400 | 45 | 59 | 44 |  |  | 13 |  |  | JUN-23 |  |  |  |  | Patan dist.: Section 16 (1) Orders awaited: 1 loc.
| 2 |  |  | 765/400kV Bansakantha (PG) SS Extension (1x1500MVA 765/400kV ICT) |  |  | PGCIL |  |  |  | 765/400 | 1500 | [7 empty] | MAR-25
Remark:
Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part B (SPV Name: KHAVDA II-B TRANSMISSION LIMITED)
| 1 |  |  | 765kV D/C Lakadia PS- Ahmedabad line |  |  | PGCIL | D/C |  |  | 765 | 368 | 474 | 115 |  |  | 21 |  |  | MAR-25 |  |  |  |  | RoW Issues are being faced at 113 locs. in Morbi Dist., 43 locs. in Surendranagar Dist.
Remark:
Transmission scheme for evacuation of 4.5GW RE injection at Khavda PS under Phase II- Part C (SPV Name: KHAVDA II-C TRANSMISSION LIMITED)
| 1 |  |  | 765kV D/C Ahemdabad- South Gujrat (New Navsari ) line |  |  | PGCIL | D/C |  |  | 765 | 577 | 807 | 231 |  |  | 52 |  |  | MAR-25 |  |  |  |  | RoW Issues are being faced at 32 locs. in Navsari Dist., 68 locs. in Bharuch Dist., 14 Locs. in Vadodara Dist., 119 Locs. in Surat Dist., 59 Locs. in Ahmedabad dist., 60 locs. in Anand dist. & 7 Locs. in Kheda dist.
| 2 |  |  | 765/400kV 3x1500MVA Ahmedabad New SS |  |  | PGCIL |  |  |  | 765/400 | 45000 | [7 empty] | MAR-25
Remark:
Transmission system associated with IPPs of Nagapattinam / Cuddalore Area- Package A (TBCB)
| 1 |  |  | Nagapattinam PS - Salem (PNMTL-TBCB) |  |  | PGCIL | D/C |  |  | 765 | 406 | 543 | 543 |  |  | 543 |  | 406 | MAR-15 |  |  | OCT-16 |  | Commissioned 10/2016.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 52 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 2 |  |  | Salem - Madhugiri (PNMTL-TBCB) |  |  | PGCIL | S/C |  |  | 765 | 219 | 575 | 575 |  |  | 575 |  | 219 | DEC-15 |  |  | JAN-19 |  | Commissioned 01/19.
|  | Remark: |  |  | SPV/BPC - Powergrid Nagapattinam Transmission Ltd. / PFC
Transmission System Associated with Mauda Stage-II (2x660MW) Gen. Proj. - PGCIL
| 1 |  |  | Mauda-II - Betul (Quad) line |  |  | PGCIL | D/C |  |  | 400 | 393 | 551 | 551 |  |  | 551 |  | 393 | MAY-16 |  |  | JUL-17 |  | Commissioned 07/2017.
| 2 |  |  | Betul - Khandwa (Quad) line |  |  | PGCIL | D/C |  |  | 400 | 338 | 435 | 435 |  |  | 435 |  | 338 | MAY-16 |  |  | AUG-16 |  | Ready for Commissioning 08/16.
| 3 |  |  | Khandwa - Indore line |  |  | PGCIL | D/C |  |  | 400 | 344 | 479 | 479 |  |  | 479 |  | 344 | MAY-16 |  |  | AUG-16 |  | Ready for Commissioning 08/16.
Remark:
Transmission System Associated with Mundra Ultra Mega Power Project - PGCIL
| 1 |  |  | Mundra -Limbdi ( part Line) |  |  | PGCIL | S/C |  |  | 400 | 384 | [6 empty] | 192 |  |  |  | NOV-11 |  | 192 Ckm part line commissioned 11/11.
| 2 |  |  | Bachchau - Ranchodpura |  |  | PGCIL | D/C |  |  | 400 | 566 | 755 | 755 |  |  | 755 |  | 566 |  |  |  | SEP-11 |  | Commissioned 9/11.
| 3 |  |  | Mundra - Jetpur (Balance portion) |  |  | PGCIL | S/C |  |  | 400 | 358 | 918 | 918 |  |  | 918 |  | 358 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 4 |  |  | Mundra - Limbdi |  |  | PGCIL | D/C |  |  | 400 | 244 | 863 | 863 |  |  | 863 |  | 244 |  |  |  | FEB-12 |  | Commissioned 02/12.
| 5 |  |  | Mundra - Bachchau |  |  | PGCIL | D/C |  |  | 400 | 198 | 285 | 285 |  |  | 285 |  | 198 |  |  |  | AUG-11 |  | Commissioned 8/11
| 6 |  |  | Mundra - Jetpur (Part line) |  |  | PGCIL | S/C |  |  | 400 | 314 | 424 | 424 |  |  | 424 |  | 314 |  |  |  | AUG-12 |  | Commissioned 8/12.
| 7 |  |  | Wardha |  |  | PGCIL |  |  |  | 765/400 | 3000 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | FEB-12 |  | Commissioned 02/12.
| 8 |  |  | Navsari GIS |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JUL-12 |  | Commisisoned 7/12
| 9 |  |  | Bachchau S/S |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-11 |  | Commissioned.
| 10 |  |  | Wardha 3rdTrf |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-12 |  | commissioned 3/12.
Remark:
Transmission System associated with Pallatana gas Based Power Project and Bongaigaon Thermal Power Station (BTPS) - PGCIL
| 1 |  |  | Imphal S/S |  |  | PGCIL |  |  |  | 132/33 | 100 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | ICT-I (50MVA) commissioned in Mar'13 & ICT-II commissioned in Apr'13.
| 2 |  |  | Mokokchung (ICT-II) |  |  | PGCIL |  |  |  | 220/132 | 30 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-15 |  | Commissioned 08/15.
| 3 |  |  | Silchar (New) |  |  | PGCIL |  |  |  | 400/220 | 400 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | MAR-12 |  | Commissioned 3/12.
| 4 |  |  | Mokokchung (New) |  |  | PGCIL |  |  |  | 220/132 | 30 | 100 | 100 |  |  | 100 |  | 100 | DEC-12 |  |  | JUL-15 |  | Commissioned 07/15.
| 5 |  |  | Melriat S/S (Upgadable to 400 kV) |  |  | PGCIL |  |  |  | 132/33 | 100 | 100 | 100 |  |  | 100 |  | 100 | [5 empty] | Completed on 28.11.18.
Remark:
Transmission system for evacuation of power from Neemuch Solar Park (1000 MW): SPV Name: Neemuch Transmission Limited (NTL)
| 1 |  |  | Neemuch PS - Mandsaur s/s 400kV D/C line |  |  | PGCIL | D/C |  |  | 400 | 236 | 0 | 0 |  |  | 0 |  | 236 | FEB-24 |  |  | MAR-24 |  | Commissioned 03/24.
| 2 |  |  | Neemuch PS - Chhittorgarh (PG) s/s 400kV D/C line |  |  | PGCIL | D/C |  |  | 400 | 233 | 0 | 0 |  |  | 0 |  | 233 | FEB-24 |  |  | MAR-24 |  | Commissioned 03/24.
| 3 |  |  | 2x500MVA ICT 1 and 2 at Neemuch under Trans. system for evacuation of power from Neemuch Solar Park |  |  | PGCIL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | FEB-24 |  |  | MAR-24 |  | Commissioned 03/24.
Remark:
Transmission system for evacuation of Power from Pakaldul HEP in Chenab Valley HEPs - LTA System
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 53 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | 2nd Circuit of Kishenpur - Dulhasti 400kV D/c (Q) line (Kishtwar - Kishenpur Section) |  |  | PGCIL | S/C |  |  | 400 | 130 | 29 | 21 |  |  | 17 |  | 73.15 | MAR-25
Remark:
Transmission system for evacuation of power from REZ in Rajasthan (20GW) under Phase-III Part J
| 1 |  |  | 765/400kV 1x1500MVA Transformer (5th) at Bhadla-2 PS (Rajasthan (20GW) under Phase-III Part J) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 0 | 0 |  |  | 0 |  | 0 | MAR-25
Remark:
Transmission System for Karur Pooling Station (at a location in between Karur Wind zone and Tiruppur wind zone) along with LILO of both circuits of Pugalur  Pugalur (HVDC) 400 kV D/C line (with Quad Moose ACSR Conductor) at Karur PS
| 1 |  |  | LILO of both Ckts. of Pugalur-Pugalur (HVDC) (with Quad Moose ACSR conductor) at Karur PS |  |  | APL | D/C |  |  | 400 | 9 | 0 | 0 |  |  | 0 |  | 9 | JUL-23 |  |  | OCT-23 |  | Commissioned 10/23.
| 2 |  |  | 2x500MVA (400/230 kV) Karur Pooling Station |  |  | APL |  |  |  | 400/230 | 1000 | 100 | 100 |  |  | 100 |  | 100 | JUL-23 |  |  | OCT-23 |  | Commissioned 10/23.
Remark:
Transmission System for Kurnool Wind Energy Zone/ Solar Energy Zone (AP)  Part-A & Part-B
| 1 |  |  | Kurnool - III - Maheshwaram (PG) (PGCIL-RTM) |  |  | PGCIL | D/C |  |  | 765 | 504 | 673 | 345 |  |  | 48 |  |  | MAR-25 |  |  |  |  | Forest: 26.993 Ha: Stage-I Approval Pending
| 2 |  |  | Kurnool-III-Kurnool (New) (PGCIL)-RTM) (AP) - Part-A and Part-B |  |  | PGCIL | D/C |  |  | 765 | 225 | 299 | 175 |  |  | 35 |  |  | MAR-25 |  |  |  |  | Length of the line is to be provided.
| 3 |  |  | Establishment of 765/400/220 kV Kurnool-III (new)(9x500MVA 400/220kV ICT ) |  |  | PGCIL |  |  |  | 400/220 | 4500 | [7 empty] | NOV-24
| 4 |  |  | Establishment of 765/400/220 kV Kurnool-III (new) (3x1500MVA 765/400kV ICT ) |  |  | PGCIL |  |  |  | 765/400 | 45000 | [7 empty] | NOV-24
Remark:
Transmission system for power evacuation from Arun-3 (900MW) HEP, Nepal of M/s SAPDC-Indian Portion
| 1 |  |  | Sitamarhi (POWERGRID) (Quad Moose) - Dhalkebar (Nepal) (Indian Portion) |  |  | PGCIL | D/C |  |  | 400 | 78 | 0 | 0 |  |  | 0 |  | 78 | OCT-23 |  |  | SEP-23 |  | Commissioned 09/23.
Remark:
Transmission System for Transfer of Power from Generation Project in SIKKIM to NR/WR Part-A
| 1 |  |  | LILO of Gangtok - Melli at Rangpo |  |  | PGCIL | S/C |  |  | 132 | 19
Remark:
Transmission System for Transfer of Power from Generation Project in SIKKM to NR/WR Part-B
| 1 |  |  | LILO of Gangtok - Rangit at Rangpo |  |  | PGCIL | S/C |  |  | 132 | 7 | 21 | 21 |  |  | 21 |  | 7 | NOV-14 |  |  | MAR-17 |  | Commissioned 11/14.
Remark:
Transmission System for Ultra mega Solar Park in Rewa District, Madhya Pradesh - PGCIL
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 54 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | LILO of Vindhyachal - Jabalpur line (Q) (II Ckt.) at Rewa PS |  |  | PGCIL | D/C |  |  | 400 | 116 | 169 | 169 |  |  | 169 |  | 116 |  |  |  | FEB-18 |  | Ready for Commissioning 02/18.
Remark:
Transmission System of Phase-I Generation Projects in Orissa-Part-A
| 1 |  |  | LILO of Rourkela - Raigarh at Jharsuguda Pooling Stn. Ckt-II |  |  | PGCIL | D/C |  |  | 400 | 44 | 120 | 120 |  |  | 120 |  | 44 |  |  |  | MAY-13 |  | Commissioned 05/13.
Remark:
Transmission System strengthening in Western part of WR for IPP Generation Projects in Chhatisgsrh - part-D - PGCIL
| 1 |  |  | Aurangabad S/S |  |  | PGCIL |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | JAN-14 |  | Commissioned 01/14.
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under Phase II- Part- A1
| 1 |  |  | 400/220kV Fatehgarh-III (Ramgarh-II) PS(4x500 MVA Transformer) |  |  | PGCIL |  |  |  | 400/220 | 1600 | [7 empty] | DEC-22
| 2 |  |  | 1X1500 MVA 765/400 KV (5th) ICT at Fatehgarh-II PS (Rajasthan (8.1 GW) under Phase II- Part- A1) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 | AUG-24 |  |  | JUL-24 |  | Commissioned 07/24.
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part A SPV Name: Ramgarh Transmission Limited
| 1 |  |  | Fatehgarh-III (Ramgarh-II) - Jaisalmer-II (RVPNL 400kV D/C line (Twin HTLS) |  |  | PGCIL | D/C |  |  | 400 | 100 | 0 | 0 |  |  | 0 |  | 100 | DEC-22 |  |  | SEP-23 |  | Commissioned 09/23.
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part C SPV Name: POWERGRID Sikar Transmisison Ltd.
| 1 |  |  | Bhadla II - Sikar II 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part C) |  |  | PGCIL | D/C |  |  | 765 | 618 | 808 | 753 |  |  | 656 |  | 356.4 | DEC-24 |  |  |  |  | RoW at 26 loc. in Sikar district. Forest (0.25 HA): Online proposal submitted on 02.12.2023. Stage-I issued on 18.04.24.Working Permission Awaited.
| 2 |  |  | Sikar II - Neemrana 400kV D/C line (Twin HTLS) (Rajasthan (8.1 GW) under phase-II- Part C) |  |  | PGCIL | D/C |  |  | 400 | 270 | 368 | 354 |  |  | 312 |  | 102 | DEC-24 |  |  |  |  | Forest (13.013 Ha, Rajasthan): Stage-I clearance accorded on 22.12.2022. Payment submitted on 30.03.23. On 13.07.23, Nodal Officer, Jaipur has requested to furnish FRA certificate. FRA: FRA obtained for Sikar & Alwar is under process.
| 3 |  |  | Establishment of 765/400kV 2x1500MVA SS at Sikar -II (solar energy (8.1 GW) under phase-II- Part C) |  |  | PGCIL |  |  |  | 765/400 | 3000 | [7 empty] | DEC-22
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part D SPV Name: POWERGRID Aligarh Sikar Transmission Ltd.
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 55 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Sikar II - Aligarh 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part D) |  |  | PGCIL | D/C |  |  | 765 | 513 | 679 | 673 |  |  | 668 |  | 485.6 | DEC-24 |  |  |  |  | Forest (15.6043 Ha, Rajasthan): Online proposal submitted on 26.07.2021 & accepted by Nodal on 03.09.2021. Stage-I issued on 10.08.23. Stage-II Awaited
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part F SPV Name: POWERGRID Bikaner Transmission System Ltd.
| 1 |  |  | Fatehgarh-III (Ramgarh-II)-Fatehgarh-II 400kV D/C line (Twin HTLS) |  |  | PGCIL | D/C |  |  | 400 | 88 | 0 | 0 |  |  | 0 |  | 88 | DEC-22 |  |  | DEC-23 |  | Commissioned 12/23.
Remark:
Transmission system strengthening scheme for evacuation of power from solar energy zones in Rajasthan (8.1 GW) under phase-II- Part G SPV Name: POWERGRID Narela Transmission Ltd.
| 1 |  |  | LILO of 765kV S/C Meerut -Bhiwani line at Narela |  |  | PGCIL | S/C |  |  | 765 | 68 | 97 | 58 |  |  | 24 |  |  | JUL-24 |  |  |  |  | 1. RoW at 27 loc. in Sonipat district in Haryana. 2. RoW at 12 loc. in North Delhi district
| 2 |  |  | Khetri-Narela 765kV D/C line (Rajasthan (8.1 GW) under phase-II- Part G) |  |  | PGCIL | D/C |  |  | 765 | 340 | 463 | 366 |  |  | 320 |  | 60 | JUL-24 |  |  |  |  | 1. RoW at 88 loc. in Jhajjar district in Haryana. 2. RoW at 8 loc. in North Delhi district
| 3 |  |  | 765/400kV GIS substation at Narela (2x1500MVA) |  |  | PGCIL |  |  |  | 765/400 | 3000 | [7 empty] | NOV-23
| 4 |  |  | 1X1500 MVA 765/400KV ICT-1 at Narela (Rajasthan (8.1 GW) under phase-II- Part G) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 85 |  |  | 85 |  | 55 | JUL-24
Remark:
Tuirial HEP (2x30MW),CS,Miz,NEEPCO, U1-8/17(c),U2-11/17(c)
| 1 |  |  | Bawktlang (Kolasib) S/S - Sihhmui S/S |  |  | PEDMIZO | D/C |  |  | 132 | 47 | 135 | 135 |  |  | 135 |  | 46.67 | [5 empty] | The 132KV Sihhmui substation was constructed by P&E, Govt. of Manipur and completed on 31.03.2016. Line has completed.
| 2 |  |  | Tuirial HEP - Bawktlang (Kolasib) S/S |  |  | PEDMIZO | S/C |  |  | 132 | 42 | 85 | 85 |  |  | 85 |  | 42 | [5 empty] | Line completed on Mar-17.
Remark:
Tuticorin TPP (Ind Barath), (660MW),TN, U1-10/18
| 1 |  |  | Ind Barath TPP - Tuticorin (PS) |  |  | IBPIL | D/C |  |  | 400 | 200
Remark:
Tuticorin TPS (JV) (2x500 MW), U1-3/14,U2-7/15 (C)
| 1 |  |  | Tuticorin JV - Madurai |  |  | PGCIL | D/C |  |  | 400 | 304 | 423 | 423 |  |  | 423 |  | 304 |  |  |  | JAN-12 |  | Commissioned 01/12.
Remark:
Uchpinda TPP, (4x360MW), PS,Chg, RKMPPL, U1-10/15(C),U2-1/16(C),U3-9/17,U4-12/17
| 1 |  |  | Uchpinda (RKM Powergen Private Ltd.) - Kotra s/s (Raigarh) line |  |  | RKMPPL | D/C |  |  | 400 | 53 | 88 | 88 |  |  | 88 |  | 53 |  |  |  | OCT-16 |  | Commissioned 10/2016 (41.42 CKm on D/C & 11 CKm on M/C)
| 2 |  |  | LILO of Raigarh (Kotra) - Raipur at Uchpinda (Interim Arrangement) |  |  | RKMPPL | D/C |  |  | 400 |  | 73 | 73 |  |  | 73 |  | 38.99 | [5 empty] | Commissioned (Interim Arrangement). De-LILO activity completed.
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 56 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Udangudi STPP Stage-I (2x660 MW), TN, TANGEDCO, U1-04/22, U2-07/22
| 1 |  |  | Udangudi - Samugarengapuram (QM ACSR Conductor) line |  |  | TANTRAN | D/C |  |  | 400 | 154 | 154 | 0 |  |  | 0 | [7 empty] | Estimate approval under process.
| 2 |  |  | Udangundi - Virudhunagar (QM ACSR Condutor) line |  |  | TANTRAN | D/C |  |  | 400 | 0 | 0 | 0 |  |  | 0
| 3 |  |  | Udangudi - Ottapidaram (QM ACSR Conductor) line |  |  | TANTRAN | D/C |  |  | 400 | 141 | 206 | 206 |  |  | 206 |  | 141 | JUL-23 |  |  | DEC-23 |  | Commissioned 12/23.
Remark:
Udupi TPP (2x600 MW),PS,KAR,UPCL,U1-7/10(C),U2-4/11(C)
| 1 |  |  | UTPS-Nandikur - Khemar (partly on Multi-ckt Multi - Voltage towers & partly on D/C towers) |  |  | KPTCL | D/C |  |  | 220 | 48 | 919 | 91 |  |  | 91 |  | 48 |  |  |  | OCT-09 |  | Commissioned 10/09. (For start up power)
| 2 |  |  | Nandikur (UTPS) - Shantigrama (Hassan) |  |  | KPTCL | D/C |  |  | 400 | 358 | 529 | 529 |  |  | 529 |  | 319.32 |  |  |  | AUG-12 |  | Commissioned 8/12
Remark:
Ugo-Sugen (382.5MW), PS, Guj, Torrent Energy, Module1: 1/13(c)
| 1 |  |  | LILO of Sugen TPS- Pirana at Uno-Sugen GPP |  |  | XYZ | D/C |  |  | 400 | 1
Remark:
Uhl-III BVPCL HEP, (3x33.3MW),SS,HP, HPSEB,U1,2, & 3 (2019-20)
| 1 |  |  | Uhl-III - Hamir Pur (By BVPCL) |  |  | HPSEBL | D/C |  |  | 132 | 71 | 0 | 0 |  |  | 0 | [7 empty] | completed on Mar-14
Remark:
Ukai Extn. (2x490 MW),PS,Guj,GSECL, U6-3/13(C),U7-3/13
| 1 |  |  | Kosamba-Mobha line |  |  | GETCO | D/C |  |  | 220 | 178 | 300 | 300 |  |  | 300 |  | 178 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 2 |  |  | LILO of Asoj - Ukai at Kosamba |  |  | GETCO | D/C |  |  | 400 | 64 | 96 | 96 |  |  | 96 |  | 64 |  |  |  | JAN-12 |  | Commissioned 1/12.
| 3 |  |  | Kosamba-Chorania line |  |  | GETCO | D/C |  |  | 400 | 460 | 641 | 641 |  |  | 641 |  | 460 | JUL-11 |  |  | AUG-14 |  | Commissioned 08/14.
| 4 |  |  | UKai-Kosamba |  |  | GETCO | D/C |  |  | 400 | 145 | 215 | 215 |  |  | 215 |  | 145 |  |  |  | MAR-13 |  | Commissioned 03/13.
Remark:
Unchahar TPS (500 MW), PS,UP,NTPC, U6-03/17(C)
| 1 |  |  | Unchahar - Fatehpur line (PUTL-TBCB) |  |  | PGCIL | D/C |  |  | 400 | 107 | 145 | 145 |  |  | 145 |  | 107 | SEP-16 |  |  | SEP-16 |  | Ready for Commissioning 09/2016.
Remark:
Uppur SCTPP, (2x800MW), Tamilnadu, TANGENDCO, U1-3/21,U2-9/21
| 1 |  |  | Virudhnagar - Kamuthi |  |  | TANTRAN | D/C |  |  | 400 | 114 | 0 | 0 |  |  | 0 |  |  | MAR-21 |  |  |  |  | Tender to be floated. Revised estimate under preparation.
| 2 |  |  | Virudhnagar - Coimbatore |  |  | TANTRAN | D/C |  |  | 765 | 498 | 725 | 556 |  |  | 527 |  | 200 | MAR-21 |  |  |  |  | Work in progress in all the 3 reaches awarded.
| 3 |  |  | Virudhnagar - Kayathar |  |  | TANTRAN | D/C |  |  | 400 | 158 | 201 | 201 |  |  | 201 |  | 140.1 | MAR-21 |  |  |  |  | Work completed
| 4 |  |  | Virudhnagar - Thappagundu |  |  | TANTRAN | D/C |  |  | 400 | 160 | 0 | 0 |  |  | 0 |  |  | MAR-21 |  |  |  |  | Tender to be floated.
| 5 |  |  | Uppur SCTPP - Virudhunagar |  |  | TANTRAN | D/C |  |  | 765 | 204 | 0 | 0 |  |  | 0 |  |  | MAR-21 |  |  |  |  | Tender to be floated.
| 6 |  |  | Virudhunagar |  |  | TANTRAN |  |  |  | 765/400 | 3000 | 100 | 95 |  |  | 95 |  | 90 | MAR-21 |  |  |  |  | Work in progress.
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 57 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
URI-II HEP (4x60 MW), CS,J&K,NHPC,U1-9/13(C),U2-11/13(C),U3-9/13(C),U4-2/14 (C)
| 1 |  |  | URI I - URI II |  |  | PGCIL | S/C |  |  | 400 | 11 | 32 | 32 |  |  | 32 |  | 11 |  |  |  | AUG-11 |  | Commissioned 08/11.
| 2 |  |  | URI II -Wagoora |  |  | PGCIL | S/C |  |  | 400 | 105 | 288 | 288 |  |  | 288 |  | 105 | MAY-11 |  |  | DEC-11 |  | Commissioned 12/11.
Remark:
Utraula IIPP (2x45 MW),PS,UP,BAJAJ,U1-2/12 (C),U2-3/12(C)
| 1 |  |  | Balrampur-Utraula line |  |  | BEPL | D/C |  |  | 132 | [13 empty] | Existing line.
Remark:
Utraula TPP, (2x45 MW), PS, UP, Bajaj
| 1 |  |  | Dumariaganj- - Utraula |  |  | UPPTCL | S/C |  |  | 132 |  | 114 | 114 |  |  | 114 |  | 40 | [5 empty] | Commissioned in January-2019. To be deleted.
Remark:
VallureTPS. (3x500 MW),CS,TN,NTPC,U1-2/12(C), U2-2/13(c), U3-2/14
| 1 |  |  | Tiruvelam (PG) - Chitoor |  |  | PGCIL | D/C |  |  | 400 | 42 | 59 | 59 |  |  | 59 |  | 42 |  |  |  | MAR-14 |  | Commissioned 03/14.
| 2 |  |  | Vallur JV Project-NCTPS St.II |  |  | TANTRAN | D/C |  |  | 400 | 7 | 14 | 14 |  |  | 14 |  | 7 | MAR-11 |  |  | AUG-12 |  | Commissioned 8/12.
| 3 |  |  | Vallure TPS - Melakottaiyur line |  |  | PGCIL | D/C |  |  | 400 | 71 | 104 | 104 |  |  | 104 |  | 71 |  |  |  | MAR-13 |  | Commissioned 03/13.
| 4 |  |  | LILO of Alamathy - Sriperumbdur at Vallure TPS |  |  | PGCIL | D/C on M/C |  |  | 400 | 131 | 129 | 129 |  |  | 129 |  | 131 | JUL-10 |  |  | JUL-11 |  | Commissioned 7/11
Remark:
various private generators
| 1 |  |  | Thervaikandikai - Manali |  |  | TANTRAN | D/C |  |  | 400 | 73 | 113 | 111 |  |  | 106 |  | 58.6 | JUN-24 |  |  |  |  | Work under progress. Row issues Enter upon permission awaited.
Remark:
Various wind energy generators
| 1 |  |  | LILO of one ckt of Thappagundu - Anaikadavu 400 line at Udumalpet (PGCIL) S/S |  |  | TANTRAN | D/C |  |  | 400 | 40 | 60 | 60 |  |  | 60 |  | 16.76 | NOV-23 |  |  |  |  | 3.252 KM of stringing and 20.012 KM OPGW stringing pending.Work will be taken up after payment of Tree /Crop compensatation.
| 2 |  |  | LILO of 230 kV Abishekapatti - Udayathur line at Nanguneri |  |  | TANTRAN | D/C |  |  | 230 | 40 | 84 | 84 |  |  | 84 |  | 40.35 | SEP-24 |  |  |  |  | Line work completed. Will be energised on energisation of Nanguneri 230KV Substation.
| 3 |  |  | Nanguneri |  |  | TANTRAN |  |  |  | 230/110 | 200 | 100 | 90 |  |  | 50 |  | 0 | SEP-24 |  |  |  |  | Work under progress
Remark:
Vijayawada TPS (Extn. -IV),500 MW,SS,AP,APGENCO, -10/09 (C )
| 1 |  |  | LILO of Srisaliam -Nunaa at Vijayawada TPS |  |  | APTRANS | M/C |  |  | 400 | 24 | 22 | 22 |  |  | 22 |  | 24 |  |  |  | JUL-09 |  | Commisioned 7/09
| 2 |  |  | Narsapur-Suryapet |  |  | APTRANS | D/C |  |  | 400 | 149 | 199 | 199 |  |  | 199 |  | 149 |  |  |  | FEB-13 |  | Commissioned 02/13.
| 3 |  |  | Vijayawada TPS-Suryapeta |  |  | APTRANS | D/C |  |  | 400 | 226 | 316 | 316 |  |  | 316 |  | 226 | JUN-11 |  |  | FEB-13 |  | Commissioned 02/13.
| 4 |  |  | Vijayawada TPS-Tallapally |  |  | APTRANS | D/C |  |  | 220 | 266 | 411 | 411 |  |  | 411 |  | 266 | JAN-11 |  |  | AUG-11 |  | Commissioned 8/11.
| 5 |  |  | Malkaram-Narsapur |  |  | APTRANS | D/C |  |  | 400 | 147 | 209 | 209 |  |  | 209 |  | 147 |  |  |  | FEB-13 |  | Commissioned 02/13.
Remark:
Vindhyachal-IV ,CS,MP,NTPC, U11-6/12(C) C), U12-3/13(C), U13-08/15 (C) Rihand - III,(1000MW each) Gen. U5- U6-11/13(C)
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 58 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Satna - Gwalior line (Ckt-I) |  |  | PGCIL | S/C |  |  | 765 | 337 | 901 | 901 |  |  | 901 |  | 337 |  |  |  | FEB-14 |  | Commissioned 02/14.
| 2 |  |  | Sasan - Vindhyachal Pooling station |  |  | PGCIL | D/C |  |  | 400 | 12 | 18 | 18 |  |  | 18 |  | 12 |  |  |  | DEC-12 |  | Commissioned 12/12.
| 3 |  |  | Vindhyachal Pooling Station - Satna Ckt-II |  |  | PGCIL | S/C |  |  | 765 | 271 | 586 | 586 |  |  | 586 |  | 271 |  |  |  | AUG-15 |  | Commissioned 08/15.
| 4 |  |  | Gwalior - Jaipur (Ckt 1) |  |  | PGCIL | S/C |  |  | 765 | 305 | 834 | 834 |  |  | 834 |  | 305 | MAR-14 |  |  | AUG-15 |  | Commissioned 08/15.
| 5 |  |  | Rihand - Vindhyachal Pooling Station (1st Ckt) |  |  | PGCIL | S/C |  |  | 765 | 31 | 91 | 91 |  |  | 91 |  | 31 | NOV-12 |  |  | JUN-14 |  | Commissioned 06/14.
| 6 |  |  | Bassi (PG)- Jaipur (RVPN) 765 KV line (Q) |  |  | PGCIL | D/C |  |  | 400 | 97 | 138 | 138 |  |  | 138 |  | 97 |  |  |  | DEC-13 |  | Commissioned 12/13.
| 7 |  |  | Sasan - Vindhyachal Pooling Station line |  |  | PGCIL | S/C |  |  | 765 | 12 | 19 | 19 |  |  | 19 |  | 12 | NOV-12 |  |  | DEC-12 |  | Commissioned 12/12
| 8 |  |  | Vindhyachal-IV - Vindhyachal Pooling Station line (Q) |  |  | PGCIL | D/C |  |  | 400 | 58 | 84 | 84 |  |  | 84 |  | 58 |  |  |  | DEC-12 |  | Ready for commissioning 12/12.
| 9 |  |  | Satna - Gwalior line (60 Km D/C Portion) Ckt-II |  |  | PGCIL | D/C+S/C |  |  | 765 | 300 | 782 | 782 |  |  | 782 |  | 300 | NOV-12 |  |  | AUG-14 |  | Commissioned 08/14.
| 10 |  |  | Rihand - Vindhyachal Pooling Station (2nd Ckt) |  |  | PGCIL | D/C |  |  | 765 | 31 | 91 | 91 |  |  | 91 |  | 31 | NOV-12 |  |  | AUG-15 |  | Ready for Commissioning in 08/15.
| 11 |  |  | Vindhyachal Pooling Station - Satna line (2 Km D/C Portion) Ckt-I |  |  | PGCIL | D/C+S/C |  |  | 765 | 271 | 586 | 586 |  |  | 586 |  | 271 | NOV-11 |  |  | MAR-15 |  | Commissioned 03/15.
| 12 |  |  | Vindhyachal Pooling Station (ICT-I) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 | NOV-12 |  |  | MAR-15 |  | Commissioned 03/15.
| 13 |  |  | Vindhyachal Pooling Station (ICT-II) |  |  | PGCIL |  |  |  | 765/400 | 1500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | AUG-15 |  | Commissioned 08/15.
Remark:
Visa Power TPP (2x600 MW) PS, Chh, VPL, U1 & U2-uncertain
| 1 |  |  | Visa Power TPP - Raigarh Pooling Station |  |  | VISA | D/C |  |  | 400 | 26 | 37 | 33 |  |  | 26 |  | 0 | [5 empty] | Work is under Construction.
Remark:
Vizag (Hinduja National Power) (2x520MW),PS,AP,U1-12/15 (C), U2-3/16 (C)
| 1 |  |  | Vizag TPP(HNPCL) - Kamavarapukota |  |  | APTRANS | D/C |  |  | 400 | 486 | 697 | 697 |  |  | 697 |  | 486 | NOV-15 |  |  | JUN-17 |  | Ready for Commissioning 06/2017. (Earlier the line was of 712 ckm now the length is revised to 485 ckm ).
| 2 |  |  | Vizag TPP - Kalpaka |  |  | APTRANS | D/C |  |  | 400 | 14 | [6 empty] | 14 |  |  |  | JUL-15 |  | Commissioned 07/15.
| 3 |  |  | Kamavarapukota - Surypet (Kamavarrapukota - Chinnakorukondi) |  |  | APTRANS | D/C |  |  | 400 | 179 | 242 | 242 |  |  | 242 |  | 179 | SEP-15 |  |  | OCT-16 |  | Ready for Commissioning 10/2016.
| 4 |  |  | Kamavarapukota - Surypet ( Chinnakorukondi - Suryapet) |  |  | TSTRANS | D/C |  |  | 400 | 170 | 234 | 234 |  |  | 234 |  | 170 | SEP-15 |  |  | OCT-16 |  | Ready for Commissioning 10/2016
| 5 |  |  | Vizag ( Hinduja) TPP - Kalpaka |  |  |  | D/C |  |  | 400 | 15 | 25 | 25 |  |  | 25 |  | 15 | [5 empty] | Commissioned 05/14. for startup power.
| 6 |  |  | Suryapet S/S |  |  | TSTRANS |  |  |  | 400/220 | 630 | 100 | 100 |  |  | 100 |  | 100 | MAR-15 |  |  | MAR-16 |  | Commissioned 03/16.
| 7 |  |  | Kamavarapukota s/s (ICT-1) |  |  | APTRANS |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | MAR-16 |  |  | FEB-17 |  | Commissioned 02/2017
| 8 |  |  | Shankarpally |  |  | TSTRANS |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 |  |  |  | OCT-18 |  | Commissioned 10/18.
| 9 |  |  | Kamavarapukota s/s (ICT-2) |  |  | APTRANS |  |  |  | 400/220 | 315 | 100 | 100 |  |  | 100 |  | 100 | MAR-16 |  |  | MAR-17 |  | Commissioned 03/2017
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 59 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
Vyasi HEP(2x60MW), Yamuna river,UK,UJVNL, (12/20)
| 1 |  |  | LILO of Lakhwar- Dehradun at Vyasi |  |  | PTCUL | D/C |  |  | 220 | 71 | 113 | 113 |  |  | 113 |  | 71 | APR-22 |  |  | APR-22 |  | Commissioned 04/22.
Remark:
Wanakbori TPS(1x800), SS, Guj,GSECL,U8-10/18
| 1 |  |  | Wanakbori TPS-Soja |  |  | GETCO | D/C |  |  | 400 | 212 | 343 | 272 |  |  | 271 |  | 144.09 | DEC-19 |  |  |  |  | WIP
| 2 |  |  | Soja - Zerda line (Pkg-1) with Twin AL-59 conductor |  |  | GETCO | D/C |  |  | 400 | 134 | 198 | 198 |  |  | 198 |  | 134 | AUG-21 |  |  | JAN-22 |  | Commissioned 01/22.
| 3 |  |  | LILO of Wanakbori -Soja line at Dehgam (PG) S/S |  |  | GETCO | D/C |  |  | 400 | 13 | 24 | 24 |  |  | 24 |  | 13 |  |  |  | OCT-19 |  | Commissioned 10/19.
| 4 |  |  | Wanakbori S/y -Wanakbori S/y (existing) |  |  | GETCO | D/C |  |  | 400 | 2 | 5 | 5 |  |  | 5 |  | 2 |  |  |  | MAR-18 |  | Ready for Commissioning 03/18.
Remark:
Welspun Energy Annupur,( 2x660 MW), PS,Annupur,MB Power, U1-4/15(C),U2-3/15
| 1 |  |  | Welspun Anuppur TPS - Vindhyachal Pooling Station |  |  | XYZ | D/C |  |  | 400
Remark:
Western Region Expansion Scheme-XXX (WRSS-XXX)
| 1 |  |  | Bhadravati(PG)-Parli(PG) |  |  | PGCIL | D/C |  |  | 400 | 768 | 1049 | 1049 |  |  | 1049 |  | 768 | JUL-10 |  |  | MAR-11 |  | Line charged Mar'11.
Remark:
WRES-XXVII SPV Name: Raipur Pool Dhamtari Transmission Limited
| 1 |  |  | Raipur Pool - Dhamtari 400kVD/C line (Q) |  |  | PGCIL | D/C |  |  | 400 | 176 | 232 | 149 |  |  | 11 |  |  | DEC-24
Remark:
Yadadri TPS (5x800 MW), Telangana, TSGENCO/BHEL, U1-09/22, U2-10/22, U3-05/23, u4-05/23, U5-09/23
| 1 |  |  | Yadadri TPP switchyard - Damaracherla S/S |  |  | TSTRANS | D/C |  |  | 400 | 10 | 16 | 16 |  |  | 16 |  | 10 | JUL-22 |  |  | DEC-22 |  | Commissioned 12/22.
| 2 |  |  | YTPP Switchyard - 400kV Dindi SS |  |  | TSTRANS | D/C |  |  | 400 | 208 | 290 | 290 |  |  | 290 |  | 208 | APR-24 |  |  | JUN-24 |  | Commissioned 06/24.
| 3 |  |  | Yadadri TPP Switchyard - Choutuppal S/S |  |  | TSTRANS | D/C |  |  | 400 | 185 | 259 | 259 |  |  | 258 |  | 66.3 | JUN-24 |  |  |  |  | Standing crops issue
| 4 |  |  | Yadadri TPP switchyard - Jangaon S/S |  |  | TSTRANS | D/C |  |  | 400 | 278 | 402 | 367 |  |  | 283 |  | 44 | DEC-19 |  |  |  |  | Works under progress.
| 5 |  |  | LILO of both circuits of 400kV Khammam - Mamidipally to Choutuppal S/S |  |  | TSTRANS | D/C |  |  | 400 | 33 | 48 | 48 |  |  | 48 |  | 33 | SEP-22 |  |  | MAR-23 |  | Commissioned 03/23.
| 6 |  |  | Damaracherla S/S |  |  | TSTRANS |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | JUL-22 |  |  | DEC-22 |  | Commissioned 12/22.
| 7 |  |  | Choutuppal S/S (T/F-I) |  |  | TSTRANS |  |  |  | 400/220 | 500 | 100 | 100 |  |  | 100 |  | 100 | SEP-22 |  |  | MAR-23 |  | Commissioned 03/23.
Remark:
Yaddari Thermal Power Evacuation Scheme
| 1 |  |  | Choutuppal (Ist Transformer) |  |  | TSTRANS |  |  |  | 400/220/132 | 500 | 100 | 100 |  |  | 100 |  | 100 | SEP-23 |  |  | NOV-23 |  | Commissioned 11/23.
Remark:
Yelanhanka CCPP (370MW), KPTL, Kar, U1-06/18
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 60 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected
Associated Transmission Lines and Substations | [6 empty] | State/Agency Executing Asociated Trans. | Ckts (S/C) & (D/C) |  |  | Voltage Level (KV) | Ckm/ MVA | Construction progress Status | [6 empty] | Original Target Date | Revised Target Date |  |  | Month of Completion | Remark (Status of all statutory clearences particularly forest clearence and ROW problem, if any needs to be mentioned here.)
[13 empty] | TL(Nos)/Land Acq. (%) | STC(Nos)/Civil Work |  | TE(Nos)/Recp.Materia |  | STG(Ckm)/Erection
1. | [6 empty] | 2. | 3. |  |  | 4. | 5. | 6. | 7. |  | 8. |  | 9. |  | 10. | 11. |  |  | 12. | 13.
| 1 |  |  | Yelanhanka CCPP - Yelanhanka(KPTCL) |  |  | KPTCL | D/C |  |  | 220 | 1 | 3 | 3 |  |  | 3 |  | 1 |  |  |  | MAY-18 |  | Commissioned 12/15 (Late Reported)
| 2 |  |  | Yelanhanka(KPTCL)- Yelanhanka(PG) |  |  | KPTCL | D/C |  |  | 220 | 6 | 0 | 0 |  |  | 0 |  | 11.6 | [5 empty] | Commissioned on 14.09.2018.
Remark:
Yermarus TPS (2 x 800 MW), Karnataka, KPCL, U1-3/16 (C), U2-6/16
| 1 |  |  | Bellary (PS) - C.N. Hally |  |  | KPTCL | D/C |  |  | 400 |  | 0 | 0 |  |  | 0
| 2 |  |  | JSW TPS - Bellary (PS) |  |  | JPL | D/C |  |  | 400 | 19 | 39 | 39 |  |  | 39 |  | 19 |  |  |  | JUN-17 |  | Ready for commissioning 06/2017.
| 3 |  |  | Yermarus TPS - Gulbarga |  |  | KPTCL | D/C |  |  | 400 |  | 331 | 331 |  |  | 331 |  | 234.11 | [5 empty] | Repeated work. Commissioned
| 4 |  |  | Yermarus TPS - Bellary Pooling Station (BPS) |  |  | KPTCL | D/C |  |  | 400 | 285 | 392 | 392 |  |  | 392 |  | 285 | AUG-17 |  |  | MAR-18 |  | Ready for Commissioning 03/18.
| 5 |  |  | Bellary (PS) - New Madhugiri (near Tumakur) |  |  | KPTCL | D/C |  |  | 400 | 450 | 520 | 520 |  |  | 520 |  | 450 | DEC-16 |  |  | JUN-17 |  | Ready for commissioning 06/2017.
| 6 |  |  | LILO of Both ckt of Nelamangala - Talaguppa at CN Halli |  |  | KPTCL | D/C |  |  | 400 |  | 0 | 0 |  |  | 0 | [7 empty] | S/S Land to be Acquired
| 7 |  |  | Bellary (TPS) - Bellary (PS) |  |  | KPTCL | D/C |  |  | 400 | 5 | 0 | 0 |  |  | 0 | [7 empty] | This work is not in planned works.
| 8 |  |  | Gulbarga S/S |  |  | KPTCL |  |  |  | 400/220 | 1000 | 100 | 100 |  |  | 100 |  | 100 | SEP-19 |  |  |  |  | Commissioned
Remark:
Legends
[10 empty] | Report generated through |  |  |  |  | 2024-08-13 12:06 | [6 empty] | 45517.5042
[15 empty] | STG: Stringing Completed | [11 empty] | Page 61 of | 61
|  |  | TL: Total Location |  |  | STC: Stubs Cast |  |  | TE: Towers Erected